## Instruction
Instructions
This spreadsheet was developed to minimize the workload when submitting information after each meeting to the Committee Secretary. After initial completion, the maintenance should be much simpler and all the information is in a single document. However, this also implies that if not updated and provided with minutes after each meeting then rooms will not be available at the next meeting and minutes will not be posted to the web, none of which is desirable. If something is missing or desired then please let us know. If this template is updated the existing subcommittee copies will be modified with the updates. This template is intended for a single use by each subcommittee and then maintained and submitted with minutes after each meeting.
Officers Tab | Self explanatory. The "*" highlights the two rows that are required all others is desired but optional.
Table Tab | The table is setup so you can set the first seven columns to print and create a PDF file for addition to your subcommittee minutes. If you need to make changes after initial submittal, you can update this spreadsheet and sent it to the Committee Secretary for action, similar to revised minutes. More rows can be added by copying existing rows. The Column heading definintions descriptions are shown below.
| Document | The document number, i.e. C37.xx.x. If it is a Task Force then enter "Task Force" in this column.
| Title | The published document title or title on the PAR, or Task Force title and brief description.
| Chairperson | The name of the chairperson or "Vacant" if the document is inactive. Vacant in effect is a default to the Subcommittee Chair, but this doesn't need to be reflected in the table. Please do not put the Subcommittee Chair's name unless he is the WG chair and not a default.
| Activity | Self explanatory
| Status | These fields change based on whether the document is active or inactive. For active documents the "PAR Date" should reflect the date the PAR was approved. The "PAR Expires" entry is the expiration date of the approved PAR. The "Ballot Date" entry is the date of the first Ballot. For inactive documents the "New WG" entry is when the WG will reconvene to start work on revising the published document. The "Approved" entry is the RevCom approval date for the published document. The "Expires" entry is the expiration date of the document (ten years from publication). A star ("*") can be use to show dates that are expected or planned. These fields will be blank for Task Forces.
| Notes | This is an open area for notes that are desired that will be included in the minutes but not on the webpage.
| Sessions | The number of sessions needed on the schedule at the next meeting location.
| Room Size | The room size required at the next meeting location.
| AMS | This entry has two functions first to identify who needs AMS permissions and second to request a WG addition to AMS. The options are "Add", "Remove", "N/A". If "Add" is selected the WG is built in AMS with the Chair as the first participant and the Chair is given AMS permissions. If "Remove" is selected the permissions will be removed and the WG participant entries will be cleaned and ready for the next use.
| Booklet | The information on each WG meeting at the next location and what is happening or being discussed at the next meeting. This information will be used to populate the meeting Booklet either printed, online, or both.
What's New tab | This tab is for information published on the website above the table for information that is new in the subcommittee, working group, document, and/or task force. The tab is setup so tabbed content can be provided. If no tabbed content is desired then that row can be deleted.
Questions? | If you have any questions or comments about this spreadsheet please contact the Committee Secretary.

## Officers
| Chair | Secretary
Name:* | Darryl Moser | Jared Hines
Email:* | darryl.moser@us.abb.com | jaredkhines@ieee.org
Address: | ABB Inc. Wichita Falls, TX Phone: 940-613-4256 | Eaton Greenwood, SC
Term: | 2022-2025 | Phone: 864-450-5691
* Minimum required

## Table
Document | Title | Chairperson | Secretary | Activity | Status* |  | Notes | Sessions | Room Size | AMS | Booklet
C37.20.1 | IEEE Standard for Metal-Enclosed Low-Voltage (1000 Vac and below, 3200 Vdc and below) Power Circuit Breaker Switchgear | Mike Lafond | Robert Burns | Active | PAR Expires: | 2024-12-31 | Active WG | 2 | 35 | N/A | Working Group, full document revision
[5 empty] | Ballot Date: | TBD
[5 empty] | Completion: | TBD
C37.20.2 | IEEE Standard for Metal-Clad Switchgear | Vacant | Vacant | Inactive | New WG: | Target 2030 |  | 0 | N/A | N/A | None
[5 empty] | Approved: | TBD
[5 empty] | Expires: | TBD
C37.20.3 | IEEE Standard for Metal-Enclosed Interrupter Switchgear (1 kV-48.3 kV) | Ron Hartzel | Randy Creach | Active | PAR Expires: | 2023-12-31 | Active WG | 2 | 45 | N/A | Working Group, full document revision Avoid conflict with C37.20.4, C37.20.6 and C37.301
[5 empty] | Ballot Date: | TBD
[5 empty] | Completion: | Target 2023
C37.20.4 | IEEE Standard for Indoor AC Switches (1 kV to 52 kV) for Use in Metal-Enclosed Switchgear | Bob Cohn | Russell Boyce | Active | PAR Expires: | 2023-12-31 | Active WG | 1 | 35 | N/A | Working Group, full document revision Avoid conflict with C37.20.3, C37.20.6 and C37.20.7
[5 empty] | Ballot Date: | TBD | Requesting PAR extension
[5 empty] | Completion: | Target 2023
C37.20.5 | Not Used | Vacant | Vacant | Inactive | New WG: |  |  | No | N/A | N/A | None
Approved:
Expires:
C37.20.6 | IEEE Standard for 4.76 kV to 48.3 kV Rated Ground and Test Devices Used in Enclosures | Ron Hartzel | Paul Gingrich | Active | PAR Expires: | 2025-12-31 | Active WG | 1 | 45 | N/A | Working Group, full document revision Avoid conflict with C37.20.2, C37.20.3 and C37.20.6
[5 empty] | Ballot Date: | TBD
[5 empty] | Completion: | TBD
C37.20.7 | IEEE Guide for Testing Switchgear Rated Up to 52 kV for Internal Arcing Faults | Dan Hrncir | John Kaminski | Active | PAR Expires: | 2024-12-31 | Active WG | 2 | 65 | N/A | Working Group, full document revision Schedule at a time to allow participation by HVCB members
[5 empty] | Ballot Date: | TBD
[5 empty] | Completion: | TBD
C37.20.8 | IEEE Draft Standard for Metal-Enclosed Low-Voltage (3200V and below) Direct Current Power Circuit Breaker Switchgear For Traction Power Applications | Withdrawn by IEEE-SA Board 2012-12 | Withdrawn by IEEE-SA Board 2012-12 | Inactive | New WG: |  | Joint SASC/VTRT | No | N/A | N/A | None
[5 empty] | Approved: |  | Withdrawn 2012-12
[5 empty] | Expires: |  | by IEEE-SA Board
C37.20.9 | IEEE Standard for Metal-Enclosed Switchgear Rated 1 kV to 52 kV Incorporating Gas Insulating Systems | Eldridge Byron | Terry Woodyard | Active | PAR Expires: | Target 2024 | Active WG | 1 | 45 | N/A | Working Group, for document amendment Avoid conflict with C37.04, C37.09, C37.20.6, C37.24 and C37.100.1
[5 empty] | Ballot Date: | 2019-03-21
[5 empty] | Completion: | 2029-12-31
C37.20.10 | IEEE Standard for Definitions for AC (52 kV and Below) and DC (3.2 kV and Below) Switchgear Assemblies | Dan Delfino | Truett Thompson | Active | PAR Expires: | 2025-12-31 | Active WG | 1 | 35 | N/A | Working Group, full document revision Avoid conflict with C37.13, .14, .17, .20.1, and 20.2
[5 empty] | Ballot Date: | 2016-09-22
[5 empty] | Completion: | 2026-12-31
C37.21 | IEEE Standard for Control Switchboards | Christo Thomas | Chris French | Active | PAR Expires: | 2027-12-31 | Active WG | 1 | 35 | N/A | Working Group, full document revision Avoid conflict with C37.13.1
[5 empty] | Ballot Date: | TBD
[5 empty] | Completion: | TBD
C37.22 | Preferred Ratings and Related Required Capabilities for Indoor AC Medium-Voltage Switches Used in Metal-Enclosed Switchgear | Superceded by C37.20.4 |  | Inactive | New WG: |  | Superceded by C37.20.4 | No | N/A | N/A | None
Approved:
Expires:
C37.23 | Standard for Metal-Enclosed Bus | Jared Hines | Mark Roberson | Active | PAR Expires: | 2024-12-31 | Active WG | 1 | 45 | N/A | Working Group, full document revision Avoid conflict with 20.3, 20.4, 20.9 & .24
[5 empty] | Ballot Date: | TBD
[5 empty] | Completion: | TBD
C37.24 | IEEE Guide for Evaluating the Effect of Solar Radiation on Outdoor Metal-Enclosed Switchgear | Terry Woodyard | Terry Neighbours | Active | PAR Expires: | 2026-12-31 | Active WG | 1 | 35 | N/A | Working Group, full document revision Avoid conflict with C37.20.3, C37.20.6 and C37.20.7
[5 empty] | Ballot Date: | TBD
[5 empty] | Completion: | TBD
C37.59 | IEEE Standard Requirements for Conversion of Power Switchgear Equipment | N/A | N/A | Inactive | New WG: | See ADSCOM S/C page for details | See ADSCOM S/C for details | See ADSCOM | N/A | N/A | None
[5 empty] | Approved: |  | Joint with HVCB, SASC, LVSD
Expires:
C37.81 | IEEE Guide for Seismic Qualification of Class 1E Metal-Enclosed Power Switchgear Assemblies | Russell Boyce | Carl Schneider | Active | PAR Expires: | Target 2022 | Target 2022 WG formation | 1 | 35 | N/A | PAR Study Group Avoid conflict with C37.20.4
[5 empty] | Ballot Date: | 2017-03-23 | PAR Study Group to begin Spring 2023
[5 empty] | Completion: | 2027-12-31
C37.82 | IEEE Standard for the Qualification of Switchgear Assemblies for Class 1E Applications in Nuclear Power Generating Stations | Russell Boyce | Carl Schneider | Active | PAR Expires: | Target 2022 | Target 2022 WG formation | 1 | 35 | N/A | PAR Study Group Avoid conflict with C37.20.4
[5 empty] | Ballot Date: | 2017-09-28 | PAR Study Group to begin Spring 2023
[5 empty] | Completion: | 2027-12-31
C37.121 | IEEE Guide for Switchgear - Unit Substation - Requirements | Vacant | Vacant | Inactive | New WG: | Target 2026 | Target 2026 WG Formation | 0 | N/A | N/A | None
[5 empty] | Approved: | 2020-09-24
[5 empty] | Expires: | 2030-12-31
C37.122.2 | IEEE Draft Guide for the Application of Gas Insulated Substations 1 kV to 52 kV | Eldridge Byron | Terry Woodyard | Active | New WG: | TBD | See ADSCOM S/C for details | See ADSCOM | N/A | N/A | None
[5 empty] | Ballot Date: | TBD | Joint with Substations, SASC
[5 empty] | Completion: | TBD | New Document
S/C | SA Sub-Committee | Darryl Moser | Jared Hines | Active |  |  |  | 1 | 65 | N/A | None
* All future dates are expected dates

## What's New
What's New
Title: | What's new in SA Subcommittee?
Content: | SA S/C is actively working to revise 12 documents (C37.20.1, C37.20.3, C37.20.4, C37.20.6, C37.20.7, C37.20.9a, C37.20.10, C37.21, C37.23, C37.24, C37.81 and C37.82) prior to their expiration dates.
Content: | C37.20.7 will revise the PAR to change from a guide to a recommended practice
Content: | A PAR will be submitted for C37.20.9 for an amendment
Content: | A PAR will be submitted for C37.21 for a full document revision
Content: | C37.20.2 activity has been completed and WG disbanded
Content: | C37.81 & C37.82 began work as a PAR Study Group
Content: | Activity is on schedule and actively working to be completed before expiration

## Doc Action Forecast
Expiration Date | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044
Target WG Date | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039
SA S/C Documents | C37.20.3 |  | C37.20.1 | C37.20.10 | C37.21 |  | C37.20.9 | C37.121 |  | C37.20.3 | C37.20.2 | C37.20.1 | C37.23 | C37.20.10 | C37.21 | C37.81 | C37.20.9 |  | C37.121 |  | C37.20.3
| C37.20.4 |  | C37.20.2 | C37.24 | C37.24 |  | Application guide for C37.20.7 equipment |  |  | C37.20.4 | C37.20.6 |  | C37.20.7 | C37.24 | C37.24 | C37.82 |  |  |  |  | C37.20.4
|  |  | C37.20.6 |  |  | C37.81
|  |  | C37.23 |  |  | C37.82
C37.20.7
WG/PAR Activity Started & Current Pacing on Target
WG/PAR Activity under Time Constraint
WG/PAR Activity not Started & Needs Action

## Adhoc Arc Res Applications
Adhoc for Arc Res Equipment Applications - formed during the F22 SASC meeting
Marcelo Valdes: During C37.20.7 WG sessions it was realized that a great deal of information resides and/or needs to be updated for the application of C37.20.7 type equipment and much of this information would conflict with the scope of C37.20.7. Currently C37.20.7 is a testing guide and not an application document. M. Valdes motions to form an ad-hoc for a potential new document for the application of C37.20.7 internal arc res equipment. 2nd by M. Wactor. General consensus was to create the adhoc as recommended but to not delay nor change the current C37.20.7 WG PAR or activities. SA S/C chair would like to have the adhoc to research where this document should reside such as ADSCOM or which S/C.
Adhoc members
M. Valdes - Lead | marcelo.valdes@us.abb.com
Mike Wactor | michael.wactor@powellind.com
Terry Woodyard | mr.terrance.woodyard@ieee.org
Paul Barnhart | paul.d.barnhart@ul.com
Tom Hawkins | tom.hawkins@ieee.org
Ted Burse | ted.burse@powellind.com
Terry Neighbors | terry.l.neighbours@us.abb.com
Albert Livshitz | livshitz@ieee.org
Garret Sims | danielgsims@eaton.com
Christo Thomas | Christo.thomas@se.com
Mina Youssef | mina.youssef@eaton.com
Owen Parks | owen.parks@us.abb.com
Adrian Lopez | Adrian.lopez@powellind.com
Fiori Cozivc | Fiori.cozivc@sandc.com

## C37.20.2 AdHoc Voltage Dividers
Current revision states:
“This annex covers voltage dividers intended to be used in equipment to provide voltage measurement or signaling, such that there is no galvanic isolation between circuits operating above 254 V ac or 280 V dc and those operating at lower voltages.
This annex provides construction and testing requirements for voltage dividers as an alternative to requirements found in applicable IEC standards for these products. Capacitive voltage dividers complying with Annex A of IEC 61243-5 [B1] need not comply with this annex. Other voltage dividers complying with IEC 62271-206 [B3] need not comply with this annex.”
Proposed Action
1.Maintain the current references for voltage dividers
2.Add the reference to IEC 60044-7 – 1999: Electronic voltage transformers to the Annex D language and to the Bibliography:
“This annex provides construction and testing requirements for voltage dividers as an alternative to requirements found in applicable IEC standards for these products. Capacitive voltage dividers complying with Annex A of IEC 61243-5 [B1] need not comply with this annex. Other voltage dividers complying with IEC 62271-206 [B3] or IEC 60044-7 [B19] need not comply with this annex.”
Note: IEC 62271-206 will be replaced by 62271-213 and IEC 60044-7 will be replaced by IEC 61869-7 when those documents are published.

## C37.20.2 AdHoc View windows
Ad Hoc members: P. Barnhart, J. Bowen, C. Schneider, D. Elliott, S. Flores, M. Wactor, M. Valdez, T. Rohrer and T. Woodyard.
The following was persented by Paul Barnhart at the Spring 2018 SA S/C meeting in Orlando
Proposed revision to IEEE C37.20.2 with respect to barriers:
7.7 Metallic barriers
MC switchgear shall be provided with metal barriers between primary sections of adjacent vertical sections and between major primary sections of each circuit. Primary sections include the bus compartment, the primary entrance compartment, the removable element compartment, the voltage transformer(s) compartment, and the control power transformer(s) compartment. To minimize the possibility of communicating faults between primary sections, the barriers between primary sections shall have no intentional openings.
Barriers between adjacent vertical sections and between compartments shall not be provided with windows or ports for visual inspection, infrared scanning, or any other purpose.
Barriers are provided to segregate the voltage transformers for each polyphase circuit but not to segregate them individually.
Where buses penetrate barriers, suitable bushings or other insulation shall be provided.

## Air around cables
From "2019-04-30 V3 temperatures surrounding cables - report to SA.pptx"
Ad Hoc WG Chair was Paul Barnhart
This report was presented and approved at the Spring 2019 SASC meeting in Burlibton, VT

## Hidden (hidden)
Active | Yes | Add | 35
Inactive | No | Remove | 45
|  | N/A | 65
N/A