## Cover Page
Document number: 6-11-0049-03-0000
Title: Technical Working Items of the IEEE 1900.6a Project
Date: March 9, 2012
Notice: This document has been prepared to assist IEEE DYSPAN-SC and its Working Groups. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE DYSPAN-SC.
Patent Policy and Procedures: The contributor is familiar with the IEEE Patent Policy and Procedures including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to IEEE DYSPAN-SC and its Working Groups of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE DYSPAN-SC. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## Working Items
The working group is open for stage 1 contributions and stage 2 contributions
Item No. | Status | Problem statement | Stage-1 contribution | Stage-2 contribution | Stage-3 contribution
1 | Approved as working item on Sep. 28, 2011 Call for contributions for this working item was issued on Sep. 30, 2011 | The IEEE Std 1900.6-2011 defines logical entities Sensor, Cognitive Engine and Data Archive. The current logical entities require further enhancement to improve interworking with noncompliant spectrum sensing systems, noncompliant legacy sensors, or with systems and services integrated with current or future wireless communication systems. For example, a new entity may be included into the 1900.6 reference model to integrate with legacy sensing systems (e.g., wireless sensors networks) non-conformant with the 1900.6, and to encourage manufacturers and operators to consider the 1900.6 more closely in their systems’ migration path. | Proposal to adopt legacy sensing hardware with 1900.6 compliant Sensors, DCN 6-11-0030-02-0000 Proposed on Sep. 28, 2011 | Open for contributions
2 | Approved as working item on Sep. 28, 2011 Call for contributions for this working item was issued on Sep. 30, 2011 Apporoved stage-2 contributions DCN 6-0056-01-0000 and DCN 6-0064-01-0000 as solutions to the technical issue | To have further detailed contributions, e.g., use cases, that will motivate IEEE 1900.6 enhancements to provide an (enhanced) standardized interface facilitating detection of distinct wireless signals for, eg., the design of energy aware and/or energy saving wireless systems. | P1900.6a Functional Requirements Green Cognitive Radio, 6-11-21-02-0000, Proposed on Sep. 28, 2011 Local link proximity and channel awareness for energy saving in IEEE 1900.6, 6-11-0039-00-0000, Proposed on Sep. 28, 2011 | Open for contributions IEEE P1900.6a: Enhanced Interface for Green Cognitive Radio, DCN 6-0056-01-0000 presented on Dec. 12 in Scottsdale Connectivity and Proximity Awareness for Energy Saving using 1900.6: Use Cases, DCN 6-0064-01-0000 presented on Dec 14 in Scottsdale Connectivity and Proximity Awareness for Energy Saving using 1900.6; Text Relating to Use Case 1, DCN 6-12-0009-02, presented on Feb 17 11:00 (UTC) telephone conference DCN 6/12/12: “Proposed text contributions to P1900.6a draft standard”, DCN: 6/12/14 “Explanation of proposed text in DCN 6-12-12”, DCN:6/12/16, “Connectivity and Proximity Awareness using 1900.6; Proposal and Text for Use Case 1” presented Mar. 08, 2012 telephone conference
3 | Approved as working item on Oct. 17, 2011 Call for contributions for this working item was issued on Oct. 18, 2011 | The baseline specification may only give guideline to implementers without constraining to follow specific protocols Lack of such protocols may hinder the complete realization of interoperability between different vendors. To cope with this, vendors would relay on their proprietary solutions to fill in the gaps. | Proposal to include spectrum sensing protocol in 1900.6a, DCN 6-11-0037-02-0000, Proposed on Oct. 17, 2011 | Open for contributions Message flow chart for spectrum sensing, control and related information exchange in 1900.6a, DCN 6-11-0057-02-0000, presented on Dec. 13 in Scottsdale
4 | Approved as working item on Oct. 17, 2011 Call for contributions for this working item was issued on Oct. 18, 2011 | New use cases are envisioned in 1900.6a where spectral measurements/spectral utilization-related information would be obtained in order to mount a spectrum map for a large region. GPS is a very diffused technique to obtain “location” and time information provided there is unobstructed line of sight to multiple satellites. How to obtain “location” and time information from sensor/devices that are performing spectral measurements located indoors? | IEEE 1900.6a: Sensor Location Information, DCN 6-11-0043-00-0000, Proposed on Oct. 17, 2011 | Open for contributions IEEE 1900.6a: Sensor Location Information – Direct Input, DCN 6-11-0055-00-0000, proposed on Dec. 1, 2011 Proposal to enhance A-SAP primitives, DCN 6-11-0062-00-000, presented on Dec 12 as complementary doc to DCN 55 IEEE 1900.6a: Sensor Location Information – Direct Input, DCN 6-11-0055-01-0000, proposed on Dec. 13 in Scottsdale
5 | Approved as working item on Nov. 4, 2011 Call for contributions for this working item was issued on Nov. 7, 2011 | The 1900.6a scope includes “specifications for the exchange of sensing related and other relevant data and specifies related interfaces between the data archive and other data sources” However potential external data sources, their relevant contents, and the interfaces/protocols supported by those data sources are not identified. It is important to know the above information in order to develop the specifications to meet the purpose and scope stated by the 1900.6a PAR | P1900.6a: Data sources identification, DCN 6-11-0044-01-0000, Prposed on Nov. 4, 2011 | Open for contributions Data sources identification - Stage 2, DCN 6-11-0058-00-0000 presented on Dec. 14 in Scottsdale
6 | Approved as working item on Nov. 4, 2011 Call for contributions for this working item was issued on Nov. 7, 2011 | The IEEE Std 1900.6-2011 defines the Communication Service Access Point (C-SAP) which abstracts communication mechanisms for use by IEEE 1900.6 service providers and service users through a dedicated set of generic service primitives. However there are different communication mechanisms (e.g. transport layer, network layer, data link layer) which requires further considerations in order to map commands and messages through C-SAP (bidirectional) with each communication system. It is important to map C-SAP with current widely used communication systems in order to develop the protocols between different entities when they are not co-located. The mapping shall be technology-agnostic and shall consider existing or upcoming cognitive radios | P1900.6a: Communication service extension, DCN 6-11-0045-00-0000, Proposed on Nov. 4, 2011 | Open for contributions
7 |  | The current IEEE 1900.6 standards lacks use case for spectrum map. | EE 1900.6a: Spectrum Map, 6-11-0061-00-0000, presented on Dec. 13 in Scottsdale
8 |  | The detection ability needed for SU has a strong relationship with the distance between SU and PU. Normally the shorter the distance is, the lower the detection ability could be, since the primary user is stronger and easier to be detected when SU is closing PU. Add new case(s) related to the dynamic detection ability of SUs. Introduce geo-location entities (such as geo-location database) to CE and define the communication between these entities and sensors | Three-zone division scheme, DCN 6-12-0001-00-0000, Proposed on Jan 30 06:00 (UTC) telephone conference Three zone divison scheme 2nd edition, DCN 6-12-0011-02-0000, Presented on Feb 17 11:00 (UTC) telephone conference.