## Sheet1
N | Commenter | Comment | Response
1 | Sajeev Manikkoth | Use of Word doc will make reviews and edits easier till a base draftis established. | PDF file will be used for review
2 | Sajeev Manikkoth | Reference model to include interfaces to User Equipment (UE), as well as another WS Network | Postpone to next meeting
3 | Sajeev Manikkoth | Section 5.3.3 - Interface with TVWS DB, can it not be PAWS standard protocol, than an implementation specific protocol? | Based on the discussion with 1900.6 WG, this interface should be implementation depended or use, for example, PAWS protocol. Will be further discussed inside 1900.7.
4 | Sajeev Manikkoth | As this standard is for fixed as well as mobile, use of term MS does not look ok. Name can be User Equipment (UE) or user device or something similar | Postpone to next meeting
5 | Sajeev Manikkoth | There were few many whitespace trials at different places. What kind of radio interface layers they were using? Are those in line with this standard or using any competing standards? | Postpone to informational discussion in the next meeting
6 | Sajeev Manikkoth | Attached document is a proposal for multiple simultaneous secondary transmissions in a given location. I would like to have a discussion and feedback from the group on this. | Postpone to next meeting
7 | Stanislav Filin | 1.1 Scope is empty. Shall be taken from PAR. | Assigned to Technical Editor
8 | Stanislav Filin | 1.2 Purpose is empty. Shall be taken from PAR. | Assigned to Technical Editor
9 | Stanislav Filin | 3 Definitions is empty | Postpone to next F2F meeting (March/April 2015)
10 | Stanislav Filin | 4 Abbreviations and acronyms is empty | Request technical editor to update the draft as in 40r0
11 | Stanislav Filin | 5.1 Target frequency bands is empty | Assigned to Ding
12 | Stanislav Filin | 5.2 Network topology is empty | Assigned to Ding
13 | Stanislav Filin | In 5.3.5 why interface with spectrum sensing device is TBD. Are not there is in 1900.6? | Based on the discussion with 1900.6 WG, interface with geolocation device should be implmentation dependend, interface with spectrum sensing device can use 1900.6 interface. Will be further discussed inside 1900.7.
14 | Stanislav Filin | Are 5.3, 5.4, and 5.5 consistent with PHY and MAC? For exmaple, with Figure 4? | Assigned to Dominique 5.4 assigned to Hoang 5.5 assigned to Hoang
15 | Stanislav Filin | 6 Convergence sublayer is empty. | Delete section
16 | Stanislav Filin | 7.5 ARQ and support for H-ARQ is empty | Delete section
17 | Stanislav Filin | 7.6 Procedures to support mobility is empty | Postpone to next F2F meeting (March/April 2015)
18 | Stanislav Filin | 7.7 Power saving procedures is empty | Delete section
19 | Stanislav Filin | 7.8 Support for relay stations is empty | Delete section
20 | Stanislav Filin | 7.9 Measurement procedures is empty | Postpone to next F2F meeting (March/April 2015)
21 | Stanislav Filin | 8 Security sublayer is empty | Delete section
22 | Stanislav Filin | 9.6 Measurements is empty | Postpone to next F2F meeting (March/April 2015)
23 | Stanislav Filin | 9.7 HARQ is empty | Delete section
24 | Stanislav Filin | 9.8 MIMO is empty | Delete section
25 | Stanislav Filin | 9.10 Receiver requiremnts is empty | Delete section
26 | Stanislav Filin | 10 Coginitive plane is empty | Postponed, waiting for contributions
27 | Stanislav Filin | 11 Message encoding is empty | Delete section
28 | Stanislav Filin | 12 MIB is empty | Delete section
29 | Stanislav Filin | Annex A Bibliography is empty | Postpone to next F2F meeting (March/April 2015)