## comments
Comment # | Name | Vote | Category | Page | Subclause | Line | Comment | Must Be Satisfied | Proposed Change | Disposition Status | Disposition Detail
r02-33 | SAJEEV, M K | Approve | Editorial | 43 | 5.1.2.3 | 31 | PLME-SET-TRX-STATE.request primitive overflowing to the new page. | No | Move line 30 and 31 to the next page. | Rejected | All such topics will be addressed during preparation of the draft to publication. Lines and layout will change after track changes are removed.
r02-32 | SAJEEV, M K | Approve | Editorial | 42 | 5.1.2 | 19 | 5.1.2 PHY data service | No | 5.1.2 PHY Management Service | Accepted | Modify as porposed by the commenter.
r02-31 | SAJEEV, M K | Approve | General | 27 | 4.5.1.2 |  | Instead of dummy line, a brief description can be here | No | In the spec where ever empty headings or dummy lines are present add brief description text. | Rejected | Line 16 on page 30 is not "dummy", it has actual technical content. Also, correct type, change "CSMA/CA" to "CSMA-CA".
r02-30 | SAJEEV, M K | Approve | Editorial | 27 | 4.5 |  | This section MAC Functional description can be just after clause 4.1 for better readability | No | Move Section 4.5 as Section 4.2 | Rejected | WG disagrees that the proposed change will improve readability.
r02-29 | SAJEEV, M K | Approve | Editorial | 16 | 4.4.2.2 | 4 | The MLME disassociation primitives define how a device can disassociate. | No | The MLME disassociation primitives define how a device can disassociate from the network. | Accepted | Modify as porposed by the commenter.
r02-28 | SAJEEV, M K | Approve | Editorial | 16 | 4.4.2.1.5 |  | Figure 4 can be at the beginning of message description in Page 13 for better readability | No | Message sequence chart Figure - 4, Figure -5, Figure -8, etc. to be placed before its respective descriptions for better readability | Rejected | WG disagrees that the proposed change will improve readability.
r02-27 | SAJEEV, M K | Approve | General | 13 | 4.4.2.1 |  | Rather than leaving blank sections, brief description about the primitives, and typical sequence for successful operation can be described. | No |  | Rejected | It is not good practice in a standard to give multiple description of the same mechanisms.
r02-26 | SAJEEV, M K | Approve | General | 11 | 4.4.1.1 |  | Figure -3, MAC-DATA.Indication to recipient next layer, does it trigger a response back to MAC layer? | No | Inclusion of recipient next higher layer to recipient MAC message in the message sequence | Revised | Add following sentences to section 4.4.4.1, after figure 3. "When an acknowledgement is requested by the originator MAC, MAC-DATA.confirm primitive is generated upon receipt of the acknowledge message with the appropriated status, otherwise the MAC-DATA.confirm primitive is sent back with status SUCCESS. The recipient MAC generates an acknowledgement (if requested) upon receipt of a valid message from the originator MAC."
r02-25 | SAJEEV, M K | Approve | General | 10 | 4.4 |  | Section 4.4, 4.4.1 - May include brief description text instead of leaving blank headings | No |  | Rejected | It is not good practice in a standard to give multiple description of the same mechanisms.
r02-24 | SAJEEV, M K | Approve | General | 12 | 4 | 16 | Instead of dummy line, a brief description of MAC layer can be here | No |  | Revised | Delete line 16 on page 4.
r02-23 | SAJEEV, M K | Approve | Editorial | 4 | 3 | 4 | Talks about clause 6 and 7, but no such clauses present | No | change the references to the right clause numbers | Revised | Request technical editor to update the references.
r02-22 | SAJEEV, M K | Approve | Editorial | 10 | 2.1 | 3 | "the following terms and definitions apply. "But no such definitions present in the section | No | Include terms and definitions or change the wording. | Revised | Delete the sentence "For the purposes of this document, the following terms and definitions apply."
r02-21 | SAJEEV, M K | Approve | General |  |  |  | Page 9 Scope, Page 7 Introduction and Page 2 Abstract all reads the same text. | No | Slightly different wording based on the heading needed in different sections mentioned. | Rejected | The need to slighly modify wording is not clear. The important point is to deliver consistent technical content.
r02-20 | SAJEEV, M K | Approve | General |  |  |  | PHY and MAC layer descriptions are missing the whitespace and master-slave operation context. Descriptions to improve context connect needed in those sections. Also to improve readability the Overview section can include the different techniques in use. | No |  | Rejected | There are no specific parts of PHY and MAC related excusively to WS and master-slave operations. Rather, all PHY and MAC oparation is designed in the context of WS environment and master-slave topology.
r02-19 | SAJEEV, M K | Approve | Editorial |  |  |  | Page numbers in the 'Contents' does not match with the page numbers of the PDF document, making it difficult to navigate to a page from the content. Table of contents can include 3rd level headings too. | No | Page number sin the PDF doc, and the numbers in the page to be same. Include 3rd levels headings in Table of Contents | Rejected | Page numbers in the document are exactly the same as in the ToC. Please not that they are different from PDF pages, because front matter has separate numbering. Also, ToC is designed as required by the IEEE style manual.
r02-18 | Noguet, Dominique | Disapprove | Editorial | 60 | 5.4.2 | 4 | The cross reference to figure 19 should point to figure 16 | Yes | Replace "Figure 19" by "Figure 16". | Accepted | Modify as porposed by the commenter.
r02-17 | Noguet, Dominique | Disapprove | General | 47 | 5.1.2.1 | 5 | If the primitive has no parameter, semantics shall not be provided (as done for MLME-RESET.request. | No | Replace lines 5 to 7 by " The PLME-CCA.request primitive has no parameter." | Accepted | Modify as porposed by the commenter.
r02-16 | Noguet, Dominique | Disapprove | Editorial | 37 | 4.5.3.1 | 26 | Typo | No | Replace "All devices shall be able to acquire synchronization beacon." by "All devices shall be able to acquire synchronization beacons." | Accepted | Modify as porposed by the commenter.
r02-15 | Noguet, Dominique | Disapprove | Editorial | 30 | 4.5.1.1 | 7 | Add reference to figure 6. | No | Replace "duration is mMASDuration." by "duration is mMASDuration. The timing structure is shown in Figure 6." | Accepted | Modify as porposed by the commenter.
r02-14 | Noguet, Dominique | Disapprove | Editorial | 29 | 4.4.2.8.2 | 4 | Typo | Yes | Replace "MLMESYNC.request" by "MLME-SYNC.request" | Accepted | Modify as porposed by the commenter.
r02-13 | Noguet, Dominique | Disapprove | General | 28 | 4.4.2.8.2 | 15 | Channel is redundant with LbFreq | Yes | Remove "Channel" parameter from Table 27 | Accepted | Modify as porposed by the commenter.
r02-12 | Noguet, Dominique | Disapprove | General | 28 | 4.4.2.8.2 | 8 | Channel is redundant with LbFreq | Yes | Remove "Channel" parameter from semantics | Accepted | Modify as porposed by the commenter.
r02-11 | Noguet, Dominique | Disapprove | General | 27 | 4.4.2.8.1 | 1 | Channel is redundant with LbFreq | Yes | Remove "Channel" parameter from Table 26 | Accepted | Modify as porposed by the commenter.
r02-10 | Noguet, Dominique | Disapprove | General | 27 | 4.4.2.8.1 | 13 | Channel is redundant with LbFreq | Yes | Remove "Channel" parameter from semantics | Accepted | Modify as porposed by the commenter.
r02-9 | Noguet, Dominique | Disapprove | General | 26 | 4.4.2.7.1 | 1 | Channel is redundant with LbFreq | Yes | Remove "Channel" parameter from Table 24 | Accepted | Modify as porposed by the commenter.
r02-8 | Noguet, Dominique | Disapprove | General | 25 | 4.4.2.7.1 | 21 | Channel is redundant with LbFreq | Yes | Remove "Channel" parameter from semantics | Accepted | Modify as porposed by the commenter.
r02-7 | Noguet, Dominique | Disapprove | Technical | 23 | 4.4.2.5.1 | 11 | The width of the channels to be scanned is not clearly defined. It should be 2MHz (the smalest BW the standard can address. Considering US potential WS in the UHF band, the frequency ranges from 470MHz to 698MHz, i.e. 114 channels of 2MHz. 128 bits is compliant with this granularity. 128 bits is also compliant with the size of the ChannelMapMask parameter. | Yes | Replace in table 20 "The 128 bits (b0, b1,... b127) indicate which channels are to be scanned" by "The 128 bits (b0, b1,... b127) indicate which 2MHz channels are to be scanned (1 = scan, 0 = do not scan), starting from the lower bound frequency as defined by the LbFreq parameter." | Accepted | Modify as porposed by the commenter.
r02-6 | Noguet, Dominique | Disapprove | Editorial | 19 | 4.4.2.2.4 | 15 | Reference should be Figure 5 | Yes | Replace "Figure 6" by "Figure 5". | Accepted | Modify as porposed by the commenter.
r02-5 | Noguet, Dominique | Disapprove | General | 5 | 4.2 | 12 | DeviceAddress are 16 or 48 bits | Yes | Replace "64 bit integer" by "16/48 bit integer (see subclause 4.3.2.1.1)" | Accepted | Modify as porposed by the commenter.
r02-4 | Noguet, Dominique | Disapprove | General | 5 | 4.1 | 7 | Clarify network coordinator | No | Replace "(network coordinator)" by "(also referred to as network coordinator hereafter)" | Accepted | Modify as porposed by the commenter.
r02-3 | Noguet, Dominique | Disapprove | Editorial | 4 | 4 | 16 | Clarify part versus clause for consistency. | No | Replace "This part" by "This clause" | Revised | Substitute "This part gives a detailed description of the MAC layer." by "This clause gives a detailed description of the MAC sublayer."
r02-2 | Noguet, Dominique | Disapprove | General | 3 | 2.2 | 21 | WS acronym is not defined | No | Add on line 21 "WS White Space" | Accepted | Modify as porposed by the commenter.
r02-1 | Noguet, Dominique | Disapprove | General | 4 | 3 | 13 | The WS_DB_SAP is not specific to TV WS database and there is no mention of TV WS database anywhere eles in the draft. | No | Replace "provides the interface to a TV WS database" by "provides the interface to a white space (WS) database" | Accepted | Modify as porposed by the commenter.