## Action Items from Nov Workshop
EC-12/03r0 |  | November 2011 IEEE 802 EC Workshop Action Item Register;
AI ID | Who | Due Date | Action Item description | Status | Reported complete
WS11-1 | Kraemer | 2012-01-10 | Get Letter to SC6 posted Prepared an EC ballot with time to post final letter to SC6 Get Input from Edit committee and other EC members
WS11-2 | Rosdahl | 2012-01-31 | Prepare a list of all the Booked and Contracted venues for Plenaries and a list of open dates within the next 5 years.
WS11-3 | Rosdahl | 2012-01-31 | Evaluation of 2014 venues for potential Non-North America venue substitution.
WS11-4 | Rosdahl | 2012-01-31 | Prepare a proposal for a rule change ballot to provide guidance for future regional choice of venues. (Ballots to close with sufficient time to allow the proposal to be presented for final approval in the 802 EC Closing Plenary in March)
WS11-5 | Rosdahl | 2012-01-31 | Prepare a proposal for a rule change ballot to require venue selection be approved by the EC prior to contract signing. (Ballot to close with sufficient time to allow the proposal to be presented for final approval in the 802 EC Closing Plenary in March)
WS11-6 | Gilb | 2012-01-31 | Create a proposed plan for how the e-tools can go into open source.
WS11-7 | Law | 2012-01-31 | Setup a meeting to discuss with the SA–Open Application Interfaces, and Open source.
WS11-8 | Diab | 2012-01-31 | Identify a proces with staff to prioritize and discuss Frame version transitions.
WS11-9 | Sherman | 2012-01-31 | Add to Chair's Guideline an explaination of Tutorial registration requirement: No registration required -- No Fee -- No other WG meetings to be held in parrallel during Monday night Tutorials.
WS11-10 | Nikolich | 2012-01-31 | Work with the SA to reduce the 802 Standards price point
WS11-11 | Diab / Law | 2012-01-31 | Start a dialog with the CAG about updating the SASB operation manual to allow for joint Entity and Individual balloting.
WS11-12 | All WG Chairs | 2012-01-31 | Review attendance rolls and for all affiliations that are obviously not valid, should be reported to the SASB Secretary
WS11-13 | Rosdahl | 2012-01-31 | Add a ticket for IMAT to not use the word "Affiliation" on the main login page -- changing the wording in the instructions (see screenshot from Roger)
WS11-14 | Nikolich | 2012-01-31 | Setup a discussion with SA senior staff to specify the IEEE 802 IEEE-SA Standards Service provider relationship
WS11-15 | Rosdahl | 2012-01-31 | Post report of Tool Error from AI-14-Nov-11
WS11-16 | Rosdahl | 2012-01-31 | Report on Session Expectation Criteria -- Poll WG chairs on the following: Max Session fee tolerance, Min Service expecation, location rotation expectations, Session fee leveling tolerance (some Sessions have surplus, some do not).
WS11-17 | Diab | 2012-01-31 | Create an ADHOC to prepare material for "WG VC to vote during EC meetings in the absense of the WG Chair" for the Feb Telcon and have material ready for March. (Adhoc members: Jon, Rakesh, Roger, Bruce, David and Matthew)
WS11-18 | Gilb | 2012-12-01 | Update the home page for the public vs EC information. Update the initial statement to match the Scope in the P&P.
WS11-19 | Sherman | 2012-01-31 | Prepare proposal for updating the Scope statement in the P&P.
WS11-20 | Kraemer | 2012-01-31 | make a list of what 802 projects and standards that operate above layer 2.
WS11-21 | Jeffree | 2012-01-31 | Internal statement – O&A about what the scope of projects in 802 are – ensure that it is consistent with P&P
WS11-22 | Marks | 2012-01-31 | Adhoc: Prepare a proposal for changing LMSC OM 12.5.2 Compatibility to specify a specific procedural element to that criterion.
WS11-23 | Rosdahl | 2012-03-01 | Report on the status of the EC Workshop Action items.
WS11-24 | Sherman | 2012-01-31 | Prepare a Rule change for clarifying the WG term limitation exemption starting with EC Chair interpertation email.
WS11-25 | Sherman | 2012-01-31 | Prepare a Rule change for clarifying the recirculation requirement following a conditional approval starting with the EC Chair Interpretation email.
WS11-26 | Rosdahl | 2012-01-31 | Identify possible venues that can host the futureWorkshop.