## Action Items from Nov Workshop
EC-12/03r1 |  | November 2011 IEEE 802 EC Workshop Action Item Register;
AI ID | Who | Due Date | Action Item description | Status | Reported complete
WS11-1 | Kraemer | 2012-01-10 | Get Letter to SC6 posted Prepared an EC ballot with time to post final letter to SC6 Get Input from Edit committee and other EC members | Done -- Letter sent to SC6 and posted to 802EC Mentor: https://mentor.ieee.org/802-ec/dcn/12/ec-12-0001-01-00EC-liaison-to-sc6-re-8802-standards.doc
WS11-2 | Rosdahl | 2012-01-31 | Prepare a list of all the Booked and Contracted venues for Plenaries and a list of open dates within the next 5 years. | 2012-2014 Public listing: http://802world.org/plenary/future-plenary-sessions/ See Tab WS11-2
WS11-3 | Rosdahl | 2012-01-31 | Evaluation of 2014 venues for potential Non-North America venue substitution. | Current Assignment is to move one of the currently scheduled 2014 events and schedule Singapore in its place for 2014.
WS11-4 | Rosdahl | 2012-01-31 | Prepare a proposal for a rule change ballot to provide guidance for future regional choice of venues. (Ballots to close with sufficient time to allow the proposal to be presented for final approval in the 802 EC Closing Plenary in March) | due by Friday
WS11-5 | Rosdahl | 2012-01-31 | Prepare a proposal for a rule change ballot to require venue selection be approved by the EC prior to contract signing. (Ballot to close with sufficient time to allow the proposal to be presented for final approval in the 802 EC Closing Plenary in March) | due by Friday
WS11-6 | Gilb | 2012-01-31 | Create a proposed plan for how the e-tools can go into open source. | update to be provided in March plenary
WS11-7 | Law | 2012-01-31 | Setup a meeting to discuss with the SA–Open Application Interfaces, and Open source. | waiting on item WS11-6
WS11-8 | Diab | 2012-01-31 | Identify a proces with staff to prioritize and discuss Frame version transitions. | ad hoc has been initialized in the CAG . will continue until 2 weeks after the SASB March series meetings complete March 29 .
WS11-9 | Sherman | 2012-01-31 | Add to Chair's Guideline an explaination of Tutorial registration requirement: No registration required -- No Fee -- No other WG meetings to be held in parrallel during Monday night Tutorials. | In the Chair's Guide at the end of Section 2.5 add: "Attendance at tutorials is free to tutorial attendees (unless other IEEE 802 meetings are attended). Registration is not required to attend an IEEE 802 Tutorial. Monday evening are reserved for Tutorials, and other IEEE 802 meetings should not be scheduled during tutorial times on Monday nights. "
WS11-10 | Nikolich | 2012-01-31 | Work with the SA to reduce the 802 Standards price point | Announced 2-2-2012 -- 802 Standards available for $5. http://www.standardsinsight.com/ieee_news/802sale2012 | 2012-02-07
WS11-11 | Diab / Law | 2012-01-31 | Start a dialog with the CAG about updating the SASB operation manual to allow for joint Entity and Individual balloting. | Wael has contacted the CAG, and it looks promising, further discussion necessary. Initial Call was held earlier today (2-7-12) Two more calls needed to complete.
WS11-12 | All WG Chairs | 2012-01-31 | Review attendance rolls and for all affiliations that are obviously not valid, should be reported to the SASB Secretary | WG11 pending - WG19 has corrected one.still pending to look at older lists.
WS11-13 | Rosdahl | 2012-01-31 | Add a ticket for IMAT to not use the word "Affiliation" on the main login page -- changing the wording in the instructions (see screenshot from Roger) | IMAT Ticket #1105 -- Expected completion date: May 2012
WS11-14 | Nikolich | 2012-01-31 | Setup a discussion with SA senior staff to specify the IEEE 802 IEEE-SA Standards Service provider relationship | ongoing -- Regular meetings every 6 weeks (Nikolich/McCabe)
WS11-15 | Rosdahl | 2012-01-31 | Post report of Tool Error from AI-14-Nov-11 | Report given: See TAB WS11-15
WS11-16 | Rosdahl | 2012-01-31 | Report on Session Expectation Criteria -- Poll WG chairs on the following: Max Session fee tolerance, Min Service expecation, location rotation expectations, Session fee leveling tolerance (some Sessions have surplus, some do not). | poll to be sent out to the WG chairs on 2-9-2012 -- discuss later if we want to have a WG Membership Poll later.
WS11-17 | Diab | 2012-01-31 | Create an ADHOC to prepare material for "WG VC to vote during EC meetings in the absense of the WG Chair" for the Feb Telcon and have material ready for March. (Adhoc members: Jon, Rakesh, Roger, Bruce, David and Matthew) | Telecon held 30Jan2012: See Tab WS11-17: .Possible new 6.3 in OM: "A WG Chair who is unable to attend a Sponsor voting meeting is eligible to designate, by notification to the Sponsor, a duly confirmed Vice Chair of that WG to act as the voting representative of that WG at that meeting. In the absence of a WG Chair at a Sponsor voting meeting without prior notification, the meeting chair is authorized and encouraged to recognize a duly confirmed Vice Chair of that WG to act as the voting representative of that WG. In either of these cases, if the designated WG represative is a member of the Sponsor in a standing capacity, that individual is ineligible to vote in that standing capacity. The requirements of 6.2 shall apply to the designated WG representative."
WS11-18 | Gilb | 2012-12-01 | Update the home page for the public vs EC information. Update the initial statement to match the Scope in the P&P. | Need to review intent from workshop minutes. Is this about public vs private information or providing a better website for use by the general public?
WS11-19 | Sherman | 2012-01-31 | Prepare proposal for updating the Scope statement in the P&P. | Replace the content of P&P section 1.1 with: "The scope of the LMSC is to develop and maintain standards and recommended practices for local, metropolitan, and other area networks, using an open and accredited process, and to advocate them on a global basis. It's technical scope is intended to be flexible and is ultimately determined by the sum of it's approved PARs."
WS11-20 | Kraemer | 2012-01-31 | make a list of what 802 projects and standards that operate above layer 2. | More difficult and controversial than expected. Needs more discussion time in Waikoloa. Candidates include 802.21, 802.1X (management plane comprehends layer 3),others?
WS11-21 | Jeffree | 2012-01-31 | Internal statement – O&A about what the scope of projects in 802 are – ensure that it is consistent with P&P
WS11-22 | Marks | 2012-01-31 | Adhoc: Prepare a proposal for changing LMSC OM 12.5.2 Compatibility to specify a specific procedural element to that criterion. | See Tab WS11-22
WS11-23 | Rosdahl | 2012-03-01 | Report on the status of the EC Workshop Action items. | Action item file posted to 802EC Mentor: see doc ec-12/3r1 for updated status.
WS11-24 | Sherman | 2012-01-31 | Prepare a Rule change for clarifying the WG term limitation exemption starting with EC Chair interpertation email. | Paul's rulling: If a WG/TAG chair or vice-chair has served 5 or more full or partial terms they shall obtain >75% approval of the WG/TAG at the NOV plenary session in order to stand for election in the MAR plenary session. In the WG P&P Clause 9.3 replace "e) Permit officer to run for election who has held the office for five (5) or more partial terms" with "e) Permit an officer to run for election who has held the office for five (5) or more full or partial terms. Any full or partial terms for a given office count towards this requirement even if not held consecutively. Permission to run should be sought at the plenary session prior to the session when the election will be held."
WS11-25 | Sherman | 2012-01-31 | Prepare a Rule change for clarifying the recirculation requirement following a conditional approval starting with the EC Chair Interpretation email. | See Tab WS11-25
WS11-26 | Rosdahl | 2012-01-31 | Identify possible venues that can host the future Workshop. | Target is Nov 2013 Dallas We have possible sites of Dallas, Atanta and San Antonio. So we could hold a workshop each year instead of every second year. The topic of how often will be added to the March EC agenda for discussion.
WS11-27 | Law | 2012-03-01 | Actually from Nov 2012 Closing Plenary: Univerisity Outreach: how can we encourage participation in Standards activities by University students? | Draft recommendation is being prepared for circulation. (2 AdHoc Calls have been held). Fee waivers for Get802 have been acknowledged, need to ensure contracted participant fees from meeting planners and network providers do not include them.

## WS11-2
IEEE 802 Plenary Meeting Contract Tracker
Year | Month | Session START | Session END | Session Type | IEEE Region | Host ? YES/NO | Host Name | Country | City | State / Province | Event Venue | Meeting Planner Contract Status | Notes/Comments | Document Updated | IEEE contract #
2012 | March | 11 | 16 | Plenary | Asia & Pacific | NO |  | USA | Waikoloa | Hawaii | Hilton Waikoloa Village | Confirmed |  |  | n/a
2012 | July | 15 | 20 | Plenary | North America | NO |  | USA | San Diego | California | Manchester Grand Hyatt | Confirmed |  |  | n/a
2012 | November | 11 | 16 | Plenary | North America | NO |  | USA | San Antonio | Texas | Grand Hyatt San Antonio | Confirmed |  |  | n/a
2013 | March | 17 | 22 | Plenary | North America | NO |  | USA | Orlando | Florida | Caribe Royale Resort | Confirmed |  |  | # 09-4250-13
2013 | July | 14 | 19 | Plenary | Europe | NO |  | SWITZERLAND | Geneva |  | ITU | Contract Pending | MOU in development stage, SWAG Budget due February 3, 2012
2013 | November | 10 | 15 | Plenary | North America | NO |  | USA | Dallas | Texas | Hyatt Regency Dallas | Confirmed |  |  | # 09-4217-13
2014 | March | 16 | 21 | Plenary | North America | NO |  | USA | Atlanta | Georgia | Hyatt Regency Atlanta | Confirmed |  |  | n/a
2014 | July | 13 | 18 | Plenary | North America | NO |  | USA | San Diego | California | Manchester Grand Hyatt | Confirmed |  |  | n/a
2014 | November | 2 | 7 | Plenary | North America | NO |  | USA | San Antonio | Texas | Grand Hyatt San Antonio | Confirmed |  |  | # 09-4219-14
2014 | TBD - M/J/N ? |  |  | Plenary | Asia/Pacific | Yes |  | Singapore | Singapore |  |  | Tenative
2015 | March |  |  | Plenary
2015 | July |  |  | Plenary
2015 | November |  |  | Plenary | North America | NO |  | USA | Dallas | Texas | Hyatt Regency Dallas |  |  |  | # 09-4218-15
2016 | March |  |  | Plenary
2016 | July |  |  | Plenary
2016 | November | 3 | 15 | Plenary | North America | NO |  | USA | San Antonio | Texas | Grand Hyatt San Antonio |  |  |  | # 09-4220-16
2017 | March
2017 | July
2017 | November
Note on B15: jr05: An Effort is being made to find if one of the confirmed 2014 venues that can be moved to 2015 to allow a Non-North America venue.

## WS11-15
Summary:
========
A security patch applied to an apache web server instance on 9
Nov 2011 caused a service outage to several IEEE-SA applications,
including IMAT. The outage lasted approximately 2.5 hours,
between 04:00 and 06:35 EST.
Technical details and remediation steps follow.
Details:
========
At 10:10 AM on 9 Nov, a patch from the OpenSuSE
repository for apache was downloaded and applied, apparently
successfully:
/var/log/zypp/history:
2011-11-09 10:10:23 apache2-2.2.12-1.18.1.x86_64.rpm installed ok
The patch contained several security bugfixes:
http://www.apache.org/dist/httpd/CHANGES_2.2
At 04:00 on 10 Nov, the apache server was restarted.
At 04:00:02, a problem is noted in the error_log:
httpd2-prefork: Syntax error on line 144 of /web/conf/httpd.conf: Syntax error on line 37 of /web/conf/sysconfig.d/loadmodule.conf: Cannot load /usr/lib64/apache2-prefork/mod_include.so into server: /usr/lib64/apache2-prefork/mod_include.so: undefined symbol: ap_escape_html2
At 04:00:04 a failed request to this server was the first public
indication of a problem, noted in the upstream server weblog:
mentor.ieee.org $ANONYMIZED_SOURCE_IP - - [10/Nov/2011:04:00:04 -0500] "GET /802.11/dcn/07/11-07-2454-01-000s-performance-evaluation-of-express-forwarding-for-a-single-channel-mesh.ppt HTTP/1.0" 503 - " http://www.google.co.jp/search?q=express+forwarding+in+multi-hop+wireless+802.11-07-2454r1&hl=ja&lr=&gbv=2&gs_sm=e&gs_upl=5922l9391l0l9828l8l8l0l7l0l0l62l62l1l1l0&oq=express+forwarding+in+multi-hop+wireless+802.11-07-2454r1&aq=f&aqi=&aql= " "Mozilla/4.0 (compatible; MSIE 6.0; Windows NT 5.1; SV1; i-NavFourF; InfoPath.1; .NET CLR 1.1.4322)"
(Files in our front-end cache were requested/served
successfully after 04:00, but the majority of requests failed
until the web server was back up and running.)
Nagios triggered an alert at 05:00, and members of the tech team
were receiving them by 05:04.
This was an unusual issue, and it took a little while to debug
and fix. Service was restored and document requests were
successfully served out at 06:35:41:
mentor.ieee.org $ANONYMIZED_SOURCE_IP - - [10/Nov/2011:06:35:41 -0500] "GET /802.15/dcn/09/15-09-0518-00-0000-smart-grid-802.ppt HTTP/1.1" 200 1051387 "-" "Mozilla/5.0 (compatible; bingbot/2.0; +http://www.bing.com/bingbot.htm)"
Remediation:
============
We regret the disruption in service and have made (or are
making) several changes as a result:
- Changing the periodicity of monitoring checks.
- Discussing how automated patching can bite and how to avoid it.
- Looking for additional sysadmin resources.
Walter

## WS11-22
Marks 12/01/31 Adhoc: Prepare a proposal for changing LMSC OM 12.5.2 Compatibility to specify a specific procedural element to that criterion.
Tony has joined the ad hoc group. He and I are proposing the following change:
--------------
Current:
12.5.2 Compatibility
IEEE 802 LMSC defines a family of standards. All standards should be in conformance with the IEEE 802.1 Architecture, Management, and Interworking documents as follows: IEEE 802.1 Overview and Architecture, IEEE 802.1D, IEEE 802.1Q, and parts of IEEE 802.1F. If any variances in conformance emerge, they shall be thoroughly disclosed and reviewed with IEEE 802.1.
Each standard in the IEEE 802 LMSC family of standards shall include a definition of managed objects that are compatible with systems management standards.
Proposed:
12.5.2 Compatibility
IEEE 802 LMSC defines a family of standards. All standards should be in conformance with IEEE Std 802, IEEE Std 802.1D, and IEEE Std 802.1Q. If any variances in conformance emerge, they shall be thoroughly disclosed and reviewed with the IEEE 802.1 Working Group.
In order to demonstrate compatibility with this criterion, the Five Criteria statement must answer the following questions:
*Does the PAR mandate that the standard will comply with IEEE Std 802, IEEE Std 802.1D, and IEEE Std 802.1Q?
*If not, how will the Working Group ensure that the resulting draft standard is compliant or, if not, receives appropriate review from the IEEE 802.1 Working Group?
--------------
Please let me know if you have comments or would like to participate in followup email discussions. Write to Tony and me; I don't see a need to copy everyone at this time. I'll make sure we get something ready by the deadline so the EC has an opportunity, at the Feb telecon, to decide to open a rules change ballot.
Roger

## WS11-25
Proposed changes to the IEEE 802 LMSC OM:
Clarification to recirculation requirements following Conditional approval:
In Clause 14 replace:
"Seeking conditional approval is only appropriate when ballot resolution efforts have been substantially completed and the approval ratio is sufficient. The conditional approval expires at the opening of the next plenary."
With:
"Seeking conditional approval is only appropriate when ballot resolution efforts have been substantially completed and the approval ratio is sufficient. "Substantially complete" is when in the judgment of the WG Chair there is a very low likelihood of receiving valid new Disapprove comment(s)/vote(s) upon the next recirculation ballot. If a new valid disapprove comment/vote is received as a result of the recirculation ballot in process (or pending) at the time of conditional approval, the WG Chair may issue one subsequent recirculation ballot in an attempt to meet the conditional approval conditions. If the conditions are not met by the subsequent recirculation ballot, the conditional approval terminates. Otherwise the conditional approval expires at the opening of the next plenary. "