## Action Items from Nov Workshop
EC-12/03r4 |  | November 2011 IEEE 802 EC Workshop Action Item Register;
AI ID | Who | Due Date | Action Item description | Status | Reported complete
WS11-1 | Kraemer | 2012-01-10 | Get Letter to SC6 posted Prepared an EC ballot with time to post final letter to SC6 Get Input from Edit committee and other EC members | Done -- Letter sent to SC6 and posted to 802EC Mentor: https://mentor.ieee.org/802-ec/dcn/12/ec-12-0001-01-00EC-liaison-to-sc6-re-8802-standards.doc | 2012-02-07
WS11-2 | Rosdahl | 2012-01-31 | Prepare a list of all the Booked and Contracted venues for Plenaries and a list of open dates within the next 5 years. | 2012-2014 Public listing: http://802world.org/plenary/future-plenary-sessions/ See Tab WS11-2 for all known venue schedules. Updated during the March 2012 plenary -- Published Public Schedule to be updated after the Plenary | 2012-03-16
WS11-3 | Rosdahl | 2012-01-31 | Evaluation of 2014 venues for potential Non-North America venue substitution. | Current Assignment is to move one of the currently scheduled 2014 events and schedule Singapore in its place for 2014. The Proposed Non-NA Venue for 2014 is not available, Booked Singapore for March 2015. | 2012-03-16
WS11-4 | Rosdahl | 2012-01-31 | Prepare a proposal for a rule change ballot to provide guidance for future regional choice of venues. (Ballots to close with sufficient time to allow the proposal to be presented for final approval in the 802 EC Closing Plenary in March) | OM - Add new clause 5.1.1.2 IEEE 802 LMSC Plenary Venue selection The IEEE 802 LMSC Executive Secretary presents proposed plenary venues to the Sponsor. Venue selection shall consist of venues located in various locations around the world. Each year there shall be at least one venue location that is outside the United States and North American continent. Venue selection shall be consistent with the changing needs of IEEE 802 membership. The location, date, and fees for each plenary session require the approval of the Sponsor prior to signing contracts on behalf of the IEEE 802 LMSC.” See Doc: 802 EC-12/0008r1 for final proposed text | 2012-03-16
WS11-5 | Rosdahl | 2012-01-31 | Prepare a proposal for a rule change ballot to require venue selection be approved by the EC prior to contract signing. (Ballot to close with sufficient time to allow the proposal to be presented for final approval in the 802 EC Closing Plenary in March) | Change LMSC P&P 3.4.5 c) From “c) Present summaries of venue options to the Sponsor, select venues under oversight of the Sponsor, and sign approved proposals on behalf of 802 “ To “c) Present summaries of venue options to the Sponsor, select venues with approval of the Sponsor, and sign approved proposals on behalf of 802. See Doc: 802 EC-12/0008r1 for final proposed text | 2012-03-16
WS11-6 | Gilb | 2012-01-31 | Create a proposed plan for how the e-tools can go into open source. | update to be provided in March plenary
WS11-7 | Law | 2012-01-31 | Setup a meeting to discuss with the SA–Open Application Interfaces, and Open source. | waiting on item WS11-6
WS11-8 | Diab | 2012-01-31 | Identify a process with staff to prioritize and discuss Frame version transitions. | ad hoc has been initialized in the CAG . will continue until 2 weeks after the SASB March series meetings complete March 29 . 2012-03-29: Wael met with some of the editorial team the week of March 26 to close out the last AI he had from the EC workshop. The action related to identifying a process for Frame Maker upgrades. While the staff are very helpful in accepting files in different versions, conversions, and associated issues / level of confidence with that, can be an issue at the front end or back end of the process (e.g. receiving files when there is a version mismatch). The process we agreed to was that Kim and her team would reach out to 802 a quarter prior to when they are thinking to go for an upgrade and solicit our comments / inputs which they would consider in their decision making process. From my perspective, that seems like a good process and resolves the AI. In addition, as an informational item they informed us that they will be moving to FM v. 10 in the next few weeks. This is a welcome upgrade as FM v 9 was not supported for long by Adobe and in fact our editors cannot purchase 9 as Adobe will send v 10 instead. Finally, the staff editorial team will still accept Frame Maker 8 and 9 until they advise differently and that they will not cease accepting or working in a particular version of any software without significant notice (e.g., minimum of 6 months). Regards, Wael P.S. As Adrian was in the SASB series, I asked him to join our discussion. Note that .1 and .3 rely solely on FM while .11 has produced documents in different tools including FM | 2012-03-29
WS11-9 | Sherman | 2012-01-31 | Add to Chair's Guideline an explaination of Tutorial registration requirement: No registration required -- No Fee -- No other WG meetings to be held in parrallel during Monday night Tutorials. | In the Chair's Guide at the end of Section 2.5 add: "Attendance at tutorials is free to tutorial attendees (unless other IEEE 802 meetings are attended). Registration is not required to attend an IEEE 802 Tutorial. Monday evening are reserved for Tutorials, and other IEEE 802 meetings should not be scheduled during tutorial times on Monday nights. " See Doc: 802 EC-12/0005r3 | 2012-03-16
WS11-10 | Nikolich | 2012-01-31 | Work with the SA to reduce the 802 Standards price point | Announced 2-2-2012 -- 802 Standards available for $5. http://www.standardsinsight.com/ieee_news/802sale2012 | 2012-02-07
WS11-11 | Diab / Law | 2012-01-31 | Start a dialog with the CAG about updating the SASB operation manual to allow for joint Entity and Individual balloting. | Wael has contacted the CAG, and it looks promising, further discussion necessary. Initial Call was held earlier today (2-7-12) Two more calls needed to complete. | 2012-02-07
WS11-12 | All WG Chairs | 2012-01-31 | Review attendance rolls and for all affiliations that are obviously not valid, should be reported to the SASB Secretary | WG11 pending - WG19 has corrected one.still pending to look at older lists. WG1 - Tony reviews these regularly when I update my membership lists.
WS11-13 | Rosdahl | 2012-01-31 | Add a ticket for IMAT to not use the word "Working Group Affiliation" on the main login page -- changing the wording in the instructions (see screenshot from Roger) | IMAT Ticket #1105 -- Expected completion date: March 2012 See Tab WS11-13. | 2012-02-07
WS11-14 | Nikolich | 2012-01-31 | Setup a discussion with SA senior staff to specify the IEEE 802 IEEE-SA Standards Service provider relationship | ongoing -- Regular meetings every 6 weeks (Nikolich/McCabe) | 2012-02-07
WS11-15 | Rosdahl | 2012-01-31 | Post report of Tool Error from AI-14-Nov-11 | Report given: See TAB WS11-15 | 2012-02-07
WS11-16 | Rosdahl | 2012-01-31 | Report on Session Expectation Criteria -- Poll WG chairs on the following: Max Session fee tolerance, Min Service expecation, location rotation expectations, Session fee leveling tolerance (some Sessions have surplus, some do not). | 2 Polls were open from Feb 10-17 for the WG chairs to respond An agenda item to discuss the results will be made for the March Plenary. -- The EC may discuss if we want to have a WG Membership Poll later. Opening EC Meeting a request to issue a poll to the membership. Closed noon 16 March -- See report: 802 EC Doc: | 2012-03-16
WS11-17 | Diab | 2012-01-31 | Create an ADHOC to prepare material for "WG VC to vote during EC meetings in the absense of the WG Chair" for the Feb Telcon and have material ready for March. (Adhoc members: Jon, Rakesh, Roger, Bruce, David and Matthew) | Telecon held 30Jan2012: See Tab WS11-17: .Possible new 6.3 in OM: "A WG Chair who is unable to attend a Sponsor voting meeting is eligible to designate, by notification to the Sponsor, a duly confirmed Vice Chair of that WG to act as the voting representative of that WG at that meeting. In the absence of a WG Chair at a Sponsor voting meeting without prior notification, the meeting chair is authorized and encouraged to recognize a duly confirmed Vice Chair of that WG to act as the voting representative of that WG. In either of these cases, if the designated WG represative is a member of the Sponsor in a standing capacity, that individual is ineligible to vote in that standing capacity. The requirements of 6.2 shall apply to the designated WG representative." See Doc: 802 EC-12/0008r1 for final proposed text | 2012-03-16
WS11-18 | Gilb | 2012-12-01 | Update the home page for the public vs EC information. Update the initial statement to match the Scope in the P&P. | Feb-7-2012: Need to review intent from workshop minutes. Is this about public vs private information or providing a better website for use by the general public?
WS11-19 | Sherman | 2012-01-31 | Prepare proposal for updating the Scope statement in the P&P. | Replace the content of P&P section 1.1 with: "The scope of the LMSC is to develop and maintain standards and recommended practices for local, metropolitan, and other area networks, using an open and accredited process, and to advocate them on a global basis. It's technical scope is intended to be flexible and is ultimately determined by the sum of it's approved PARs." See Doc: 802 EC-12/0005r3 for final version. | 2012-03-16
WS11-20 | Kraemer | 2012-01-31 | make a list of what 802 projects and standards that operate above layer 2. | More difficult and controversial than expected. Needs more discussion time in Waikoloa. Candidates include 802.21, 802.1X (management plane comprehends layer 3),others?
WS11-21 | Jeffree | 2012-01-31 | Internal statement – O&A about what the scope of projects in 802 are – ensure that it is consistent with P&P | The O&A is in the Letter Ballot Process - Comments to resolve this item should come from that process. This item is resolved by the Sponsor LB process | 2012-03-29
WS11-22 | Marks | 2012-01-31 | Adhoc: Prepare a proposal for changing LMSC OM 12.5.2 Compatibility to specify a specific procedural element to that criterion. | See Tab WS11-22 See Doc: 802 EC-12/0008r1 for final proposed text | 2012-03-16
WS11-23 | Rosdahl | 2012-03-01 | Report on the status of the EC Workshop Action items. | Action item file posted to 802EC Mentor: see doc ec-12/3r1 for updated status. | 2/7/2012; 3/12/2012 3/16/2012
WS11-24 | Sherman | 2012-01-31 | Prepare a Rule change for clarifying the WG term limitation exemption starting with EC Chair interpertation email. | Paul's rulling: If a WG/TAG chair or vice-chair has served 5 or more full or partial terms they shall obtain >75% approval of the WG/TAG at the NOV plenary session in order to stand for election in the MAR plenary session. In the WG P&P Clause 9.3 replace "e) Permit officer to run for election who has held the office for five (5) or more partial terms" with "e) Permit an officer to run for election who has held the office for five (5) or more full or partial terms. Any full or partial terms for a given office count towards this requirement even if not held consecutively. Permission to run should be sought at the plenary session prior to the session when the election will be held." See Doc: 802 EC-12/0005r3 for final proposed text | 2012-03-16
WS11-25 | Sherman | 2012-01-31 | Prepare a Rule change for clarifying the recirculation requirement following a conditional approval starting with the EC Chair Interpretation email. | See Tab WS11-25 See Doc: 802 EC-12/0005r3 for final proposed text | 2012-03-16
WS11-26 | Rosdahl | 2012-01-31 | Identify possible venues that can host the future Workshop. | Target is Nov 2013 Dallas We have possible sites of Dallas, Atanta and San Antonio. So we could hold a workshop each year instead of every second year. The topic of how often will be added to the March EC agenda for discussion. | 2012-03-16
WS11-27 | Law | 2012-03-01 | Actually from Nov 2012 Closing Plenary: Univerisity Outreach: how can we encourage participation in Standards activities by University students? | Draft recommendation is being prepared for circulation. (2 AdHoc Calls have been held). Fee waivers for Get802 have been acknowledged, need to ensure contracted participant fees from meeting planners and network providers do not include them. Motion to approve done 3-12-2012 | 2012-03-12

## WS11-2
IEEE 802 Plenary Meeting Contract Tracker
Year | Month | Session START | Session END | Session Type | IEEE Region | Host ? YES/NO | Host Name | Country | City | State / Province | Event Venue | Meeting Planner Contract Status | Notes/Comments | Document Updated | IEEE contract # | Workshop capable | IETF offset
2012 | March | 11 | 16 | Plenary | Asia & Pacific | NO |  | USA | Waikoloa | Hawaii | Hilton Waikoloa Village | Confirmed |  |  | n/a |  | +2
2012 | July | 15 | 20 | Plenary | North America | NO |  | USA | San Diego | California | Manchester Grand Hyatt | Confirmed |  |  | n/a |  | +2
2012 | November | 11 | 16 | Plenary | North America | NO |  | USA | San Antonio | Texas | Grand Hyatt San Antonio | Confirmed |  |  | n/a |  | -1
2013 | March | 17 | 22 | Plenary | North America | NO |  | USA | Orlando | Florida | Caribe Royale Resort | Confirmed |  |  | # 09-4250-13 |  | -1
2013 | July | 14 | 19 | Plenary | Europe | NO |  | SWITZERLAND | Geneva |  | ITU | Contract Pending | MOU in development stage, SWAG Budget due February 3, 2012 |  |  |  | +2
2013 | November | 10 | 15 | Plenary | North America | NO |  | USA | Dallas | Texas | Hyatt Regency Dallas | Confirmed |  |  | # 09-4217-13 | Yes | -1
2014 | March | 16 | 21 | Plenary | North America | NO |  | USA | Atlanta | Georgia | Hyatt Regency Atlanta | Confirmed |  |  |  | Yes | -2
2014 | July | 13 | 18 | Plenary | North America | NO |  | USA | San Diego | California | Manchester Grand Hyatt | Confirmed |  |  | n/a |  | +1
2014 | November | 2 | 7 | Plenary | North America | NO |  | USA | San Antonio | Texas | Grand Hyatt San Antonio | Confirmed |  |  | # 09-4219-14 | Yes | +1
2015 | March | 8 | 13 | Plenary |  |  |  |  | Singapore | Singapore | Marina Bays Sands Hotel | Hotel property reserved | Hotel was not available March 2014, took next availability March 2015 |  |  |  | +2
2015 | July | 12 | 17 | Plenary |  |  |  |  | Kona | Hawaii | Hilton Waikoloa Village | [5 empty] | +1
2015 | November | 8 | 13 | Plenary | North America | NO |  | USA | Dallas | Texas | Hyatt Regency Dallas |  |  |  | # 09-4218-15 |  | -1
2016 | March | 13 | 18 | Plenary | North America | NO |  | USA | Atlanta | Georgia | Hyatt Regency Atlanta |  |  |  | n/a |  | +2
2016 | July | 24 | 29 | Plenary |  |  |  |  | San Diego | California | Manchester Grand Hyatt | [5 empty] | -1
2016 | November | 3 | 15 | Plenary | North America | NO |  | USA | San Antonio | Texas | Grand Hyatt San Antonio |  |  |  | # 09-4220-16 | Yes | +1
2017 | March | 12 | 17 | [13 empty] | +2
2017 | July | 9 | 14 | Plenary |  |  |  |  | Kona | Hawaii | Hilton Waikoloa Village | [5 empty] | +1
2017 | November | 5 | 10 | [13 empty] | +1
2018 | March
2018 | July | 8 | 13 | Plenary |  |  |  |  | San Diego | California | Manchester Grand Hyatt
2018 | November

## WS11-13
With regard to the comment from Roger:
So the term "Working Group" was removed from the page?
Working Group Affiliation
You do not currently have an affiliation declared for this working group. Please enter your affiliation for
"WG802.16" and click on "Submit" at the bottom of the page.
This can be done immediately.
In addition the training slides changed to point to the more recent location. This was ticket #1105
On the login page there is a "click here" that opens an old presentation. This needs to be updated.
https://seabass.ieee.org/imat/static/files/imat.pdf
The new pointer is now at:
https://mentor.ieee.org/etools_documentation/dcn/11/etools_documentation-11-0011-IMAT-imat-overview.ppt

## WS11-15
Summary:
========
A security patch applied to an apache web server instance on 9
Nov 2011 caused a service outage to several IEEE-SA applications,
including IMAT. The outage lasted approximately 2.5 hours,
between 04:00 and 06:35 EST.
Technical details and remediation steps follow.
Details:
========
At 10:10 AM on 9 Nov, a patch from the OpenSuSE
repository for apache was downloaded and applied, apparently
successfully:
/var/log/zypp/history:
2011-11-09 10:10:23 apache2-2.2.12-1.18.1.x86_64.rpm installed ok
The patch contained several security bugfixes:
http://www.apache.org/dist/httpd/CHANGES_2.2
At 04:00 on 10 Nov, the apache server was restarted.
At 04:00:02, a problem is noted in the error_log:
httpd2-prefork: Syntax error on line 144 of /web/conf/httpd.conf: Syntax error on line 37 of /web/conf/sysconfig.d/loadmodule.conf: Cannot load /usr/lib64/apache2-prefork/mod_include.so into server: /usr/lib64/apache2-prefork/mod_include.so: undefined symbol: ap_escape_html2
At 04:00:04 a failed request to this server was the first public
indication of a problem, noted in the upstream server weblog:
mentor.ieee.org $ANONYMIZED_SOURCE_IP - - [10/Nov/2011:04:00:04 -0500] "GET /802.11/dcn/07/11-07-2454-01-000s-performance-evaluation-of-express-forwarding-for-a-single-channel-mesh.ppt HTTP/1.0" 503 - " http://www.google.co.jp/search?q=express+forwarding+in+multi-hop+wireless+802.11-07-2454r1&hl=ja&lr=&gbv=2&gs_sm=e&gs_upl=5922l9391l0l9828l8l8l0l7l0l0l62l62l1l1l0&oq=express+forwarding+in+multi-hop+wireless+802.11-07-2454r1&aq=f&aqi=&aql= " "Mozilla/4.0 (compatible; MSIE 6.0; Windows NT 5.1; SV1; i-NavFourF; InfoPath.1; .NET CLR 1.1.4322)"
(Files in our front-end cache were requested/served
successfully after 04:00, but the majority of requests failed
until the web server was back up and running.)
Nagios triggered an alert at 05:00, and members of the tech team
were receiving them by 05:04.
This was an unusual issue, and it took a little while to debug
and fix. Service was restored and document requests were
successfully served out at 06:35:41:
mentor.ieee.org $ANONYMIZED_SOURCE_IP - - [10/Nov/2011:06:35:41 -0500] "GET /802.15/dcn/09/15-09-0518-00-0000-smart-grid-802.ppt HTTP/1.1" 200 1051387 "-" "Mozilla/5.0 (compatible; bingbot/2.0; +http://www.bing.com/bingbot.htm)"
Remediation:
============
We regret the disruption in service and have made (or are
making) several changes as a result:
- Changing the periodicity of monitoring checks.
- Discussing how automated patching can bite and how to avoid it.
- Looking for additional sysadmin resources.
Walter

## WS11-22
Marks 12/01/31 Adhoc: Prepare a proposal for changing LMSC OM 12.5.2 Compatibility to specify a specific procedural element to that criterion.
Tony has joined the ad hoc group. He and I are proposing the following change:
--------------
Current:
12.5.2 Compatibility
IEEE 802 LMSC defines a family of standards. All standards should be in conformance with the IEEE 802.1 Architecture, Management, and Interworking documents as follows: IEEE 802.1 Overview and Architecture, IEEE 802.1D, IEEE 802.1Q, and parts of IEEE 802.1F. If any variances in conformance emerge, they shall be thoroughly disclosed and reviewed with IEEE 802.1.
Each standard in the IEEE 802 LMSC family of standards shall include a definition of managed objects that are compatible with systems management standards.
Proposed:
12.5.2 Compatibility
IEEE 802 LMSC defines a family of standards. All standards should be in conformance with IEEE Std 802, IEEE Std 802.1D, and IEEE Std 802.1Q. If any variances in conformance emerge, they shall be thoroughly disclosed and reviewed with the IEEE 802.1 Working Group.
In order to demonstrate compatibility with this criterion, the Five Criteria statement must answer the following questions:
*Does the PAR mandate that the standard will comply with IEEE Std 802, IEEE Std 802.1D, and IEEE Std 802.1Q?
*If not, how will the Working Group ensure that the resulting draft standard is compliant or, if not, receives appropriate review from the IEEE 802.1 Working Group?
--------------
Please let me know if you have comments or would like to participate in followup email discussions. Write to Tony and me; I don't see a need to copy everyone at this time. I'll make sure we get something ready by the deadline so the EC has an opportunity, at the Feb telecon, to decide to open a rules change ballot.
Roger

## WS11-25
Proposed changes to the IEEE 802 LMSC OM:
Clarification to recirculation requirements following Conditional approval:
In Clause 14 replace:
"Seeking conditional approval is only appropriate when ballot resolution efforts have been substantially completed and the approval ratio is sufficient. The conditional approval expires at the opening of the next plenary."
With:
"Seeking conditional approval is only appropriate when ballot resolution efforts have been substantially completed and the approval ratio is sufficient. "Substantially complete" is when in the judgment of the WG Chair there is a very low likelihood of receiving valid new Disapprove comment(s)/vote(s) upon the next recirculation ballot. If a new valid disapprove comment/vote is received as a result of the recirculation ballot in process (or pending) at the time of conditional approval, the WG Chair may issue one subsequent recirculation ballot in an attempt to meet the conditional approval conditions. If the conditions are not met by the subsequent recirculation ballot, the conditional approval terminates. Otherwise the conditional approval expires at the opening of the next plenary. "
A working group chair may seek conditional approval when ballot resolution efforts have been substantially completed and the approval ratio is sufficient.

## JUL09 EC WorkshoAction Register
July 2009 IEEE 802 EC Workshop Action Register revision 1.5
Revision | 1.20 | by Paul Nikolich on 16NOV2009
Revision | 1.3 | by Paul Nikolich on 14MAR2010
Revision | 1.4 | by Paul Nikolich on 28MAY2010
Revision | 1.5 | by Paul Nikolich on 05NOV2010--minor updates
Index | Area | Current Task List | Prime/sub | Status
1 | 802 Architecture | WG/TAG Chairs to announce to their members Revision of IEEE Std 802-2001 Overview and Architecure is in 802.1 WG ballot | EC WG/TAG chairs | completed @ NOV09 opening EC mtg
2 | 802 Architecture | IEEE Std 802 to be an EC ballot | Nikolich/Jeffree | EC ballot starts after next draft is available, likely March 2010
3 | 802 Architecture | Emphasize that conformance to 802 O&A is part of the evaluation criteria by the EC in approving a PAR and that the text in the O&A be an effective tool – Nikolich, EC | Nikolich/EC | completed @ NOV09 opening EC mtg
4 | 802 Architecture | Post the revision document to the web page | Jeffree | ?
6 | 802 Architecture | EC seeks qualified editor who has support for the project | Nikolich/EC | completed @ NOV09 opening EC mtg--James Gilb accepted
7 | 802 Architecture | EC seeks qualified, supported chair of O&A project from 802 wide | Nikolich/EC | completed @ NOV09 opening EC mtg--James Gilb accepted
8 | Disparaties in WG practice for common problems | Update 802 P&P to use "return" instead of "voting members", explicitly call out that abstains count towards the 50% return, align terminology with SA P&P and OM (as determined by Rosdahl) (5.4.3.1) – Rosdahl (in Nov. ballot document)? | Rosdahl | to be implemented at NOV09 Plenary Session
9 | Disparaties in WG practice for common problems | Define recusal rate for EC OM | Rosdahl | ?
10 | Disparaties in WG practice for common problems | List of WG participants list in the front matter of the published standard is determined by WG chair, use correct terminology to describe the list, (Law to emphasize to project editing staff). EC doesn't have a strong preference (one suggestion: list of voters in the ballot pool when the WG ballot started) | Law, WG chairs | ?
11 | Disparaties in WG practice for common problems | If draft has passed Sponsor ballot and WG refuses to ask the Sponsor forward to RevCom, then the WG chair may bring the issue to the EC. Materially interested parties can file an appeal to ask this to forward to RevCom, add clarification to chair's guidelines | Nikolich | to be implemented by MAR10 Plenary Session
12 | Succession Training | submit existing Sponsor/RevCom process tutorial to web site | Gilb/Kraemer | ?
13 | Succession Training | Add to Chair's guideline, suggested duties for vice-chair, attendance at the EC meetings, run Sponsor ballot, how to get help | Nikolich/Kraemer | to be implemented by MAR10 Plenary Session
14 | Succession Training | Add to Chair's guideline, MEC and ballot pool and other uses – Kraemer, Nikolich | Nikolich/Kraemer | to be implemented by MAR10 Plenary Session
15 | Succession Training | Update training page on web site (recommended tools), send note to EC reflector that the page is being updated and soliciting comments | Gilb | ?
16 | Succession Training | Make 802.3 tools available to 802 | Law | ?
18 | Succession Training | Add link to standards companion to web site | Gilb | ?
19 | Succession Training | Need a WG Chair's guidelines and bus* documents (private, distributed to limited set of officers) (* i.e. WG chair is run over by a bus) | WG chairs | target: 9/30/2009
21 | Succession Training | Opening EC agenda, survey of Vice Chairs regarding the status of the progress of WG Chair guidelines | Gilb | to be implemented at NOV09 Plenary Session
22 | Succession Training | EC members may join any WG email list without attendance requirements, add this to Chair's guidelines | EC chairs/Nikolich | to be implemented at NOV09 Plenary Session
23 | Succession Training | Copy WG ballot announcements to the EC reflector without draft access information, add this to the Chair's guidelines | EC chairs/Nikolich | to be implemented by MAR10 Plenary Session
30 | Downloadable and machine readable content | Create guideline on how down loadable content should appear in 802 standards to be put in the 802 OpMan or guideline | Thompson | target: OCT09
33 | Process changes/tool needs/operational philosophy (lease or buy?) etc. | IMAT either requires on-site or help desk that is staffed during business hours (e.g., 8:00 am to 10 pm in the meeting time zone on some days, i.e., when registration is available) needs to be a phone and on-line chat. Get commitment from IEEE-SA to support | Gilb | target: 31AUG09
34 | Process changes/tool needs/operational philosophy (lease or buy?) etc. | Add IMAT tutorial from Stevens to web site and meeting planner site – Rosdahl, Gilb, Aug. 31, 2009 | Rosdahl/Gilb | target: 31AUG09
35 | Process changes/tool needs/operational philosophy (lease or buy?) etc. | Enhancement, able to register attendance, but not credit for overlapping time-slot | Gilb | status report at NOV09 Plenary Session
36 | Process changes/tool needs/operational philosophy (lease or buy?) etc. | New members orientation needs to include a link to the IMAT tutorial | Thaler | target: 31AUG09
37 | Process changes/tool needs/operational philosophy (lease or buy?) etc. | Review new members orientation slides | EC members | target: 30SEP09
38 | Process changes/tool needs/operational philosophy (lease or buy?) etc. | Tutorial on mentor for EC members who have not used it | Gilb | target: NOV09
39 | Process changes/tool needs/operational philosophy (lease or buy?) etc. | Administrator responsibilities options for mentor tutorial | Kraemer | target: NOV09
40 | Process changes/tool needs/operational philosophy (lease or buy?) etc. | It is OK that the groups use different email reflectors – Law, Aug. 09, No change | Law | target: 31AUG09
41 | Process changes/tool needs/operational philosophy (lease or buy?) etc. | All groups need to make sure that archiving is turned on, archive may be public or private as required, guideline is that technical discussions happen on public reflector – WG chairs, Gilb (report), Sept. 2009 | WG/TAG chairs | target: SEP09
42 | Process changes/tool needs/operational philosophy (lease or buy?) etc. | For reciprocal credit, 802.11, 802.15(?), 802.16, 802.19, 802.20(?) and 802.21, 802.22 meeting credit is by hours – Respective WG chairs, Marks, Sep. 09 | Respective WG Chairs/Marks | target: SEP09
43 | Inter-group complaints/relationships | Conference call for items potentially worthy of discussion is encouraged prior to submittal and after submittal. WG judgment call to determine that there might be issues and arrange the calls. Add this to the Chair's guidelines – Nikolich, Sep. 30, 2009 | Nikolich | target: 30SEP09
44 | Inter-group complaints/relationships | Develop training on the function of a PAR | Marks | target: NOV09
50 | Scope of 802.21 | Multi-MAC power management could well be within the feature set of handover (i.e., 802.21). Early review by multiple WGs is strongly suggested. In scope is abstraction/interface to control, not the low level techniques or power management. Gupta will communicate this to interested parties in 802.21 | Gupta | target: NOV09
51 | Scope of 802.21 | Future multi-MAC items should be considered for 802.1 (bridging and security), 802.21 (handover) or new group (on as considered basis) | Gupta/Jeffree | ongoing
52 | Domination and other distortions to the consensus process | Add 'tool kit' suggestions to Chair's guide | Thaler/Nikolich | target: NOV09
| 35 | count of remaining open items
Completed
Index | Area | Current Task List | Prime/sub | Status
1 | 802 Architecture | WG/TAG Chairs to announce to their members Revision of IEEE Std 802-2001 Overview and Architecure is in 802.1 WG ballot | EC WG/TAG chairs | completed @ NOV09 opening EC mtg
3 | 802 Architecture | Emphasize that conformance to 802 O&A is part of the evaluation criteria by the EC in approving a PAR and that the text in the O&A be an effective tool – Nikolich, EC | Nikolich/EC | completed @ NOV09 opening EC mtg
6 | 802 Architecture | EC seeks qualified editor who has support for the project | Nikolich/EC | completed @ NOV09 opening EC mtg--James Gilb accepted
7 | 802 Architecture | EC seeks qualified, supported chair of O&A project from 802 wide | Nikolich/EC | completed @ NOV09 opening EC mtg--James Gilb accepted
5 | 802 Architecture | WG chairs name at least one candidate who (Nov.-Mar.)‏ - Champion 802 O&A within the WG - Does work on resolving comments | WG/TAG chairs | completed @ NOV09 Plenary Session
17 | Succession Training | Should we formalize mentor assignments? | Nikolich | to be implemented at NOV09 Plenary Session complete: 28MAY2010
20 | Succession Training | Invite SASB to co-locate with 802 | Nikolich, Grow, Law | DEC09 SASB meetings
24 | Leverage | Gather information by first contacting the account managers with authorized distributors to make our standards available – Marks (IHS), Nikolich (techstreet) (Sep/Nov. 2009)? - IEEE member discount honored? - Look for click through or ad revenue - Mechanism for supplying drafts for sale directly - Negotiate pricing - Update links on our web site - Static links directly to specific documents? - Support for ongoing relationship into our organization | Marks/Nikolich | overcome by events
25 | Leverage | Talk with the IEEE SA staff member that is in charge of the authorized distributors to visit with EC representatives | Nikolich | overcome by events
26 | Leverage | Monitor when 802.1Qay (~30 July 2009) and 802.1Qaw is 'published' and when it is available at the authorized distributors | Jeffree/Gilb/Marks | completed @ NOV09 Plenary Session
27 | Leverage | What is the definition of 'published' relative to availability on IEEE shop, availability at authorized distributors, notice to WG, start time for IEEE 802 | Law | completed @ NOV09 Plenary Session
28 | Leverage | EC asks Karen Kenney if GetIEEE 802 program gets credit for single sales through authorized distributors, e.g., IHS and techstreet | Hawkins | overcome by events
29 | Distribution of Standards and Drafts | Compose letter defining problem, send to Judy Gorman and Tony Durniak | EC | completed 17JUL09, responses received 11SEP09 and 19OCT09 MAR10--SA staff begins invesigation of Amazon as a sale channel MAY20--Amazon appears to have deprecated PDF sales from their business operations, SA staff and BuzzR working with Amazon contact to determine final viability of this channel
31 | Downloadable and machine readable content | Normative is determined on a case-by-case basis | Law | case-by-case
32 | Process changes/tool needs/operational philosophy (lease or buy?) etc. | Mentor site for EC document distribution | Gilb | completed @ NOV09 opening EC mtg
45 | 30th Anniversary Celebration | Celebration will be at Orlando meeting, request cake from F2F | Rigsbee | completed @ MAR10 Plenary Session
46 | 30th Anniversary Celebration | Invitees list to be generated by Thompson and Kraemer for approval by EC | Thompson/Kraemer | completed @ MAR10 Plenary Session
47 | 30th Anniversary Celebration | Attendee gift is a nice polo shirt with pocket, only pre-registered attendees will be guaranteed a size, Marks and F2F to put together budget ($30k for additional expenses) and selections – Rigsbee | Marks/Rigsbee | completed @ MAR10 Plenary Session
48 | 30th Anniversary Celebration | The EC will make decision in November considering travel reimbursement or honorarium | Gilb | completed @ MAR10 Plenary Session
49 | 30th Anniversary Celebration | Collocate with IEEE awards for cost sharing – Marks | Marks | target: SEP09 actual: Overcome By Events
Will Not Finish
Index | Area | Current Task List | Prime/sub | Status
| 20 | count of completed items
count of will not finish items
| 35 | count of remaining open items
| 55 | total number of items