– Updated July 1, 2013 –

Background

The IEEE 802 Interim meeting in May served as a venue for video interviews with 15 IEEE 802.3™ Working Group members. Members celebrated the 40th anniversary of the invention of Ethernet by sharing insight on the development of the technology, the standards development process and their vision for the future of Ethernet. Paul Nikolich, IEEE 802 chair was video taped separately during a visit to IEEE-SA in Piscataway and he offered on-camera congratulations and thanks to the members who continue to move Ethernet standards forward.

Strategy

Build on the momentum around Ethernet using subject matter expert (SME) video interviews to foster industry discussion and maximize visibility for IEEE 802.3 Ethernet standards in the business and trade press and through social media channels.

Tactics

Edit each individual video down to create a library of several (3-6) short video segments per person. These will be used as rich media resources to further IEEE-SA PR efforts promoting SMEs, technology, standards and standard groups, consensus building, and membership.

With 16 individual videos, the library should end up consisting of 100+ short video segments for continual use in IEEE 802.3 Ethernet-related PR activities.

Videos will be used in a variety of ways including, but not limited to:

- IEEE-SA 40th Anniversary Ethernet Facebook

  - Post videos on a regular basis throughout 2013

  - Create a video scrapbook on Facebook to archive the videos

- IEEE-SA 40th Anniversary Landing Page

  - Share videos for landing page

- YouTube

  - Publish and promote videos on IEEE-SA YouTube channel

- Twitter

  - Tweet links to the videos and where they’re published out on various accounts to promote the video topic and SME and drive traffic to the IEEE-SA 40th web site landing page and Facebook

- Press releases

  - Include links to videos in relevant IEEE 802 press releases

- Contributed Articles

  - Include hyperlinks to videos in contributed articles

- Don’t Bet Against Ethernet Themed Series

  - Leveraging the video interviews, create a series of short articles for the Standards Insight Blog with hyperlink to supporting video

  - Tweet the Don’t Bet against Ethernet video by SMEs driving followers to the coordinated Standards Insight blog

- Pitch video segments to the media

- Leverage video segments with the media to plant story ideas, foster a dialog and reinforce thought leadership on Ethernet-related topics

- Create a montage video to support the IEEE 802 plenary in November

Video Project Timeline

| Week | Deadline | Activity |
| --- | --- | --- |
| 1 | May 15-16 | Video shoot in Victoria, BC, Canada at IEEE 802 Interim – 15 candidates |
| 2 | May 24 | Ship video drive from Canada to US video production team |
| 3 | May 31 | Review first half of videos (8) and create of video index (copied below) |
| 4 | June 7 | Review second half of videos (7) and update/add to video index |
|  |  | June 5: conduct video shoot for Paul Nikolich at IEEE-SA in NJ |
| 5 | June 14 | Begin editing process; send video to John D’Ambrosia for review/edits |
| 6 | June 21 | Edit all videos into selected segments |
|  |  | June 24: First of John D’Ambrosia’s video segments was linked in the 30th Anniversary Ethernet standards press release, posted to Facebook |
|  | June 21 | Begin sharing videos for Don’t Bet Against Ethernet Series 1st blog sent to John D’Ambrosia for review. |
| 7 | June 28 | Distribute individual videos to each subject matter expert for approval |
| 8 | July 1-July 5 | Incorporate Edits from Subject Matter Experts |
| 9 | July 8, | Finalize all videos |
|  |  | Begin weekly postings of videos on Facebook Share videos with Shuang to post on YouTube Channel |
| 10 | July 15 | Begin series of Don’t Bet Against Ethernet blogs Twitter: Tweet out DBAE video segment Post: Standards Insight Blog, link to Facebook |
| 11 | July 22 - ongoing | Explore press opportunities to post video on various sites |
|  | July 22 - ongoing | Work with SMEs to establish opportunities to further leverage videos through personal blogs/ social sites and individual companies |

Adam Healey Secretary, IEEE 802.3™ Ethernet Working Group Distinguished Engineer, LSI - Backplane Ethernet - Ethernet Is Everywhere

Daniel Dove Chair, IEEE P802.3bm™ 40 Gb/s and 100 Gb/s Fiber Optic Task Force Senior Director of Technology, Applied Micro - Ethernet Exposure - New Ethernet Applications - Long Run of Networking (Ethernet) - IEEE 802.3™ Development Process - Importance of an Open Standards Process - Lessons Learned from IEEE 802.3™ Standards - IEEE Collaboration and Cooperation - Don’t Bet Against Ethernet - Happy Anniversary

Dave Dwelley Member, IEEE P802.3bp™ Reduced Twisted Pair Gigabit Ethernet Task Force Product Line Manager, Mixed Single Product, Linear Technology - Participating in the Standardization Process - IEEE Collaboration and Cooperation - Measuring the Success of Ethernet - Ethernet: Here, There, Everywhere - Ethernet Roadmap - Crosspollination in the Standards Process - Happy Anniversary - Don’t Bet Against Ethernet

Geoff Thompson Member, IEEE 802® Executive Committee IEEE Registration Authority; Past Chair, IEEE 802.3™ Ethernet Working Group Principal, GraCaSI - Impressive Ethernet - Ethernet Based “Wi-Fi®” - History of Ethernet - Ethernet, Robust & Adaptable - IEEE Standardization Process - Success of IEEE 802.3 - Ethernet in the Auto Industry - Participating in the IEEE 802.3 Standardization Process - Original Ethernet - Story of 10BASE-T

Howard Frazier Member, IEEE 802.3™ Ethernet Working Group Chair, IEEE P802.3.1™ Ethernet MIBs Task Force Senior Technical Director, Office of the CTO, Broadcom - Ethernet’s Evolution - Ethernet’s Staying Power - Ethernet in the First Mile - Collaboration and Cooperation - IEEE 802.3™ Success - What Drives Ethernet’s Success

John D’Ambrosia Chair, IEEE 802.3™ 400 Gb/s Ethernet Study Group Chief Ethernet Evangelist, CTO Office, and Distinguished Engineer, Dell - Metcalfe’s Law - Success of Ethernet - Global Issues and Applications - Entertainment - Road to 400 Gb/s - Evolution Is Key to the Success - Consensus Building - More Data - Ethernet in the Automobile - Ethernet is the Universal Language - Happy Anniversary - Don’t Bet Against Ethernet

Kirsten Matheus Need IEEE title Ethernet Project Manager, BMW - Ethernet: In Car Networking - Data Rates & Applications - Market Opportunity - IEEE Standardization Process - Bob Metcalfe’s Ethernet Invention

Marek Hajduczenia Chair, IEEE P802.3bk™ Extended EPON Task Force Standardization Director, ZTE - Personal Experience - Solutions Driven by the Market - Standardization Process - Ethernet for the Long Run - Global Ethernet - IEEE P802.3bk - Don’t Bet Against Ethernet - Happy Anniversary

Mark Laubach Chair, IEEE P802.3bn™ EPON Protocol over Coax (EPoC) Task Force Technical Director, Broadcom - EPoC: EPoN Protocal Over Coax - EPoC: Focused on Business - The Success of IEEE 802.3™ “Standard for Ethernet” - Open Process for Global Adoption - IEEE 802.3™ Ethernet Standards Process - Ethernet Is Limitless

Michael Johas Teener Chair, IEEE 802.1™ Time Sensitive Networking Task Group Plumbing Architect and Sr. Technical Director, Broadcom - Time Sensitive Networking - Ethernet Assets - Standards Process - Market Shaping - Where is Ethernet Headed? - Ethernet Working Group Collaboration - Ethernet as a Connection Model - Happy Anniversary - Don’t Bet Against Ethernet

Pat Thaler 1st Vice Chair, IEEE 802® LAN/MAN Standards Committee Chair, IEEE 802.1™ Data Center Bridging Task Group Senior Technical Director, Office of the CTO, Broadcom - Networking: From Bus to Star - Increasing Speed & Added Capabilities - Ethernet: Today Tomorrow - The Standardization Process

Robert Grow Past Chair, IEEE 802.3™ Ethernet Working Group; IEEE Standards Board Governance Consultant - Ethernet Reflections - Why Was Ethernet So Quickly Accepted? - New Technologies - Surprises about the Ethernet Evolution - Ethernet … Moving Forward - Applications and Devices for Ethernet - IEEE 802.3 Ethernet Success - Ethernet’s Rich Ecosystem

Scott Kipp IEEE 802.3™ Ethernet Working Group President of Ethernet Alliance Principal Engineer, Brocade - 100/400 Gig - What’s Driving the Need for Speed? - How do you Measure the Success of Ethernet? - The Ethernet Standard - Ethernet’s Future Markets - Fiber Optics and Ethernet - From Megabit to Terabit - Happy Anniversary - Don’t Bet Against Ethernet

Steve Carlson Executive Secretary, IEEE 802.3™ Ethernet Working Group Chair, IEEE P802.3bp™ Reduced Twisted Pair Gigabit Ethernet PHY Task Force President, High Speed Design - Background - Ethernet in the Entertainment Industry - Building Automation - Carrier Ethernet - Ethernet in the Entertainment Industry - Automotive Ethernet - IEEE 802.3 Ethernet Standardization - Happy Anniversary - Don’t Bet Against Ethernet

Wael Diab Vice Chair, IEEE 802.3™ Ethernet Working Group Senior Technical Director, Office of the CTO, Broadcom - Evolution of Ethernet - Standards, Principles and Governance - Looking Forward with Ethernet - Internet of Things—Where Science Fiction Meets Science Faction - Innovations and Standards

Paul Nikolich Chair, IEEE 802® LAN/MAN Standards Committee Chief Strategy Officer, YAS Broadband Ventures, LLC - Congratulations! - Key Success Factors of IEEE 802.3™ “Standard for Ethernet”