## Summary
| New | In process | Proposed | Closed | Total
P&P | 0 | 1 | 0 | 6 | 7
OM | 1 | 0 | 2 | 7 | 10
WG P&P | 0 | 0 | 0 | 5 | 5
CG | 1 | 3 | 1 | 8 | 13
| New | In process | Proposed | Closed | Total
Totals | 2 | 4 | 3 | 26 | 35

## P&P changes
Item # | Summary | Proposed change | Action taken | Status | Date entered | Date closed | Submitted by | Assigned to
1 | Clarify that it is voting members of the Sponsor | 4.1 Voting membership “Members of the Sponsor obtain voting rights at the end of the plenary session where they are first confirmed or elected by the Sponsor. If election/appointment and confirmation by the Sponsor occur outside a plenary session, that member receives voting rights immediately upon Confirmation.” Should say "Voting members of the Sponsor" | Proposed for March 2014 | Closed | 2013-06-04 | 2014-03-21 | Gilb | Gilb
2 | Can the rules in the P&P be suspended? | Add clarification somewhere. | Referred to AudCom, awaiting decision. | In process | 2013-06-04 |  | Gilb | Nikolich/Gilb
3 | Not clear how appointed positions are appointed. All are mostly defined except for Member Emeritus and perhaps the Chair of hibernating groups | Add “A Member Emeritus is appointed by the Sponsor Chair subject to confirmation by the Sponsor” | Proposed for March 2014 | Closed | 2013-11-15 | 2014-03-21 | Jeffree/Rosdahl | Gilb
4 | There is no way to remove appointed members other than the Sponsor (i.e., only officers are subject to removal). | Add that non-voting members may be removed for cause as well. |  | Closed | 2013-11-15 | 2014-03-21 | Gilb | Gilb
5 | Some instances of “802” with out preceding “IEEE” | Search and replace all “802” with “IEEE 802” when the preceding acronym is not present | For example, see 5.2, fourth paragraph. | Closed | 2014-01-23 | 2014-03-21 | Gilb | Gilb
6 | Term limits for WG Chairs | Remove the requirement to seek permission and term limit | WG P&P issues, not P&P | Closed | 2014-02-14 |  | Jeffree | Gilb
7 | Sponsor chair is elected by 5 appointed positions. | Change to be elected only by WG Chairs | Proposed for March 2014 | Closed | 2014-02-14 | 2014-03-21 | Jeffree | Gilb
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35 | [8 empty] | f
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99

## OM changes
Item # | Summary | Proposed change | Action taken | Status | Date entered | Date closed | Proposed by | Assigned to
1 | 5C/CSD update | Proposed 5C is in ec-13-0009-11-00EC-Proposed-5C.pdf | Sent to WGs for consideration, will ask for approval in Nov. 2013 | Closed | 2013-03-01 | 2013-11-15 | Gilb | Gilb
2 | Private letter ballot process. | Changes proposed in ec-13-0032-01 | To be considered on October conference call. Did not happen, propose for July. | Closed | 2013-06-04 | 2013-11-15 | Nikolich | Thompson
3 | Define private process, can we have “private” email discussion | AudCom says that there is neither private email discussion or private email ballot. So delete private letter ballot process. | Submitted for July 2014 plenary | Closed | 2013-06-04 | 2014-07-18 | Nikolich | Nikolich/Gilb
4 | Status of Chair's Guidelines | In order to maintain some consistency of operation, the Sponsor Chairmay, at his discretion, maintain a public document to be called the "Chair's Guidelines". This document will give the reader a hint at how the chair will be expected to deal with situations described therein. This is considered useful for recurring situations and to avoid managment which appears to be capricious. The scope of the document is to be limited to matters of decision that are within the powers of the Sponsor Chair. | Proposed for consideration at November 2013 plenary | Closed | 2013-10-09 | 2013-11-15 | Thompson | Gilb
5 | Missing word at the end of 5.2.3 | “ a shall prepare and submit all” should be “a WG shall prepare and submit all | Submitted for July 2014 plenary | Closed | 2014-03-09 | 2014-07-18 | Chaplin | Gilb
6 | Policy for distribution of standards should be in electronic format. | “All IEEE 802 LMSC standards will be distributed on an annual basis to registered attendees.” should be “All IEEE 802 LMSC standards will be distributed in an electronic format on an annual basis to registered attendees.” | Submitted for July 2014 plenary, suggestion rejected as not necessary. | Closed | 2014-05-21 | 2014-07-12 | Gilb | Gilb
7 | The OM voting rules should reference the P&P and not contradict them. | Unknown at this point. | Submitted for July 2014 plenary | Proposed | 2014-05-21 | 2014-07-18 | Stephens | Gilb
8 | Face to face meetings should have explicit exceptions for dial-in participation. |  | Submitted for July 2014 plenary | Closed | 2014-05-22 | 2014-07-18 | Various | Gilb
9 | Review rules for endorsement and affiliation letters |  | Suggest that this belongs in the Chair's guidelines. Submitted for July 2014 plenary. | Proposed | 2014-05-22 |  | D'Ambrosia | D'Ambrosia/Gilb
10 | The sentence in 4.2 “Revised drafts approved in subsequent WG letter ballot for forwarding to the Sponsor Ballot Group do not require Sponsor approval for forwarding.” should be removed | Delete it. | Propose for July 2015 or June 2015 conference call. | New | 2014-06-24 |  | Thaler | Gilb
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99

## WG P&P changes
Item # | Summary | Proposed change | Action taken | Status | Date entered | Date closed | Proposed by | Assigned to
1 | Reciprocal credit | Reciprocal credit - attendance credit in two groups simultaneously Anisotropic rights - maintain rights in one group while attedning another, but not gaining rights (802.18 and 802.19). This needs to be able to be described in software so that IMAT will yield the correct result. | Proposed in ec-13-0053-00, scheduled for review in Nov. 2013, Still under review, awaiting results of the Workshop. | Closed | 2013-09-09 | 2014-03-21 | Gilb | Gilb
2 | Remove term limit for WG Chairs | As it says. | Proposed for March 2014 | Closed | 2013-11-15 | 2014-03-21 | Jeffree | Gilb
3 | Clarify rules for loss and retention of membership. | Add that loss due to non-attendance does not result in a loss of participation credit. Clarify what ballots count towards loss due to failure to respond. Clarify the return requirements and approval requirements. | Submitted for July 2014 plenary | Closed | 2014-02-28 | 2014-07-18 | Stephens/Jeffree | Gilb
4 | Add requirement to maintain up to date contact information. | To establish and retain voting rights participants must record and maintain valid contact information in the WG database. All acknowledgements and information required by the IEEE Standards Association (e.g., Employer and Affiliation) shall also be provided and current. | Submitted for July 2014 plenary. Rejected during rules meeting, no action to be taken. | Closed | 2014-03-06 | 2014-07-13 | Thaler | Group
5 | Clarify that WG meetings at plenaries and interims are in person only and that dial-ins are an exception. | Text is proposed for the OM. | Submitted for July 2014 plenary. Currently proposed for OM. | Closed | 2014-03-21 | 2014-07-18 | Jeffree | Gilb
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99

## CG changes
Item # | Summary | Proposed change | Action taken | Status | Date entered | Date closed | Submitted by | Assigned to
1 | 802 Electronic Media Production Agreement | Submitted as ec-13-0013-00 | Scheduled for review in Nov. 2013 | In process | 2013-09-09 |  | D'Ambrosia | D'Ambrosia
2 | Definition for reciprocal credit | Should be in WG P&P | Moved to WG P&P issue | Closed | 2013-09-09 | 2013-10-09 | Gilb | Gilb
3 | Guideline on public statements |  | Not practical, no action taken. | Closed | 2013-09-09 | 2013-11-10 | Gilb | Gilb/Nikolich
4 | Relax commercialization requirements for sponsors | At IETF meeting, they allow for a run of tables in the registration area for the meeting sponsors to hand out information and trinkets. They also had a glossy program (labeled IETF 82 Taipei, Taiwan On-SITE INFORMATION) that included quarter page to 2 page ads for the sponsors in addition to meeting venue and transportation information. Also, at our Singapore meeting, we had a couple of tables in the hall where our sponsors handed out some literature. | Use text from motion to add to CG. | Closed | 2013-09-09 | 2014-03-21 | EC | Gilb/Thompson
5 | Guidelines for consent agenda items |  | Add new text | Closed | 2013-09-09 | 2013-11-15 | Gilb | Gilb
6 | Industry connections information. |  | D'Ambrosia to submit | In process | 2013-09-09 |  | D'Ambrosia | D'Ambrosia
7 | Ballot announcements | 2.9 Last line says that announcements of WG ballots should be copied to the reflector. I don't recall anyone copying them to the EC reflector and given the number of projects underway, it might be excessive to do so. I guess one could argue that doing so would help EC members who want to exercise their ex-officio voting rights, but generally when I want to do that, I sign up for the WG reflector and monitor the project progress through WG minutes. | Currently, the requirement is to announce, review with EC members on June 2015 teleconference and at July 2015 plenary to see if it is working | In process | 2013-09-09 |  | Thaler | Gilb
8 | Copy WG ballot information to EC reflector | 2.10 also says that WG ballot information should be copied to the EC reflector | Currently, the requirement is to announce, review with EC members on June 2015 teleconference and at July 2015 plenary to see if it is working | In process | 2013-09-09 |  | Thaler | Gilb
9 | Hyperlinks missing | 2.16 - I assume that the blue bits are intended to be hyperlinks, they aren't. (editorial) | No vote required, will be handled with the next revision editorially. | Closed | 2013-09-09 |  | Thaler | Gilb
10 | Executive Secretary Designee | Add guideline for designee based on email from Rosdahl | Copy in text from email. | Closed | 2013-09-25 | 2013-11-15 | Gilb | Gilb
11 | Fee waivers for SDO officers | Allow one time waiver for observation | Draft text created, need feedback from Kraemer. | Closed | 2013-10-09 | 2013-11-15 | Kraemer | Gilb/Thompson/Kraemer
12 | Clarify what it means for the Sponsor to review CSD during WG ballot. | Use wording from David found in email. | Proposed for July 2014 plenary | Proposed | 2014-04-04 | 2014-07-18 | Law | Gilb
13 | Add to the CG that during July plenary subgroup charters are reviewed. |  |  | New | 2014-07-14 |  | Gilb | Gilb
14 | Create policy for email reflector access. | Thaler proposed text by email. | Propose for July 2015 plenary | Closed | 2014-03-16 | 2014-03-21 | Thaler | Thaler
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99