## Slide 1: Executive Secretary Agenda items February Telecon
Jon Rosdahl, CSR
Slide 1
Date: 2015-02-03
Authors:

## Slide 2: Abstract
Jon Rosdahl, CSR
Slide 2
Agenda Items for Executive Secretary:
2.10 II January 2015 Post Mortem
3.00 II Report on Status of Venue Contracts – Macao 2016
4.0 II Status of Future Venues in General
5.0 II Network Provider RFP Adhoc Status
7.00 DT Status of Berlin Plenary – Registration/Venue etc.

## Slide 3: 2.10 II January 2015 Post Mortem
Network
  Swisscom Hospitality Services was network provider
  8 hours of down time during the week
  Root causes of failures continue to be under investigation,
  No definitive findings at this time, final analysis at March EC mtg
Attendance
  665 0f planned 700
Budget (as of Jan 30)
  665 attendees at about $467 each
  Actual Income: $433,990
  Actual cost: $310,800
  Net surplus estimated to be transferred to 802: $123,190
  Final Financial charges not included

## Slide 4: IEEE 802 Interim Session - January 11-16, 2015 Registration Report by Working Group
Working Group | Number
802.3 | 287
802.11 | 278
802.15 | 62
802.xx | 10
802.1 | 45
802.19 | 5
none | 7
802.18 | 4
802.21 | 4
802.24 | 2
Privacy EC SG | 2
Notes: None = 5 staff and 2 that did not indicate a primary group

## Slide 5: Atlanta, GA- January 2015
Registration Income: $392,500 $379,150 $378,150.00
  Hotel Credits $50000 $50,000 $55,839.56
  Registrations 700 664 665
Meeting Expense Estimate: $251,875 $304,057 $310,799.99
  AV $51,000 $50,000 $54,999.48
  Financial Fees $20,625 $19,968 $19,907.50
  Food & Beverage $85,000 $75,000 $81,373.75
  Meeting Planner $78,000 $73,000 $79,337.20
  Network Services $12,000 $12,200 $ 0
  Social $ 0 $ 0 $ 0
  Shipping $ 750 $ 1,000 $ 1,511.30
  Misc $ 4,500 $ 5,000 $ 3,170.72
  -- Foreign Venue Set Aside $ $ 67,900 $70,500.00
  -- Get 802 Attendee fee $ 0 $ 0 $ 0
Surplus/(Deficit) $190,625 $125,093 $123,189.61
Average cost per attendee $458 $467.37
Proposed
Budget
Oct 2014
Ben Rolfe , BCA
Estimated
Budget
Jan 10, 2015
Jon Rosdahl, CSR
Actual
Jan. 30, 2015
Notes: Contract F&B Min = 50k

## Slide 6: 3.00 II Report on Status of Venue Contracts – Macao 2016
Contract executed – Sept 3, 2014
Initial Deposit paid Oct 20, 2014 from Singapore cash
Next payment due: Dec 31, 2015
HKD/MOP 250,000 – about US$31,000

## Slide 7: 4.0 II Status of Future Venues in General
Future Venue Information:
  802 EC-12/40r10: ec-12-0040-10-00EC-802-plenary-future-venue-contract-status.xlsx
Working on openings:
  2018 – March - November
  2019 – March – July
Site Visit Report:
  Vienna – Looks promising – working on final Bid
  Brussels – Was not feasible – have informed decline
802 Interim - 2016 Atlanta
  802 EC Workshop – January 23, 2016
  Note potential cost of non attendance by All WGs

## Slide 8: 802 Interim - 2016 Atlanta
Review 802 Interim Session 2015 Atlanta
  Total Room nights = 2518
  802.3 attendees ~287*3 = 861 min estimate of rm nights
Possible 2016 Attrition costs if attendance similar to 2015:
  2016 Contracted Room nights:
    Original Contract: 4000 room nights
    Contract allows reduction of 30% = 2800 room nights
    Fees start below 70% of 1960 room nights
  Possible Penalty= (1960-1657) *.75*$159 = $36,132.75
Actual Penalty would most likely be higher
Notes: Current Addendum has room nights at 2950  $48,000 penalty if attendance matches 2015.

## Slide 9: 5.0 II Network Provider RFP Adhoc Status
Network Contract Extension has been accepted by Verilan
  6 Meetings – 2 year equivalent
  Through end of 2016
RFP and other Network assessment
  RFP being created (Jon)
  Network Assessment options proposal due March (James)

## Slide 10: 7.00 DT Status of Berlin Plenary – Registration/Venue etc.
Current Registration: 445
Room allocation and meeting schedule
  Thanks to the WG that submitted timely request
  Late Change requests holding schedule up for all
  Targeting end of week for draft
Hotel Reservation Pickup report
  Wash block option: 3030 nights
  Current Pickup: 3346
  Hotel still allowing hotel reservation at Group Rate

## Slide 11: IEEE 802 Plenary Session - March 8-14, 2015 Registration Report by Working Group
Working Group | Number
802.11 | 201
802.3 | 156
802.15 | 43
802.1 | 38
none | 8
802.19 | 6
802.22 | 4
802.21 | 2
802.xx | 2
802.18 | 1
802.24 | 1
Privacy EC SG | 0

## Slide 12: Survey Results
See document: 802 EC-15/7r0:
https://mentor.ieee.org/802-ec/dcn/15/ec-15-0007-00-00EC-Survey Results- January 2015.pdf