## Sheet1
Item | Assignee | Status | Description
-615067 | Parsons | Open | Track ITU-T FG IMT2020 and will update on it in March 2016 during the IEEE 802 ITU-T SC.
2016-01-02 | All EC | Closed | Formulate ideas for the three questions regarding 5G
2016-01-03 | Nikolich | Closed | Take pictures of the flip chart and email them to the EC, Yvette and PatCom administrator
2016-01-04 | Stephens | Closed | Consensus is that no action needs to be taken regarding attendance requirements for obtaining membership
2016-01-05 | D'Ambrosia | Closed | Create a schedule for a plenary week that shows EC meetings, standing committees slot and 802.18 slot
2016-01-06 | Thaler | Open | Lead the discussion to hone RR mission statement.
2016-01-07 | Thaler | Open | Prepare a motion in March to cover the operation changes of the RR TAG.
2016-01-08 | Thompson | Closed | Draft language for duly authorized activities.
2016-01-09 | Parsons | Closed | Start an EC email ballot of the scope and duties for an IEEE 802 5G/IMT-2020 Standing Committee.
2016-01-10 | Nikolich | Closed | Appoint a chair of the new IEEE 802 5G/IMT-2020 Standing Committee if it is created.
2016-01-11 | Gilb | Open | Write Chair's Guidelines submission for multiple PARs in an SG.
2016-01-12 | Nikolich | Open | Send the proposed definition of duly authorized activity to Agassi, Lach and Wiggins
2016-01-13 | Rosdahl | Open | Fill out a ProCom submission based on the proposed definition of duly authorized activity.
2016-01-14 | Nikolich | Open | Monitor Agassi, Lach and Wiggins action to provide public information.
2016-01-15 | Rosdahl | Closed | Add a consent agenda item to approve the Get IEEE 802 Program Guidelines and confidential attachment as the last item on the agenda for the February conference call. Prepare a second conference ID for the potential executive session.monitor Agassi, Lach and Wiggins action to provide public information.