## Slide 1: IEEE 802WCSC Meeting Venue Manager Report
Date: 2021-07-07
Authors:
Notes: R2 was created during discussion with MTG Events after the Wireless Chairs Meeting on Feb 11.
R3 – March 03 plenary 802 WCSC telecon
R4 – May 5 802 WCSC Telecon –
R5 – May 5 802 WCSC Telecon - - Updated with Motion information during the telecon.

## Slide 2: Abstract
Current Status of 802 Wireless Interim Session venue plans as of July 7, 2021.

## Slide 3: Future Venue Status – May 5, 2021
2021-05 WG Electronic Interim
2021-09 802W Electronic Interim Waikoloa, HI –
2022-01 Panama – Contract with IEEE
2022-05 Warsaw
2022-09 Waikoloa, HI
2023-01 Baltimore, MD
2023-05 open – TBD – Target Asia Venue (Osaka?)
2023-09 Atlanta – Buckhead, GA
2024-01 Irvine, CA
2024-05 open – TBD – Target Europe
2024-09 Waikoloa, HI
MTG Events has highlighted Venues
Notes: Future Wireless Interim Meetings: review and status May 5, 2021
  May 9-14, 2021, WG Electronic Interim
  Sept 12-17, 2021, Hilton Waikoloa Village – Contract executed, in repository – Go/NoGo discussion May 5, 2021
  Jan 16-21, 2022, Hilton Panama – contract in negotiations – Hotel Irvine contract moving to 2024 in process.
  May 15-20, 2022, Warsaw Marriott– Contract executed, in repository (802WFIN-20/22r0)
  Sept 11-16, 2022, Hilton Waikoloa Village– Contract executed, in repository (802WFIN-20/32r0)
  Jan 15-20, 2023, Baltimore Marriott Waterfront – Contract executed, in repository (802WFIN-20/18r0)
  May 2023 - open
  September 10-15, 2023, Atlanta Buckhead – Contract executed, in repository (802WFIN-21/1r0)
  Jan 2024 – Hotel Irvine – Contract in the final signature process (May 2021 – 802WFIN-21/17r5)).
  May 2024 Open
  Sept 2024 Hilton Waikoloa Village – Contract executed, in repository (802WFIN-20/12r0)
  Sept 2025 Hilton Waikoloa Village – Approved March 2020 by 802WCSC – in negotiations
  Sept 2026 Hilton Waikoloa Village – Approved March 2020 by 802WCSC – in negotiations

## Slide 4: 2022-01/2024-01 - Irvine
We had a contract in place for January 2022.
A draft contract was sent IEEE for changing to 2024
The Contract is in the final approval process.

## Slide 5: 2022-01 Hilton Panama
Working with Mtg Events and the hotel for planning and contract.
Initial Contract room block, and meeting space plan is underway.
IEEE Contract Legal Review and Execution in process.

## Slide 6: 2025 Sept and 2026 Sept Interim
One of the last set of Contracts that Bob worked on was to book the Hilton Waikoloa Village – This action was approved during the March 2020 by 802WCSC –
The Hotel Contact reached out to find out the status.
We are in negotiations to close the contracts.
May 2021 – Still working to execute the contract.
Expected close by end of Aug 2021. (delayed)

## Slide 7: Open Dates – as of July 2021
May 2023 (Asia) and May 2024 (Europe) are open dates

## Slide 8: Sept 2021 Interim Discussion

## Slide 9: 802W Electronic Interim Sept 10-24, 2021
2021 September 802 Wireless Electronic Interim
Registration open July 14th
    USD$50 payable 15 days prior to start (July 14 – Aug 27)
    USD$75 until the start of the Interim Session, (Aug 28 – Sept 9)
    USD$125 thereafter (after Sept 9)

## Slide 10: References