## Slide 1: IEEE 802WCSC Meeting Venue Manager Report 2023
Date: 2023-09-10
Authors:
Notes: R0 – New report for 2022 –Status updated.
R1 – Report for February
R2 – Report for March

## Slide 2: Abstract
Current Status of 802 Wireless Interim Session venue plans as of Sept 09, 2023, as presented to the IEEE 802 Wireless Chairs Standing Committee in conjunction with the 2023 Sept 802W Interim in the Grand Hyatt Buckhead, Atlanta on September 10th, 2023.

## Slide 3: Future Interim Venue Status
2023-09 (10-15) Atlanta – Buckhead, GA
2024-01 (14-19) Panama (Rebooked from Jan 2022)
2024-05 (12-17) Warsaw, Poland – (TBC Rebook from May 2022)
2024-09 (8-13) Waikoloa, HI
2025-01 (12-17) Kobe, Japan – TBC (Moved from May 2023)
2025-05 (11-16) – RFP - Europe
2025-09 (14-19) Waikoloa, HI
2026-01 (11-16) - RFP
2026-05 (10-15) – RFP - Europe
2026-09 (13-18) Waikoloa, HI
2027-01 (10-15) - RFP
2027-05 (9-14) – RFP Asia (could rotate J-M-S)
2027-09 (12-17) - RFP
Meeting Planner:
Starred Venues :MTG Events Dotted Venues: Face to Face Events
As of Sept 8, 2023
Notes: Future Wireless Interim Meetings: review and status Sept 1, 2023
In General, Each year one Session must be Non-NA/US – Odd years Asia – Even Years Europe
  2023 September 10-15 – Grand Hyatt, Atlanta Buckhead – Contract executed (802WFIN-21/1r0)
  2024 January 14-19 – Hilton Panama, Panama – Contract executed (802WFIN-21/31r0)
  2024 May 12-17 - Warsaw Marriott, Warsaw, Poland– in negotiations
  2024 Sept 8-13 - Hilton Waikoloa Village – Contract executed (802WFIN-20/12r0)
  2025 Jan 12-17 – Kobe, Japan – in negotiations
  2025 May 11-16 – Open – Target Europe - RFP
  2025 Sept 9-14 - Hilton Waikoloa Village, Waikoloa, HI – Contract executed (802WFIN-22-0007r0)
  2026 Jan 11-16 – RFP – Open (NA/Asia)
  2026 May 10-15– RFP – Open (Asia/NA)
  2026 Sept 13-18 Hilton Waikoloa Village, Waikoloa, HI – Contract executed (802WFIN-22-0008r0)
  2027 Jan 10-15 – RFP – Open (NA/Asia)
  2027 May 9-14 – RFP – Open (Asia/NA)
  2027 Sept 12-17 – RFP – Open (NA/Asia)

## Slide 4: Future Venue Contract Status
2023 Nov 12-17 – Hawaiian Village, Oahu, Hawaii, United States
2024 March 10-15 – Hyatt Regency Denver at Colorado Convention Center, Denver, CO, (March 2021)
2024 July 14-19 – Sheraton Le Centre Montreal, Montreal, Quebec, Canada (July 2020)
2024 Nov 10-15 –Hyatt Regency Vancouver, Vancouver, Canada (Nov 2021)
2025 March 9-14 –Hilton Atlanta, Atlanta, GA, United States (2 of 2 – March 2020).
2025 July 13-18 –Marriott Madrid Auditorium, Madrid, Spain (July 2021) / NEW RFP – Europe/NA?
2025 Nov 9-24 – Open – RFP NA/Europe
2026 March 8-13 - Hyatt Regency Chicago, Chicago, IL, United States (March 2024)
2026 July 13-18 – Le Centre Sheraton Montreal, Montreal (July 2022 attrition offset)
2026 Nov 8-13 - Open – RFP Asia
2027 March –Hilton Atlanta, Atlanta, GA, United States ( offset potential shortfall 2023/2025)
2027 July 11-16 - Open –RFP Europe
2027 Nov 14-19 – Hawaiian Village, Oahu, Hawaii, United States
802 EC Approved – Contract is being Negotiated.
As of Sept 8, 2023

## Slide 5: 2023 September 802 Wireless Interim Grand Hyatt Atlanta, Buckhead
Date: Sept 10- 15, 2023
Location: Grand Hyatt Atlanta, Buckhead, GA, USA
Mtg Planner: Face to Face Events
Registration Target to open July 1, 2023 Opened:
Budget: $600/$800/$1000 – 264+273 = 537 attendees (originally 600)
Income: $358,902.05
Expense: $347,457.18
Net Meeting: $ 11,444.87
Per Attendee: Cost = $647.03 Revenue = $633.05
(Updated Sept 8, 2023)

## Slide 6: 2024 January 802 Wireless Interim Panama Hilton, Panama
Date: January 14-20, 2024
Location: Panama City, Panama
Mtg Planner: MTG Events
Rebooked due to Covid-19 from 2021 May and 2022 January
Registration Target to open Nov 1, 2023
Budget: $600/800/1000 (hotel Discount) -- 275 + 325 = 600 attendees
Income: $328,867.08
Expense: $335,726.60
Net Meeting: $(6,859.42)
Per Attendee: Cost = $559.54 Revenue = $523.83
Notes: Contract executed: 802WFIN-21/31r0

## Slide 7: 2024 May 802 Wireless Interim JW Marriott Warsaw, Warsaw, Poland
Date: 2024 May 12-17
Location: JW Marriott Warsaw, Warsaw, Poland
Mtg Planner: Face to Face Events
Rebook from 2020 May and 2022 May
Registration Target to open March 12, 2024
Budget: -- 275 + 325 = 600 attendees
Income:
Expense:
Net Meeting:
Per Attendee: Costs = Revenue =

## Slide 8: 2024 Sept 802 Wireless Interim: Hilton Waikoloa
Date: 2024 September 8-13
Location: Hilton Waikoloa, Waikoloa, HI
Rebook from 2020-09
Mtg Planner: Face to Face Events
Registration Target to open July 1, 2024
Budget: -- 275 + 325 = 600 attendees
  Income:
  Expense:
  Net Meeting:
Per Attendee: Costs = Revenue =

## Slide 9: Open RFP for 802W Interims – as of Sept 8, 2023
The IEEE 802W Interim Sessions are the week of the 2nd Sunday in Jan/May/Sept each year
  One in Asia in Odd years and one in Europe In Even years.
  The estimated room block is about 1350 – Estimate 250-275 in person.
Specific Requirements for Meeting Space/Network/AV etc. are in Doc 802 EC-23146r0:
  https://mentor.ieee.org/802-ec/dcn/23/ec-23-0146-00-WCSG-ieee-802w-rfp-2023.xlsx
Potential Open Dates:
  2025-05 (11-16) – Targeting Europe
  2026 Jan 11-16
  2026 May 10-15 -- Targeting Europe
  2027 Jan 10-15
  2027 May 9-14 -- Targeting Asia
  2027 Sept 12-17

## Slide 10: Locations being considered
Huawei would like to host an IEEE 802W meeting in either Macau or Sanya (Hainan) in either 2025 or 2026.
Requests to consider the following general regions:
Australia
Egypt
UAE
Western Europe
Eastern Europe
Singapore
China

## Slide 11: Future Interim Meeting Fees – 2023/2024
IEEE 802 Wireless Interim Session meeting fees are set by
the IEEE 802W Exec Committee of the Joint Treasury
          Meeting fees are expected to balance actual costs to zero over 2-3 years.
          2023 Sept 802W fees: $600/$800/$1,000
Proposed Meeting Fees set for 2024 802W Interims –
    $600/$800/$1,000 Mixed Mode – (In Hotel Stay Discount $300)
IEEE 802 Plenary Session meeting fees are set by the IEEE 802 Executive Committee
  – Currently base fee set by the 802 EC is $700/$900/$1100 (In Hotel Stay Discount $300).
  -- Meeting fees increase to cover mixed mode expenses and Lunches
    2023 July Plenary in Berlin, Germany = $700/$1,000/$1,300
    2023 Nov Plenary in Hawaii = $800/$1,100/$1,400 (In Hotel Stay Discount $300)

## Slide 12: 1. Motion to approve 2024 802W Interim Registration Fees 2023-09-10
Move to approve Session fees for the 2024 802 Wireless Mixed-mode Interims: January at the Hilton Panama, Panama City, Panama; May at the Marriot Warsaw, Warsaw, Poland, and September at the Hilton Waikoloa, Waikoloa, HI, USA at $600/$800/$1000 for any in-person or virtual attendee with a $300 discount for staying at least 3 nights in the session hotel.
Moved: Ben Rolfe
2nd:
Results: (ECJT voters)

## Slide 13: 2. Motion to approve Site Visit for Kobe, Japan 2023-09-10
Move to authorize the 802W Venue Manager, Jon Rosdahl, to go on a site visit with Linespeed and Mtg Events with the purpose to prepare for 2025 January IEEE 802 Wireless Mixed-mode Interim in Kobe, Japan. Expenses not to exceed: $10,000.
Moved: Ben Rolfe
2nd:
Results: (ECJT voters)
Notes: Airfare: $8,800
Transfers: $200
Meals: $400
Hotel: $600

## Slide 14: 3. Motion to approve Site Visit for Warsaw, Poland 2023-09-10
Move to authorize the 802W Venue Manager, Jon Rosdahl, to go on a site visit with Linespeed and Mtg Events with the purpose to prepare for 2024 May IEEE 802 Wireless Mixed-mode Interim in Warsaw Poland. Expenses not to exceed: $5,000.
Moved: Ben Rolfe
2nd:
Results: (ECJT voters)
Notes: Airfare: $3,800
Transfers: $200
Meals: $400
Hotel: $600

## Slide 15: References
  From the WCSC Operations Manual 2.8 Meeting Venue Manager
The Meeting Venue Manager is responsible for the following tasks:
Ensure that WCSC sponsored sessions are compliant with the IEEE Finance Operations Manual (FOM). The FOM contains policies and information related to IEEE finances, including policies and information related to financial stability, reporting requirements, asset and liability management, reserves, insurance coverage, business expense reporting, fund-raising, and contracts and purchase orders.
Work with the Professional Conference Organizer (PCO) to get a Request for Proposal (RFP) for the assigned dates.
Work with the PCO to send the RFP to one or more venues.
Review RFP responses from venue(s).
Perform venue site visits as needed, potentially with the PCO and network service provider, to determine suitability of a venue.
Present summaries of venue options to the WCSC for WCSC decision/selection.
Negotiate contract proposals on behalf of the WCSC.
Review venue contract terms and conditions with the WCSC.
Submit venue contract(s) to the IEEE Meetings Contracts and Events (MCE), IEEE legal and IEEE-SA Procurement to formally execute the contract.
Coordinate with the PCO and the WCSC chair on major decisions.
Attend the venue pre-conference meeting, walk the venue space with the PCO and meet with the hotel staff as the IEEE 802 WCSC point of contact. The PCO is the primary hotel contact.
Monitor the terms of the contract to ensure that IEEE 802 WCSC meets its obligations and that the venue meets theirs.
  If the contract requires deposits, confirm that the Treasurer will make the deposits on time.
  Monitor contract review points (room block, food and beverage minimum requirements) and file contract addendums as necessary.

## Slide 16: Email Ballot: Motion to approve Site Visit for Panama 2023-08-08
Ballot opens 2023-08-08 and closes either 2023-08-18 or when sufficient votes have been received to know the outcome:
Move to authorize the 802W Venue Manager, Jon Rosdahl, to go on a site visit with Mtg Events with the purpose to prepare for 2024 January IEEE 802 Wireless Mixed-mode Interim. Expenses not to exceed: $3,000
Moved: Jon Rosdahl
2nd: Ben Rolfe
Results: 6-0-0 (ECJT – 6/8 responded)

## Slide 17: 1. Motion to set Interim Session Type for 2024 2023-07-09
Motion: Hold the 2024 Wireless Interim sessions in mixed mode (in-person
and electronic)
  o Moved: Tuncer Baykas, 2nd: Ann Krieger
  o No objection to approving by unanimous consent
  o [Voters - WC standing committees (WG and TAGs chairs, vice-chairs and
  secretaries)] [13 present]

## Slide 18: 1. Motion to approve Location for Jan 2025 – Kobe, Japan 2023-05-14
Approve holding the January 19-24, 2025, Wireless Interim session in Kobe, Japan.
  · Moved: Jon Rosdahl, Second: Stephen McCann
  · Note: This is a wireless chairs’ motion.
  · Results: Approve by unanimous consent. (Voter's present = 11)

## Slide 19: 1. Motion to approve 2023 May Fees - Orlando. 2023-01-15
Move to approve Session fees for the 2023 May 802 Wireless Mixed-mode Interim, Hilton Orlando Lake Buena Vista Hotel (May 14-19, 2023), as $600/$800/$1000 for any in-person or virtual attendee. Registration Target to open No later than March 1, 2023
Rate Changes are Early-bird until March 31; Standard until April 28,2023.
Refund Schedule: Full until March 31, $150 fee until April 28, and no refund after April 28, 2023.
Moved: Jon Rosdahl
2nd: Ben Rolfe
Results: 8-0-0 Motion Passes.

## Slide 20: 2. Motion to approve 2023 Sept Fees Buckhead. 2023-01-15
Move to approve the 2023 Sept 802 Wireless Session as a Mixed-mode Interim at the Grand Hyatt Atlanta, Buckhead Atlanta Georgia (Sept 10-15, 2023) and approve the session fees as $600/$800/$1000 for any in-person or virtual attendee. Registration Target to open no later than July 1, 2023
Rate Changes are Early-bird until July 28; Standard until August 25, 2023.
Refund Schedule: Full until July 28, $150 fee until August 25, and no refund after August 25, 2023.
Moved: Jon Rosdahl
2nd: Ben Rolfe
Results: Unanimous – 8-0-0 Motion Passes

## Slide 21: 3. Motion to approve Site Visit for Buckhead 2023-01-15
Move to authorize the 802W Venue Manager, Jon Rosdahl, to go on a site visit with Linespeed and Face to Face Events with the purpose to prepare for 2023 September IEEE 802 Wireless Mixed-mode Interim. Expenses not to exceed: $2,600.
Moved: Ben Rolfe
Second: Stephen McCann
Results: Unanimous 8-0-0 – Motion passes.

## Slide 22: Motion to approve Site Visit for Orlando 2022-12-14
Move to authorize the 802 WCSC Venue Manager, Jon Rosdahl to go on a site visit with Linespeed and Face to Face Events with the purpose to prepare for 2023 May IEEE 802 Wireless Mixed-mode Interim. Expenses not to exceed: $2,600.
Moved: Ben Rolfe, Seconded: Stephen McCann
Result: 6-0-0 Passes

## Slide 23: Motion to approve 2023 January Fees. 2022-11-02
Move to approve Session fees for the 2023 January 802 Wireless Mixed-mode Interim, Hilton Baltimore, Baltimore, MD, as $700/$900/$1100 for any in-person or virtual attendee. Registration Target to open Nov 15, 2022
Rate Changes are Early-bird until Dec 9; Standard until Jan 6, 2023.
Refund Schedule: Full until Dec 9, $150 fee until Jan 6, and no refund after Jan 6, 2023.
Moved: Jon Rosdahl
2nd: Stephen McCann
Results: 6-0-0

## Slide 24: -Motion to approve Site Visit 2022-09-11
Move to authorize the 802W Venue Manager, Jon Rosdahl to go on a site visit with Linespeed and Face to Face Events with the purpose to prepare for 2023 January IEEE 802 Wireless Mixed-mode Interim. Expenses not to exceed: $2,600.
Note: We expect the Marriott to cover all the site visit costs (meals, travel, hotel, vendor).
Moved: Ben Rolfe
Second: Phil Beecher
Results: 7-0-1 Motion Passes.

## Slide 25: Motion to approve Site visit to Waikoloa 2022-08-03
Move to authorize the 802W Venue Manager, Jon Rosdahl to go on a site visit with Linespeed with the purpose to prepare for Virtual access for the 2022 Sept IEEE 802 Wireless Mixed-mode Interim. Expenses not to exceed: $2,600
Moved: Dorothy Stanley
2nd: Clint Powell
Results: 5-0-0 Motion Passes (ECJT voters)
Notes: Airfare $1300
Meals: $300 Transfers: $400 Hotel: $600
Not to exceed: $2,600