## Slide 1: 06AUG2024 History Ad Hoc Update
Reiterate Scope/Duties/Membership/Voting
Review plan
Status of plan
Solicit Volunteers – one from each WG/TAG
Set up meeting schedule
Begin execution

## Slide 2: 19JUL2024 Motion: Approve the formation of an 802 History Ad Hoc, with the scope, duties, membership and voting as shown in EC 24-182-01
Scope:
      Initiate electronic preservation of historical 802 documents
      Identify pertinent materials of historical interest, e.g., documents, audio recordings, video recordings, etc.
      Find a location(s) at which to store/display pertinent physical artifacts
      Capture recollections of long time 802 LMSC participants
      Develop a plan and budget for curation and presentation of materials
      Solicit support of IEEE History Center
      Review potential sources of funds, e.g., IEEE SA, IEEE Computer Society and IEEE New Initiatives
  Duties: Provide regular status reports to 802 LMSC
  Membership: Open to any interested participant
  Voting: straw polls only
  Moved: Chaplin
  Seconded: Zimmerman
  Approve by Unanimous Consent

## Slide 3: 802 History Ad Hoc Plan of Record
Prioritize preserving the first 15 years (1979-1994) of historical material
Investigate partnering with Ethernet Alliance
Tentative Next Steps
  Motion to form 802 History Ad Hoc.
    If approved, flesh out Ad Hoc logistics by October 2024 EC telecon
  Geoff Thompson to investigate preservation of documents in his possession
  Peter Jones to investigate EA collaboration
  Paul Nikolich to investigate Computer Society collaboration
  Tuncer Baykas to support activity as needed

## Slide 4: 802 History Ad Hoc Plan Status
Prioritize preserving the first 15 years (1979-1994) of historical material
Tentative Next Steps
  Form 802 History Ad Hoc -- COMPLETE.
    If approved, flesh out Ad Hoc logistics by October 2024 EC telecon
  Geoff to investigate preservation of documents in his possession
  Peter to investigate EA collaboration – IN PROCESS
  Paul to investigate Computer Society collaboration – IN PROCESS
  Tuncer to support activity as needed -- ONGOING

## Slide 5: 802 History Ad Hoc Volunteers
Current Membership Roster
  Interim Chair PaulN, looking for a longer term (at least until MAR2026) Chair
  Paul Nikolich, James Gilb, Tuncer Baykas, Peter Jones, Geoff Thomson, Srinivas Kandala (802.11WG), Edward Au (802.18 TAG)
  Looking for at least one person from each WG/TAG—any volunteers?

## Slide 6: 802 History Ad Hoc Meeting Schedule
Establish regular meeting cadence
  Initial 1hour telecon 3pm Monday 12 August 2024
    Obtain and review status on ongoing activities
    Obtain agreement on a regular meeting cadence and tentative dates
      Monthly, bi-monthly, other?
    Any other business