## NO
Voter (Last name, First name) | Clause | Comment Type (E or T) | Part of No Vote? (Y or N) | Comment / Explaination | Recommended Change | Adoped Resolution | Status (Accept, Reject, Counter) | Commenter Satisfied
Myles, Andrew | 3 | T | Y | The definition of a "protection mechanism" seems to imply that protection can only be provided by use of the NAV mechanism. This implies that CCK-OFDM cannot be used as a protection mechanism when b1 in table 7.3.2.9 is set equal to 1. This means that CCK-OFDM is useless because: * it is not allowed to be used when it is needed * is not needed when it may be used. | A number of choices exist: * Remove CCK-OFDM (I pefer this choice for other reasons) * Rewrite the definition and other text to make it clear CCK-OFDM can be used as a protection mechanism (I suspect the group will prefer this choice) | The wording of Table 7.3.2.9 is not as clear as possible. We will modify to state that protection mechanism is required for MPDUs transmitted at one of the ERP-OFDM rates. Thus, PBCC, CCK-OFDM, CCK, and Barker modulation formats are allowed when b1 is set without use of a protection mechanism. CCK-OFDM does not provide a particularly useful protection mechanism for ERP-OFDM, and CCC-OFDM has been included in part because it does not require a protection mechanism itself. The commenter's suggestion to remove CCK-OFDM is rejected. The commenter's alternative is rejected because CCK-OFDM is not a recommended protection mechanism. Clarification is added to help clarify that CCK-OFDM can be used when b1 is set. | Countered
Myles, Andrew | 9.6 | T | Y | The rate rules as currently stated are broken: * Suppose an AP specifies all rates for all PHYs as "supported" (including PBCC 22Mb/s) * Suppose the AP specifies the "basic rate set" equal to the mandatory rates only (or possibly even a subset of the mandatory rates) * Assume this is an ERP environment * Suppose an STA sends a fragment chain using PBCC 22MB/s (allowed as it is "supported" by the AP) * Under the proposed rules the AP would send the ACKs using PBCC 22Mb/s * Any STA that only implemented the basic rates only or didn't implement PBCC 22Mb/s would fail to receive the ACKs * Therefore the NAV protection mechansim in fragment chains would fail | The rate rules appear to have been thrown together. It is a difficult problem. However, there are a variety for solutions possible including a combination of: * Remove PBCC, which will simplify the problem * Competely rethink rate rules to account for all possible cases (a non-trival task) | The commenter states that the NAV mechanism is not provided through a BSS for a fragment sequence modulated with PBCC data and control responses. This is certainly not true when physical carrier sense can be relied upon as all devices in a network must decode the barker PLCP header and obtain the duration. Devices not capable of the PBCC decoding will not be able to receive the virtual carriser sense information. When there are hidden nodes, the commenter's assertion may be true. However, this is not specifically a fault that must be corrected. Devices may use alternative means for delivery of fragmented sequences when such a situation arises. The commenter's solution to remove PBCC is rejected. The commenter's other solution is not specific enough for us to evalute. | Declined
Myles, Andrew | 9.6 | T | Y | The text in the 802.11b standard says, "All Control frames shall be transmitted at …". This draft changes it to, "All Control frames sent in response to nonERP frames …". The new text removes any specification of what rate should be used for the initial control frame. | Clarify what rate shall be used to send the initial control frame. I suggest you keep the old specification | Add an initial sentence to the paragraph that states: All control frames initiating a frame exchange sequence shall be transmitted at one of the rates in the BSS rate set so they will be understood by all STAs in the BSS. | Accepted
Yee, Jung | 18.2.2.2 | T | Y | Improper context for text addition | This section refers to clause 18 type modulations only. Remove the section, as it has no bearing on clause 19 modulations
Gilb, James | 19.1.2 | T | Y | Improper use of the word "can" when "may" is the correct word. | The word "can" is not equivalent to "may" and its use is deprecated in the standard. Search the draft and change "can" to "may" as appropriate or restructure the sentences to avoid the use of this word. | Accept. Editor will make changes. | Accepted | YES
Heile, Robert | 19.1.2 | T | Y | Improper use of the word "can" when "may" is the correct word. | The word "can" is not equivalent to "may" and its use is deprecated in the standard. Search the draft and change "can" to "may" as appropriate or restructure the sentences to avoid the use of this word. | Accept. Editor will make changes. | Accepted | YES
Jalfon, Marc | 19.1.2 | T | Y | "This implies that ERP and clause 18 CCA detectors are active simultanously because in most cases the receive modulation will not be known a-priori". This implication is not true, and doesn't add any normative or informative value anyway. | Remove this sentence from the draft | Sentence has been changed to: "Since protection mechanisms are not required in all cases, the ERP CCA mechanisms for all preamble types shall be active at all times." | Counter.
Jalfon, Marc | 19.1.2 | T | Y | ERP-DSSS/CCK maximum input signal level -20dBm is different from its counterpart in 802.11b | Change the limit to -10dBm | The maximum input signal level was relaxed to simplify the design of 802.11g radios. The 802.11a standard allows -30 dBm maximum signal level and increasing the level to -10 dBm would require 802.11g devices to cover a much larger dynamic range. This greatly complicates the design of AGC algorithms. Also, it should be noted that this is the minimum requirement. Manufacturers can provide larger dynamic ranges if they feel this gives a competitive advantage. | Rejected.
Jalfon, Marc | 19.1.2 | T | Y | The line:"In addition, the mandatory and optional waveforms utilized by clause 19 are designed to be robust against more general interference sources" is too generic and doesn't carry any vluable information or requirement. | Specify the increased robustness or remove sentence from the draft | Accepted. The editor has been instructed to remove the sentence. | Accepted. | YES
Walker, Jesse | 19.1.2 | T | Y | "This implies that ERP and clause 18 CCA detectors are active simultanously because in most cases the receive modulation will not be known a-priori". This implication is not true. | Please remove this sentence from the draft | Sentence has been changed to: "Since protection mechanisms are not required in all cases, the ERP CCA mechanisms for all preamble types shall be active at all times." | Counter.
Walker, Jesse | 19.1.2 | T | Y | ERP-DSSS/CCK maximum input signal level -20dBm is different from its counterpart in 802.11b | Please change the limit to -10dBm, or provide justification for the difference | The maximum input signal level was relaxed to simplify the design of 802.11g radios. The 802.11a standard allows -30 dBm maximum signal level and increasing the level to -10 dBm would require 802.11g devices to cover a much larger dynamic range. This greatly complicates the design of AGC algorithms. Also, it should be noted that this is the minimum requirement. Manufacturers can provide larger dynamic ranges if they feel this gives a competitive advantage. | Rejected.
Myles, Andrew | 19.1.4 | T | Y | This comment is repeated from LB41. The "hidden node capability" is not described in these terms in 9.2.1 | Either change 9.2.1 to refer to the "hidden station capability" or remove the term from 19.1.4. | Accepted. Sentence has been changed to: "Interoperability is addressed by use of the virtual carrier sense mechanism specified in 9.2.1." | Accepted | YES
Gilb, James | 19.2 | T | Y | The text here claims that the ERP "By design, 802.11g coexists with 802.11b and as a result coexists with all approved IEEE standards for the 2.4GHz ISM band as of July 2002." However, the current requirments do not necessarily provide coexistence with non-ERP STAs. In fact, the ERP PHYs will negatively impact adjacent and alternate channel WLANs. In addition, the draft does not address coexistence with 802.15.1 and 802.11 FHSS, which are both IEEE 802 standards in the 2.4 GHz band. | Add a subclause that: 1) Describes what was done to provide coexistence with 802.11b STAs. Expand on the techniques listed in this paragraph to describe what was done and what is the impact. 2) Shows the degredation of the performance of 802.11b networks in the presence of ERPs with the higher TX spectral mask. This could either be FER, BER or range for a given error ratio. 3) Lists what networks may be used in overlapping areas and what wireless networks should not be used in overlapping areas. 4) Contains a short summary of the types of coexistence methods that are available for 802.11b/g systems that operate in conjunction with 802.15.1 systems based on the work done by 802.15.2 | Reject. In Draft 4.0 (Letter Ballot #49), the following changes were made as a counter to this comment. 1) Editorial: Remove the statement "…and as a result coexists with all approved IEEE standards for the 2.4 GHz ISM band as of July 2002." 2) Coexistence and backward compatibility with 802.11b is provided by the protection mechanism described in Section 7.3.2.9 of Draft 4.0 3) The 802.11g group has discussed the possible degradation of 802.11b networks with the introduction of ERP devices. It has been our opinion that the impact is minimal or non-existence for most scenarios. Quantifying the impact is beyond the scope of the standard. | Reject.
Heile, Robert | 19.2 | T | Y | The text here claims that the ERP "By design, 802.11g coexists with 802.11b and as a result coexists with all approved IEEE standards for the 2.4GHz ISM band as of July 2002." However, the current requirments do not necessarily provide coexistence with non-ERP STAs. In fact, the ERP PHYs will negatively impact adjacent and alternate channel WLANs. In addition, the draft does not address coexistence with 802.15.1 and 802.11 FHSS, which are both IEEE 802 standards in the 2.4 GHz band. | Add a subclause that: 1) Describes what was done to provide coexistence with 802.11b STAs. Expand on the techniques listed in this paragraph to describe what was done and what is the impact. 2) Shows the degredation of the performance of 802.11b networks in the presence of ERPs with the higher TX spectral mask. This could either be FER, BER or range for a given error ratio. 3) Lists what networks may be used in overlapping areas and what wireless networks should not be used in overlapping areas. 4) Contains a short summary of the types of coexistence methods that are available for 802.11b/g systems that operate in conjunction with 802.15.1 systems based on the work done by 802.15.2 | Reject. In Draft 4.0 (Letter Ballot #49), the following changes were made as a counter to this comment. 1) Editorial: Remove the statement "…and as a result coexists with all approved IEEE standards for the 2.4 GHz ISM band as of July 2002." 2) Coexistence and backward compatibility with 802.11b is provided by the protection mechanism described in Section 7.3.2.9 of Draft 4.0 3) The 802.11g group has discussed the possible degradation of 802.11b networks with the introduction of ERP devices. It has been our opinion that the impact is minimal or non-existence for most scenarios. Quantifying the impact is beyond the scope of the standard. | Reject.
Jalfon, Marc | 19.2 | T | Y | Transmit powerlevels are not defined. | Define the 8 level or state that they are up to the implementation. | Accept. Editor will add the statement that these 8 levels are up to the implementation. | Accept | YES
O'Hara, Bob | 19.2 | T | Y | The resolution of my comment to 19.2 regarding the technical incompaibility of the various PHYs was dismissed with a procedural explanation, without any technical justification. Just because the lemmings are going to jump off the cliff, does not mean that it is the right thing to do. | Accept original comment and resolution. | Rejected. Compatibility of the various PHYs is achieved through both the physical carrier sense mechanisms and the virtual carrier sense mechanisms. | Rejected.
Petrick, Al | 19.2 | T | Y | Table 19.2.1 Modulation rates unclear Mandatory? Optional | The table calls out CCK and ER-OFMD mandatory PBCC rates should be labeled as "optional" | Counter. This table has been modified. All references to which rates are mandatory and which rates are optional have been removed. | Counter
Walker, Jesse | 19.2 | T | Y | Transmit power levels are not defined. | Please define the transmit power levels or state that they are up to the implementation. | Accept. Editor will add the statement that these 8 levels are up to the implementation. | Accept | YES
Yee, Jung | 19.2 | T | Y | Insufficient description | Move the parameter descriptions out of the table and into the body of the text. State the associate primitive for each parameter, especially for the the new PreambleType and Modulation parameters. | TBD
Gilb, James | 19.2, 19.4.3.10.3, 19.5.3.6.2 | T | Y | This version of the standard has relaxed the input signal level from -10 dBm to -20 dBm. With the possibility of peer-to-peer connections with Tge in a BSS, peer-to-peer connections in an IBSS as well as APs that are small and may be located close to the STA, it is likely that STAs will exceed this limit. With +14 dBm TX power, -10 dBm is approximately 0.2 m while -20 dBm is about 0.5 m (based on 802.11 model). | Change the maximum input signal level to -10 dBm for All ERP modes. | The maximum input signal level was relaxed to simplify the design of 802.11g radios. The 802.11a standard allows -30 dBm maximum signal level and increasing the level to -10 dBm would require 802.11g devices to cover a much larger dynamic range. This greatly complicates the design of AGC algorithms. Also, it should be noted that this is the minimum requirement. Manufacturers can provide larger dynamic ranges if they feel this gives a competitive advantage. | Reject.
Heile, Robert | 19.2, 19.4.3.10.3, 19.5.3.6.2 | T | Y | This version of the standard has relaxed the input signal level from -10 dBm to -20 dBm. With the possibility of peer-to-peer connections with Tge in a BSS, peer-to-peer connections in an IBSS as well as APs that are small and may be located close to the STA, it is likely that STAs will exceed this limit. With +14 dBm TX power, -10 dBm is approximately 0.2 m while -20 dBm is about 0.5 m (based on 802.11 model). | Change the maximum input signal level to -10 dBm for All ERP modes. | The maximum input signal level was relaxed to simplify the design of 802.11g radios. The 802.11a standard allows -30 dBm maximum signal level and increasing the level to -10 dBm would require 802.11g devices to cover a much larger dynamic range. This greatly complicates the design of AGC algorithms. Also, it should be noted that this is the minimum requirement. Manufacturers can provide larger dynamic ranges if they feel this gives a competitive advantage. | Reject
Chen, Hung Kun | 19.3.1 | T | Y | No point to make short preamble mandatory in 802.11g, since it is not backward compatible with 802.11b, and the major traffic for 802.11g will be OFDM, so there is no point to make CCK-oriented short preamble mandatory. | Make short preamble optional | While the gains are small, the Short preamble was made mandatory in order to increase the throughput as much as possible for this and any future extensions based on 802.11g. Note that all 802.11g devices must support long preamble so there are no interoperability issues. | Reject.
Liu, Shawn | 19.3.1 | T | Y | No point to make short preamble mandatory in 802.11g, since it is not backward compatible with 802.11b, and the major traffic for 802.11g will be OFDM, so there is no point to make CCK-oriented short preamble mandatory. | Make short preamble optional | While the gains are small, the Short preamble was made mandatory in order to increase the throughput as much as possible for this and any future extensions based on 802.11g. Note that all 802.11g devices must support long preamble so there are no interoperability issues. | Reject
Maa, Yeong-Chang | 19.3.1 | T | Y | No point to make short preamble mandatory in 802.11g, since it is not backward compatible with 802.11b, and the major traffic for 802.11g will be OFDM, so there is no point to make CCK-oriented short preamble mandatory. | Make short preamble optional | While the gains are small, the Short preamble was made mandatory in order to increase the throughput as much as possible for this and any future extensions based on 802.11g. Note that all 802.11g devices must support long preamble so there are no interoperability issues. | Reject
Petrick, Al | 19.3.1 | T | Y | Did not call out 1Mbit/s | Last sentence needs to read " when using the existing 1, 2, 5.5, and 11Mbit/s modes." | Counter. This sentence will be deleted. | Counter.
Gilb, James | 19.3.2.3.1 | T | Y | If RTS/CTS is mandatory, the non-ERP STAs will know how long to wait for the ERP-OFDM frame to finish. However, if this is not used, an non-ERP STA may start counting its backoff furing the length extension field since it is quite time on the air. | Change the length extension field to be a transmission of random bits rather than a period of no transmission. | The length extension field was designated as a quiet time to allow more time for the radios to switch from transmit mode to receive mode. If the length extension consisted of random bits, this would greatly reduce the transmit to receive turn around time and could increase the complexity of the radio design. | Reject.
Heile, Robert | 19.3.2.3.1 | T | Y | If RTS/CTS is mandatory, the non-ERP STAs will know how long to wait for the ERP-OFDM frame to finish. However, if this is not used, an non-ERP STA may start counting its backoff furing the length extension field since it is quite time on the air. | Change the length extension field to be a transmission of random bits rather than a period of no transmission. | The length extension field was designated as a quiet time to allow more time for the radios to switch from transmit mode to receive mode. If the length extension consisted of random bits, this would greatly reduce the transmit to receive turn around time and could increase the complexity of the radio design. | Reject
Petrick, Al | 19.3.3.2 | T | Y | Section doesn't describe when the clock switch occurs. Looking at figure 19.3.3.2-3 its unclear where the bits are aligned and which edge the clock is switched. If this isn't described carefully, this could cause interoperability problems! | Add text describing when the clock is switched, rising, falling edge, were are the bits aligned. And update Figure 19.3.3.2-3 | As described in the text below Figure 19.3.3.2-3, the clock switch occurs between the 'tail' and the 'head' portion of the shift window. Resynchronization will occur during the 'ReSync' portion of the shift window. This resynchronization will ensure interoperability. | Reject
Jalfon, Marc | 19.3.4 | T | Y | The terms "ERP rates" and "non-ERP rates" are not defined. | define | Counter. In the last sentence of the first paragraph in 19.3.4, the acronym ERP has been removed. The sentence now reads: "For the rates of 6, 12, 24 and the rates of 9, 18, 36, 48, and 54 Mbit/s, the PLCP transmit procedure shall follow 17.3.11. " | Counter
Jalfon, Marc | 19.3.6 | T | Y | The sentence:" For short preamble and long preamble using Barker,CCK, or PBCC modulations,…" seems to imply that all implementations have to support PBCC, which is actually an option. | specify behavior of receiver when receiving a non-implemented, optional, modulation scheme. | Counter. As stated in section 19.3.6, a receiver shall follow Subclause 18.2.6 for all three modulations. If the modulation or rate is not supported, Subclause 18.2.6 specifies the behavior. | Counter
Walker, Jesse | 19.3.6 | T | Y | The sentence:" For short preamble and long preamble using Barker,CCK, or PBCC modulations,…" seems to imply that all implementations have to support PBCC, which is actually an option. | Please specify the required behavior of receiver when receiving a non-implemented, optional, modulation scheme. | Counter. As stated in section 19.3.6, a receiver shall follow Subclause 18.2.6 for all three modulations. If the modulation or rate is not supported, Subclause 18.2.6 specifies the behavior. | Counter
Yee, Jung | 19.3.6 | T | Y | Incorrect reference | RXVECTOR as described in 12.3.4.4 cannot report the described values. Give the correct reference or define the new RXVECTOR | Accept. Editor shall change the reference to 19.2. | Accept | YES
Venugopal, Madan | 19.4.2 | T | Y | To reduce adjacent channel interference and avoid transmit power reduction for FCC compliance require 2channel operation for the 11g standard as proposed in doc:IEEE 802.11-02/420r0 | Add the following text under 19.4.2 as proposed in doc:IEEE 802.11-02/420r0 : "Operating channel frequencies of 2422 MHz and 2452 MHz (channels 3 and 9) are preferred in order to a) maximize transmit power while being FCC compliant, and b) to reduce adjacent channel interference." | Operating channels are an implementation specific issue. It is not clear that using only two channels would be preferred in all cases. For instances, existing deployments frequently use three channels. In this case, the 802.11g system, in order to be compatible, should use three channels. | Reject
Gilb, James | 19.4.3.8.4 | T | Y | In order to ensure fair access to non-ERP STAs, the text here needs to say that the shorter slot time shall only be used when there are no non-ERP STAs associated. | Change the sentence to read "except that an optional 9 µs slot time may be used when the network consists of only ERP devices. The optional 9 µs slot time shall not be used if the network has one or more non-ERP devices associated." | Accept. Editor will make the suggested change. | Accept | YES
Heile, Robert | 19.4.3.8.4 | T | Y | In order to ensure fair access to non-ERP STAs, the text here needs to say that the shorter slot time shall only be used when there are no non-ERP STAs associated. | Change the sentence to read "except that an optional 9 µs slot time may be used when the network consists of only ERP devices. The optional 9 µs slot time shall not be used if the network has one or more non-ERP devices associated." | Accept. Editor will make the suggested change. | Accept | YES
Smart, Kevin | 19.4.4 | T | Y | The short slot time is a nice option from an 802.11a compatability standpoint, but the details of how to switch between short and long slots are missing or very weak. | Either add a mechanism to switch between short and long or long and short to handle the case of a long slot time device leaving or remove the short slot time option completely. If the short slot time option is removed, that option could be handled in the HTSG. | Discuss as part of short slot time | TBD
Jose, Bobby | 19.4.5 | T | Y | As with the current standar the ERP is required to perform CCA according to at least one of three methods. However it is beneficial to require that the ERP support all the methods so that the entire BSS can be configured to use the same CCA method, using the dot11CurrentCCAMode PHY MIB Attribute. Response to adopted resolution to comment in LB 41. Although this is not possible with legacy devices in the BSS, the change will become beneficial when legacy devices are phased out over time. | change the line to " The ERP shall provide the capability to perform CCA according to all of the following three methods", dot11CCAModeSupported may still be supported for legacy reasons, and be shown to have all options. Update PICS accordingly. | There are currently no mechanisms available for an AP to specify the CCA mode or threshold. The PHY MIB, dot11CCAModeSupported communicates the CCA mode being used to the MAC. Consequently, the recommended change would have no immediate benefit and could burden the radio with added complexity. For example, mandating all three CCA modes, a manufacturer could be forced to implement a lower performing CCA mode. And, as noted previously, legacy 802.11b systems must be supported in 802.11g networks. Consequently, any future method that relies on the support of all CCA modes would not apply to these legacy systems. | Reject
Jalfon, Marc | 19.4.6 | T | Y | The CCA detect probability should be changed to 70% for 4uSec, this will match the 15uSec probability value of 99%. Otherwise reciever that has 90% probability of success in 4uSec will get the 99% in 8uSec and the other requirement is not necessary. | Change from 90% to 70% in the table | The 90% within 4 useconds was selected to match the performance of 802.11a. The implementation of the 9 usecond slot time is optional and therefore a more stringent CCA requirement is appropriate. | Reject
Walker, Jesse | 19.4.6 | T | Y | The CCA detect probability should be changed to 70% for 4uSec, to match the 15uSec probability value of 99%. | Please change from 90% to 70% in the table | The 90% within 4 useconds was selected to match the performance of 802.11a. The implementation of the 9 usecond slot time is optional and therefore a more stringent CCA requirement is appropriate. | Reject
Jalfon, Marc | 19.5 | T | Y | A clause similar to 19.5 defining ERP-DSSS/CCK is missing. | Add new equivalent clause for ERP-DSSS/CCK | Accept. Editor will change title to reflect that Subclause 19.5 covers both ERP-OFDM and ERP-DSSS/CCK. Also, editor will add the appropriate references or values for the ERP-DSSS/CCK performance in each subsection. | Accept | YES
Walker, Jesse | 19.5 | T | Y | A clause similar to 19.5 defining ERP-DSSS/CCK is missing. | Please add a new clause for ERP-DSSS/CCK | Accept. Editor will change title to reflect that Subclause 19.5 covers both ERP-OFDM and ERP-DSSS/CCK. Also, editor will add the appropriate references or values for the ERP-DSSS/CCK performance in each subsection. | Accept | YES
Tsai, Allen | 19.5.2 | T | Y | An OFDM signals generate more in-band interference to a CCK signal, the adjacent channel rejection specification in clause 18.4.8.3 is obsolete. | Specification for a new adjacent channel rejection requirement is needed. For example, apply the 802.11b TX power mask to ERP-OFDM. | The adjacent channel requirements are specified in 19.4.3.10.2. This issue has been extensively discussed in previous meetings. Based on those discussions and the votes that were taken as a result, we feel that the test in 19.4.3.10.2 will be sufficient to ensure adequate performance for all possible cases. | Reject
Jalfon, Marc | 19.5.3 | T | Y | This clause shouldn't refer to ERP-DSSS/CCK rates | Add another clause for 1,2,5.5 and 11Mbit/s data rates. | Accept. See Row 42 & 43 | Accept | YES
Jalfon, Marc | 19.5.3 | T | Y | This clause should be identical to the corresponding clause in 17. | Remove the content and add a reference "shall follow ..." with the exception of minimal input level of -20dBm | Accept. See Row 42 & 43 | Accept | YES
Walker, Jesse | 19.5.3 | T | Y | It seems like this clause should be identical to the corresponding clause in 17. | Please replace the clause content with a reference "shall follow ...", with the exception of minimal input level of -20dBm | Accept. See Row 42 & 43 | Accept | YES
Walker, Jesse | 19.5.3 | T | Y | This clause shouldn't refer to ERP-DSSS/CCK rates | Please add a new clause for 1,2,5.5 and 11Mbit/s data rates. | Accept. See Row 42 & 43 | Accept | YES
Smart, Kevin | 19.5.4 | T | Y | The spectral mask of the OFDM signal will cause more interference to adjacent channels than CCK or PBCC. This will degrade the performance of existing systems. | Tighten the spectral mask so that it will guarantee no more adjacent channel interference than exists in current 802.11b systems. For a potential solution, see 11-02-347r1 by Steve Halford. | The group has extensively studied the issue of adjacent channel interference. It is not clear that there will be a performance impact on legacy 802.11b. Further, adopting a more restrictive mask will reduce the amount of transmit power available for the ERP-OFDM modes. This will have a definite impact on the range. | Reject
Gilb, James | 19.5.4 and 19.4.7 | T | Y | The adoption of the 802.11a transmit spectral mask will have a negative impact on overlapping 802.11 WLANs as well as on 802.15.1 piconets. | Revise the transmit spectral mask to match the requirements of 802.11b | The group has extensively studied the issue of adjacent channel interference. It is not clear that there will be a performance impact on legacy 802.11b. Further, adopting a more restrictive mask will reduce the amount of transmit power available for the ERP-OFDM modes. This will have a definite impact on the range. | Reject
Heile, Robert | 19.5.4 and 19.4.7 | T | Y | The adoption of the 802.11a transmit spectral mask will have a negative impact on overlapping 802.11 WLANs as well as on 802.15.1 piconets. | Revise the transmit spectral mask to match the requirements of 802.11b | The group has extensively studied the issue of adjacent channel interference. It is not clear that there will be a performance impact on legacy 802.11b. Further, adopting a more restrictive mask will reduce the amount of transmit power available for the ERP-OFDM modes. This will have a definite impact on the range. | Reject
Chen, Hung Kun | 19.6 | T | Y | There is an uncertainty whether it pays to have a third PHY, PBCC-22/33, which may have side-effect to CCK and OFDM. | The PBCC-22/33 option should be insured that there is no ill impact to CCK and OFDM. | Reject/Tradeoffs were previously explored. The ill effect that was commented is not known to exist. The commenter offered no new specifications for review. | Reject
Liu, Shawn | 19.6 | T | Y | There is an uncertainty whether it pays to have a third PHY, PBCC-22/33, which may have side-effect to CCK and OFDM. | The PBCC-22/33 option should be insured that there is no ill impact to CCK and OFDM. | Reject/Tradeoffs were previously explored. The ill effect that was commented is not known to exist. The commenter offered no new specifications for review. | Reject
Maa, Yeong-Chang | 19.6 | T | Y | There is an uncertainty whether it pays to have a third PHY, PBCC-22/33, which may have side-effect to CCK and OFDM. | The PBCC-22/33 option should be insured that there is no ill impact to CCK and OFDM. | Reject/Tradeoffs were previously explored. The ill effect that was commented is not known to exist. The commenter offered no new specifications for review. | Reject
Myles, Andrew | 19.6 | T | Y | This comment is repeated from LB41 The additional throughput performance from using CCK-OFDM (at 12, 18, 24, 36, 48, 54Mb/s) compared to 11b (at 11Mb/s) for a typical packet length distribution is small (<2Mb/s). So small that the specification of CCK-OFDM is just not worth the effort. In response to the TG's reponse from LB41. For long packets at all rates the CCK-OFDM mechanism will provide some benefit. However, in these cases you you be better off using the CTS@11b -> Data@OFDM - > ACK@OFDM protection mechanism rather than Data@CCK-OFDM -> ACK@CCK-OFDM | Remove CCK-OFDM, even as an option | Reject/Leave CCK-OFDM option as is. Tradeoffs were previously explored. | Reject
Gilb, James | 19.6.3 | T | Y | Improper use of the word "cannot" when "shall not" is the correct word. | Change “cannot” to “shall not” | Accept/Change to "shall not" | Accept | YES
Gilb, James | 19.6.3 | T | Y | The adjacent channel rejection is specified for an interferer that adheres to the transmit spectral mask. However, an interferer that just met the mask would put so much power into the passband that it would be impossible to achieve the error requirements. | Either change the adjacent channel rejection specification or indicate that this requires a jamming source whose TX spectral mask is more stringent than the one for the transmitter. | Reject/The adjacent channel rejection specifications all assume a .11 transmit waveform that meets the transmit spectral mask as the interferer. | Reject
Heile, Robert | 19.6.3 | T | Y | Improper use of the word "cannot" when "shall not" is the correct word. | Change “cannot” to “shall not” | Accept comment Editoral/Change to "shall not" | Accept | YES
Heile, Robert | 19.6.3 | T | Y | The adjacent channel rejection is specified for an interferer that adheres to the transmit spectral mask. However, an interferer that just met the mask would put so much power into the passband that it would be impossible to achieve the error requirements. | Either change the adjacent channel rejection specification or indicate that this requires a jamming source whose TX spectral mask is more stringent than the one for the transmitter. | Reject/The adjacent channel rejection specifications all assume a .11 type transmit waveform as the interferer that meets the transmit spectral mask | Reject
Chen, Hung Kun | 19.7 | T | Y | There is no need to have ERP using a fourth PHY, CCK-OFDM, other than CCK and OFDM. | The CCK-OFDM option should be insured to have a better way to work with CCK and OFDM. | Reject/Previously explored | Reject
Liu, Shawn | 19.7 | T | Y | There is no need to have ERP using a fourth PHY, CCK-OFDM, other than CCK and OFDM. | The CCK-OFDM option should be insured to have a better way to work with CCK and OFDM. | Reject/Previously explored as above | Reject
Maa, Yeong-Chang | 19.7 | T | Y | There is no need to have ERP using a fourth PHY, CCK-OFDM, other than CCK and OFDM. | The CCK-OFDM option should be insured to have a better way to work with CCK and OFDM. | Reject/Previously explored as above | Reject
Gilb, James | 19.7.2.1.2 | T | Y | Improper use of the word "can" when "may" is the correct word. | The word "can" is not equivalent to "may" and its use is deprecated in the standard. Search the draft and change "can" to "may" as appropriate or restructure the sentences to avoid the use of this word. | Editorial/Editor may change where appropriate | Accept | YES
Heile, Robert | 19.7.2.1.2 | T | Y | Improper use of the word "can" when "may" is the correct word. | The word "can" is not equivalent to "may" and its use is deprecated in the standard. Search the draft and change "can" to "may" as appropriate or restructure the sentences to avoid the use of this word. | Editorial/Editor may change where appropriate | Accept | YES
Moore, Tim | 19.8.1 | T | Y | MIB variables defined in this section are not consistent with Annex D | Correct MIB variables to be consistent with MIB definiation in Annex D
Moore, Tim | 19.8.1 | T | Y | No MIB variable to enable/disable ERP-OFDM | Add MIB variable dot11ERP-ODFMOptionEnabled and to Annex D
Moore, Tim | 19.8.1 | T | Y | Two mib variables dot11CCK-OFDMOptionImplemented | One variable should be dot11CCK-OFDMOptionEnabled
Jalfon, Marc | 19.9.4.3 | T | Y | RSSI primitive is not consistent with the values range of it in RXVECTOR. | Fix it to be consistent.
Jalfon, Marc | 19.9.4.3 | T | Y | The RATE primitive definition is not consistent between ERP-DSSS/CCK rate and ERP-OFDM rates. For DSSS and CCK we use the net data rate which are 1,2,5.5 and 11M and not the gross rate which are 11M and 22M. For OFDM it uses the gross rates. | Fix it to be consistent.
Walker, Jesse | 19.9.4.3 | T | Y | The RATE primitive definition is not consistent between ERP-DSSS/CCK rate and ERP-OFDM rates. The DSSS and CCK specifications use the net data rate which are 1,2,5.5 and 11M, not the gross rate which are 11M and 22M. The OFDM specification uses the gross rates. | Please make these definitions consistent.
O'Hara, Bob | 7.2.3.1 | T | Y | The resolution of my comment to 7.2.3.1 about the inappropriate use of the Beacon to carry two bots of PHY information in an information element was dismissed with a "belief" and no technical justification. It is not an adequate technical response to a technical comment. | Accept original comment and resolution. | The proposed solution by the commenter is to delete the 2 bits contained in the NonERP Indication Element and to move them to the PHY header. These bits are essential to the propagation of information used to provide compatibility with Clause 16 and 18 devices. Deleting these bits would break essential function. The bits are used for MAC to MAC functions and the they do not belong in the PHY header. The group declines to delete these bits and move them to the PHY header. | Reject
O'Hara, Bob | 7.2.3.9 | T | Y | The resolution of my comment to 7.2.3.9 about the inappropriate use of the Beacon to carry two bots of PHY information in an information element was dismissed with a "belief" and no technical justification. It is not an adequate technical response to a technical comment. | Accept original comment and resolution. | The resolution fo comment 71 applies to this comment as well. | Reject
Jose, Bobby | 7.3.1.4 | T | Y | Page 9, lines 1-3 Allowing an AP to use short slot time based on receiption of a single beacon from one other AP is not a good idea, Consider the presence of other APs, or other STA that do not use ShortSlotTime. | Resolution A: Replace lines 1-3 with the following text. "An AP may set the ShortSlotTime Subfield to 1, only if its MIB attribute dot11ShortSlotTimeOptionImplemented is true and it has never received a beacon with a NonERP Indication Element with bit 0 set to true during the past aLongSlotScanPeriod (default value of 1000) TBTTs). | A group has been formed to specify a method to coordinate oerlapping BSS. Their solution should include resolution to this comment. | TBD
Jose, Bobby | 7.3.1.4 | T | Y | Page 9, lines 1-3 B) Is the exclusion of IBSS beacon's a sideeffect ? C) One AP has no idea of the MIB attribute of the other BSS, so it cannot make a decision by directly observing if the MIB attribute for the other BSS is true. | if resolution A above is not acceptable, use the following alternate resolution. Replace lines 1-3 with the following text. "When an AP receives a beacon with a NonERP Indication Element with bit 0 set to false, it may set the Short Slot Time Subfield to 1, if the MIB attribute dot11ShortSlotTimeOptionImplemented is true." | A group has been formed to specify a method to coordinate oerlapping BSS. Their solution should include resolution to this comment. | TBD
Davis, Barry | 7.3.1.4 | T | Y | the "shall" clause for selecting short or long slot times specifies that the longest supported slot time be used. Since all stations are required to implement the longer slot time, short slot time will never be used | delete the short slot time option | The group has agreed that the statement contains an editorial error. This will be fixed. Additionally a group has been formed to speicfy any necessary method(s) to coordinate overlpapping BSSs. | Counter
Davis, Barry | 7.3.1.4 | T | Y | The short slot time specification relies upon a definition of a "neighbor" AP which is not using short slot time. However, there is no specification for what constitutes a "neighbor" or how it should be discovered. Nonetheless, the resultant behavior is the subject of a "shall" clause which makes it a normative requirement. | delete the short slot time option | The group agreed to remove the sentence in question (See comment 98). Additionally a group has been formed to specify any necessary method(s) to coordinate overlapping BSSs. | Counter
Davis, Barry | 7.3.1.4 | T | Y | this clause requires an AP to know the values of MIB parameters in other Aps in order to correctly implement the protocol, but there is no mechansim defined for this to happen | delete the short slot time option | The group agrees in principle with the comment that this sentence is not implementable as is. A group has been formed to specify any necessary method(s) to cooridnate overlapping BSSs. Their solution should include resolution to this comment. | Counter
Fischer, Matthew | 7.3.1.4 | T | N | page 9, line 3 -- how do I know what the dot11ShortSlotTimeOptionImplemented value is in the other BSS? | refer to the information that is in the received frame, which is the short slot bit of the capability field, but a value of 0 for the short slot bit does not tell me anything about the other STA's dot11ShortSlotTimeOptionImplemented value. (It is implied that the dot11ShortSlotTimeOptionImplemented MIB is true if the short slot bit is set to 1, but I don't actually observe that MIB -- and what about the case of short slot = 0?!) | The group agrees in principle with the comment that this sentence is not implementable as is. A group has been formed to specify any necessary method(s) to cooridnate overlapping BSSs. Their solution should include resolution to this comment. | Counter
Green, Evan | 7.3.1.4 | T | Y | page 9, first paragraph: "and the MIB attribute dot11ShortSlotTimeOptionImplemented is true in both BSSs". How does an AP know the value of MIB attributes in another AP? Is it required to implement SNMP? There is a normatively specified behavior defined here (the sentence contains the word "shall"), but for which there exists no mechanism whatever. | There is no possible mechanism within the scope of the PAR to implement this normative requirement, and, indeed, none is specified; replace it with something that is implementable and within the scope of the PAR, or delete the short slot time option. | The group agrees in principle with the comment that this sentence is not implementable as is. A group has been formed to specify any necessary method(s) to cooridnate overlapping BSSs. Their solution should include resolution to this comment. | Counter
Green, Evan | 7.3.1.4 | T | Y | page 9, second paragraph: "...but with knowledge of a neighboring co-channel BSS having long slot time traffic; the AP shall switch…". This includes a "shall" clause, indicating normative behavior, but is vastly too vague to be testable. How does one test whether an AP "has knowledge" of a "neighboring" BSS? And what constitutes "neighboring". | Either define a testable, normative behavior, and the definitions of the enclosed terms, or delete the short slot time option. | The group agreed to remove the sentence in question (See comment 98). Additionally a group has been formed to specify any necessary method(s) to coordinate overlapping BSSs. | Counter
Green, Evan | 7.3.1.4 | T | T | page 9, second paragraph: "corresponding to the longest supported slot time of all associated STAs". Since all STAs are required to implement long slot times, the longest supported slot time is always long slot time. Hence the definition prevents short slot time from ever being used. The logic here is backwards; the intended behavior is, I believe, that the shortest slot time permitted is the shortest that is supported by all associated STAs. | Either fix the text to permit short slot times to be used, or delete the short slot time option. | The group has agreed that the statement contains an editorial error. This will be fixed. | Accept
Green, Evan | 7.3.1.4 | T | Y | page 9, second paragraph: "If a STA that supports long slot time associates, the AP shall revert to long slot time at the first beacon subsequent…" this logic is, again, backwards, since all STAs support long slot time. Hence this requirement forces an AP to always use long slot time. | change the quoted text to "If a STA that does not support short slot time associates, the AP shall revert to long slot time at the first beacon subsequent…" | The group has agreed that the statement contains an editorial error. This will be fixed. | Accept
Kitchen, Duncan | 7.3.1.4 | T | Y | page 9, first paragraph: "and the MIB attribute dot11ShortSlotTimeOptionImplemented is true in both BSSs". How does an AP know the value of MIB attributes in another AP? Is it required to implement SNMP? There is a normatively specified behavior defined here (the sentence contains the word "shall"), but for which there exists no mechanism whatever. | There is no possible mechanism within the scope of the PAR to implement this normative requirement, and, indeed, none is specified; replace it with something that is implementable and within the scope of the PAR, or delete the short slot time option. | The group agrees in principle with the comment that this sentence is not implementable as is. A group has been formed to specify any necessary method(s) to cooridnate overlapping BSSs. Their solution should include resolution to this comment. | Counter
Kitchen, Duncan | 7.3.1.4 | T | Y | page 9, second paragraph: "...but with knowledge of a neighboring co-channel BSS having long slot time traffic; the AP shall switch…". This includes a "shall" clause, indicating normative behavior, but is vastly too vague to be testable. How does one test whether an AP "has knowledge" of a "neighboring" BSS? And what constitutes "neighboring". | Either define a testable, normative behavior, and the definitions of the enclosed terms, or delete the short slot time option. | The group agreed to remove the sentence in question (See comment 98). Additionally a group has been formed to specify any necessary method(s) to coordinate overlapping BSSs. | Counter
Kitchen, Duncan | 7.3.1.4 | T | T | page 9, second paragraph: "corresponding to the longest supported slot time of all associated STAs". Since all STAs are required to implement long slot times, the longest supported slot time is always long slot time. Hence the definition prevents short slot time from ever being used. The logic here is backwards; the intended behavior is, I believe, that the shortest slot time permitted is the shortest that is supported by all associated STAs. | Either fix the text to permit short slot times to be used, or delete the short slot time option. | The group has agreed that the statement contains an editorial error. This will be fixed. | Accept
Kitchen, Duncan | 7.3.1.4 | T | Y | page 9, second paragraph: "If a STA that supports long slot time associates, the AP shall revert to long slot time at the first beacon subsequent…" this logic is, again, backwards, since all STAs support long slot time. Hence this requirement forces an AP to always use long slot time. | change the quoted text to "If a STA that does not support short slot time associates, the AP shall revert to long slot time at the first beacon subsequent…" | The group has agreed that the statement contains an editorial error. This will be fixed. | Accept
Myles, Andrew | 7.3.1.4 | T | Y | "APs shall set the Short Slot Time subfield corresponding to the longest supported slot time of all associated STAs in transmitted Beacon, Probe Response, Association Response, and Reassociation Response MMPDUs to indicate the currently used slot time value within this BSS." contradicts the previous paragraph and the following sentences, which both say that the subfield is also a function of neighbouring BSS's | Fix | The group has agreed that the statement contains an editorial error. This will be fixed. Additionally a group has been formed to speicfy any necessary method(s) to coordinate overlpapping BSSs. | Accept
Myles, Andrew | 7.3.1.4 | T | Y | All the text at the end of this clause is written in terms of AP's in BSS's. What about IBSS's? | Fix | A group has been formed to specify a method to coordinate oerlapping BSS. Their solution should include resolution to this comment. | Accept
Myles, Andrew | 7.3.1.4 | T | Y | In, "When an AP receives a beacon from another AP, the receiving AP shall be allowed to set the Short Slot Time subfield to 1 if bit0 of NonERP Indication Element is set false and the MIB attribute dot11ShortSlotTimeOptionImplemented is true in both BSSs." it is not clear how the first AP would know whether or not dot11ShortSlotTimeOptionImplemented is true in the other AP. | I am not sure if this a technical problem or a language problem. In either case this needs to be fixed | The group agrees in principle with the comment that this sentence is not implementable as is. A group has been formed to specify any necessary method(s) to cooridnate overlapping BSSs. Their solution should include resolution to this comment. | Accept
Myles, Andrew | 7.3.1.4 | T | Y | Suppose a vast network of partially overlapping BSS's all used short slot times. Then suppose a single long slot time STA turned up. The entire network of BSS's would revert to long slot times (with a consequent loss of performance). Now suppose the long slot time STA went away. How would the vast network of BSS's recover such that they all used short slot times? | Clarify | A group has been formed to specify a method to coordinate oerlapping BSS. Their solution should include resolution to this comment. | Accept
Myles, Andrew | 7.3.1.4 | T | Y | This comment is repeated from LB41. The arrival of a single 11b STA (possibly in a neighbouring BSS belonging to a different organisation) can force an entire network of BSS's (possibly even an entire city) to revert to using long slot times, with a consequent loss of performance (possibly for 10's, 100's or even 1000's of STA's). | Change the mechanisms so that this is not required to occur | A group has been formed to specify a method to coordinate oerlapping BSS. Their solution should include resolution to this comment. | Accept
O'Hara, Bob | 7.3.1.4 | T | Y | The resolution of my comment to 7.3.1.4 about the inappropriate use of the CIF to carry PHY specific information was dismissed without technical justification. This is not an adequate response. | Accept original comment and resolution. | Discuss previous response and idetnify technical response. | TBD
Rettig, Danny | 7.3.1.4 | T | Y | page 9, first paragraph: "and the MIB attribute dot11ShortSlotTimeOptionImplemented is true in both BSSs". There is a normatively specified behavior defined here (the sentence contains the word "shall"), but for which there exists no mechanism whatever. | There is no possible mechanism within the scope of the PAR to implement this normative requirement, and, indeed, none is specified; replace it with something that is implementable and within the scope of the PAR, or delete the short slot time option. | The group agrees in principle with the comment that this sentence is not implementable as is. A group has been formed to specify any necessary method(s) to cooridnate overlapping BSSs. Their solution should include resolution to this comment. | Accept
Richkas, Dave | 7.3.1.4 | T | Y | Page 9, first paragraph: "and the MIB attribute dot11ShortSlotTimeOptionImplemented is true in both BSSs". How does an AP know the value of MIB attributes in another AP? Is it required to implement SNMP? There is a normatively specified behavior defined here (the sentence contains the word "shall"), but for which there exists no mechanism. | There is no possible mechanism within the scope of the PAR to implement this normative requirement, and, indeed, none is specified; replace it with something that is implementable and within the scope of the PAR, or delete the short slot time option. | The group agrees in principle with the comment that this sentence is not implementable as is. A group has been formed to specify any necessary method(s) to cooridnate overlapping BSSs. Their solution should include resolution to this comment. | Accept
Richkas, Dave | 7.3.1.4 | T | Y | Page 9, second paragraph: "...but with knowledge of a neighboring co-channel BSS having long slot time traffic; the AP shall switch…". This includes a "shall" clause, indicating normative behavior, but is vastly too vague to be testable. How does one test whether an AP "has knowledge" of a "neighboring" BSS? And what constitutes "neighboring". | Either define a testable, normative behavior, and the definitions of the enclosed terms, or delete the short slot time option. | The group agreed to remove the sentence in question (See comment 98). Additionally a group has been formed to specify any necessary method(s) to coordinate overlapping BSSs. | Counter
Richkas, Dave | 7.3.1.4 | T | T | page 9, second paragraph: "corresponding to the longest supported slot time of all associated STAs". Since all STAs are required to implement long slot times, the longest supported slot time is always long slot time. Hence the definition prevents short slot time from ever being used. The logic here is backwards; the intended behavior is, I believe, that the shortest slot time permitted is the shortest that is supported by all associated STAs. | Either fix the text to permit short slot times to be used, or delete the short slot time option. | The group has agreed that the statement contains an editorial error. This will be fixed. Additionally a group has been formed to speicfy any necessary method(s) to coordinate overlpapping BSSs. | Accept
Richkas, Dave | 7.3.1.4 | T | Y | page 9, second paragraph: "If a STA that supports long slot time associates, the AP shall revert to long slot time at the first beacon subsequent…" this logic is, again, backwards, since all STAs support long slot time. Hence this requirement forces an AP to always use long slot time. | change the quoted text to "If a STA that does not support short slot time associates, the AP shall revert to long slot time at the first beacon subsequent…" | The group has agreed that the statement contains an editorial error. This will be fixed. Additionally a group has been formed to speicfy any necessary method(s) to coordinate overlpapping BSSs. | Accept
Sloan, Don | 7.3.1.4 | T | Y | I may be miss interpreting this but it appears that on page 9, lines 8 through 10, it says an AP with knowledge of an adjacent 11b cell SHALL switch to the long slot time. I understood this to be an option but the wording here says the AP must do so. The problem is this could propagate from one client through all BSSs in a given region. The implementor or installer must be allowed to not do this. This should be an option if included at all. | Change the word "shall" to "may" | The group agrees in principle. The group has determined to remove the sentnece in question entirely. Additionally a group has been formed to specify any necessary method(s) to coordiante overlappbing BSSs. | Couner
Somayazulu, Srinivasa | 7.3.1.4 | T | Y | page 9, second paragraph: text says "If a STA that supports long slot time associates, the AP shall revert to long slot time at the first beacon subsequent…" -- since all STAs support long slot time, this requirement forces an AP to always use long slot time. | change the quoted text to "If a STA that does not support long slot time associates, the AP shall revert to long slot time at the first beacon subsequent…". Fix similar text in the same paragraph that also refers to longest slot times, change to instead refer to shortest slot time supported by all STAs | The group has agreed that the statement contains an editorial error. This will be fixed. Additionally a group has been formed to speicfy any necessary method(s) to coordinate overlpapping BSSs. | Accept
Spiess, Gary | 7.3.1.4 | T | Y | pg 9 ln 3 -- An AP hearing another AP's beacon has no way to discover if the sending AP has dot11ShortSlotTimeOptionImplemented true in its MIB. | Explain what mechanism is used by one AP to make the MIB variable determination in another AP. | The group agrees in principle with the comment that this sentence is not implementable as is. A group has been formed to specify any necessary method(s) to cooridnate overlapping BSSs. Their solution should include resolution to this comment. | Accept
Stephens, Adrian | 7.3.1.4 | T | Y | "Aps shall set the short slot subfield … this BSS". Seeing as all stations support the longest slot time, the outcome of this evaluation will always be the long slot time. | Replace with: "APs shall set the Short Slot Time subfield to the shortest slot time supported by all its associated STAs. | The group has agreed that the statement contains an editorial error. This will be fixed. Additionally a group has been formed to speicfy any necessary method(s) to coordinate overlpapping BSSs. | Accept
Stephens, Adrian | 7.3.1.4 | T | Y | Capability information should be static because there is no MAC-layer protocol for signalling a change in capability information (i.e. how frequency should stations check this, how quickly should they respond to a change?). | Change so that the AP signals whether short or long slot times are to be used. Change so that STA indicates capability to do short slot times and allow AP to refuse association if it doesn't. Remove sentence allowing AP to change this value. Alternatively, if it really needs to be dynamic, put this in a different management element. | Discuss previous response to similar comment and determine technical response. | TBD
Petrick, Al | 7.3.2.1 | T | Y | Remove TBDs | Fill in TBDs… | There is no section 7.3.2.1. TBDs in 7.2.3.1 and 7.2.3.9 and explained and will be filled in at an appropriate time in the process when the values can be determined by the ANA. Editor directed to fill in based on 802.11h draft, 802.11g draft, and ANA curretn database. | Accept
Myles, Andrew | 7.3.2.9 | T | Y | Table 7.3.2.9 refers to "associated stations", which does not apply to an IBSS and yet the previous paragraph has been clearly written with IBSS's in mind. | Clarify how these bits are set in an IBSS | Comment accepted in principle. Change the words "assocated STA" to "STA within the BSS" | Accept
Myles, Andrew | 7.3.2.9 | T | Y | There is no way to verify conformance in an IBSS to the "shall" requirement that, "An ERP STA that is aware …" | Specify a verifiable mechanism that works and is verifiable in an IBSS | Discuss: Should we enumerate the ways a STA can become aware of a nonERP Sta within the BSS? | TBD
O'Hara, Bob | 7.3.2.9 | T | Y | The resolution of my comment to 7.3.2.9 includes incorrect technical justification. In particular, it is incorrect to state that the information in the PHY header is unavailable to the MAC. An example to the contrary is the rate at which a frame was received that is passed to the MAC in the RXVECTOR. | Accept original comment and resolution. | The original comment is "It seems that there might be more wasteful ways to communicate two bits than to use 24 bits to carry them. But I can't think of one offhand." And the original resolution is "Delete this information element and put the two bits it carries in the PHY header, where they belong." The indication of nonERP devices does not inherently belong in the PHY header and the group declindes to delete the nonERP Legacy Indication Element and to put these bits into each PHY header. The overall use of 24 bits in an information elemtn contained within managment frames is far more efficient that putting the bits in each PHY header. | Declined.
Gilb, James | 7.3.2.9, 19.4.3.8.5 | T | Y | While the TG has done good work to assist coexistence with non-ERP STAs, allowing the ERP sender (AP in BSS or STA in IBSS) to not use protection mechanisms when non-ERP STAs are present will result in unfair (e.g. preferential) access for the ERP STAs | Remove the option here to set bit b0 to 1 and bit b1 to 0 in this subclause. Add text to the appropriate place in Clause 19 that says that the AP shall set the bits to require protection there are non-ERP STAs associated. | Straw poll? Call for technical reasons for the poll outome. | TBD
Heile, Robert | 7.3.2.9, 19.4.3.8.5 | T | Y | While the TG has done good work to assist coexistence with non-ERP STAs, allowing the ERP sender (AP in BSS or STA in IBSS) to not use protection mechanisms when non-ERP STAs are present will result in unfair (e.g. preferential) access for the ERP STAs | Remove the option here to set bit b0 to 1 and bit b1 to 0 in this subclause. Add text to the appropriate place in Clause 19 that says that the AP shall set the bits to require protection there are non-ERP STAs associated. | Duplicate of 108. | TBD
Myles, Andrew | 9.2.11 | T | Y | Why can't the CTS mechanism be used with data packets at "basic" rates as well as "non-basic" rates, which will allow it to be used to protect the packet against STA's in neighbouring BSS's? | Don't restrict the use of the CTS mechanism, allow it to be used at any time | Accept in principle. The clause contains no direction against the function the commenter wants. The non-basic rates scenario is an example only. No change required. | Accept
Gilb, James | 9.2.11, 19.4.3.8.5, 19.5.2.2 | T | Y | As the text is currently written, if the AP supports ERP, then all ERP STAs will receive preferential access to the channel over other non-ERP STAs in the BSS | Change the setting of aCWmin to be based on the setting of the protection bits. If the protection is turned on for the WLAN, then aCWmin shall be set to 31, otherwise, it may be set to 15. This requires changes in 19.4.3.8.5 and 19.5.2.2 as well other places. | The clause 9.2.11 does not deal with the material described. Commenter probably means 9.2.12. Discuss the proposal. Take a straw poll. Solicit and include in comment resolution the reasons for the straw ballot outcome. | TBD
Heile, Robert | 9.2.11, 19.4.3.8.5, 19.5.2.2 | T | Y | As the text is currently written, if the AP supports ERP, then all ERP STAs will receive preferential access to the channel over other non-ERP STAs in the BSS | Change the setting of aCWmin to be based on the setting of the protection bits. If the protection is turned on for the WLAN, then aCWmin shall be set to 31, otherwise, it may be set to 15. This requires changes in 19.4.3.8.5 and 19.5.2.2 as well other places. | Same as 110. | TBD
Fischer, Matthew | 9.6 | T | Y | the entire 9.6 section is still difficult to follow -- Why are we restricted to being allowed to respond only at the rates specified in lines 23-30 on page 11 -- i.e. why don't the response rules follow the same intent as the original spec's rules -- generally speaking, highest BSS Basic Rate that is not higher than the received frame? -- Also, the terms ERP frame and nonERP frame are still undefined and I believe, completely confused with the terms ERP device and nonERP device, and as such, it is impossible to determine what a nonERP frame or an ERP frame is: Is a frame transmitted by a clause 18 device a nonERP frame? If so, then how does a receiver recognize the difference between a clause 18 CCK RX and a clause 19 CCK RX, where presumably, the caluse 19 CCK frame is an ERP frame, because clause 19 is the ERP clause! These frames are identical at the receiver! ERP/nonERP device is OK, ERP frame and nonERP frame are worthless terms. In other sections there are terms ERP-OFDM and ERP-CCK - using these terms might help. | Replace all of 9.6 with the following text: Some PHYs have multiple data transfer rate capabilities that allow implementations to perform dynamic rate switching with the objective of improving performance. The algorithm for performing rate switching is beyond the scope of this standard, but in order to ensure coexistence and interoperability on multirate-capable PHYs, this standard defines a set of rules to be followed by all STAs. --- All Control frames sent in response to a received frame shall be transmitted at the highest rate in the basic rate set which is less than or equal to the rate of the received frame, and which is of the same modulation type as the received frame. If no rate in the basic rate set meets these conditions, then the control frame sent in response to a received frame shall be transmitted at the highest mandatory rate of the phy which is less than or equal to the rate of the received frame, and which is of the same modulation type as the received frame. This is to insure that the response frames will be understood by all STAs in the BSS. -- All frames with multicast and broadcast RA/DA shall be transmitted at one of the rates included in the BSS basic rate set, regardless of their type or subtype. -- Data and/or management MPDUs with a unicast RA/DA shall be sent on any supported data rate selected by the rate switching mechanism. No STA shall transmit at a rate that is not supported by the destination STA, (as reported in any supported rate element that it transmits). For frames of type Data + CF – ACK, Data + CF –Poll + CF – ACK, and CF – Poll + CF – ACK, the rate chosen to transmit the frame should be supported by both the addressed recipient STA and the STA to which the ACK is intended. To allow the transmitting STA to calculate the contents of the Duration/ID field, a STA responding to a received frame shall transmit its Control Response (either CTS or ACK) frames at the highest rate in the BSS basic rate set that is less than or equal to the rate of the immediately previous frame in the frame exchange sequence (as defined in 9.7) and which is of the same modulation type as the received frame. If no rate in the basic rate set meets these conditions, then the control frame sent in response to a received frame shall be transmitted at the highest mandatory rate of the phy which is less than or equal to the rate of the received frame, and which is of the same modulation type as the received frame. In addition, the Control Response frame shall be sent using the same PHY options as the received frame, unless they conflict with the requirement to use the basic rate set. -- For clause 17, 18, and 19 PHYs, the time required to transmit a frame for use in the Duration/ID field is determined using the PLME-TXTIME.request primitive and the PLME-TXTIME.confirm primitive, both defined in subclauses 17.4.3, 18.3.4, 19.4.4.1, 19.5.2.2, or 19.6.3.2 depending on the PHY options. | Ask commenter to present new text. Discuss key changes embodied. Straw poll on how to proceed. Solicit technical explation of vote outcome and include here. | TBD
Green, Evan | 9.6 | T | Y | page 11, paragraph 6: "…in the set [6, 12, 24]…" this is at odds with the defintion in IEEE Std 802.11-1997 which permits a MAC to use any PHY rate in the basic rate set. This requirement would therefore make a MAC conforming to the original standard nonconformant, which is not permitted. The same comment also applies to the other PHY definitions, but these have not changed since the previous letter ballot. | Change the defintion to ensure that MACs conforming to the original standard remain confirmant. | The extended rate PHY is not defined in the previous editions of IEEE 802.11. The commenter is incorrect that the sited paragraph has any effect on devices conforming to the previous editions (i.e. clause 15, 16, 17, or 18). Comment is declined. | Declined.
Jalfon, Marc | 9.6 | T | Y | Basic rate set is not defined | Define basic rate set | This is an editorial error. The term basic rate set should be replace with BSS basic rate set, which is defined in 3.8 of 802.11b | Accept
Jose, Bobby | 9.6 | T | Y | PHY Rate Fall Back :Several 11b implementations perform dynamic rate switching with the objective of improving performance. The algorithm for performing rate switching is beyond the scope of this standard. Unfortunately many implementations have very simple algorithms based on number of number of successive unacklowledge data packets, or number of frames dropped. Many of these algorithms do not clearly identify the cause of packet loss is actually link quality, and do not clearly separate the impact of hidden terminals. A mixed 11b/11g env -> potential for increased hidden terminals. The group should explore solutions to help the STA identify the optimal rate for the link. Consider: 1) allowing the receiver indicate feedback about the right rate to be used by the sender. 2) consider adding an informative annexure with some ideas on how better rate fall back algorithms should be implemented in a mixed 11b/11g environment. For example recommend that STA consider RSSI, etc ctc.. | Insert the following text as informative annexure. ............ E-4 Use of Dynamic Rate Switching........ Phys with multiple data transfer rates may perform dynamic rate switching to improve performance. Dynamic rate algorithms should clearly separate the impact of hidden terminals from packet loss because of link failures. Implementors are cautioned about the increased presence of hidden terminals in an environment consisting of mixed ERP and non ERP devices. | Refer to Annex comment resolution team | TBD
Kitchen, Duncan | 9.6 | T | Y | page 11, paragraph 6: "…in the set [6, 12, 24]…" this is at odds with the defintion in IEEE Std 802.11-1997 which permits a MAC to use any PHY rate in the basic rate set. This requirement would therefore make a MAC conforming to the original standard nonconformant, which is not permitted. The same comment also applies to the other PHY definitions, but these have not changed since the previous letter ballot. | Change the defintion to ensure that MACs conforming to the original standard remain confirmant. | Comment withdrawn by commenter | Withdrawn | Yes
Myles, Andrew | 9.6 | T | Y | I suspect the draft wants to say a STA responding to a non-ERP frame should: * use the highest rate with the same PHY options in the basic rate set less than or equal to the received rate, if such a rate is available * otherwise, use the highest rate in the basic rate set less than or equal to the received rate The current text might say this but it is hard to tell | Clarify draft text | Changed to editorial. We have changed this section several times. Editor should make changes so long as we are not flip flopping back and forch. | TBD
Myles, Andrew | 9.6 | T | Y | This comment is repeated in similar form from LB41. Why is the control frame in response to an OFDM frame sent at the highest mandatory OFDM rate (now specified as 6, 12, 24MB/s rather than mandatory rates) less than or equal to the rate of the received frame? Why not use the highest basic rate less than or equal to the received rate (possibly with a preference to using an OFDM rate), which is more consistent with the current rate rules? | Clarify | Because a protection mechanism has been applied in situations prescribed by the NonERP Legacy Indication element, there is no need to require use of BSS basic rate for the ACK to ERP-OFDM frames. What the commenter desires would place a significant inefficienty burden on the ERP and mixed ERP/Clause 18 network. This is why this has been done. No change required to the draft, but discuss if we should explain this point in the text? | Accept
Rettig, Danny | 9.6 | T | Y | page 11, paragraph 6: "…in the set [6, 12, 24]…" this is at odds with the defintion in IEEE Std 802.11-1997 which permits a MAC to use any PHY rate in the basic rate set. This requirement would therefore make a MAC conforming to the original standard nonconformant, which is not permitted and would do dammage to this standard. The same comment also applies to the other PHY definitions, but these have not changed since the previous letter ballot... | Change the defintion to ensure that MACs conforming to the original standard remain conformant!! | Same as 113 | Decline
Richkas, Dave | 9.6 | T | Y | page 11, paragraph 6: "…in the set [6, 12, 24]…" this is at odds with the defintion in IEEE Std 802.11-1997 which permits a MAC to use any PHY rate in the basic rate set. This requirement would therefore make a MAC conforming to the original standard nonconformant, which is not permitted. The same comment also applies to the other PHY definitions, but these have not changed since the previous letter ballot. | Change the defintion to ensure that MACs conforming to the original standard remain confirmant. | Same as 113 | Decline
Spiess, Gary | 9.6 | T | Y | pg 11 ln 17 -- Because ERP control responses are sent at a PHY mandatory rate, there should be no case where the basic rate forces a change in PHY options. It is possible to configure the basic rate set such that 6Mbps is required and 11Mbps is optional. This would force a HR/DSSS frame to be acked using OFDM. What insanity. | Do not permit a change in PHY options when sending a control response frame. Alternately, change the following ERP paragraphs to agree that the proper response rate comes from the basic rate set. | This is necessitated even in the 802.11b specification. We have only attempted to clairy the words added in 802.11b. Example: 11/5.5/2/1 are in basic rate set. PBCC is supported. PBCC 11 is transmitted. Response must be 11 CCK. This is an example that shows why will will are rejecting the request. | Reject
Spiess, Gary | 9.6 | T | N | pg 11 ln 23 -- These three paragraphs seem to mean that ERP transmits the ACK/CTS according to Phy mandatory rates instead of BSS basic rates. | Replace the three sentences with something similar to "For the ERP PHY, all control response frames are sent at the highest rate in the PHY mandatory rate set (See table 19.2.2) that does not exceed the rate of the immediately previous frame in the frame exchange sequence." | This is a similar concern as 118. The explanation there explains why we do not want what the commenter suggests and why what the commenter suggests is a large inefficienty. | Reject
Jalfon, Marc | A.4.10 | T | Y | ERP32 should refere to ERP-OFDM only, another one is required for ERP-DSSS/CCK | Add note and add another primitive. | Move to editor
Jalfon, Marc | A.4.10 | T | Y | ERP34 referes to ERP-OFDM rates only. Need another primitive for ERP-DSSS/CCK rates which doen't have reference clause in the draft. | Seperate the primitives for OFDM and CCK and add the relevant clause for CCK in the draft. | Move to editor
Jalfon, Marc | A.4.10 | T | Y | ERP35 referes to ERP-OFDM rates only. Need another primitive for ERP-DSSS/CCK rates which doen't have reference clause in the draft. | Seperate the primitives for OFDM and CCK and add the relevant clause for CCK in the draft. | Move to editor
Jalfon, Marc | A.4.10 | T | Y | ERP4 defined as mandatory for CF8, it requires support of ERP3 which is optional. | Chage CF8:M to CF8:O | Move to editor
Jalfon, Marc | A.4.10 | T | Y | ERP6 defined as mandatory for CF8, it requires support of CCK-OFDM which is optional. | Chage CF8:M to CF8:O | Move to editor
Jalfon, Marc | A.4.10 | T | Y | ERP7 defines b1 to b4 which include b2 which contradict ERP8. | Exlude b2 | Move to editor
Jalfon, Marc | A.4.10 | T | Y | ERP9 reference is an optional the status is mandatory. | Change CF8:M to CF8:O or change the reference number. | Move to editor
O'Hara, Bob | Annex A | T | Y | The resolution of my comment to Annex A is an arbitrary dismissal of a technical comment, without any technical justification for that dismissal. The original comment is entirely clear to anyone with half a brain that would care to complete a useful standard. The Standards Board Operations Manual does not require that I provide specific changes as part of a proposed resolution, only that the method for resolving the comment be clear. | Accept original comment and resolution. | The editor provided additional text in draft 4.0 that attempts to address this comment. | rejected
Chen, Hung Kun | Annex C | T | Y | The changes to the MAC Proposed by this document should include a formal definition. | A formal definition on MAC change due to 802.11g should be provided. | move to non-clause 19
Liu, Shawn | Annex C | T | Y | The changes to the MAC Proposed by this document should include a formal definition. | A formal definition on MAC change due to 802.11g should be provided.
Maa, Yeong-Chang | Annex C | T | Y | The changes to the MAC Proposed by this document should include a formal definition. | A formal definition on MAC change due to 802.11g should be provided.
O'Hara, Bob | Annex C | T | Y | The resolution of my comment to Annex C, regarding inclusion of a formal description of the changes made to the MAC, is an arbitrary dismissal of a technical comment, without any technical justification for that dismissal. The comment is clear and provides a straightforward method for its resolution. | Accept original comment and resolution.
O'Hara, Bob | Annex C | T | Y | The resolution of my comment to Annex C, regarding the deletion of the Annex going beyond the scope of the PAR for TGg, is an arbitrary dismissal of a valid technical comment, without technical justification. | Accept original comment and resolution. | move to non-clause 19
Tsai, Allen | Annex C | T | Y | The changes to the MAC Proposed by this document must include a formal definition. | Include a formal definition | move to non-clause 19
Gilb, James | Annex E | T | Y | Annex E is a good start on describing the coexistence issues, but it should also include more information. | Add text that addresses the following issues: | move to non-clause 19
Heile, Robert | Annex E | T | Y | Annex E is a good start on describing the coexistence issues, but it should also include more information. | Add text that addresses the following issues: - Higher allowed TX power in spectral mask (about 5 dB total more in the adjacent channel and 10 dB more in the alternate channel.). The draft should show the range or FER degredation of overlappling IBSS and BSS with the higher PSDs. - Shorter aCWmin which allows ERP STAs preferential access to the medium. The AP can set it to the long value, but it is not required. - Short slot: The use is addressed in the draft, but the discussion should be moved to the coexistence section. - Different preamble: The mandatory modes use a different preamble which legacy STAs will not recognize. Thus, they may not backoff of these transmissions. The fix (RTS/CTS an other NAV methods) are optional, not mandatory, when legacy STAs are in the BSS or IBSS. This is addressed somewhat in the draft, but it should be gathered into the coexistence section. - The draft does not address coexistence with 802.11 FHSS or 802.15.1. - The draft should point out that 802.16, 802.11a and 802.11 IR are out of band and so should not pose a problem. | Editorial
Stephens, Adrian | Annex E | T | Y | The suggestion that STA re-associate with different ShortSlot capabilities if they observe an overlapping non-ShortSlot network is problemmatical. 1. It penalises the detecting STA, because during the re-association process it may loose buffered MSDUs at the AP 2. It abuses the meaning of the capability bit. Two short-capable BSSs that momentarily saw a non-short-capable STA would both stop operating in short slot mode, and then each would keep the other in that state. | Recommend that it be the responsibility of the AP to make this determination. STA only ever signal their capabilities. If STA signalling of overalapped non-short-capable STA is necessary, define a management packet to carry this information, and provide a timeout (i.e. low pass filter) on the observation to limit the rate of generation of these packets. | move to non-clause 19
Jalfon, Marc | E-1 | T | Y | The suggestion that the AP sets the use protection bit to the same value as the NonERP present bit contredict E_2, | Add reservations and refer to E-2 | accept
Jalfon, Marc | E-2 | T | Y | "The RTS/CTS frames are sent using clause 15 or clause 18 waveforms" This must be mandatory and writen in 7.3.2.9 | Add this requirements to the draft in 7.3.2.9 and add in A.10 table. | Editorial
Jalfon, Marc | E-2 | T | Y | ACK waveframe is not defined. | Define ACK waveframe | reject
Amman, Keith | General | T | Y | Although I voted yes on letter ballot #41 (D3.0) I feel the need to change my vote to no for this ballot. The issue is that it is impossible for me to identify the clauses/text that changed from D3.0 to D4.0, thus ensuring that I can accept all of those modifications. My time is valuable to both the committee, and my employer. Given the number of letter ballots issued over the last 2 months, and the fact that I have a commitment to my employer, it is impossible to provide a thorough review of this draft without some help from the task group in identifying the specific changes that were made between drafts. | Complete ballot #49, and immediately issue another letter ballot with the altered text clearly identified. This will allow those with concerns to quickly identify the modifications to the draft, and ensure a complete and thorough review. | Editor is showing all the changes for D3.0 to D4.0 in one color and changes in D4.0 to D5.0 in a different color | Commenter satisfied | YES
Jose, Bobby | General | T | Y | The use of mixed slottimes, in cases where the STA using short slottime does not see an OBSS AP using a long slottime but is within the coverage of an STA associated with the OBSS AP using short slot time. Require an STA to reassociate with Short Slotime subfield =0 if it receives any frame from another BSS that has the bit set to 0. | Insert in section 7.3.1.4 "An STA associated to an AP using the Short Slottime option shall reassociate with Short Slotime subfield =0 if it receives any frame from another BSS that has the short slottime subfield bit set to 0". | After discussion within the body, it was determined that the procedure for handling short slottimes in overlapping BSS should remain a recommended practice and not mandatory. Thus, it was not included in section 7.3.1.4 | rejected
Jose, Bobby | General | T | Y | After reading the draft and the comments and their resolutions for the last two LBs it is clear that coexistance issue with legacy 11b terminals need more attention. Several good proposals that attempt to address the issues were heard and not adopted. The adopted resolution to my comment in 02/535 said that these topics seem like good mateiral for the new HTSG and is in the category of what Tge are doing under their QoS PAR. TGe currently do not specifically address the issue of good performance with multiple rates and modulation schemes. The HTSG will take years to come up with a standard, and 11g cannot depend on HTSG to comeup with a solution. |  | It is not clear that there are still co-existence issues with legacy 11b terminals. A greal deal of time and effort has been dedicated to this matter. The suggestion by the commenter to provide a switching mechanism in this draft was rejected by the TGg body based on a straw poll conducted. | rejected
Jose, Bobby | General | T | Y | Even if STAs are close enough for energy detection, the use of different Slot time will cause cases of partial slotime differences between transmissions from STA that use different slot times. Fraction of slotimes are often not suffient to detect CCA and will cause increased collisions. | Insert text to achieve the following change. Allowing the use of short slot time only for cases where the first frame of the frame exchange is ERP-OFDM. Require STA implementations switch to long slot times when transmitting CCK-OFDM or non ERP frames. | commenter will revised and email to chair
Jose, Bobby | General | T | Y | The transmission of a Non ERP frames to acquire protection should not use short slot time, as the basic assumption is that there are non ERP STA within coverage. Restrict the use of short slot time option to the case where an ERP OFDM frame is the initial frame of a frame exchange sequence. | Insert the following text in 19.1.2. The short slot time option may be used only when transmitting a ERP OFDM Frame as the initial frame of a frame exchange sequence. | commenter will revised and email to chair
Moore, Tim | General | T | Y | Modulation names of ERP-DSSS/CCK, ERP-OFDM, ER-PBCC, CCK-OFDM are not consistent in document | Decide the right name for each modulation and correct Section 4, 7.3.1.4, 19.1.1, 19.1.2, 19.3.2, 19.3.2.2, 19.3.2.3, 19.3.2.3.1, 19.3.2.4, 19.3.3.3, 19.3.6, 19.5, 19.5.1, 19.5.4, 19.6, 19.7, 19.7.1, 19.7.2, 19.8.3.1, 19.8.3.2, 19.8.3.3, 19.8.4, 19.9.5.5, 19.9.5.6, 19.9.5.15, A.4.4.1, A.4.10, Annex D, Annex E and table 19.2-1, 19.2-2, 19.3.2-1, 19.8.1, 19.9.4.3 | Editorial
Myles, Andrew | General | T | Y | The current draft will result in major interoperability issues in its current state, particulaly in relation to rate rules and mixed environments | Simplify the scope of the draft to limit the scope of the potential issues, at least to the point we can undestand the problems. A good starting point would be to delete CCK-OFDM and PBCC competely. However, an alternative might be to invest the time to structure the problem in such a way that solution is possible and verifiable. | In the last meeting, the body of TGg maintained its position of the inclusion of CCK-OFDM and PBCC in sections 19.6 and 19.7. There are no known interoperability issues with CCK-OFDM or PBCC. Further, the group maintains that value is added to the draft by the inclusion of CCK-OFDM and PBCC in the draft. Motion by K. Smart to remove section 19.6. Motion failed 3/30/8. | rejected
Myles, Andrew | General | T | Y | This comment is repeated from LB41. There is no CCK in the "CCK-OFDM" proposal. | Replace "CCK-OFDM" by "DSSS-OFDM". | Instruct editor to change "CCK-OFDM" to "Barker-OFDM" | accepted | YES
Smart, Kevin | General | T | Y | CCK-OFDM is an option that adds little value. It is there for historical reasons and weakens the standard by having too many incompatible options. | Remove CCK-OFDM and all references to it | In the last meeting, the body of TGg maintained its position of the inclusion of CCK-OFDM in section 19.6. There are no known interoperability issues with CCK-OFDM. Further, the group maintains that value is added to the draft by the inclusion of CCK-OFDM in the draft. Motion by K. Smart to remove section 19.6. Motion failed 3/30/8. | rejected
Venugopal, Madan | General | T | Y | Many comments returned in the previous balloting, including the one above, have been rejected with the assertion "the suggested change would result in more no votes than it would solve." This is an inadequate reason for rejection and is based on conjecture. | Assess actual voting member opinions with a voting process to back up the assertions for rejection. | The comments in 9-12 in the General section of 11-02-535r9 are based on either straw polls or unanimously consent of the TGg body | rejected
Venugopal, Madan | General | T | Y | Many comments such as 9,10, 11 and 12 in the General section in document 11-02-535r9-G are rejected based on subjective opinions. The reviewers have raised valid issues and the opinions are being rejected outright. This would lead to a confusing standard being released without adequate consideration to all ideas proposed. | Assess actual voting member opinions with a voting process to back up the assertions for rejection. |  | rejected

## YES
Voter (Last name, First name) | Clause | Comment Type (E or T) | Part of No Vote? (Y or N) | Comment / Explaination | Recommended Change | Adoped Resolution | Status (Accept, Reject, Counter) | Commenter Satisfied
Cole, Terry | 7.2.3.1 | E | N | Assuming that 802.11g will be approved after 802.11h and before others in the WG, the order of this element will be 19. But the ANA has not yet documented assignments for any of the current task groups so this may have to change after 802.11g is published if any groups have lower numbers than the element id of 47. | Change the TBD to 19, indicating that this is the most likely number, depending on ANA assignments and order of amendment approval. Someday somebody should change the base MAC to state in 7.2.3 that "the order of information elements appearing in any management frame shall be in monotonically increase order of their information element id as listed in Table 20" and delete all "Order" columns from the tables defining each management frame format in each section 7.2.3.n. | changed to 19
Cole, Terry | 7.2.3.9 | E | N | Assuming that 802.11g will be approved after 802.11h and before others in the WG, the order of this element will be 19. But the ANA has not yet documented assignments for any of the current task groups so this may have to change after 802.11g is published if any groups have lower numbers than the element id of 47. | Change the TBD to 18, indicating that this is the most likely number, depending on ANA assignment and order of amendment approval. See my alternate resolution described for my comment in 7.2.3.1. | changed to 18
Cole, Terry | 7.3.2 | E | N | Why are we using element id of 47. These are not assigned by ANA according to the database. Last element used by 802.11h is 41. Assuming an order of approval, we might best use 42. | Change the 47 to 42, indicating this is the most likely number, depending on ANA assignment.
Cole, Terry | 7.2.3.9 | E | N | Length of nonERP Indication element is parenthetically indicated as 2 in the figure. | Change to 1, corresponding to the single octet that follows the length indication. | fixed
Cole, Terry | 19.3.5 | TR | N | It is necessary that the CCA function signal which type of preamble is found. This is necessary because the PLCP receive procedure in 19.3.6 depends upon this knowledge to follow either the BARKER PLCP branch of the PLCP procedure or the OFDM branch of the PLCP procedure. This is described as "the receive shall first distinguish between the ERP-OFDM preamble and the single carrier modulations." | There are several solutions to resolve this. We can add a parameter to the primitives used to signal CCA to the PLCP receive procedure, but this is problematic as there are more than one and the same ones are not always used. I.e., PMD_CS, PMD_ED, and PMD_RSSI are all defined and available. I suggest that we state the PMD_CS and/or PMD_ED are used by the PMD to indicate that a single carrier preamble has been detected. The PMD_RSSI is used by the PMD to indicate a ERP-OFDM preamble has been detected. This is in keeping with the original clause 17 and 18 receive PLCP procedures that we reference and extend in 19.3.6. Modify CCA Mode 1 to indicate that "upon detection of BARKER, PMD_ED shall be asserted" and that "upon detection of ERP-OFDM, PMD_RSSI shall be asserted." Modify CCA Mode 5 to indicate that "PMD_ED and PMD_CS shall be asserted to indicate detection of BARKER" and that "PMD_RSSI shall be asseted to indicate ERP-OFDM."
Cole, Terry | 19.4.6 | E | N | The phrase "if there is no energy detect or carrier sense" can be interpreted multiple ways. I.e. (no ed) or CS; no (ed or CS); no (ed or CS). | Please limit interpretation to "no (ed or CS)". I suggest "if there is no energy detect and no carrier sense."
Cole, Terry | 19.4.6 | E | N | The phrase "with probability CCA_Detect_Probability within a CCA_time" is confusing and can be interpreted multiple ways. I.e. Shall be within 4us 90% of the time, Shall always be within 4us and shall be accurate 90% of the time. Shall be correctly asserted within 4us 90 times out of 100. | Please limit interpretation to "shall be correctly asserted within 4us 90 times out of 100". I suggest that you restate the first (long) sentence of bullet a) as follows: "When a valid signal (according to the CCA mode of operation) with a signal power of -76dBm at the receiver antenna connector is present at the start of the PHY slot, a correctly performing CCA shall report the channel busy within CCA_time, where CCA_time does not exceed SlotTime - RxTxTurnaroundTime. Incorrect performance (e.g., signal not asserted within CCA_time, signal incorrectly asserted) shall occur with a probability less than 1- CCA_Detect_Probability." | fixed a different way
Cole, Terry | 19.4.6 | T | N | The parameter CCA_Detect_Probability is defined as a performance measure but it is not very precisely defined. It is open for interpretations. | Provide a much more precise definition of the probability. Others can define how to measure it but give them good guidance of what it is supposed to be.
Cole, Terry | 19.9.4.2 | T | N | This table is a superset of 802.11a and 802.11b. However, the use of PMD_ANTSEL.indicate, PMD_MODULATION.indicate, PMD_PREAMBLE.indicate, and PMD_RATE.indicate are not clear to me. I have provided comments on each elsewhere. | After resolving my comments on sections 19.9.5.4, 19.9.5.6, 19.9.5.10, 19.9.5.13, update Table 19.9.4.2 as appropriate. My comments would suggest that you should delete all of PMD_ANTSEL.indicate, PMD_MODULATION.indicate, PMD_PREAMBLE.indicate, and PMD_RATE.indicate. Clarify the use of this primitive or remove. Is this primitive needed in order to provide the required RXVECTOR information reported to the MAC?
Cole, Terry | 19.9.4.3 | T | N | This table is a contains an overview of the remaining sub-clauses of 19.9.4. However the use of PMD_ANTSEL.indicate, PMD_MODULATION.indicate, PMD_PREAMBLE.indicate, and PMD_RATE.indicate are not clear to me. I have provided comments on each elsewhere. Also, I have suggested in comments elsewhere that we modify the use of PMD_CS, PMD_ED, and PMD_RSSI. | After resolving my comments on sections 19.9.5.4, 19.9.5.6, 19.9.5.10, 19.9.5.13, and 19.3.5, update Table 19.9.4.3 as appropriate. My comments would suggest that you should delete all of PMD_ANTSEL.indicate, PMD_MODULATION.indicate, PMD_PREAMBLE.indicate, and PMD_RATE.indicate. You would state the PMD_CS and PMD_ED are used only for BARKER CCA detection and that PMD_RSSI is used only for ERP-OFDM CCA detection.
Cole, Terry | 19.9.5.4 | T | N | This primitive is indicated in a table of 802.11b (similar to table 19.9.4.2) but is not described in text. This primitive is not shown in the CCK PLCP receive procedure. The function of knowing what modulation is in use is enabled by the PCLP receiver as it receives the data fields prior to the actual data modulation. This is clearly shown and described in the PLCP rx procedure of clause 18. | Remove the section and PMD_MODULATION.indicate primitive.
Cole, Terry | 19.9.5.4 | T | N | This primitive is indicated in a table of 802.11b (similar to table 19.9.4.2) and described in text. However, this primitive is not shown in the CCK PLCP receive procedure. The function of knowing what preamble is in use is enabled by the PCLP receiver as it receives all the scrambled preamble data bits (distinctly all 1s or all 0s) and the distinctly SFD fields prior to the modulated PLCP header. This is clearly shown and described in the PLCP rx procedure of clause 18. The PMD_PREAMBLE.indicate primitive is not shown in the PLCP rx procedure or described in the text. | Remove the section and PMD_PREAMBLE.indicate primitive. If we decide to keep it, provide a new rx PLCP procedure that shows how and when to use this primitive.
Cole, Terry | 19.9.5.10 | T | N | This primitive is indicated in a table of 802.11b (similar to table 19.9.4.2) but described in text of clause 18. This primitive is not shown in the CCK PLCP receive procedure. The function of knowing which receive antenna was selected is not discussed as being transferred from PMD to PLCP. However, the PLCP receive procedure does state that this information is transferred from PLCP procedure to MAC. It is unclear if the decision of antenna to receive from is made by the PLCP procedure or the PHY. | Clarify the need for this primitive. Delete this section if we do not need it. If we do need it, add clarification to this section when this should be used. I would suggest that it should be asserted right after the CCA function indicates detection of a preamble.
Cole, Terry | 19.9.5.14 | T | N | The PMD_RSSI was expanded to include functions already described in clauses 17 and 18. However, the PMD_RSSI are defined quite differently fro the case of receiving OFDM and receive CCK in those two clauses. PMD_RSSI is shown in 802.11a in the Rx PLCP procedure, and PMD_RSSI is not shown in the Rx PLCP procedure of 802.11b. I have suggested changed in 19.3.5 that would make this primitive only applicable to ERP-OFDM within clause 19. The only potential problem I see is that the RxVECTOR of clause 18 states that it contains the RSSI value. How is this transferred from PMD to PLCP? | Update this text to align with decisions made by committee. If you acted on my suggestion, then remove the "and 18.4.5.11" from this section. If this is not the case, then please indicate how this primitive should be used.
Cole, Terry | 19.9.5.15 | T | N | The PMD_SQ was taken as described in clauses 18 (and there is no such primitive for clause 17). PMD_SQ is not shown in 802.11b in the Rx PLCP procedure. But the Rx PLCP procedure of 802.11b states that the RxVECTOR contains the SQ value. How is this transferred from PMD to PLCP? | Indicate how this primitive should be used in the Rx PLCP procedure, if at all.
Cole, Terry | 19.9.5.16 | T | N | The PMD_CS was described in clauses 18 (and not described in clause 17). However, the function has been expanded by the clause 19 CCA function to apply for all ERP modes. I have provided comments in 19.3.5 that would make this primitive only applicable to BARKER preambles (CCK long, CCK short, PBCC long, PBCC short, CCK-OFDM long, CCK-OFDM short) within clause 19. | If you act on my suggestions for 19.3.5, add that "this primitive is used only when Barker preamble is detected by the CCA function."
Cole, Terry | 19.9.5.17 | T | N | The PMD_ED situation is the same as that described for 19.9.5.16. | If you act on my suggestions for 19.3.5, add that "this primitive is used only when Barker preamble is detected by the CCA function."
Cole, Terry | 19.9.5.17 | E | N | Extra page after this section and before Annex A | Delete elements causing extra page unless it is intentional to make Annex A end up on an even page number. | fixed
Cole, Terry | A.4 | E | N | CF8 has already been used. | The next available number, assuming 802.11h will be approved just prior to 802.11g, will be CF10. I would remove all the other entries CF1 to CF7 and leave only CF10 in this table. | accepted
Cole, Terry | A.4.4.1 | E | N | The base documents and all approved documents (and even 802.11h) go no higher than PC15 in this section. | Renumber the items start from PC16
Cole, Terry | A.4.10 | E | N | A.4.10 is already used. | The next available subclause number, assuming 802.11h will be approved just prior to 802.11g, will be A4.12 | accepted
Williams, Steven | 7.3.1.4 | T | Y | page 9, first paragraph: "and the MIB attribute dot11ShortSlotTimeOptionImplemented is true in both BSSs". How can an AP know the value of the MIB attributes in other APs? Is SNMP implementation a requirement? There is a normatively specified behavior defined here (the sentence contains the word "shall"), but there's no mechanism defined. | Delete the short time slot or replace with something that can actually be implemented.
Williams, Steven | 7.3.1.4 | T | T | page 9, second paragraph: "corresponding to the longest supported slot time of all associated STAs". Since all STAs are required to implement long slot times, the longest supported slot time is always long slot time. The short slot time will never be used. | Fix text to allow short slot times to be used, or delete the short slot time option.
Williams, Steven | 7.3.1.4 | T | Y | page 9, second paragraph: "If a STA that supports long slot time associates, the AP shall revert to long slot time at the first beacon subsequent…" As all STAs support the long time slot, APs will always use it. | change quoted text to "If a STA that does not support short slot time associates, the AP shall revert to long slot time at the first beacon subsequent…"
Williams, Steven | 7.3.1.4 | T | Y | page 9, second paragraph: "...but with knowledge of a neighboring co-channel BSS having long slot time traffic; the AP shall switch…". This includes a "shall" clause, indicating normative behavior, but this is not testable. How does one test whether an AP "has knowledge" of a "neighboring" BSS? And what does "neighboring" mean? | Define testable, normative behavior or delete the short slot time option.
Williams, Steven | 9.6 | T | Y | page 11, paragraph 6: "…in the set [6, 12, 24]…" this is at odds with the defintion in IEEE Std 802.11-1997 which permits a MAC to use any PHY rate in the basic rate set. This requirement would therefore make a MAC conforming to the original standard nonconformant, which is not permitted. The same comment also applies to the other PHY definitions, but these have not changed since the previous letter ballot. | Change the defintion to ensure that MACs conforming to the original standard remain confirmant.
Halford, Steve | 9.9 | E | N | The sentence "ERP STAs shall use the NONERP Indication Element….." seems confusing. | Replace the sentence with: ERP STAs shall use protection mechanisms (e.g., RTS/CTS) when bit b1 in the NONERP Indication Element is set to 1. | accepted
Halford, Steve | 19.1.2 | E | N | In the second paragraph, the sentence "This implies that ERP and clause 18 CCA detectors are active…" doesn't clearly express what the standard is trying to require. | Replace the sentence with: Since protection mechanism are not required in all cases, the ERP CCA mechanisms for all packet types shall be active at all times. | accepted
Halford, Steve | 19.3.2 | E | N | This paragraph is misleading in places. The long preamble provides interoperability for the CCK-OFDM modes as well as the PBCC high rate modes. | Add CCK-OFDM and the CCK-OFDM data rates to the list of waveforms and rates for which long preamble provides interoperability. If the concern is that CCK-OFDM uses additional 802.11a preamble, then PBCC-33 should be removed from the list since it requires an additional 'clock switching' preamble as specified in Figure 19.3.3.2-3. | fixed
Halford, Steve | 19.6.1 | E | N | There is a typo at the end. The word shall is stranded without punctuation or other words to keep it company. | Remove the shall | fixed
Halford, Steve | 19.6.2 | E | N | The requirements of this section conflict with the requirements of section 19.5.3. | Remove this section or remove the PBCC rates from the specification in 19.5.3. | removed clause 19.6.2
Moreton, Mike | 9.6 | E | N | The second changed paragraph used (in the base standard) to apply to RTS frames. The changed wording removes this, even for non-ERP operation, which I presume wassn't the groups's intentions. | Reword so that RTS frames in a non-ERP environment are still sent at a basic rate.
Moreton, Mike | 9.6 | E | N | There are changes to the base standard text that are not highlighted. This makes it extremely difficult to reliably review the document. | Highlight all text changed from the base standard. | rejected, the text has been carefully reviewed with respect to the base standard (this includes all approved supplements such as b corr.)
Thrasher, Jerry | 7.2.3.1 | E | N | The order of the NonERP Element should be determined by now. | Update Supplement with the correctly assigned order. | done
Thrasher, Jerry | 7.2.3.9 | E | N | The order of the NonERP Element should be determined by now. | Update Supplement with the correctly assigned order. | done
Hillman, Garth | 4.0; line 40 | E | N | PHY is redundant | extended rate (clause 19) PHYs | accepted
Hillman, Garth | 4.0; line 37 | E | N | ER-PBCC => | ERP-PBCC | rejected, this was by intention
Hillman, Garth | 7.2.3.1 and 7.2.3.9; | E | N | could not find 19.5.1.1 | clarify | removed reference to 19.5.1.1
Hillman, Garth | 9.6; line 23 | E | N | 19.3.3.1 => | 19.8.4 | accepted, but was in 9.2.12
Hillman, Garth | 9.2.12; line 37 | E | N | could not find 19.4.4.1, 19.5.2.2, 19.6.3.2 | clarify | accepted, changed to 19.8.3
Hillman, Garth | Table 19.2.1 | E | N | 19.4.x and 19.6.x indeterminant | clarify | accepted, removed those references
Hillman, Garth | 19.4.6; where did the line numbers go? | E | N | CCA_time => | CCA_Time | accepted
Hillman, Garth | Table 19.8.4 | E | N | ATxRx => | aTxRx | accepted
Hillman, Garth | A 4.10 | E | N | What are the PHY Features? | remove | accepted

## Editorial
Voter (Last name, First name) | Clause | Comment Type (E or T) | Part of No Vote? (Y or N) | Comment / Explaination | Recommended Change | Adoped Resolution | Status (Accept, Reject, Counter) | Commenter Satisfied
Spiess, Gary | 18.2.2.2 | E | N | pg 12 ln 21 -- Consistency suggests a wording change. | Change "...optional for HR/DSSS." to "…optional for clause 18 devices." | changed as specified
Spiess, Gary | 19.2 | E | N | table 19.2-2 -- DATERATE does not indicate what PBCC rates are mandatory. | Add "; support for 5.5, 11, and 22 is mandatory." | removed all words on mandatory rates as they do not belong in this section.
Gilb, James | 19.3.2.3.1 | E | N | Need to have a 19.3.2.3.2 to justify a 19.3.2.3.1 | Delete the heading, leave it as part of 19.3.2.3 | paragraph title removed
Heile, Robert | 19.3.2.3.1 | E | N | Need to have a 19.3.2.3.2 to justify a 19.3.2.3.1 | Delete the heading, leave it as part of 19.3.2.3
Petrick, Al | 19.3.3.2 | E | n | Missing word | replace the letter "s" whith "shown" in last paragraph of page 22. | fixed
Spiess, Gary | 19.8.1 | E | N | dot11Supported data rates Tx and Rx values are OFDM-centric. PBCC adds 22Mbps as mandatory instead of 6/12/24. | Notes about how optional OFDM and PBCC each add their own mandatory rates.
Myles, Andrew | 7.2.3.1 | E | N | It is probably time to work with the ANA to fill in the order fields | Fix | done
Fischer, Matthew | 7.3.1.4 | E | N | APs (as well as STAs in IBSSs) shall set the Short Preamble subfield in transmitted Beacon, -- for some silly reason, the "to 1" part was stricken, while "to 0" and "to 1" appear liberally throughout the section. Look at the next sentence for an example. | Un-strike the "to 1" so that we know to what value the bit is being set. | rejected, this change was accepted as comment resolution in the last session
Myles, Andrew | 7.3.1.4 | E | N | The phrase, "so a bit indicating ERP capability is not necessary" is not necessary because standards only need to state "what" not "why". | Remove phrase | removed phrase
Spiess, Gary | 7.3.1.4 | E | N | pg 9 ln 5 -- All stations "support" long slot times. The sentence can be reworded. | Reword "… to the longest supported slot time…" to "… to the longest required slot time…". | changed supported to required
Myles, Andrew | 7.3.2.9 | E | N | There is no need to specify b0 and b1 together in the same table as they are orthogonal to each other | Specify b1 (appropriately named) as an indication whether or not a nonERP station is present in one table. Specify b0 (appropriately named) as an indication as whether or not the use of protection mecahnisms are required in another table. | table split into two tables as suggested
Jalfon, Marc | 9.2.12 | E | N | page 10. Reference about aCWmin is not clear. The 19.3.3.1 does not conatin any aCWmin suggestion | fix reference | reference changed to 19.8.4
Gilb, James | All | E | N | The table number is incorrect in this draft, it numbers by subclause and number rather than being continuous throughout. | Fix the table numbering to start at 1 and increment continually throughout the document up to the first Annex. | rejected as this will be fixed up in the IEEE final roll-up. Numbering that way is a pain as one added table or figure causes lots of work the suggested way.
Heile, Robert | All | E | N | The table number is incorrect in this draft, it numbers by subclause and number rather than being continuous throughout. | Fix the table numbering to start at 1 and increment continually throughout the document up to the first Annex.
Myles, Andrew | General | E | N | This comment is repeated from LB41. The draft is very difficult to read (too wordy, compressed layout, poor structure - although that is often a result of the structure of the base standard, limited overviews). I know that this is an unlikely thing to occur. However, it is something that 802.11 needs to do to ensure the readability and thus correctness of the standard in the future. | Undertake a complete editorial rewrite (possibly with a professional editor) | rejected, a fairly significant rewrite was done in the last revision. Many paragraphs were moved and the text re-aligned.
Petrick, Al | Introduction | E | n | Missing period at end of paragraph | Add period at end of sentence 20Mbit/s. | fixed
Myles, Andrew | 4 | E | Y | "ER-PBCC" should be "ERP-PBCC" here and in at least one other location | Fix | rejected as this was by design
Jalfon, Marc | 19.1.2 | E | Y | SIFS time is 10uSec | Add comment refering to the 6uSec extension | a reference to 19.3.2.3 was added
Myles, Andrew | 19.1.2 | E | Y | This comment is repeated from LB41. "existing" implies a point in time whereas this draft needs to apply for all time into the future | Rewrite to remove "existing" here and many other locations | the word existing was removed from 6 or so places
Jalfon, Marc | 19.3.2 | E | Y | " The short preamble supports the same rates as the long…". This is wrong. |  | same removed
Jalfon, Marc | 19.3.2 | E | Y | The third (mandatory) is specified in 19.3.2.3.1 not 19.3.2.3, there is a mix here and in several other places between mandatory and options. | Fix the reference and separate between mandatory and optional requirement in separate clauses. Otherwise it is almost imposibble to understand what is mandatory. | paragraph title 19.3.2.3.1 was removed
Petrick, Al | 19.3.2 | E | Y | Cannot find reference to 18.2.2.1 | Add reference to draft | what do you mean you can't find 18.2.2.1?
Yee, Jung | 19.3.2.1 | E | Y | Cannot find reference | The bits are not defined in section 19.6. Either remove the text or give a new reference. | references fixed to 19.3.3.4 and 19.3.3.2
Yee, Jung | 19.3.2.1.2 | E | Y | Section out of context | Move to the optional PBCC description section | rejected, this was moved to make it more in context. The optional sections were split up and placed in the appropriate places in the main text to make it flow better; in response to comments in the last session.
Yee, Jung | 19.3.2.4 | E | Y | Section out of context | Move to the optional CCK_OFDM descripton section
Yee, Jung | 19.3.2.5 | E | Y | Section out of context | Move to the optional CCK_OFDM descripton section
Petrick, Al | 19.3.3.2 | E | Y | Section out of context | Move to the optional PBCC description section
Yee, Jung | 19.3.3.2 | E | Y | Section out of context | Move to the optional PBCC description section
Petrick, Al | 19.3.3.3 | E | Y | Section out of context | Move to the optional CCK_OFDM descripton section
Yee, Jung | 19.3.3.3 | E | Y | Section out of context | Move to the optional CCK_OFDM descripton section
Petrick, Al | 19.3.3.4 | E | Y | Section out of context | Move to the optional CCK_OFDM descripton section
Yee, Jung | 19.3.3.4 | E | Y | Section out of context | Move to the optional CCK_OFDM descripton section
Petrick, Al | 19.3.3.4.1 | E | Y | Figure 19.3.3.4.1: Mbps | Make text in figure consistance with rest of draft, change to Mbit/s | fixed
Yee, Jung | 19.3.6 | E | Y | Paragraph out of context | Move last paragraph describing CCK-OFDM to the optional CCK_OFDM description section | see 25
Jalfon, Marc | 19.4.5. | E | Y | SIFS not SIFs | Fix to SIFS | fixed
Jalfon, Marc | 19.5.1 | E | Y | This clause should be identical to the corresponding clause in 17. | Remove the content and add a reference "shall follow 17.3.10..." | rejected, the text is better worded than the clause 18 text. A previous comment resolution changed it slightly from clause 18 form.
Petrick, Al | 19.7.2 | E | Y | Figure 19.7.2 : Mbps | Make text in figure consistance with rest of draft, change to Mbit/s | will fix later
Myles, Andrew | 19.8.4 | E | Y | Table 19.8.4 makes reference to "conditions" in 9.2.12. There are no applicable conditions in 9.2.12 | Move the sentence just above the table into the table replacing, "…as specified in 9.2.12" with ".. where the characteristic rate set is defined in 9.2.12" | done
Jalfon, Marc | 7.2.3.1 | E | Y | Clause 19.5.1.1 is referenced and does not exit | Fix the reference or delete | reference deleted
Jalfon, Marc | 7.2.3.9 | E | Y | Clause 19.5.1.1 is referenced and does not exit | Fix the reference or delete
Myles, Andrew | 7.3.1.4 | E | Y | "shall be allowed" should be "may" | Fix | fixed
Myles, Andrew | 7.3.1.4 | E | Y | "set false" should be "set equal to 0" | Fix | fixed
Myles, Andrew | 7.3.1.4 | E | Y | "respond accordingly" is inappropriate language in a standard. If there is an "accordingly" then specify it. If not, then remove it. | Fix | respond accordingly removed
Stephens, Adrian | 7.3.1.4 | E | Y | "bit 0 of the NonERP…". You are normatively defining the structure for this information element in more than one place. | Give this bit a name "NonERP Present". Use this name in 7.3.2.9 and 7.1.3.4. | fixed
Jose, Bobby | 7.3.1.4 | E | Y | Page 9 , lines 7-8 All STA supports long slot times. | Change to "if a STA that does not support the short slot time associates, the AP shall revert to long slot time." | fixed
Myles, Andrew | 7.3.2.9 | E | Y | The length in Figure 7.3.2.9 should be 1, not 2, as the information field appears to be only one octet in length | Fix | fixed
Jose, Bobby | 9.2.11 | E | Y | Why does the description talk about a short frame first and later describe that it shall be the CTS, instead of just saying , the may first transmit a CTS frame with RA equal to its own mac address ? | Change to "may first transmit a CTS frame with RA equal to its own mac address, and a duration value that protects the pending frame and popssible and ACK. | accepted
Myles, Andrew | 9.2.12 | E | Y | It is claimed that 19.3.3.1 contains values of aCWmin applicable to ERP. It does not. | Fix the reference | changed to table 19.8.4
Jalfon, Marc | 9.6 | E | Y | nonERP frame is not defined | Define the term nonERP frame | rejected, the term is defined in the second paragraph.
Yee, Jung | 9.7 | E | Y | Wrong Heading | Change "Frame Sequences" to "Frame Exchange Sequences" | fixed
Jalfon, Marc | A.4.10 | E | Y | "frame structure" is not defined | Change to Service field | done
Jalfon, Marc | A.4.10 | E | Y | ERP10 is the same as ERP7 | Remove ERP10 | I disagree, the reference is different
Jalfon, Marc | A.4.10 | E | Y | Table 91 doesn't exist in this draft. | Fix the reference | fixed
Jalfon, Marc | A.4.10 | E | Y | ERP41 reference 19.8.3.3.1does not exist. | Change to 19.8.3.1 | fixed
Stephens, Adrian | General | E | Y | I cannot determine what text has changed since the previous draft. | Add tracking so that changes since the previous draft can be identified and commented on. | tracking is done