## Sheet1
RRM Functional Services, Basic Measurements and Work Schedule
Services Supported
Section (1) | Functional Services | Basic Measurements | Setup | Type | Documents | Status | Schedule | Comments | Network Management
13.1 | Initial Pre-Association Services (STA already in the BSS) | .11k capability |  | NA | D0.1 | NA |  | Needed (bit in MLME primitive)
|  | Probe Response (Channel Map) |  |  | D0.2 |  |  | Channel Map added at DFW2
|  | Beacon (passive scan) | [5 empty] | Needed
|  | Initialization Power Measurements (RCPI) |  | NA | 03/317r0, D0.2 | 2003-05-13 |  | MIB entries for new RCPI measurements
|  | SNR (EVM?) Data Quality Measure |  | NA |  |  |  | EVM entries need to be part of EVM proposal
|  | Site Report |  |  | 03/417r0 |  |  | Not needed, in Site Report
| Reassociation (class 3 service, section 5) Roaming | Site Report |  |  | D0.2 |  |  | Site Reports added at DFW2
|  | Inputs from UPnP and Zero Config | [5 empty] | Needed
13.2 | AP MIB Service | MAC MIBS |  | passive | 03/171r5 03/338r0 03/416r0 |  |  | Needed
|  | STA statistics tables |  | passive | 03/171r7 |  |  | Needed
|  | SMT MIB for configuration parameters | [5 empty] | Needed
|  | Neighbor Maps |  |  | 03/417r0 |  |  | Not needed, in Site Report
13.3 | AP Measurements Outside the MIB (per AP) | Site Reports and AP Channel Maps |  | both | D0.2 03/174r3 | 2003-05-13 |  | Done
[5 empty] | 03/318r1 | needs motion |  | Done
|  | Neighborhood Maps |  |  | 03/417r0 | no motion |  | Not needed, in Site Report
|  | Security of management frames |  |  | 03/362r0 | needs motion |  | ????????
13.4 | STA Measurements Outside the MIB (per STA)
|  | Site Reports and AP Channel Maps |  | both | D0.2 03/174r3 | 2003-05-13 |  | Done
[5 empty] | 03/318r1 | needs motion |  | Done
|  | Neighborhood Maps |  |  | 03/417r0 | no motion |  | Not needed, in Site Report
|  | Security of management frames |  |  | 03/362r0 | needs motion |  | ????????
13.5 | Distribution Service of RRM Information to APs and STAs | NA |  |  | 03/234r1 03/417r0 03/338r0 | partial |  | Needed
|  | Site Reporting |  |  | D0.1
13.6 | AP and STA Statistics Gathering Service | Periodic and conditional reporting mechanisms |  | both | 03/408r0 |  |  | Needed
13.7 | Commanded STA Action Service | Measurement request/response frames |  | active | 03/174r3
03/372r0
|  | -- Beacon Report |  | active | D0.1 |  |  | Done - Kaiser Mods Needed (Patrick Worfolk)
|  | -- Frame Report |  | active | D0.1 |  |  | Done - Kaiser Mods Needed (Patrick Worfolk)
|  | -- Noise histogram |  | active | D0.1 |  |  | Done - Kaiser Mods Needed (Patrick Worfolk)
|  | -- Channel Report |  | active | D0.1 |  |  | Done - Kaiser Mods Needed (Patrick Worfolk)
|  | -- RCPI histogram |  | active | D0.1 |  |  | Done - Kaiser Mods Needed (Patrick Worfolk)
|  | -- Medium sensing time histogram |  | active | 03/340r1 | 2003-05-13 |  | Done
|  | Station statistics & RRM distribution |  | active | 03/338r0 |  |  | Needed
13.8 | STA Autonomous Action Service | Threshold triggered scanning |  | active | 03/234r1 |  |  | Needed
[5 empty] | 03/174r3 |  |  | Needed
Notes: 1) See RRM vision and architecture document section on functional services 03/135r8.