## Sheet1
ID | Source | Citation | 802.11 Ref | Assessment | Recommendation | Status | Priority
1 | 03-382r0 | Page 3, left | 5.4.2.2 | Beyond PAR of 802.11m project because it would be defining new functionality | Consider for future work and PARs. 802.11 WGTE to include in a database, if desired. | Closed
2 | 03-382r0 | Page 3 right, bullet 1 & 2 | 5.5 | Technically correct -- possible wording changes might improve text |  | Needs Assignment
3 | 03-382r0 | Page 3 right, bullet 1 | 5.5 | Incorrect conclusion because bits are subject to rules in section 7. Imroved wording may be warranted. |  | Needs Assignment
4 | 03-382r0 | Page 3 right, bullet 1 | 5.5 | We believe that the statement is not true. Research and editorial clarificaiton may be warranted. |  | Needs Assignment
5 | 03-382r0 | Page 4 left | 5.5 | Research and editorial clarificaiton may be warranted. |  | Needs Assignment
6 | 03-382r0 | Page 4 right | 5.6 | More research is required to determine if association/disassociation is disallowed elsewhere in the document |  | Needs Assignment
7 | 03-382r0 | Page 5 | 5.5 & 5.6 | Same as 6
8 | Internal Discussion | none | Figure 8 | Text labels incorrect from state 2 to 3. Needs simple fix. |  | Needs Assignment
9 | Internal Discussion | None | 5 | Section 5 largely is descriptive. Review of each may and shall is warranted for section 5. |  | Needs Assignment
10 | 03-382r0 | Page 6 | 6.2.1.2.2 | Further research required. |  | Needs Assignment
11 | 03-382r0 | Page 7 left | 7.2.3.10 | We feel the spec is unambigous. Title of Table 14 will be ammended by adding Element at the end. |  | Editor Needs to implement.
12 | Internal Discussion | None | 7.3.2.1, 10.3.2.1.2, 11.1.3 & 11.1.3.2.1 | Clarify the broadcast SSID is actually the wildcard SSID. |  | Needs Assignment
13 | 03-382r0 | Page 7 right bullet 1 | 7.3.2 | Correct. Statement should be added in 17 pointing out that this is correct and OK. We should state that the DS IE should not be used for this purpose. Clarification in section 10 needed that you must fill in the PHY paramter set even though it wasn't on air. |  | Needs Assignment
13 | 03-382r0 | Page 8 | 7.3.2.6 | A couple of examples, especially any special cases should be developed. |  | Needs Assignment
14 | 03-382r0 | Page 9 left | 8 | Beyond PAR of 802.11m project and is within the scope of PAR for P802.11i |  | Closed
15 | 03-382r0 | Page 9 right | 8.1.1.2 | Text should be chagned to match MIB. |  | Needs Assignment
16 | 03-382r0 | Page 10 | 8.3.2 | Text in MIB should be brought in line with 8.3.2 |  | Needs Assignment
17 | 03-382r0 | Page 11 left | 9.1.4 | Research and editorial clarificaiton may be warranted espeically to align MIB and text. |  | Needs Assignment
18 | 03-382r0 | Page 11 left | 9.2.3.3 & 9.2.3.4 | Research and editorial clarificaiton may be warranted. |  | Needs Assignment
19 | 03-382r0 | Page 12 left | 9.2.4 | Research and editorial clarificaiton may be warranted. |  | Needs Assignment
20 | 03-382r0 | Page 12 right | 9.2.5.4 | Research and editorial clarificaiton may be warranted. Perhaps look more deeply into 802.11a (and also g) |  | More discussion needed after research.
21 | 03-382r0 | Page 13 left | 9.2.5.4 | Research and editorial clarificaiton may be warranted. |  | Needs Assignment
22 | 03-382r0 | Page 13 right | 9.2.5.7 | Clarificaiton and alignment of SDL with text may be warranted. |  | Needs Assignment
23 | 03-382r0 | Page 14 left | 9.2.8 | Clarificaiton and alignment of SDL with text may be warranted. |  | Needs Assignment
24 | 03-382r0 | Page 14 right | 9.3.2.1 | Research and clarificaiton is desired. |  | Needs Assignment
25 | 03-382r0 | Page 15 | 9.3.2.2 | SDL and text need alignment. |  | Needs Assignment
26 | Internal Discussion | none | 9.3.2.2 | The special exception for timing of PCF beacon is 9.3.3.2 should be tied to the normal situations. |  | Needs Assignment
27 | 03-382r0 | Page 20 | 10.3.2.1 | Research and editorial clarificaiton may be warranted. |  | Needs Assignment
28 | 03-382r0 | Page 21 left | 11.1.2 | Clarificaiton is warranted. |  | Needs Assignment
29 | 03-382r0 | Page 21 right | 11.1.2 | Research required on how the 4us was derrived and is anything required for OFDM? |  | Needs Assignment
30 | 03-382r0 | Page 22 left | 11.1.2.1 | Research and editorial clarificaiton may be warranted. |  | Needs Assignment
31 | 03-382r0 | Page 22 right | 11.1.2.1 | Research and editorial clarificaiton may be warranted. |  | Needs Assignment
32 | 03-382r0 | Page 23 left | 11.1.2.2 | Research and editorial clarificaiton may be warranted. |  | Needs Assignment
33 | 03-382r0 | Page 23 right | 11.1.3.2.2 | Text seems clear. |  | Closed
34 | 03-382r0 | Page 24 left | 11.2.1.1 | Clarificaiton desired but text is accurate. |  | Needs Assignment
35 | 03-382r0 | Page 24 right | 11.2.1.5 | Reserarch requried as to what the document specifies in text and/or SDL |  | Needs Assignment
36 | 03-382r0 | Page 25 left | 11.2.1.6 | Review document for consistency of 0 and 1 lower bounds for backoff. Research exceptions for accuracy. |  | Needs Assignment
37 | 03-382r0 | Page 25 right | 11.2.1.6 | Clarificaiton Required to state that no back-off required if only one bit set in TIM. |  | Needs Assignment