## Sheet1
ID | Source | Citation | 802.11 Ref | Assessment | Recommendation | Status | Priority | Date Completed
1 | 03-382r0 | Page 3, left | 5.4.2.2 | Beyond PAR of 802.11m project because it would be defining new functionality | Consider for future work and PARs. 802.11 WGTE to include in a database, if desired. | Closed
2 | 03-382r0 | Page 3 right, bullet 1 & 2 | 5.5 | Technically correct -- possible wording changes might improve text | Change text to "Data frames in an IBSS with frame control (FC) bits To DS and From DS both false." | Brian Mathews, done.
3 | 03-382r0 | Page 3 right, bullet 2 | 5.5 | Incorrect conclusion because bits are subject to rules in section 7. Imroved wording may be warranted. | change of ID 2 recommendation also corrects this.
4 | 03-382r0 | Page 3 right, bullet 3 | 5.5 | We believe that the statement is not true. Research and editorial clarificaiton may be warranted. | This is true only in an IBSS. See rx_coord_2b in station SDL code for confirmation. No change required, unless we want to prohibit this behavior. Since authentication and association are both optional in an IBSS
5 | 03-382r0 | Page 4 left | 5.5 | Research and editorial clarificaiton may be warranted. | Remove "Management frame" text, including deauthentication frame from 5.5 c) 2)
6 | 03-382r0 | Page 4 right | 5.6 | More research is required to determine if association/disassociation is disallowed elsewhere in the document | Association is optional in an IBSS, making state 2 and both class 2 and class 2 frames possible in an IBSS. No text changes required.
7 | 03-382r0 | Page 5 | 5.5 & 5.6 | Same as 6 | Authentication is optional and needs to be described, as it is in the standard. No text changes are required.
8 | Internal Discussion | none | Figure 8 | Text labels incorrect from state 2 to 3. Needs simple fix. | "Successful Authentication or Reassociation" should be "Successful Association or Reassociation"
9 | Internal Discussion | None | 5 | Section 5 largely is descriptive. Review of each may and shall is warranted for section 5. |  | Needs Assignment
10 | 03-382r0 | Page 6 | 6.2.1.2.2 | Further research required. |  | Needs Assignment
11 | 03-382r0 | Page 7 left | 7.2.3.10 | We feel the spec is unambigous. Title of Table 14 will be ammended by adding Element at the end. | Change title of table 14 to "Presence of challenge text information element" | Terry Cole
12 | Internal Discussion | None | 7.3.2.1, 10.3.2.1.2, 11.1.3 & 11.1.3.2.1 | Clarify the broadcast SSID is actually the wildcard SSID. |  | Simon Black
13 | 03-382r0 | Page 7 right bullet 1 | 7.3.2 | Correct. Statement should be added in 17 pointing out that this is correct and OK. We should state that the DS IE should not be used for this purpose. Clarification in section 10 needed that you must fill in the PHY paramter set even though it wasn't on air. |  | Needs Assignment
13 | 03-382r0 | Page 8 | 7.3.2.6 | A couple of examples, especially any special cases should be developed. |  | Needs Assignment
14 | 03-382r0 | Page 9 left | 8 | Beyond PAR of 802.11m project and is within the scope of PAR for P802.11i |  | Closed
15 | 03-382r0 | Page 9 right | 8.1.1.2 | Text should be chagned to match MIB. | Change dot11AuthenticationType to dot11AuthenticationAlgorithm
16 | 03-382r0 | Page 10 | 8.3.2 | Text in MIB should be brought in line with 8.3.2 | The undecryptable counter must not be incremented, except as described in 8.3.2. There are no other frames that may validly carry the WEP bit set.
17 | 03-382r0 | Page 11 left | 9.1.4 | Research and editorial clarificaiton may be warranted espeically to align MIB and text. | Change the first sentence of the third paragraph of 9.1.4 to "When a directed MSDU, plus MAC header and FCS, is received from the LLC or a directed MMPDU is received from the MAC sublayer management entity (MLME) with a length greater than dot11FragmentationThreshold, ..." (two changes in this sentence!) Also change all "aFragmentationThreshold" to "dot11FragmentationThreshold"!
18 | 03-382r0 | Page 11 left | 9.2.3.3 & 9.2.3.4 | Research and editorial clarificaiton may be warranted. |  | Needs Assignment
19 | 03-382r0 | Page 12 left | 9.2.4 | Research and editorial clarificaiton may be warranted. |  | Needs Assignment
20 | 03-382r0 | Page 12 right | 9.2.5.4 | Research and editorial clarificaiton may be warranted. Perhaps look more deeply into 802.11a (and also g) |  | More discussion needed after research.
21 | 03-382r0 | Page 13 left | 9.2.5.4 | Research and editorial clarificaiton may be warranted. |  | Needs Assignment
22 | 03-382r0 | Page 13 right | 9.2.5.7 | Clarificaiton and alignment of SDL with text may be warranted. |  | Needs Assignment
23 | 03-382r0 | Page 14 left | 9.2.8 | Clarificaiton and alignment of SDL with text may be warranted. |  | Needs Assignment
24 | 03-382r0 | Page 14 right | 9.3.2.1 | Research and clarificaiton is desired. |  | Needs Assignment
25 | 03-382r0 | Page 15 | 9.3.2.2 | SDL and text need alignment. |  | Needs Assignment
26 | Internal Discussion | none | 9.3.2.2 | The special exception for timing of PCF beacon is 9.3.3.2 should be tied to the normal situations. |  | Needs Assignment
27 | 03-382r0 | Page 20 | 10.3.2.1 | Research and editorial clarificaiton may be warranted. |  | Needs Assignment
28 | 03-382r0 | Page 21 left | 11.1.2 | Clarificaiton is warranted. |  | Needs Assignment
29 | 03-382r0 | Page 21 right | 11.1.2 | Research required on how the 4us was derrived and is anything required for OFDM? | should be clarified to reflect the use of symbol timing of some PHYs | Bob
30 | 03-382r0 | Page 22 left | 11.1.2.1 | Research and editorial clarificaiton may be warranted. |  | Needs Assignment
31 | 03-382r0 | Page 22 right | 11.1.2.1 | Research and editorial clarificaiton may be warranted. |  | Needs Assignment
32 | 03-382r0 | Page 23 left | 11.1.2.2 | Research and editorial clarificaiton may be warranted. |  | Needs Assignment
33 | 03-382r0 | Page 23 right | 11.1.3.2.2 | Text seems clear. |  | Closed
34 | 03-382r0 | Page 24 left | 11.2.1.1 | Clarificaiton desired but text is accurate. |  | Needs Assignment
35 | 03-382r0 | Page 24 right | 11.2.1.5 | Reserarch requried as to what the document specifies in text and/or SDL |  | Needs Assignment
36 | 03-382r0 | Page 25 left | 11.2.1.6 | Review document for consistency of 0 and 1 lower bounds for backoff. Research exceptions for accuracy. |  | Needs Assignment
37 | 03-382r0 | Page 25 right | 11.2.1.6 | Clarificaiton Required to state that no back-off required if only one bit set in TIM. |  | Needs Assignment
38 | 03-754r0 |  | 7.3.2.9 | clarification is warranted | clarify that Tx Power level is interpreted according to the local regulations | Needs Assignment
39 | Internal Discussion |  | 10 | Missing primitive in Associate sequence |  | Darwin
40 | Internal Discussion |  | Table 4 (7.2.2) | Clarify columns 1 and 2 with respect to RA and TA. |  | Darwin, done
41 | Internal Discussion |  | 7.2.2 | Validate BSSID on all receive decisions? |  | Needs Assignment
42 | 03-667r0 |  | 6.2.1.3 | Discuss TGe changes to the primitives | Rename unitdata-status.indication to be unitdata.confirm and keep all status values, both synchronous and asynchronous. There is no support in X.210 for separation of synchronous and asynchronous status. | Needs Assignment
43 | Internal Discussion |  | 11.2.1.6 | AP might discard frames before a STA would wake and request them |  | Needs Assignment
44 | 03-382r0 | page 26 left | 11.2.1.6 | PS-Poll priority is not stated in the standard. Text seems clear and describes intended operation where first PS-Poll is sent immediately (after random (0,Cwmin) backoff) and subsequent PS-Polls are sent at discretion of STA. |  | Closed
45 | 03-382r0 | page 26 right | 11.2.2 | IBSS power save operation could be clarified with a few notes | add notes to the effect that a STA must stay awake if it wants to keep an accurate record of the power state of all other STAs, or always assume other STAs are asleep. | Needs Assignment
46 | 03-382r0 | page 27 left | 11.2.2.1 | clarification is warranted | see #45 | Needs Assignment
47 | 03-382r0 | page 27 right | 11.2.2.1 | compare to SDL and clarify |  | Needs Assignment
48 | 03-382r0 | page 28 left | 11.2.2.2 | clarification is warranted | email Tom T | Needs Assignment
49 | 03-382r0 | page 29 left | 12.3.5.11.3 | clarification is warranted |  | Needs Assignment
50 | 03-382r0 | page 30 | 17.4.4 table 99 | clarification is warranted |  | Needs Assignment
51 | 03-382r0 | page 31 | table G.1 | determine if statement is correct and clarify if needed |  | Needs Assignment
52 | 03-382r0 | page 32 | table g.14 | research and clarify if needed |  | Needs Assignment
53 | 03-199r0 | row 2 | 7.1.3.3.2 | clarification is warranted |  | Needs Assignment
54 | 03-199r0 | row 3 | 8 | research whether to include a warning on the weakness of WEP |  | Needs Assignment
55 | 03-199r0 | row 4 | all | out of scope |  | Needs Assignment
56 | 03-199r0 | row 5 | 17.1 | editorial removal of "all additions" | remove text as suggested | Needs Assignment
57 | 03-199r0 | row 6 | 15.1? | clarification is warranted |  | Needs Assignment
58 | 03-199r0 | row 7 | G.3.1 | correct equation |  | Needs Assignment
59 | 03-199r0 | row 7 | G.4.5 | correct equation |  | Needs Assignment
60 | 03-199r0 | row 8 | 15.4.7.9 | correct equation |  | Needs Assignment
61 | 03-199r0 | row 9 | various | Handled in the individual documents |  | closed
62 | 03-199r0 | row 10 | 9.3 | STA-STA traffic in BSS needs clarification/correction |  | Tim Wong
63 | 03-199r0 | row 11 | C | "getElem" function correction |  | Needs Assignment
64 | 03-199r0 | row 12 | C | Handled in the individual documents |  | Needs Assignment
65 | 03-199r0 | row 13 | 12 | service primitives are not conformance items, but abstract definitions |  | Closed
66 | 03-199r0 | row 14 | 10.3.4 and D | clarification is warranted |  | Needs Assignment
67 | 03-199r0 | row 15 | 9.4 | clarification is warranted |  | Needs Assignment
68 | 03-199r0 | row 16 | various | correction required |  | Needs Assignment
69 | 03-199r0 | row 17 | various | investigate and clarify if needed |  | Needs Assignment
70 | 03-199r0 | row 18 | C | correct variable naming |  | Needs Assignment
71 | 02-092r0 |  | 10.3.2.2.2 | clarify what to do when returning BSSDescription Set for PHYs without a parameter set in the frame. | send back channel number stuff was received on | Needs Assignment
72 | 02-091r0 | item 1 | 14.8.2.20 | change MIB attribute name | change "operation" to "capability" | Needs Assignment
73 | 02-091r0 | item 2 | C | change MIB attribute name | change "operation" to "capability"
74 | 02-091r0 | item 3 | C | change "integer" back to "TU" |  | Needs Assignment
75 | 02-091r0 | item 4 | C | change "true" to "false" |  | Needs Assignment
76 | 02-091r0 | item 5 | C | delete second definition |  | Needs Assignment
77 | Internal Discussion |  | C | "yBytp" should be "yBtyp" |  | Needs Assignment
78 | Internal Discussion |  | C | on same page as 77, change multidomainoperation to multidomaincpability |  | Needs Assignment
79 | 02-091r0 | item 6 | C | described operation is as intended, IBSS of 802.11d capable device shall not be started without valid information and being enabled |  | Closed
80 | 02-091r0 | item 7 | C | correct "enabled" to be "implemented" | The intent is correct, the implementation is wrong in the SDL | Needs Assignment
81 | 02-091r0 | item 8 | C | no clarification needed |  | Closed
82 | internal discussion |  | C | In AP_Start_Bss_2c, attribute name is incorrect | change "operation" to "capability" | Needs Assignment
83 | 02-091r0 | item 9 | C | described operation is as intended, BSS of 802.11d capable device shall not be started without valid information and being enabled |  | Closed
84 | 02-091r0 | item 10 | D | The MIB attribute was misspelled in the instruction. The document has the correct spelling. |  | Closed
85 | 02-091r0 | item 11 | D and 11.1.3.4 | needs investigation, looks like description in MIB is incorrect. The values listed in the MIB entry should be in the "value" part of the table. "Other" needs to be added to the enumeration in the value entry. |  | Needs Assignment
86 | 02-091r0 | item 12 | 11.1.3.4 and others | clarification is warranted | what is "adopt"? | Needs Assignment
87 | 02-091r0 | item 13 | C | correct cross reference to 7.3.2.12 on page AP_TSF_bss_3 |  | Needs Assignment
88 | Internal Discussion |  | 7.3.2.x | 802.11d numbered IEs up to 15, but only 12 are in the 2003 edition. Investigate. |  | Needs Assignment
89 | 02-091r0 | item 14 | C | need to add requested information elements to probe response process |  | Needs Assignment
90 | 02-093r0 | item 1 | 7 | no clarification needed |  | Closed
91 | 02093r0 | item 2 | 17.3.8.3.2 | caught by editor in roll-up |  | Closed
92 | SDL bugs | item 1 | C | On sta_join_4, correct "start" to "confirm" |  | Needs Assignment
93 | SDL bugs | item 2 | C | investigate and clarify if needed |  | Needs Assignment
94 | SDL bugs | item 3 | C | investigate and clarify if needed |  | Needs Assignment
95 | SDL bugs | item 4 | C | investigate and clarify if needed |  | Needs Assignment
96 | SDL bugs | item 5 | C | investigate and clarify if needed |  | Needs Assignment
97 | SDL bugs | item 6 | C | investigate and clarify if needed |  | Needs Assignment
98 | SDL bugs | item 7 | C | investigate and clarify if needed |  | Needs Assignment
99 | SDL bugs | item 8 | tables 2 and 22 | conflicting STA to STA in BSS |  | Needs Assignment
100 | PICS | internal discussion | PICS | "d" PICS is screwy |  | Needs Assignment