## No Comments from LB51
Name | Clause | E/T | Y/N | Comment/Explanation | Recommended Change | Ad-Hoc Group Responsible | Recommended Disposition | Draft Incorporating Resolution | Date Resolved (Based on Pacific Time) | Miscellaneous Comments | Comment accepted/rejected/other resolution | Status
Barber, Simon | 7.4.2 | T | Y | DLPs require inventing a complete new mechanism for negociating association, where we already have 2 such mechanisms (associations for ESS and IBSS). The existing mechanisms are more complete, and provide for security. We should not allow this new mechanism without first considering making the required additions to allow a station to use IBSS management frames while connected to an AP to achieve the same effect as these DLP messages. | remove all references to DLP from the document. | Ad hoc group on clause 7 | Comment declined. There is no association in an IBSS. DLP improves efficiency of transfer of data between two STAs. Furthermore, STAs will not be able to take full advantage of the features of enhanced access mechanisms. |  | 2003-05-28
Barber, Simon | 9.1.3 | T | Y | HCF provides worst service delivery than EDCF in most cases. HCF guarantees data will be delayed, in particular when it comes from a source that is not synchronized with the AP. In addition by bunching delivery of QoS frames this causes further delays in processing in the network due to the fact that a media processor can't process all these frames delivered at once instantaneously. These synchronization effects build up in the network causing HCF to have a significantly worse effect on typical VoIP applications than at first imagined. EDCF does not have these latency problems in the common case. In addition the HCF situation gets worse when multiple streams with differing periodicities are in use (e.g. different voice codecs). This will commonly add a delay of one whole frame period in each direction to a voip call - again making the typical case for HCF very bad. EDCF does not suffer from any of these problems caused by synchronization. | remove HCF. | Tge Ad Hoc April | Comment declined. The purpose of HCF is to provide a unified mechanism for both contention based and polled access. The purpose of polled access is to provide MSDU transport according to a specified service schedule/TSPEC. EDCF will not be able to provide this, especially under heavily loaded scenarios. What happens in polled access is that delay becomes less stochastic than it is with EDCF. Finally, polled access provides integrated services; EDCF provides priortized access. These are different types of QoS, and different mechanisms are needed for that. | D4.4 | 2003-05-01
Brennan, Jim | 9.10.2.4.2 | T | Y | There are inconsistantcies between the TSPEC request being optional and the PICS stating that HCF is mandatory. | Make the TSPEC request mandatory. |  | Comment is declined as it impacts the optional/mandatory status of the HCF and E-DCF. The current text describes a standard that provides the best tradeoff of cost, performance and ease of implementation that the task group has found. Furthermore, we believe the text accurately reflects this tradeoff, and therefore this standard meets a broad spectrum of market needs for QoS and guarantees interoperability among all implementations.” |  | 2003-03-12
Green, Patrick | 9.10.1.7.2; line 11 | T | Y | four variables' should be 'five variables' in Table 20.13; from line 11 | Change four to five; add [AC] to each variable | Ad hoc group on clause 9.10.1 | Alternate resolution. Instruct the editor to remove Distributed Admission Control and references therein from the draft.
Lefkowitz, Martin | 7.4.2.2 | T | Y | The AP needs to have control over whether any particular DLP connection can be established or not | Change the defintion of not allowed status to this DLP connection is not allowed by BSS policy. | Ad hoc group on clause 7 | Alternate resolution: Change it to "Not allowed in the BSS" | D4.6 | 2003-05-28
Lefkowitz, Martin | 7.4.2.2 | T | Y | The AP needs to have control over the security policy of the DLP connection | If adding the RSN IE the the DLP request and Response is not procedurually appropriate, Add text that states that the security policy for both the STA's as well as the security policy of the connection must be acceptable to the BSS, then fix it later when the two task groups drafts merge. Add another status defintion stating that the security policy specified in the DLP connection is not acceptable to the BSS. | Ad hoc group on clause 7 | Comment declined. Out of scope of TG. However Tgi has provided a mechanism for encryption. |  | 2003-06-25
Lefkowitz, Martin | 9.10.1.6 | T | Y | Saying that a non QOS AP must retransmit the the frame before trying another frame is different behavior than the 1999 spec. Some HW implementations allow for this not to be the case. | Take the second paragraph out | Ad hoc group on clause 9.10.1 | Alternative resolution: replace the second paragraph with "If a QSTA or QAP does not use QoS data types when transmitting frames to a particular receiver address, once an initial attempt, excluding internal collisions, has been made to transmit a frame, it shall not transmit other data frames to that receiver address until the first frame is either successfully transmitted or discarded. It may, however, transmit other frames to different receiver addresses." | D4.1 | 2003-01-17
Mahalingam, Mani | 9.10.2.4.2 | E | Y | Language implies TSPEC request management and QAP polling to be optional. | Change language to indicate that both are mandatory at AP. |  | Comment declined. The text correctly reflects the status fo the draft.
Moore, Tim | 5.8 | T | Y | The direct link protocol is not secure | Either remove direct link or add security to the protocol |  | Security is beyond the scope of the TG. However, Tgi has already defined a mechanism which can be used. |  | 2003-06-23
Moore, Tim | 5.8 | T | Y | DLP is allowed to be initiated by the AP, if this is allowed then message 3 from QSTA-1 to the AP is needed to inform the AP whether QSTA-1 can handle the DLP request. Normally message 1a and 2a can be used to inform the AP that the stations cannot handle DLP at this time, QSTA-1 by not sending the request, QSta-2 by a refused in the status field of message 2a | Remove support for AP initiating DLP | Feb adhoc | Comment accepted. Remove the following sentence from 5.8 "By omitting the first step (1a), this protocol can also be invoked by the AP to set up a Direct Link between two associated QSTAs. " | D4.3 | 2003-02-27
Moore, Tim | 7.4.2.3 | T | Y | The DLP probe containing a destination mac address, Source message address and random data, the dest and source are not required since it is in the MAC header and the random data doesn't add anything | Remove dest, source mac address and random data fields from DLP probe | Ad hoc group on clause 7 | Alternate Resolution. Delete the subclause. | D4.4 | 2003-05-15
Moore, Tim | 6.1.3 | T | Y | It is not clear whether packet reordering is allowed from a QSTA to a non-QSTA. Can a QSTA station reordering packets being sent to a non-QSTA AP? The AP will forward using prioirty 0 and Strictlyordered can't be used by the QSTA | Specifiy would is allowed |  | Comment accepted. Add the following sentence at the end of the clause "QSTAs operating in a non-QBSS shall follows the reordering rules as defined for a non-QoS STA." | D4.6 | 2003-06-24
Moore, Tim | 7.1.3.1.7 | T | Y | Why DLP not allowed when section 5.8 talks about power management and DLP | Either allow power save and DLP or remove power save from 5.8 or clarify what the purpose of the power save discussion is in 5.8 | Ad hoc group on clause 7 | Comment declined. The description about Power Save in 5.8 talks about setting up a DLP when a STA is in a power-save mode. However, once a DLP is set, the STA shall be awake. |  | 2003-01-17
Moore, Tim | 7.2.2 | T | Y | The statement "Data frames with a value of 0 in the QoS bit of the subtype field are used for basic transfers" and "Data frames with a value of 1 in the QoS bit of the subtype field are used for transmission of MSDUs to other QSTAs" is confusing should not QoS data frames be used for basic transfers to a QSTA or nor? | Decide and clarify whther QoS data frames are always used between QSTAs or not | Ad hoc group on clause 7 | Comment accepted. Add the following sentence in 9.10: " A QSTA shall always use subtype QoS data frames for data transmissions to a QAP or another QSTA (with which there is a DLP set up)." | D4.4 | 2003-03-26
Shen, Yangmin | Page 9, section 5.4.2.1 subclause b | T | Y | What is the proper process when a QSTA roams to a non-802.11e compliant AP or one that cannot provide the QoS due to traffic or or other loading | Needs clarification |  | Comment declined. This is beyond the scope of the standard as this is an implementation decision. However, if a STA roams into an 802.11e enabled QBSS, then the standard provides tools to transfer the QoS requirements to the new AP. A STA can restrict its association to 802.11e enabled BSS exclusively by setting the MIB parameter. In an ESS, it is reasonable to assume that all APs have the same capabilities and what the commenter seeks is needed only when a STA roams in a trans-ESS. |  | 2003-06-26

## No Comments from LB59
Name | Clause | E/T | Y/N | Comment/Explanation | Recommended Change | Ad-Hoc Group Responsible | Recommended Disposition | Draft Incorporating Resolution | Date Resolved (Based on Pacific Time) | Miscellaneous Comments | Comment accepted/rejected/other resolution | Status
Clements, Ken | Annex C | T | Y | lack of formal specifications of the changes to the operation of the 802.11 MAC layer. |  |  | Declined. While the claim this comment makes is true, there is no evidence that the lack of a formal description makes any difference in practice. Furthermore, 802.11h was approved without any changes to the formal description in Annex C, and IEEE 802.3 has removed Annex C completely, indicating that IEEE 802.11, 802, and RevCom all believe that updates to the formal description are not necessary for correct and interoperable implementations of the standard. |  | 2003-10-29 | Clause number changed from Annex D to Annex C.
Cole, Terry | General | E | Y | Project header must identify this draft a P802.11 and not IEEE Std 802.11. | Replace IEEE Std 802.11 with P802.11. See for example final drafts of 802.11g or 802.11h submitted to REVCOM. |  | accepted. | D5.1 | 2003-10-21
Cole, Terry | 7.2.1 | T | Y | Not that 802.11g is passed, we must consider if modification of the CTS to self is required (section 7.2.1.2) | Please consider if changes similar to 7.2.1.1 must be made to CTS to Self in 7.2.1.2. |  | Comment accepted. Incorporate the changes in 03/832r0 into the next Tge draft |  | 2003-11-11
Cole, Terry | 7.2.3.1 | T | Y | Now that 802.11g is passed, we must include changes form 802.11g in our section. | Include all 802.11g changes in 802.11e as appropriate. |  | Comment accepted. Incorporate the changes in 03/832r0 into the next Tge draft | D6.0 | 2003-11-11
Cole, Terry | 7.2.3.4 | T | Y | Now that 802.11g is passed, we must include changes form 802.11g in our section. | Include all 802.11g changes in 802.11e as appropriate. The 802.11e changes conflict with 802.11g and must be resolved. |  | Comment accepted. Incorporate the changes in 03/832r0 into the next Tge draft | D6.0 | 2003-11-11
Cole, Terry | 7.2.3.5 | T | Y | Now that 802.11g is passed, we must include changes form 802.11g in our section. | Include all 802.11g changes in 802.11e as appropriate. The 802.11e changes conflict with 802.11g and must be resolved. |  | Comment accepted. Incorporate the changes in 03/832r0 into the next Tge draft | D6.0 | 2003-11-11
Cole, Terry | 7.2.3.6 | T | Y | Now that 802.11g is passed, we must include changes form 802.11g in our section. | Include all 802.11g changes in 802.11e as appropriate. The 802.11e changes conflict with 802.11g and must be resolved. |  | Comment accepted. Incorporate the changes in 03/832r0 into the next Tge draft | D6.0 | 2003-11-11
Cole, Terry | 7.2.3.7 | T | Y | Now that 802.11g is passed, we must include changes form 802.11g in our section. | Include all 802.11g changes in 802.11e as appropriate. The 802.11e changes conflict with 802.11g and must be resolved. |  | Comment accepted. Incorporate the changes in 03/832r0 into the next Tge draft | D6.0 | 2003-11-11
Cole, Terry | 7.2.3.9 | T | Y | Now that 802.11g is passed, we must include changes form 802.11g in our section. | Include all 802.11g changes in 802.11e as appropriate. The 802.11e changes conflict with 802.11g and must be resolved. |  | Comment accepted. Incorporate the changes in 03/832r0 into the next Tge draft | D6.0 | 2003-11-11
Cole, Terry | 7.3.1.4 | T | Y | Now that 802.11g is passed, we must include changes form 802.11g in our section. | Include all 802.11g changes in 802.11e as appropriate. The 802.11e changes conflict with 802.11g and must be resolved. |  | Comment accepted. Incorporate the changes in 03/832r0 into the next Tge draft | D6.0 | 2003-11-11
Cole, Terry | 9.6 | T | Y | Now that 802.11g is passed, we must include changes form 802.11g in our section. | Include all 802.11g changes in 802.11e as appropriate. The 802.11e changes conflict with 802.11g and must be resolved. |  | Comment accepted. Incorporate the changes in 03/832r0 into the next Tge draft |  | 2003-11-11
Cole, Terry | 9.10 | T | Y | Now that 802.11g is passed, we must include changes form 802.11g in our section. | 9.10 already exists in the base document, so changes must be incorporated into 802.11e to align. Also… you need to consider the impact of 9.10 from 802.11g on the frame sequences shown in 9.12, if any. How is the NAV distributed to 802.11g and 802.11b device within each sequence prior to OFDM transmission? Also, special consideration may be required for DLP in this area as well. |  | Comment accepted. Incorporate the changes in 03/832r0 into the next Tge draft | D6.0 | 2003-11-11
Cole, Terry | Figure 62.11 | T | Y | Not that 802.11g is passed, we must consider CTS to self | Added CTS to self. |  | accepted. | D5.2 | 2003-10-29
Cole, Terry | 10.3.6.1.2 | T | Y | I don't think that the two new inserted parameters are mandatory if no QSTA | Make optional based on some parameters, variable, MIB value, etc. |  | Add to the description column: "shall only be present if the MIB attribute dot11QoSOptionImplemented is true." | D5.2 | 2003-10-29
Cole, Terry | 10.3.6.2.2 | T | Y | I don't think that the last 3 parameters are mandatory if not QSTA. | Make optional based on some parameters, variable, MIB value, etc. |  | Add to the description column: "shall only be present if the MIB attribute dot11QoSOptionImplemented is true." | D5.2 | 2003-10-29
Cole, Terry | 10.3.6.2.2 | T | Y | I don't think that the last 2 parameters are mandatory if not QSTA. | Make optional based on some parameters, variable, MIB value, etc. |  | Add to the description column: "shall only be present if the MIB attribute dot11QoSOptionImplemented is true." | D5.2 | 2003-10-29
Cole, Terry | 10.3.7.1.2 | T | Y | I don't think that the last 2 parameters are mandatory if not QSTA. | Make optional based on some parameters, variable, MIB value, etc. |  | Add to the description column: "shall only be present if the MIB attribute dot11QoSOptionImplemented is true." | D5.2 | 2003-10-29
Cole, Terry | 10.3.7.2.2 | T | Y | I don't think that the last 3 parameters are mandatory if not QSTA. | Make optional based on some parameters, variable, MIB value, etc. |  | Add to the description column: "shall only be present if the MIB attribute dot11QoSOptionImplemented is true." | D5.2 | 2003-10-29
Cole, Terry | 10.3.7.3.2 | T | Y | I don't think that the last 2 parameters are mandatory if not QSTA. | Make optional based on some parameters, variable, MIB value, etc. |  | Add to the description column: "shall only be present if the MIB attribute dot11QoSOptionImplemented is true." | D5.2 | 2003-10-29
Cole, Terry | 10.3.10.1.2 | T | Y | I don't think that the last 2 parameters are mandatory if not QSTA. | Make optional based on some parameters, variable, MIB value, etc. |  | Add to the description column: "shall only be present if the MIB attribute dot11QoSOptionImplemented is true." | D5.2 | 2003-10-29
Cole, Terry | 11.7.2 | T | Y | I don't understand how the statement and the requirement of 802.11g protection mechanism (must distribute NAV before transmitting OFDM) may interact. | Consider if DLP requires any special support in a mixed 802.11b and 802.11g network to be supported by OFDM transmissions. |  | Accepted. Instruct the editor to incorporated support for RTS/CTS with DLP. | D5.1 | 2003-09-16
Cole, Terry | A | T | Y | The goal of Annex A is to provide a statement for each shall statement in the main body. Searching for shall, I found statements in 6.1.1.1, 6.1.1.2, 6.1.3, 7.1.1, 7.1.2, 7.1.3.2, 7.1.5.3.3, 7.3.1.4, 7.3.11, 7.3.12, 7.3.2.15, 7.3.2.21, 7.4.3.1, 9.1.3, 9.1.3.1, 9.1.4, 9.1.6, 9.2.3, 9.2.3.4, 9.2.9, 9.6, 9.9, 9.9.1.2, 9.9.1.2, 9.9.1.3, 9.9.1.5, 9.9.1.6, 9.9.1.7, 9.9.1.7.1, 9.9.1.7.2, 9.9.2, 9.9.2.1, 9.9.2.1.1, 9.9.2.1.2, 9.9.2.2. 9.9.2.2.1, 9.9.2.3, 9.9.2.4, 9.10.2, 9.10.3, 9.10.4, 9.10.5, 9.10.6, 9.12 (legend?), 10.3.11.3.2, 10.3.11.3.4, 10.3.11.4.2, 10.3.11.4.4, 10.3.11.5.4, 10.3.13.1.4, 10.3.15.1.4, 10.3.15.5.4, 10.3.16.1.2, 10.3.16.1.4, 10.3.16.3.4, ... | I believe that these shalls should be translated into a set of PICS statements. I stopped going through the document as the list at left seemed rather not terribly useful. I don't think all these shall are currently reflected in the PICs. Please review. |  | Comment declined. The group believes that the PICS is sufficient. |  | 2003-11-13
Cole, Terry | Table 5 | T | Y | It may be questionable to have the word shall appear in a table column called "Note." | Avoid this if possible. Note -- is informative, unless it appears at the end of a table (in which case it is a table note and normative). Foot notes are informative (and not even part of the document). I don't make these rules… See IEEE style guide. Sigh... |  | Resolved by the resolution to comment #136 | D6.0 | 2003-10-29
Cole, Terry | Table 12 | T | Y | It may be questionable to have the word shall appear in a table column called "Note." | Avoid this if possible. Note -- is informative, unless it appears at the end of a table (in which case it is a table note and normative). Foot notes are informative (and not even part of the document). I don't make these rules… See IEEE style guide. Sigh... |  | Resolved by the resolution to comment #136 | D6.0 | 2003-10-29
Cole, Terry | C | T | Y | Deleting the SDL leaves many things unspecified from the main body. I searched for Annex C and you will find: 9.1.5, 18.1.2, Many, man references in Annex A. | Repairs these problems or put back Annex C. |  | Accepted. Resolved by the resolution to comment #183 | D5.2 | 2003-10-29
Dutkiewicz, Eryk | 7.4.1.2 | T | Y | In section 9.9.2.4, the minimum set of parameters required so that the scheduler can determine a schedule for an admitted stream are defined. A different minimum set of parameters are required by the eDCA channel access function in section 9.9.1.7.2. Therefore, when admitting an eDCA flow the HC does not receive the minimum amount of information required to determine a schedule. | 1) Change the second column of the last row in table 20.8 to read "Schedule (HCCA flows only)" 2) Change line 11 on page 56 to read "The HC announces the schedule for HCF controlled channel access flows and for the flows which are admitted as both controlled and contention-based channel access in the ADDTS response frame". |  | Alternate resolution. Instruct the Editor to incorporate the normative text in document 11-03-0698-01-000e | D5.1 | 2003-10-22
Dutkiewicz, Eryk | 9.9.2.4 | T | Y | The scope of the aggregation behavior is not limited to HCCA flows. The eDCF channel access function requires a different minimum set of TSPEC parameters than the HCCA channel access function and therefore the two types of flows can and should not be aggregated. | 1) Change line 23 on page 82 to read "The HC may aggregate admitted HCCA TS for a single non-AP QSTA and establish a Service Schedule for the non-AP QSTA. 2) Change line 26 on page 82 to read "If the QAP establishes an aggregate Service Schedule for a non-AP QSTA, it shall aggregate all HCCA streams for the QSTA. |  | Accepted. | D5.1 | 2003-09-15
Dutkiewicz, Eryk | 11.2.1.10 | T | Y | For an eDCA admitted flow in APSD mode, the specified wakeup and sleep behavior tied with Service Period (SP) for non-AP QSTA results in inefficient performance. The reason is: if the non-AP QSTA is in power save mode and wakes up to transmit this traffic prior to the scheduled SP, then it shall also wake up or remain awake for the scheduled SP. For a bi-directional or uplink flow, once a station wakes up and transmits, there is no reason why it should go back to sleep and then wake up again for a scheduled service interval to receive a frame from an AP. It would be even more inefficient, from a QoS standpoint (e.g. media access delay), to place a restriction on the non-AP QSTA that it must not transmit until the scheduled SP even the uplink frame is available to transmit prior to the SP. | Adopt the text in document 11-03-0661-00-000e |  | Accepted. Instruct the Editor to incorporate the normative text in document 11-03-0698-01-000e | D5.1 | 2003-09-17
Dutkiewicz, Eryk | 11.2.3 | T | Y | For an eDCA admitted flow in APSD mode, the specified wakeup and sleep behavior tied with Service Period (SP) for non-AP QSTA results in inefficient performance. The reason is: if the non-AP QSTA in power save mode and wakes up to transmit this traffic prior to the scheduled SP, then it shall also wake up or remain awake for the scheduled SP. For a bi-directional or uplink flow, once a station wakes up and transmits, there is no reason why it should go back to sleep and then wake up again for a scheduled service interval to receive a frame from an AP. It would be even more inefficient, from a QoS standpoint (e.g. media access delay), to place a restriction on the non-AP QSTA that it must not transmit until the scheduled SP even the uplink frame is available to transmit prior to the SP. | Adopt the text in document 11-03-0661-00-000e |  | Accepted. Instruct the Editor to incorporate the normative text in document 11-03-0698-01-000e | D5.1 | 2003-09-17
Dutkiewicz, Eryk | 11.2.3.2, 11.2.3.1 | T | Y | If Aggregation is negotiated to 0 in a TSPEC, then one would think that the Schedule for that TSPEC applies to that TS only. But this is not reflected in the behavior of APSD, because it always delivers ALL buffered frames during the SP--not just the frames in the corresponding TS. It would make more sense if, for a non-aggregated TSPEC, only frames in the particular TS would be delivered during the defined SP. | Change last line of 11.2.3.1 b) to: If the scheduled SP is part of an aggregated schedule, the QAP shall transmit all frames buffered during the SP; but if the SP is part of a non-aggregated schedule, the QAP shall transmit only frames belonging to the TS during the SP. |  | Alternate resolution. Instruct the editor to add the following text to 7.3.2.15., "When the APSD subfield is set to 1, the aggregation subfield is also set to 1." |  | 2003-11-11
Dutkiewicz, Eryk | 7.3.2.15 | T | Y | The 2-octect TSInfo field in the TSPEC element has been fully utilized. This leaves no room for possible future addition of any useful information to the TSInfo field. This assumes that it is desirable to have all the information necessary to setup a traffic stream residing within one information element. | 1) Insert an optional 1-octect "Extended TSInfo" field after the current "TSInfo" field. 2) Move the APSD bit (B10) from TSInfo field to B0 in the "Extended TSInfo" field. 3) Rename the previous APSD bit (B10) in the TSInfo field to "Extended TSInfo". 4) Set the "Extended TSInfo" bit to 1 if "Extended TSInfo" field exists and contains non-zero value. Set "Extended TSInfo" bit to 0 otherwise. |  | Alternate resolution. Make the TSInfo field 3-octets long. | D6.0 | 2003-11-11
Meyer, Klaus | 7.1.3.1.8 | T | Y | The More Data field is set to 1 in broadcast/multicast frames. Why is this restricted to zero user priority only? | Clarification requested. |  | Alternate resolution. Resolved by comment 273 which removes the restriction. | D5.1 | 2003-10-15
Meyer, Klaus | 7.3.2.13 | T | Y | Table 46.1: The number of octets specified by the Length field is wrong. | Change the number in the Length field to '5'. |  | Comment accepted. | D5.2 | 2003-10-15
Meyer, Klaus | 9.1.3.1 | T | Y | text: '… EDCA TXOP is limited to a single MSDU at any rate …'. MPDU (release D4.0) has been replaced by MSDU. MPDU (release D4.0) has been replaced by MSDU. What was the reason for that change and could that prefer data packets which are labeled AC_BK and AC_BE? | Clarification required. |  | Declined. This change was made to bring the QoS rules in line with the existing legacy rules. HC that want to limit the amount of time a given QSTA can occupy the medium may us a non zero value for TXOP duration. |  | 2003-09-18
Meyer, Klaus | 9.1.3.1 | T | Y | text: 'A QSTA shall update its MIB values … within one beacon interval after receiving an updated EDCA parameter set.' Does that mean an update needs to take place still within the same beacon interval in which the updated EDCA parameter set was received or has the beacon interval to be considered as duration? | Clarification requested. |  | Accepted. Instruct the editor to clarify that the QSTA has an interval of time equal to the Beacon Interval to adopt the updated EDCA parameters. | D5.2 | 2003-09-18
Meyer, Klaus | 9.9.1.3 | T | Y | text: 'a) Following AIFS[AC] of medium idle indication after …': The calculation based on this paragraph does not fit to the statement of 'Earliest possible transmission on-air when AIFSN=1' in Figure 62.2. According the text the calculation is specified to start after M1+D1 while the Figure indicates that it starts immediately. | Align content of text and Figure. |  | counter - the AIFS as measured by the MAC does not follow the timing as indicated on the upper portion of the diagram, but instead, the timing on the lower portion, due to the delays encountered in the signal from the air traveling from the phy to the MAC (D1) and the delays in traveling from the MAC to the PHY (RxTx time) - however, the text is incorrectly using the medium time to describe the time required to wait on the part of the MAC - editor shall change AIFS[AC] in items a) b) c) d) from AIFS[AC] to AIFSN[AC] x aSlotTime | D5.1 | 2003-09-15
Meyer, Klaus | 9.9.1.3 | T | Y | text: 'c) At the latter of the end of the ACK-Timeout interval …'. A definition of ACK-Timeout or a reference to the respective definition would be very useful for the readers. | Add the respective definition or a reference. |  | reject - a value for ACK-Timeout is found in the SDL, albeit, not exactly with the name of ACK-Timeout, but implicitly taking the role of this parameter - further clarification on this issue is to be addressed to the TGm TG, since this issue is one of cleaning up a problem that exists in the base standard. |  | 2003-09-15
Meyer, Klaus | 9.9.2.1 | T | Y | This causes all non-QoS STAs to set their NAVs to the dot11CFPMaxDuration value at DTIM TBTT, …'. That means it has to be set at the beginning of a CFP but not every DTIM starts a CFP. | Clarification required. |  | Accepted. Replace "dot11CFPMaxDuration" with "CFPDurRemaining value in the CF Parameter set element". Delete DTIM. | D5.1 | 2003-09-15
Meyer, Klaus | 9.9.2.1.3 | T | Y | Clause 9.9.2.1.3 defines recovery for polled TXOPs. Why is this different to EDCF continuation TXOP (clause 9.9.1.4)? | Clarification required (e.g. add a remark to clause 9.9.1.4). |  | Alternate Resolution. Instruct the Editor to add a statement in 9.9.2.1.3 explaining why the recovery needs for an HCCA TXOP are different than for an EDCA continuation TXOP. | D5.1 | 2003-09-15
Oakes, Ivan | 5.2.5, last paragraph | T | Y | No definition of "QoS Extensions", should they include Block Ack, DLP and APSD? | Insert an appropriate definition in "definitions" e.g. "All frames-types, IE's, reason codes, and status codes used for QoS, these being: Qos xxx frames, frames with the QoS Control field, BlockAckReq and BlockAck Frames, reason codes as in Table 18 section 7.3.1.7 and status codes in Table 19 section 7.3.1.9." |  | Alternate resolution. Replace "shall not have QoS extensions" with "shall not use the frame formats associated wiith the QoS facility." | D5.1 | 2003-08-25
Oakes, Ivan | 5.2.5, last paragraph | T | Y | Some frames sent by the AP will contain Qos Extensions, e.g. Beacon. | Insert the word "directed". "All directed frames that are sent…" |  | comment accepted. | D5.1 | 2003-08-25
O'Hara, Bob | Annex C | T | Y | Deletion of the Annex deletes technical descriptioin of the 802.11-1999 MAC that is not replaced by new text in the prose provided by 802.11e | Do not delete the annex. |  | accepted. Resolved by resolution to comment #183. | D5.2 | 2003-10-29
O'Hara, Bob | Annex C | T | Y | Functional descriptions provided in the prose by 802.11e are not represented by corresponding formal descriptions in the annex | Add formal description of the changes to the access mechanisms and frame exchanges to the annex. |  | Declined. While the claim this comment makes is true, there is no evidence that the lack of a formal description makes any difference in practice. Furthermore, 802.11h was approved without any changes to the formal description in Annex C, and IEEE 802.3 has removed Annex C completely, indicating that IEEE 802.11, 802, and RevCom all believe that updates to the formal description are not necessary for correct and interoperable implementations of the standard. |  | 2003-10-29
O'Hara, Bob | 9 | T | Y | If there is sufficient demand in the industry for adding QoS to 802.11, a single access mechanism can be found that will meet the requirements of those applications requiring QoS. | Select a single access mechanism. |  | comment declined. Different applications have different requirements, and require different services from the MAC; in particular, the mechanisms support both differentiated services and integrated serrvices. The market has not decided decisively in favor of one mechanism versus the other, and so, in order to ensure that equipment based on this standard is deployed widely, both types of services are implemented in this standard. |  | 2003-08-26
Raad, Raad | 7.4.1.2 | T | Y | In section 9.9.2.4, the minimum set of parameters required so that the scheduler can determine a schedule for an admitted stream are defined. A different minimum set of parameters are required by the eDCA channel access function in section 9.9.1.7.2. Therefore, when admitting an eDCA flow the HC does not receive the minimum amount of information required to determine a schedule. | 1) Change the second column of the last row in table 20.8 to read "Schedule (HCCA flows only)" 2) Change line 11 on page 56 to read "The HC announces the schedule for HCF controlled channel access flows and for the flows which are admitted as both controlled and contention-based channel access in the ADDTS response frame". |  | Alternate resolution. Instruct the Editor to incorporate the normative text in document 11-03-0698-01-000e | D5.1 | 2003-10-22
Raad, Raad | 9.9.2.4 | T | Y | The scope of the aggregation behavior is not limited to HCCA flows. The eDCF channel access function requires a different minimum set of TSPEC parameters than the HCCA channel access function and therefore the two types of flows can and should not be aggregated. | 1) Change line 23 on page 82 to read "The HC may aggregate admitted HCCA TS for a single non-AP QSTA and establish a Service Schedule for the non-AP QSTA. 2) Change line 26 on page 82 to read "If the QAP establishes an aggregate Service Schedule for a non-AP QSTA, it shall aggregate all HCCA streams for the QSTA. |  | Accepted | D5.1 | 2003-09-15
Raad, Raad | 11.2.1.10 | T | Y | For an eDCA admitted flow in APSD mode, the specified wakeup and sleep behavior tied with Service Period (SP) for non-AP QSTA results in inefficient performance. The reason is: if the non-AP QSTA is in power save mode and wakes up to transmit this traffic prior to the scheduled SP, then it shall also wake up or remain awake for the scheduled SP. For a bi-directional or uplink flow, once a station wakes up and transmits, there is no reason why it should go back to sleep and then wake up again for a scheduled service interval to receive a frame from an AP. It would be even more inefficient, from a QoS standpoint (e.g. media access delay), to place a restriction on the non-AP QSTA that it must not transmit until the scheduled SP even the uplink frame is available to transmit prior to the SP. | Adopt the text in document 11-03-0661-00-000e | D5.1 | Accepted. Instruct the Editor to incorporate the normative text in document 11-03-0698-01-000e | D5.1 | 2003-09-17
Raad, Raad | 11.2.3 | T | Y | For an eDCA admitted flow in APSD mode, the specified wakeup and sleep behavior tied with Service Period (SP) for non-AP QSTA results in inefficient performance. The reason is: if the non-AP QSTA in power save mode and wakes up to transmit this traffic prior to the scheduled SP, then it shall also wake up or remain awake for the scheduled SP. For a bi-directional or uplink flow, once a station wakes up and transmits, there is no reason why it should go back to sleep and then wake up again for a scheduled service interval to receive a frame from an AP. It would be even more inefficient, from a QoS standpoint (e.g. media access delay), to place a restriction on the non-AP QSTA that it must not transmit until the scheduled SP even the uplink frame is available to transmit prior to the SP. | Adopt the text in document 11-03-0661-00-000e | D5.1 | Accepted. Instruct the Editor to incorporate the normative text in document 11-03-0698-01-000e | D5.1 | 2003-09-17
Raad, Raad | 11.2.3.2, 11.2.3.1 | T | Y | If Aggregation is negotiated to 0 in a TSPEC, then one would think that the Schedule for that TSPEC applies to that TS only. But this is not reflected in the behavior of APSD, because it always delivers ALL buffered frames during the SP--not just the frames in the corresponding TS. It would make more sense if, for a non-aggregated TSPEC, only frames in the particular TS would be delivered during the defined SP. | Change last line of 11.2.3.1 b) to: If the scheduled SP is part of an aggregated schedule, the QAP shall transmit all frames buffered during the SP; but if the SP is part of a non-aggregated schedule, the QAP shall transmit only frames belonging to the TS during the SP. |  | Alternate resolution. Instruct the editor to add the following text to 7.3.2.15., "When the APSD subfield is set to 1, the aggregation subfield is also set to 1." |  | 2003-11-11
Raad, Raad | 7.3.2.15 | T | Y | The 2-octect TSInfo field in the TSPEC element has been fully utilized. This leaves no room for possible future addition of any useful information to the TSInfo field. This assumes that it is desirable to have all the information necessary to setup a traffic stream residing within one information element. | 1) Insert an optional 1-octect "Extended TSInfo" field after the current "TSInfo" field. 2) Move the APSD bit (B10) from TSInfo field to B0 in the "Extended TSInfo" field. 3) Rename the previous APSD bit (B10) in the TSInfo field to "Extended TSInfo". 4) Set the "Extended TSInfo" bit to 1 if "Extended TSInfo" field exists and contains non-zero value. Set "Extended TSInfo" bit to 0 otherwise. |  | Alternate resolution. Make the TSInfo field 3-octet long. | D6.0 | 2003-11-11
Skellern, David | 9.9.1.3 | T | Y | P71 Line 8 of the clean draft (item c). What on earth does this mean. I cannot parse this sentence. | I have no idea. What about breaking it into subclauses? |  | Comment accepted. The item will be divided into multiple sub-items. |  | 2003-08-25
Soomro, Amjad | 9.9.1.3 | T | Y | The conditions (a) through (e) for slot boundaries do not include the case when medium is sensed busy due to non 802.11 transmssions. | Complete the case scenarios to cover the situation when channel is sensed busy due to non-802.11 interferers |  | accept: Insert a case e) between d) and e) renaming e) to f) with the following text: "Following AIFSN[AC] * aSlotTime of medium idle time indication after the last indicated idle medium as indicated by the CS mechanism, which is not covered by a) through d). | D6.0 | 2003-11-10
Soomro, Amjad | 9.9.2.4 | T | Y | p82, lines 19-20. If low data rate TS, such as voice call, operates at low data rate for range and/or robustness reason then this requirement calls for allocation of several times larger TXOPS. This is certainly not desirable in all circumstances. Thoug min PHy rate has been negotiated the maximum size MSDUs are uncommon in voice applications | Remove the requirement to minimally allocate TXOPs to transmit maximum size frames at the lowest PHY rate negotiated. |  | Alternate Resolution. Change the sentence as "Additionally, the minimum TXOP duration shall be at least the time to transmit one Maximum MSDU Size successfully at the minimum PHY rate as specified in the TSPEC . If Maximum MSDU Size is not specified in the TSPEC then the minimum TXOP duration shall be at least the time to transmit one Nominal MSDU Size successfully at the minimum PHY rate." | D6.0 | 2003-11-11
Soomro, Amjad | 7.1.3.4.1 | T | Y | The sequence numbres for broadcast/multicast frames need to be set in sequential order to make higher layer synchronization mechanism work. | Add requirement to increment sequentially sequence numbers for broadcast/multicast frames. |  | accepted. Resolved by the resolution to comment 530. | D5.2 | 2003-10-28
Soomro, Amjad | 7.3.1.13 | T | Y | The Status code REFUSED and REJECTED_FOR_SOME_TIME are duplicate | Remove REFUSED status code as this condition is covered by REJECTED_FOR_SOME_TIME |  | accepted. | D5.2 | 2003-10-29
Soomro, Amjad | 7.3.2.16 | T | Y | The classifier Mask description is ambiguous and it is not clear to the author. | Rewrite the definition of the classifier mask and make it clearer. |  | comment declined. It is not clear what aspect the commenter wants further clarification and is invited to provide more information. |  |  | Commenter volunteers to bring clarifying text, after discussions with other members.
Soomro, Amjad | 7.3.2.13 | T | Y | Applications such as video are quite tolerant to frame loss conditions and yet an HC may drop an admitted stream due to frame loss condtions. In order to ensure interoperability and better expression of traffic stream requirements, acceptable frame loss rate for the traffic stream needs to be communicated between HC and a QSTA. | Add 'Acceptable Frame Loss Rate' parameter in TSPEC. This could be an optional parameter. |  | Comment declined. The commenter is invited to provide more information about the functionality. |  | 2003-11-13 | The clause should have been 7.3.2.15. Commenter volunteers to bring a contribution.
Soomro, Amjad | 7.1.3.1.3 | T | Y | Concept of WDS has not been introduced | Remove all references to WDS. Use concept of DS if needed |  | Declined. The concept of WDS has been present in the base standard. For any further clarification, the commenter is advised to refer to Task Group m. |  | 2003-10-29
Soomro, Amjad | 7.1..3.1.8 | T | Y | line 5-7. The sentence is not clear | Clarify the intent of the sentence |  | Declined. The ballot resolution group felt that the paragraph is clear. |  | 2003-11-11
Soomro, Amjad | 7.1.3.1.8 | T | Y | lines 9-14. Qulafy the conditions that these rules apply when to QBSS is in operation. | Change as indicated. |  | Alternate resolution. Resolved by resolution to comment 273 which deletes "with zero user priority" and the behavior becomes identical to that of a non-QoS BSS. | D5.2 | 2003-10-29
Soomro, Amjad | 7.3.2.14 | T | y | It is not clear what is meant by setting the parameter count to arbitrary value. | Specify the coding of the parameter. |  | Accepted. Rename the field as "Parameter Set Update Count" and replace "arbitrary" with "set to 0". | D5.2 | 2003-10-29
Soomro, Amjad | 7.3.2.14 | T | Y | line 15. The access category (AC) parameter record is undefined | Define the term |  | Accepted. Replace the sentence with, "The formats of AC_BE, AC_BK, AC_VI and AC_VO Parameters Records are identical and are illustrated in figure 46.4". Change the caption of figure 46.4 to reflect the above change. | D5.2 | 2003-10-29
Soomro, Amjad | 7.3.2.14 | T | Y | line 19. Self reference | Possibly ACI is meant here |  | accepted. Replace the first occurrence of AC with ACI. | D5.2 | 2003-10-29

## No Comments from LB63
Name | Clause | E/T | Y/N | Comment/Explanation | Recommended Change | Ad-Hoc Group Responsible | Recommended Disposition | Draft Incorporating Resolution | Date Resolved (Based on Pacific Time) | Miscellaneous Comments | Comment accepted/rejected/other resolution | Status
Myles, Andrew | 7.3.2.15 | T | Y | Table 20.6 shows both a "scheduled SP" and a "scheduled APSD" mode. The differences (if any) between these two modes is not adequately described in the draft. | Add text to clarify these differences. If there are no differences, remove one of the duplicate modes. |  | Alternate resolution. Instruct the editor to indicate that ascheduled SP may be provided to a QSTA that is not using APSD. |  | 1/13/2004
Myles, Andrew | 11.2.1.4 | T | Y | The first sentence states "QAPs capable of supporting automatic power-save delivery (APSD) shall signal this capability through the use of the APSD subfield in the Capability Information Field in Association Request management frame." But, QAPs do not transmit Association Requests. | Replace "Association Request" with "(Re)association Response" |  | Accepted. |  | 1/13/2004
Myles, Andrew | 9.9.3.1 | T | Y | The second paragraph states "If a QSTA desires to send data without admission control using an AC that mandates admission control, the QSTA shall use an AC that corresponds to a lower priority and does not require admission control." Using a different AC imples modifying the UP of the packet, thus losing the original UP. | Replace with the phrase "the QSTA shall use EDCA parameters that correspond to a lower priority and do not require admission control." |  | Accept. |  | 1/13/2004
Myles, Andrew | 3.76 | T | Y | The last sentence states "Service periods start at fixed intervals of time." However, this is not true for unscheduled service periods. | Remove the last sentence. |  | Accepted. |  | 1/13/2004
Myles, Andrew | 11.2.1.4 | T | Y | In paragraphs 3 & 4, the power management bit does not interact well with unscheduled service periods. The prime example is: what is the behavior of the AP if a STA using unscheduled SPs sends a frame with the PM bit set to 1? The SP is triggered by any frame, yet the PM bit is indicating that the STA is about to sleep. | Clarify how the PM bit interacts with unscheduled service periods. One solution is to have the AP simply ignore the PM bit when the unscheduled service period mechanism has been enabled. |  | Comment accepted. No normative changes needed. Changing the value of the PM bit changes the mode of the station between Active and PS, but the station may be either in the Awake or the Doze state while in PS mode. A station using unscheduled APSD that sends a frame with PM bit = 1 will remain in the Awake state because, although it is now in PS mode, it must be in Awake state at the start of a service period. The informative text in 04/0073 clarifies this point. |  | 1/15/2004
Myles, Andrew | 7.3.2.15 | T | Y | There doesn't seem to be any significant difference in behavior between the Aggregation bit and the APSD bit (i.e. what does it mean to set APSD unequal to Aggregation?) Both of these modes appear to be addressing the same goal. | Add text to clarify these differences. If there are no differences, remove one of the duplicate modes. |  | Alternate resolution. Instruct the editor to clarify that the Aggregation bit may be set even if APSD is not used. The reasoning is that a QSTA using HCCA may request its service periods be aggregated. |  | 1/13/2004
Myles, Andrew | General | T | Y | There have been many 100's of changes since the last LB It is unreasonable to expect voters to have the time to review all the changes in 15 days | Future LB's with a similar number of changes should be 40 days rather than 15 days. |  | Declined. Invalid comment. The correct place to change the duration of a LB is on the floor of the TG/WG. |  | 2004-01-13
Buttar, Alistair | 7.3.2.15 | T | Y | When the access policy is set to EDCA and the direction is set to uplink or downlink, the TSID and the User Priority subfields in the TSInfo field of the TSPEC element carry redundant information. | Modify text to read: When the access policy is set to EDCA, the TSID subfield in the TSInfo field of the TSPEC element is reserved. |  | accepted. |  | 1/13/2004
Buttar, Alistair | 9.9.3.1 | T | Y | The normative admissions control behavior of the QAP when admitting an ADDTS request indicating EDCA as the access policy and with the schedule subfield set to 1 and APSD subfield set to 0 is undefined. | Define the behavior. The principle purpose of the scheduled EDCA service period is to distribute SP start times across a CP, and thereby minimize the probability of collisions between uplink transmissions from different non-AP QSTA. Therefore, the HC should respond to an ADDTS request with an ADDTS response including a schedule element communicating the service schedule generated for the QSTA. |  | Alternate resolution. Instruct the editor to indicate that when the access policy is set to EDCA and the APSD subfield is set to 0, then the Schedule and aggregation subfields shall both be set to 0. |  | 1/14/2004
Buttar, Alistair | 9.9.3.1 | T | Y | The normative admissions control behavior of the QAP when admitting an ADDTS request indicating EDCA as the access policy and having both the scheduling and the aggregation subfield set to 1 is undefined. | Define the behavior. The QAP shall maintain a admissions control and scheduling status for each currently associated non-AP QSTA indicating whether the HC has accepted a resource request, and if so the scheduling policy for each uplink and downlink UP. If the QAP has previously admitted a ADDTS request with the scheduling policy set to 1, and if the HC accepts any additional ADDTS requests from the non-AP QSTA with both the schedule and the aggregate bit set to 1, the QAP ADDTS response shall include a schedule element communicating the new aggregate schedule for the scheduled EDCA traffic to or from the QSTA. The aggregate schedule provided in the schedule element shall only apply to admitted EDCA traffic using the scheduled service policy. If the QAP establishes an aggregate service schedule for HCCA streams, the HC shall communicate this schedule in a separate schedule element contained in an ADDTS response to a HCCA resource request. |  | Alternate resolution. Instruct the editor to indicate that when the access policy is set to EDCA and the APSD subfield is set to 0, then the Schedule and aggregation subfields shall both be set to 0. |  | 1/14/2004
Buttar, Alistair | 9.9.3.1 | T | Y | The normative scheduling and aggregation behavior of the HC with an admitted HCCA stream is defined in clause 9.9.3.2. The normative behavior of the QAP towards active non-AP QSTA with admitted EDCA traffic having schedule = 1 is not similarly defined in clause 9.9.3.2. Also, the scheduling behavior of a non-AP QSTA with admitted uplink EDCA traffic having schedule = 1 is undefined. | Define the behavior. When the HC establishes a service schedule for a stream, both the QAP and the non-AP QSTA should honor this schedule, both to ensure that collisions between non-AP QSTAs are minimized and that the future schedule decisions made by the HC are not rendered ineffective. The QAP and the non-AP QSTA shall buffer traffic arriving after the scheduled service time from admitted downlink TS until the next scheduled service time, at which it shall release this traffic to the EDCA channel access function. The non-AP QSTA should make an ADDTS request in the uplink direction with the schedule and APSD bits clear in cases where it would be beneficial to transmit an uplink traffic stream without such restrictions. If the QAP has admitted no streams that require scheduling, it may not find it necessary to perform the scheduling or related buffering functions. |  | Alternate resolution. Instruct the editor to indicate that when the access policy is set to EDCA and the APSD subfield is set to 0, then the Schedule and aggregation subfields shall both be set to 0. |  | 1/14/2004
Buttar, Alistair | 11.2.1.4 | T | Y | The clauses stating “The QAP uses the power save delivery currently in effect for a non-AP QSTA to deliver frames to the non-AP QSTA when it is operating in power save mode” and “When a QSTA sets the APSD subfield for any TSPEC to 1, all traffic to the station shall be delivered using APSD”, prohibits a non-AP QSTA from requesting unscheduled delivery of uplink traffic and scheduled delivery of downlink traffic without initiating an unscheduled service period after each uplink frame. | Delete the text. State the QAP shall maintain a admissions control, APSD and scheduling status for each currently associated non-AP QSTA indicating whether the HC has accepted an ADDTS request, and if so the scheduling and APSD policy for admitted uplink and downlink traffic. Permit the HC to admit ADDTS requests using EDCA channel access in the uplink and downlink directions with independent APSD and scheduling policies. Specify that the QAP shall only initiate unscheduled service periods when the QAP receives admitted uplink traffic with APSD=1 and schedule=0. Admitted traffic with APSD=0 shall not initiate an unscheduled SP. |  | Accepted. |  | 1/13/2004
Buttar, Alistair | 11.2.1.5 | T | Y | The text stating “No MSDUs or management frames received for STAs operating in the active mode or have not indicated their usage of APSD shall be buffered for power management reasons” and the text in bullet "b)" prohibits active stations employing EDCA channel access from taking short vacations from active mode to perform essential activities (e.g. active scanning). Since the principle purpose of scheduled service periods are to distribute EDCA SP start times across a CP and minimize the probability of collisions between uplink transmissions, this restriction is unnecessary and overly limiting. | Modify the text to permit buffering of all MSDU and management frames destined to non-AP QSTA in PS mode. In particular, the QAP shall temporarily buffer MSDU or management frames for admitted streams with APSD=0 and schedule=1 until the station transitions to active mode, after which the QAP will continue to temporarily buffer the scheduled MSDUs until the service start time following the transition to active mode. Additionally, the QAP shall temporarily buffer MSDU or management frames for the UP with APSD=0 and schedule=0 until the station transitions to active mode, after which the QAP shall transmit all frames buffered for the non-AP QSTA. |  | Incorporate the changes outlined in 04/133r2, slide 18. |  | 1/15/2004
Buttar, Alistair | 11.2.1.5 | T | Y | The text stating “The QAP shall transmit all frames buffered for the non-AP QSTA following a scheduled SP”, is problematic because the delivery of unadmitted traffic to a STA in PS mode leaves no means for the non-AP QSTA to pause or stop delivery of the unadmitted traffic, and because the QSTA does not enjoy the benefits of the used time function available to an AC with admitted streams. | Modify clause to permit QAP to transmit buffered APSD traffic for the non-AP QSTA following scheduled SPs. Unadmitted traffic and admitted traffic with APSD=0 is held in a separate PS buffer and is not transmitted. Use TIM bit and More Data bit to signal to the non-AP QSTA that the PS buffer is holding unadmitted traffic or admitted traffice with APSD=0, allowing the STA to retrieve this pending traffic using a power save poll frame or by transitioning to active mode. E13 |  | Incorporate the changes outlined in 04/133r2, slides 10, 11 and 12. |  | 1/15/2004
Buttar, Alistair | 11.2.1.5 | T | Y | The text stating “At each APSD SP for a non-AP QSTA, the QAP shall attempt to transmit all frames destined for the non-AP QSTA,” is problematic because it permits the delivery of admitted EDCA traffic with schedule=1 at times not compatible with the schedule established by the admissions control module. | State the QAP shall maintain an admissions control, APSD and scheduling status for each currently associated non-AP QSTA indicating whether the HC has accepted a ADDTS request, and if so the scheduling and APSD policy for admitted uplink and downlink traffic. The QAP shall only transmit buffered frames to the non-AP QSTA from UP associated with an ADDTS request having schedule=1 following a scheduled SP. However, admitted traffic using unscheduled delivery may be transmitted in any scheduled or unscheduled service period. |  | Comment declined. Setting a schedule is only the means to an end, which is the quick delivery of frames over the WM, the efficient utilization of the channel and power conservation at the station. Meeting a schedule is not a goal in itself. |  | 1/15/2004
Buttar, Alistair | 11.2.1.5 | T | Y | The normative behavior of the QAP in setting the TIM and More Data bits introduces ambiguity about whether the buffered traffic is unadmitted, admitted with schedule=0 or admitted with schedule=1. Sending a proper TIM indication in the beacon is essential for the operation of a PS STA. Setting the TIM and MD bits when the QAP has data from any channel access function buffered makes it problematic for the non-AP QSTA to choose between waiting for the next scheduled SP, initiating an unscheduled SP, or transmitting a power save poll. | At every beacon interval, the QAP shall assemble the partial virtual bitmap per destination for non-AP QSTA in power save mode containing the status of the PS buffer for unadmitted traffic and admitted traffic with APSD=0. The More Data field shall also be set to indicate the presence of buffered MSDUs or management frames in the PS buffer for unadmitted traffic and admitted traffic with APSD=0. |  | Comment declined. The change would deprive us of the possibility to use unscheduled APSD for some important applications. |  | 2004-01-15
Buttar, Alistair | 11.2.1.5 | T | Y | The text stating “If the non-AP QSTA has set up unscheduled SPs, the QAP shall buffer frames until it has received a frame from the non-AP QSTA, which indicates the start of an unscheduled SP” permits the QAP to initiate an unscheduled SP after receiving any frame from the non-AP QSTA, which can lead to wasted bandwidth if an unscheduled SP is not required. | Modify the text to state: If the non-AP QSTA has accepted a ADDTS request with schedule=0 and APSD=1, the QAP shall buffer frames associated with the request for the PS non-AP QSTA until it has received an uplink frame from a UP with APSD=1 and schedule=0, which indicates the start of an unscheduled SP. |  | Modify the text in subclause 11.2.1.4 as follows: APSD defines two different types of delivery mechanism, depending upon the SP used. An SP can be either unscheduled or scheduled. An unscheduled SP begins when the QAP receives any "trigger" frame, which is a QoS Data or Null frame associated with an admitted uplink or bidirectional TSPEC having its APSD subfield set to 1 and the schedule subfield set to 0 from the non-AP QSTA. |  | 1/15/2004
Buttar, Alistair | 11.2.1.5 | T | Y | In the draft, when the QAP does not receive an ACK to a directed MSDU or management frame sent to a STA in PS mode following receipt of a PS Poll from that STA or sent with the More Data subfield set to 0 or the EOSP set to 1, it may retransmit fewer times than the Max Retry Limit before the next TIM (but at least once). A MIB variable is needed to regulate the number of retransmissions when the ACK is not received. | Add a MIB variable to specify the number of retransmissions when the QAP does not receive the ACK for a data frame in response to a PS-Poll for a non-AP QSTA or the ACK for the last data frame sent by the QAP in the SP. |  | Comment declined. The author needs to provide normative text for changes in the TGe draft. |  | 1/15/2004
Buttar, Alistair | 11.2.1.9 | T | Y | The receive operation requires non-AP QSTA to unnecessarily transition into Active mode at scheduled start times and at the beginning of unscheduled service periods. | Change the text to say: “the non-AP QSTA shall be in the awake state” at scheduled start times and at the beginning of unscheduled service periods. The non-AP QSTA should only transition to the Active Mode during a SP after initiating and successfully completing a frame exchange having the Power Management bit in the Frame Control field of the frame sent by the QSTA set to 1. The APSD service period is consindered over once the non-AP QSTA transitions to active mode. |  | Incorporate the changes outlined in 04/133r2, slide 21. |  | 1/15/2004
Wright, Charles | 9.9.1.2 | T | Y | Last paragraph: "should" isn't strong enough. QSTA attempting the TXOP does not have the right to continue if a collision occurs. Since the QSTA doesn't detect the collision, it can't stop. Clause 9.9.1.4, pg 73, line 11-13 is also affected by this comment. | Make it mandatory that protective mechanisms shall be used if the non-ACK'ed frames are the start of the EDCA TXOP. Changes to sentence in clause 9.9.1.4 are needed to account for this frame exchange sequence. |  | Reject. The implementer may choose to not use protection mechanisms under certain circumstances, for instance if there are just a few small block ack frames to be transmitted. |  | 2004-01-13
Eastlake, Donald | 7.3.1.4 | T | Y | The APSD bit in the Capability Information field is not enough to indicate whether a QAP supports scheduled APSD, or unscheduled APSD, or both. As a result, non-AP QSTA has to test the water by trying to set up a TSPEC and see how QAP responds. This creates lots of overheads. | 1. Add an UPSD (unscheduled power save delivery) bit into Capability information field to indicate that the QAP or non-AP QSTA supports unscheduled SP power save delivery. 2. Modify the meaning of the current APSD bit to indicate that the QAP or non-AP QSTA supports scheduled SP power save delivery. |  | Comment declined. The capability bit will indicate if the general mechanism is supported. If a QSTA requires to know the full capabilities of the QAP it can determine by using the signaling provided. |  | 2004-01-13
Eastlake, Donald | 11.2.1.7 | T | Y | Bullet e) says "If a non-AP QSTA receives a QoS+CF-Ack from its QAP, …" Once again, QoS+CF-Ack can only be sent during CFP or HC initiated TXOP (see clause 9.9.2.3). | It doesn't make sense to use QoS+CF-Ack during EDCA service period. Correct the texts to make the behavior consistent. |  | Alternate Resolution. Instruct the editor to update clause 9 to allow for the usage of QoS+CF-Ack in EDCA. |  | 2004-01-15
Eastlake, Donald | 7.3.2.15 | T | Y | What does the aggregation subfield mean if Access Policy is set to use both HCCA and EDCA? In particular, how does aggregation work if a non-AP QSTA uses HCCA and unscheduled EDCA at the same time? There is no normative text for the QAP and non-AP QSTA for this mode. | Define the usage of aggregation for this scenario or remove this scenario as a possible option |  | Alternate resoluition. Resolved by the resolution to comment 176 which does not allow the behavior described in the comment. |  | 1/15/2004
Eastlake, Donald | 7.3.2.15 | T | Y | The draft says "The APSD subfield is set to 0 if the station does not engage in power saving." This statement is inaccurate. STA may engage in legacy power-saving when APSD is not used. | Change the sentence to read as "The APSD subfield is set to 0 if the station does not use APSD for power-saving." |  | accepted. |  | 2004-01-13
Eastlake, Donald | 9.9.3.1.1 | T | Y | The first sentence says "The QAP shall respond to requests for admission conveyed in the ADDTS requests for those AC with the ACM subfield set to 1." The normative behavior of QAP when it receives a request for admission for an AC with ACM subfield set to 0 is undefined. | Regardless of the AC's ACM setting, the QAP shall repond to an ADDTS request with and ADDTS response that may be to accept or deny the request |  | accepted. |  | 2004-01-13
Eastlake, Donald | 11.2.1.5 | T | Y | Bullet g) says "The QAP considers APSD QSTA to be in Active state after it has sent a QoS +CF-Ack, with the More Data bit set, to the APSD QSTA." This statement is no longer accurate. A QSTA now changes its PS state based on EOSP bit rather than the More Data bit. | Change the sentence on lines 24-25 to read "The QAP considers APSD QSTA to be in Active state after it has sent a QoS +CF-Ack, with the More Data bit set and the EOSP bit cleared, to the APSD QSTA." |  | Accepted. Use alternate text "The QAP considers APSD QSTA to be in Awake state after it has sent a QoS +CF-Ack with the EOSP bit cleared to the APSD QSTA." |  | 2004-01-13
Eastlake, Donald | 11.2.1.5 | T | Y | Bullet g) says "The More Data bit of the directed data or management frame shall be set to 1 to indicate the presence of more frames that are destined for that non-AP QSTA." The issue with the More Data is that it only provides a lump-sum indication for buffered data of all ACs. There is no specific information about which AC the buffered data belongs to. This creates some difficulties for non-AP QSTAs wishing to make an informed and optimized decision on whether to retrieve these data when current SP has ended (e.g. More Data = 1 and EOSP = 1) | 1. Using the reserved bit 8-15 in QoS Control subfield in QoS Data, QoS Null, QoS CF-ACK, and QoS Data+CF-ACK frames sent by HC (Table 3.1) to indicate buffering status of each AC. 2. Change reserved Bit 17 in TS Info subfield to "More Buffer Info". 3. Non-AP QSTA indicates its desire to receive such information by setting "More Buffer Info" bit to 1. 4. QAP confirms its support of such feature by reaffirming "More Buffer Info" bit setting in the responding TSPEC element. QAP may also decline such request by setting "More Buffer Info" bit to 0 in the responding TSPEC element. Adopt normative text in document# 11-03-XXXrX-AP-Data-Buffer-Bitmap.doc |  | Comment is declined. The commenter makes a valid observation, but the suggested proposal adds complexity. |  | 2004-01-15
Eastlake, Donald | 11.2.1.5 | T | Y | In bullet f) and g), it says "A QAP may set the More Data bit in a QoS+CF-Ack frame to 1, in response to a QoS Data frame to indicate that it has one or more pending frames buffered for the PS station identified by the RA address in the QoS+CF-Ack. The above statement contradicts what the draft says in clause 9.9.2.3 "Piggyback frames are allowed only in CFP or within TXOPs initiated by the HC". The usage of QoS+CF-Ack in bullet f) and g) clearly violated both rules set in clause 9.9.2.3 for that: 1. This is a CP, not CFP 2. Since QAP is responding with a piggyback Ack, the TXOP could not be a QAP initiated TXOP | It doesn't make sense to use QoS+CF-Ack during EDCA service period. Correct the texts to make the behavior consistent. |  | Alternate Resolution. Instruct the editor to update clause 9 to allow for the usage of QoS+CF-Ack in EDCA. |  | 2004-01-15
Eastlake, Donald | 7.1.3.5.2 | T | Y | The sentence "The HC sets the EOSP field to 1 if the SP ends after the successful transmission of the current frame and sets it to 0 otherwise." is not accurate and it brings up a missing-Ack problem. The resolution to the missing-Ack problem was that the QAP not retry in the same service period. This means that as far as the AP is concerned, the SP ends after sending the current frame with EOSP = 1. | Change the sentence to read "The HC sets the EOSP field to 1 to end a scheduled/unscheduled service period after completing its transmission and/or retransmissions of this last service period frame and sets it to 0 otherwise. Frames with EOSP=0 is not the last frame of a service period and therefore follow normal frame retransmission rules. Frames with EOSP=1, which are the last frame of a service period follow retransmission rules described in 11.2.1.5" |  | accepted. |  | 1/15/2004
Eastlake, Donald | 3 | T | Y | The sentence on lines 33-35 describing "Service Period (SP)" is no longer correct in general. It is generally correct for scheduled service period only | Replace the sentence which reads "Service periods start at fixed intervals of time." with "Service periods can be sheduled or unscheduled. Scheduled service periods start at fixed intervals of time. Unscheduled service periods start when they are triggered by non-AP STAs." Also to reflect this change, the editor should change as appropriate throughout the draft all occurrence of 'service period' to reflect the type of service period ('scheduled' or 'unscheduled') being used. |  | accepted. |  | 2004-01-14
Eastlake, Donald | 3 | T | Y | The sentence on line 36 describing "service interval (SI)" is describing the definition for scheduled service periods and therefore should be changed to be more accurate. | Change the term "service interval (SI) on line 33 to "scheduled service interval (SSI)" and change the sentence descrbing the new term to be "The interval between two successive scheduled SPs." Also to reflect this change, the editor should change as appropriate throughout the draft all occurrence of 'service interval' to 'scheduled service interval' |  | The recommended change to change the text of 3.76 is accepted. However, there is no need to rename the interval as there is no "unscheduled service interval". |  | 2004-01-14
Eastlake, Donald | 7.3.2.15 | T | Y | Figure 46.8 shows bits B1 to B4 as "TSID" when it should be "TID", which is 4 bits in length. The text on line 6 of this section which says "The TSID subfield is 4 bits in length and contains the TSID values in the format defined in 7.1.3.5.1." is therefore incorrect. | Change "TSID" to "TID" in the figure and change the sentence "The TSID subfield is 4 bits in length and contains the TSID values in the format defined in 7.1.3.5.1." to say "The TID subfield is 4 bits in length and contains the TSID or UP values in the format defined in 7.1.3.5.1." |  | Comment declined. No reason provided why the text and figure as stated are incorrect. Furthermore, UP is already encoded into the "user priority" subfield. |  | 1/15/2004
Hillman, Garth | 3.78 | T | Y | I made this comment on LB59 and will repeat it here as I believe we can do better than just say "out of scope". The comment is that we should include an indication of who/how the TC is assigned. I don't believe it is a mistery. | Add a statement that "the TC is assigned in software layers above the 802.11 MAC. The most likely layers are either the content generation layer or the Operation system. It would be rare that the TC would be set within the network." The second sentence was made to provoke discussion :-)) |  | Alternate resolution. Incorporate the first sentence with the word "software" removed. |  | 2004-01-13
Hillman, Garth | 3.79 | T | Y | This definition always confuses me. It seems like a circular definition. "The classification process …uses the parameter values of the traffic classification …. You see what I mean. Also, here you say this classification process is performed above the MAC SAP at a QSTA. This is a step in the right direction based on my comment 3.78. Now, we just need to say 'where' above the MAC SAP this classification is likely to be done. | Re - define |  | accept the first part of the comment. Replace "uses the parameter values of the traffic classification" with "parameter values". Second part of the comment is declined as a layer 2 specification can not specify where a higher layer functionality is implemented. |  | 2004-01-13
Hillman, Garth | 3.80 | T | Y | see my comment 3.78 and substitute TID for TC | see 3.78 |  | Alternate resolution. Incorporate the sentence "the TID is assigned in the layers above the 802.11 MAC". |  | 2004-01-13
Hillman, Garth | 3.83 | T | Y | see my comment 3.78 and substitute TSID for TC | see 3.78 |  | Alternate resolution. Incorporate the sentence "the TSID is assigned in the layers above the 802.11 MAC". |  | 2004-01-13
Hillman, Garth | General | T | Y | Everytime I read these (3.78, 3.79, 3.80, 3.81, 3.82, 3.83) definitions I always feel like I am being lead in a circle. It would really help if they were tied together in a logical, hierarchical manner | make these definitions more consistent |  | declined. No proposed solution, further the terms are defined with respect to each other and is self-consistent set. |  | 2004-01-13
del Prado, Javier | 6.2.1.3.2 | T | Y | Item g) Status code seems to indicate that 'Unavailable Priority (ContentionFree)' is applicable to hybrid coordinator as well while it is not. | Remove the word 'hybrid coordinator' |  | Declined. A hybrid coordinator may also generate the CFP. |  | 2004-01-13
del Prado, Javier | 7.2.2 | T | Y | From reading line 13 and line 14, it is not clear if a QSTA transmits a frame to nQSTA in a QBSS then what frame type is to be used. The QSTA transmits a frame to QAP, which is a QSTA, however the final destination is a nQSTA. | Clarify the usage of frame types. |  | Declined. The draft already describes what frames should be used. Since the transmissions from QSTA to the QAP is between two QSTAs, QoS data frames are to be used. For transmissions from QAP to non-QoS STA, non-QoS data frames are to be used. |  | 2004-01-13
del Prado, Javier | 7.3.1.4 | T | Y | The acronym ERP is not defined | Define the acronym |  | Declined. The acronym is defined in IEEE 802.11g, 2003 edition. |  | 2004-01-13
del Prado, Javier | 7.3.1.9 | T | Y | It is not clear which 'request' the status codes 37 and code 38 apply to. Probably the ADDBA is intended here. | Specify the requests where codes 37 and code 38 apply to. |  | Declined. The requests to which codes 37 and 38 corresponds to are specified in clause 11. |  | 2004-01-13
del Prado, Javier | 7.3.2.15 | T | Y | The field names 'Service Start Time' appear in both TSPEC and Schedule Element. Therefore, in draft text it is not clear which field is being referred in narration. | Assign different names for these two fields. One suggestion 'Requested Service Start Time' and 'Service Start Time' |  | declined. The commenter did not demonstrate where the text is not clear. |  | 2004-01-13
del Prado, Javier | 7.3.2.16 | T | Y | Applications such as video are quite tolerant to frame loss conditions and yet an HC may drop an admitted stream due to frame loss condtions. In order to ensure interoperability and better expression of traffic stream requirements, acceptable frame loss rate for the traffic stream needs to be communicated between HC and a QSTA. | Add 'Acceptable Frame Loss Rate' parameter in TSPEC. This could be an optional paramete |  | Comment declined. The functionality increases complexity. Furthermore, the proposal is incomplete. |  | 2004-01-13
del Prado, Javier | 7.3.2.19 | T | Y | lines 10 - 11. The Service Start Time in Schedule Element is valid even when APSD subfield is set to 0. The sentence as it is written implies that Schedule Element is not valid if APSD is not used which has not been the consensus in TGe. | Remove the sentence and clarify that it is valid regardless of APSD subfield setting. Also, renaming the 'Service Start Time' in TSPEC would help as well |  | First part accepted. Second part is declined, for reason, see comment 129. |  | 2004-01-13
del Prado, Javier | 7.3.2.20 | T | Y | It is not clear when 'QoS Capability' element is present. This sentence and notes on Table 5, order 15 and 16 need to be made consistent with each other. | Change the desciption and the table to make the rules consistent. |  | accepted. Add a "not" before "present". |  | 2004-01-13
del Prado, Javier | 9.1 | T | Y | the word '(at least to the extent EDCA) are present' implies that HCCA may not be present and this has not been intent of the draft. For example, refer to PICS. | Remove the inidcated words. |  | accepted. |  | 2004-01-13
del Prado, Javier | 9.9.2.3 | T | Y | lines 7-8. Add clarification that response with a frame with the TID indicated in poll frame is not required. | Add indicated clarification |  | accepted. Clarification is already made in 7.1.3.5.1. |  | 2004-01-13
del Prado, Javier | 9.9.3.1.1 | T | Y | The QAP may delete an admitted stream in EDCA any time by sending a DELTS frame while in HCCA it may not. | Make the rules consistent in both EDCA and HCCA. Allow similar flexilbility in HCCA. |  | Comment declined. An admitted stream with access policy of HCCA can be deleted by the HC due to inactivity |  | 2004-01-14
del Prado, Javier | 9.9.3.1.2 | T | Y | The use of 'Surplus Bnadwidth Allowance' should not be made mandatory in EDCA. | Make use of 'Surplus Bandwidth Allowance' optional |  | Declined. Surplus Bandwidth Allowance may always be set to 1 if its use is not desired. |  | 2004-01-13
del Prado, Javier | 9.9.3.1.1 | T | Y | Traffic streams are admitted per TID in EDCA, while DELTS disables an AC. This could leave one ADDTS orphaned, that is, admitted yet not serviced. | Clarify and synchronize definitions. |  | Adopt the normative changes as contained in 04/100r0, section 9.9.3.1.2, but not section 7.3.2.15. |  | 2004-01-15
del Prado, Javier | 11.2.1.4 | T | Y | The requirement that a SP ends after "the QAP has attempted to transmit all frames destined for the non-AP QSTA" is too strict. For example, depending on the priority of the traffic to be delivered to the power saving QSTA, the quantity of the traffic to be delivered to the QSTA, the time assignment of the medium for the frame priorities and other network load it should be allowed to end a SP even when delivery of all the frame destined to a power saving QSTA has not been attempted. | Clarify that QAP may end a SP even when delivery of all the buffered frames has not been atempted. |  | Incorporate the changes in document 04/62r2, slide 16. |  | 1/15/2004
Amann, Keith | 11.2 | T | Y | The power-save mechanism introduced through the submittal of document 11-03-0661-00-000e is technically flawed, and does not really accomplish the stated goals. There exist technical issues with the mechanism that have not been resolved, specifically the ordering of varying priority frames and their use of the "more data" and EOSP indications. For example, if a QSTA has requested unscheduled APSD service periods, and the QAP buffers traffic for this device, the frames buffered may have more than one priority. Assume that 2 of the frames are "high" priority, and were the first two frames received, and a third frame is best effort traffic, and was the last frame received. The QAP, upon receiving an uplink frame from the QSTA will take the buffered frames and place them in the appropriate "priority" queues. At the time that it enqueues the frames the QAP will likely set the appropriate indicates (more data & EOSP). If the last frame enqueued is the best effort frame, and it has the EOSP bit set, but there is a substantial amount of high priority traffic enqueued at the QAP and little if any best effort traffic other than this frame, then there is a probability that the QAP will send the best effort frame BEFORE the high priority frames that indicate "more data". This would prematurely terminate the service period, allowing the QSTA to go back to sleep immediately, missing traffic, and resulting in inefficient channel utilization due to retries, timeouts, etc. | Remove all text that was introduced as a result of document 11-03-0661-00-000e. |  | Incorporate the changes in document 04/133r2, slide 8. |  | 2004-01-15
Amann, Keith | 11.2 | T | Y | The power-save mechanism introduced through the submittal of document 11-03-0661-00-000e does not really accomplish the required goal of efficient power-saving for a QoS station. The QSTA transmits an uplink frame to cause the QAP to enqueue all the buffered traffic destined for the QSTA. If the channel is even moderately loaded, this mechanism will provide very inefficient behavior as the QAP has significant numbers of frames to transfer to other QSTAs before transmitting to the APSD QSTA. This will force the APSD QSTA to remain awake with it's receiver active much longer, thus consuming power. | Remove all text that was introduced as a result of document 11-03-0661-00-000e. |  | The commenter agreed for the comment to be declined as he is not unsure how to resolve the comment. |  | 2004-01-15
Amann, Keith | 9.9.2.3 | T | Y | It is not clear whether a QSTA using piggybacked frames can use the "more data" bit during polled TXOP to indicate that it has additional frames available for transfer, and that it would like to have the QAP generate another polled TXOP as soon as possible. | Add clarifying text stating how, or if, a QSTA is permitted to use the "more data" bit to indicate the presense of addition buffered traffic at the QSTA during a polled TXOP. |  | Comment declined. A non-AP QSTA never sets More data bit. A non-AP QSTA indicates presence of data by inidicating its queue size or by requesting TXOP durations. |  | 2004-01-13
Amann, Keith | 7.2.3.4 | T | Y | For an (re)association request sent with a ADDTS request QOS action, it is not clear what happens in terms of association if (1) the TSPEC is unacceptable, or (2) the QAP chooses to "suggest" a different TSPEC. In these two cases, it seems that it makes the most sense to explicitly require the QAP to refuse association until the (re)association request is sent with a mutually acceptable TSPEC. | Provide clarifying text here, clause 11.4, and/or where ever else necessary to specify the rules that should be followed in the event that the TSPEC is rejected or modified when included within a (re)association request. It is suggested that the preferred rule would be to reject the (re)association until a mutually acceptable TSPEC can be identified. |  | Alternate resolution. Clause 11.4.3 already indicates that the process is repeated. It does not appear clear why the association has to be defined. The inclusion of ADDTS request is only to provide efficiency of the channel use. Instruct the editor to add, "If the original ADDTS request is sent in a (re) association request frame, the whole process can be repeated with the exception that the request is sent in an ADDTS request |  | 2004-01-13
Amann, Keith | 7.3.2.16 | T | Y | The "definition" of the TYPE field in the TCLAS ethernet parameters is unclear. | Provide clarifying text to define the TYPE field in the ethernet TCLAS parameters. |  | Comment accepted. A referece to Ethernet standards will be provided. |  | 2004-01-13
Amann, Keith | 7.3.2.16 | T | Y | In situations where a QSTA wishes to do power saving, or aggregate all of it's traffic under a single TSPEC, it will be necessary for the QSTA to use multiple TCLAS elements to identify all of the potential sources of traffic. A QSTA may not know what all of the potential sources of traffic are in all cases. | Introduce a "wildcard" mechanism for use in TCLAS signalling that allows a QSTA to specify that traffic from ANY source, meeting the other criteria of the TCLAS, will be appropriately classified to the specified TSPEC. For example, using the source address of "FF:FF:FF:FF:FF:FF", destination address of the QSTA, and (I'm assuming) ethertype value of 0x0800, in a frame classifer of type 0 would indicate that any IP traffic destined for the QSTA from any source would be classifed to the same TSPEC. |  | Comment declined. In this case, there is no need for a TCLAS element. Furthermore, the text already indicates that the user priority value is reserved for this case. |  | 2004-01-13
Amann, Keith | 11.4 | T | Y | The TS lifecycle clause describes the various negotiations and behaviors associated with the TSPEC. As such, this should be normative, not informative. | Make this clause normative. |  | Accepted |  | 2004-01-13
Amann, Keith | 11.4.3 | T | Y | The TS lifecycle clause refers to "TS Renegotiation" and "Failed TS Renegotiation" behaviors, but does not provide text describing either of these behaviors. | Add text and state diagrams that show how these behaviors are handled. |  | Alternate resolution. Replace "modified" with "renegotiated" in the first sentence immediately below figure 68.2. |  | 2004-01-13
Amann, Keith | 9.9.3.2 | T | Y | This clause mentions the fact that a non-AP QSTA may affect the service schedule by "modifying" it's existing TSPEC. It states that this can be done following procedures stated in clause 11.4, but this particular behavior is not specified in clause 11.4, and clause 11.4 appears to be informative, not normative. | Make clause 11.4 normative, and add text and state diagrams specifying how a TSPEC can be "modified" by a non-AP QSTA. |  | Comment declined. Only sub-clauses 11.4.1 and 11.4.2 are informative while the sub-clauses 11.4.3 and 11.4.4 are normative. If a TSPEC is not admitted it can be modified by sending a different TSPEC with the same TSID and, if it has been previously admiited, sending an ADDTS request having same TSID and with different parameters would enable TSPEC modifications. |  | 2004-01-13
Amann, Keith | 9.9.3.2 | T | Y | This clause contains text that specifies that the QAP may aggregate admitted HCCA TSPECs for a single non-AP QSTA through the use of the "Aggregation field". Although this type of behavior may be convenient for the scheduling algorithm, this can have an adverse impact on the applications that originally requested the TSPECs as they may have dramatically divergent requirements in terms of TSPEC scheduling. | Remove the sentence "The HC may aggregate admitted HCCA TS for a single non-AP QSTA and establishes a Service Schedule for the non-AP QSTA". I believe this makes it clear that the non-AP QSTA is the controlling entity as far as aggregation is concerned. |  | Comment declined. By definition aggregation means that the aggregated TSPEC would meet individual TSPEC requirements. |  | 2004-01-13
Amann, Keith | General | T | Y | The PICS is incomplete. | Update the PICS to correctly, and completely, reflect the current requirements of the specification. |  | Comment declined. The PICS appropriately reflects the requirements of the specification. |  | 2004-01-14
Amann, Keith | 11.2.1.5 | T | Y | In subsection "g" it states "When the QAP has transmitted a directed frame to the non-AP QSTA the EOSP subfield set to 1 during the SP, it shall not transmit any more frames using this mechanism until the next SP". This constraint on transmission does not account for error conditions involving retry frames. | Provide clarifying text stating how retry frames should be handled in at least the following cases: (1) The QAP fails to transmit a high priority frame that is now waiting for a retry, in the meantime it is able to transfer a frame at a different priority level, that contains the EOSP bit, what should the QAP do with the retry frame? (2) The final frame (e.g. the one with the EOSP subfield set) fails to be correctly transferred, is the QAP allowed to continue transmitting retries, or must the QAP wait until the next SP? |  | Accepted. Use Alternate resolution provided here. Change text in clause g to say "When the QAP has transmitted a directed frame to the non-AP QSTA with the EOSP subfield set to 1 during the SP and has received an acknowledgement for that frame, it shall not transmit any more frames using this mechanism until the next SP" |  | 2004-01-13
Takagi, Masahiro | 6.1.1.2 | T | Y | "At QSTAs associated in an nQBSS, all MSDUs with an integer priority are considered equivalent to MSDUs with priority Contention." does not answer the question : What AC are used when an unassociated QSTA sends management frames? | Clarify. |  | alternate resolution. Instruct the editor to indicate that the management frames are to be sent using the default parameter values for AC_VO in EDCA before association in a BSS. |  | 2004-01-13
Takagi, Masahiro | 7.3.2.17 | T | Y | When TS delay is used in the ADDTS response frame with ResultCode = "reject with suggested change", delay = 0 does not make sense. | Delay = 0 shall not be used in that case. |  | Alternate Resolution. Instruct the editor to indicate that the TS Delay element is present in ADDTS response frame only when the Result code is " REJECTED_FOR_DELAY_PERIOD". |  | 2004-01-13
Takagi, Masahiro | 9.9 | T | Y | "A TXOP shall not extend across a TBTT …". If EDCA TXOP acquisition is failed to meet this condition, what will happen after TBTT? Invoking EDCA backoff procedure seems to be the correct behaviour. | Clarify. |  | Accept. Add the following clarification at the end of 9.9: "The occurrence of a TBTT implies the end of the TXOP, after which the regular access procedure is resumed. It is possible that no frame was transmitted during the TXOP. The foreshortened termination of the TXOP does not imply an error condition" |  | 2004-01-13
Takagi, Masahiro | 9.9.1.3 | T | Y | It is not clear enough what is the real access priority of AIFSN=3. I'm afraid that EDCA access with AIFSN = 3, which is employed for AC_BE, is less prioritized than legacy DCF access. | Clarify. |  | Reject. See comment 175. |  | 2004-01-13
Takagi, Masahiro | 9.9.1.5 | T | Y | If TXOP acquisition by QSTA failed to avoid TBTT crossing, invoking EDAC backoff after TBTT seems to reduce collision. | Add specification. |  | Accept. Alternate resolution per comment 324. |  | 2004-01-13
Takagi, Masahiro | 10.3.6.1.2 | T | Y | I don't think QoSAction is always present in association request. | "QoS action frame may be present …" |  | accepted. |  | 2004-01-13
Takagi, Masahiro | H.2.1 | T | Y | It seems better to prohibit admission control for AC_BE or AC_BK if AC_VO and AC_VI admission control is required. | Add specification. |  | Comment declined. While the indicated setting in the comment is recommended by the draft, it is felt that there should not be such restriction written in the draft. |  | 2004-01-14
Takagi, Masahiro | 7.3.2.16 | T | Y | The two most significant bits of DSCP field has been assigned as ECN bits by RFC 3168 "The Addition of Explicit Congestion Notification (ECN) to IP". The value of ECN bits are changed by intermediate routers according to the congestion states at the routers. The value of ECN bits are irrelevant to 802.11e QoS. These bits shall be ignored to classify the frames. | (1) Specify that the most significant 2 bits of the DSCP field of IP v4 packets shall be ignored for frame classification. OR (2) Intoroduce more flexible classifier mask. Classifier mask bitmap with each bit corresponding to each bit of classifier paramater seems to be enough. |  | Comment accepted. Incorporate the first solution provided by the commenter. |  | 2004-01-13
Takagi, Masahiro | 9.9.2.2 | T | Y | "A TXOP or transmission within a TXOP shall not extend across ... dot11CAPLimit." Two CAPs can be concatenated with PIFS period interruption. This can also be regard as one CAP because no EDCF access possible during this period. | Clafrify how to know the boundary of CAP. |  | Comment accepted. Resolved by resolution to comment 332. |  | 2004-01-14
Benveniste, Mathilde | general | T | Y | Like other name changes, the adoption of the name 'EDCA' to refer to the QoS-enhanced distributed channel access mechanism -- known as EDCF thoughout the development of the draft proposals -- adds minimally to technical clarity. The name change deprives the readers of the benefit of all the technical information in documents posted on the servers under the name EDCF, which (documents) describe the mechanism, its performance, and rationale for its specification. In addition, the mechanism has been come to be known by the technical community as EDCF, the logical name to use, as it is the QoS enhancement of the the DCF channel access mechanism. | I suggest that the name EDCF be used in place of "EDCA', for continuity and clarity. |  | Comment declined. This is a standard that will be referred to in the future, and the name should reflect what it is, rather than what it was called (mistakenly) at one time. |  | 2004-01-14
Benveniste, Mathilde | 7.3.2.15 | T | Y | Table 20.6, line 2, column 3 Usage= "Unscheduled SP" is confusing. This option should refer to Unscheduled APSD | Modify Table 20.6, line 2, column 3 Usage= "Unscheduled APSD" |  | accepted. |  | 2004-01-13
Benveniste, Mathilde | 9.9.1.3 | T | Y | The specification of the EDCA backoff rules is different from legacy (802.11-1999 standard). Traffic from legacy stations performs better than EDCA BE traffic. This provides a perceived marketable advantage for legacy, which may delay its retirement. It is advantageous to retire legacy stations, for the enhancement of QoS performance attainable by EDCA stations in the absence of legacy stations. An EDCA specification exists that does not give legacy stations an advantage. It was voted into the draft standard in Jan ’02, per doc 01/408r3. It was subsequently removed from the draft standard without technical discussion/justification and without a vote on this topic. | Adopt the EDCF backoff rules proposed in doc 03/149r1 |  | Reject. This comment was rejected in the previous letter ballot. |  | 2004-01-13
Benveniste, Mathilde | 9.9.2.3 | T | Y | The Access Policy bit was originally introduced to allow hybrid access (i.e., contention-based access by station with an admitted TSPEC) in very restricted situations, in order to simplify error recovery and scheduling for polled access. The intent was not to allow unconditional hybrid access, as that would will result in inefficient channel use, increased access delay and reduced traffic handling capacity under heavy traffic. Stations would set up TSPECs to be polled as backup while attempting contention-based channel access. All stations would have to do so; otherwise they would be at a disadvantage relative to those usng hybrid access. The polls sent to each and every station that come back empty waste channel time. | Reinstitute at the end of Clause 9.9.2.3 the text "and one of the following two conditions holds: 1. The MSDU has been sent previously but an acknowledgement has not been received 2. The poll for the MSDU is missing; i.e., a poll has not been received by the non-AP QSTA within a time interval since the time of the last -received poll that is equal to the maximum service interval." Alternatively, modify the Access Policy field to allow for both the unrestricted and the restricted hybrid access mechanisms. |  | Comment accepted. Incorporate the first change with only the first condition. |  | 2004-01-13
Benveniste, Mathilde | 11.2 | T | Y | It is not clear how APSD power management is done when hybrid channel access is used. Unscheduled APSD is only defined for contention-based access. Is scheduled APSD the only APSD option when hybrid access is chosen? | Specify |  | Accepted. Comment resolved through resolution of comment 176, which was resolved through the adoption of the motion on slide 7, Doc # 03/972r3. |  | 2004-01-15
Benveniste, Mathilde | 11.2.1.5 | T | Y | Statement (1) "The QAP considers APSD QSTA to be in Active state after it has sent a QoS +CF-Ack, with the More Data bit set, to the APSD QSTA." is in conflict with statement (2) "The QAP shall use EOSP=1 to indicate the end of SP in APSD. The More Data Bit shall be used simply to indicate whether there is data still buffered in the AP at the end of the SP." | Delete statement (1) |  | Accepted. |  | 2004-01-13
Benveniste, Mathilde | 11.2.1.5 | T | Y | Table 26.1 row 4 deals with the only non-obvious case; the table provides rather obvious suggestions for the other 3 cases; namely, that the EOSP is used to indicate the end of power-save delivery. The suggested "STA behavior" in case 4 is not recommended. It does make sense for a power-constrained station to stay awake when the AP has just indicated it cannot transmit the station's buffered. Sending a PS poll is not efficient either, especially when the reason there is more traffic than can be sent is that a data burst has arrived for the station. | Include informative text explaining the recommended STA behavior for this case, in place of the table. |  | Accepted. Use Alternate resolution provided here. Leave the table alone, but modify the text in the last row, column 4 to state "QAP transfers no more frames to the non-AP QSTA in the present SP". Change the last two sentences in the last row, column 5 to read "Non-AP QSTA may return to Doze mode immediately and waits until next SP to receive remaining buffered frames." and to "Non-AP QSTA may remain awake and may use PSPoll to receive remaining frames" |  | 2004-01-13
Benveniste, Mathilde | 7.3.2.15 | T | Y | Table 20.6, line 2, column 3 Usage= "Unscheduled SP" is confusing. This option refers to Unscheduled APSD | Modify Table 20.6, line 2, column 3 Usage= "Unscheduled APSD" |  | accepted. Repeat of comment #174 |  | 2004-01-13
Fischer, Matthew | 9.9.2.2.1 | T | Y | There's something wrong with the NAV mechanism and EDCA. If a STA receives a frame with matching RA, then it will not set NAV. In such a case, it is either the MAC in general, or a specific AC which sends an ACK in response - it is not clear which entity is performing this function. In any case, during the transmission of the ACK, with potentially, a ZERO-value DUR field, there is no CCA BUSY indication (at least as far as I can tell from the PHY specifications) and as a result, the other ACs are allowed to count out backoff during what appears to be idle network time. Actually, this same problem may have existed before EDCA. Still - should the OTHER ACs set their NAV when this AC receives a frame? And if you are DLP, can you get some frames from one AC and some from another, (especially if one STA combines two priorities into one AC, while the other separates them) causing the NAV for one AC to become set at one STA, and a subsequent reception requests a MAC ACK from that AC, but it is now impossible, because the NAV is set for that AC because it was the other AC that got the first frame with a non-zero duration? | Create a set of rules which describes how and when to set the NAV among various AC within a single MAC instance. |  | Comment declined. When an ACK frame is received, the NAV that is set is the station NAV and thus the problem described does not happen. |  | 2004-01-14
Fischer, Matthew | 7.3.1.9 | T | Y | Status code 36 - assoc denied due to non-support of block ack - this seems to be jumping the gun, since the QAP doesn't really know ahead of time what services the associating QSTA will wish to employ, and if it only wants to send a couple of best effort frames which won't require block ack, because the efficiency argument for a light flow just doesn't wash. The inclusion of this status code allows an AP to use it, which implies that there can be compatibility problems introduced, since support of the capability is optional. The compatibility issue is a serious one. | Remove status code 36. |  | accepted. |  | 2004-01-13
Fischer, Matthew | 9.2.3.4 | T | Y | first paragraph mentions the backoff expiry requirement, second paragraph does not -- the disposition from the last round of letter balloting was thus: comment declined. The text is written using parallel language wrt 9.2.3.3 -- ouch!!! -- This resolution of the comment effectively says: "there is precedent for this error, so that makes it ok to commit the same error!" Fix it! | use parallel language - either specify all of the requirements for all of the cases or specify only the IFS portion of the requirement for each case - or specify the IFS and mention that all other requirements must also be met before TX can begin |  | Reclassified as editorial. The commenter is requested to submit a text suggestion to the editor. |  | 2004-01-13
Fischer, Matthew | 9.2.9 | T | Y | poor wording | change the text: "and shall be incremented one by one" to "and shall be incremented by one for each new MSDU corresponding to the TID/receiver pair." |  | accepted. |  | 2004-01-13
Fischer, Matthew | 9.6 | T | Y | The new exception for BlockAckReq and BlockAck frames from the normal BSSBasicRateSet transmission rate selection rules introduces a potentially dangerous crack into the previously unshakeable foundation of the 802.11 protocol, which is that all STA shall be able to observe the necessary information to determine medium state. | Remove the exception for the BlockAckReq and BlockAck frames - there is no justification for allowing these frames to escape the rules. |  | Comment declined. While RTS, CTS and ACK frames protect the medium for future transmissions, this is not the case with BlockAckReq/Block as they are one-time events and future protection is not needed. |  | 2004-01-13
Fischer, Matthew | 7.3.2.15 | T | Y | In table 20.6 - the second row "usage" field should contain the phrase "Unscheduled APSD" | fix it as indicated |  | accepted. |  | 2004-01-13
Fischer, Matthew | 9.9.2.3 | T | Y | The new sentence in this clause "In frames of subtype QoS (+)CF-Poll, the TID subfield in the QoS Ctonrol field indicates the TS or UP for which the poll is intended." - it is not clear whether the "intent" is translated into a "requirement" or NOT, for the receiving QSTA. | Modify the wording of the cited sentence to insure that the information indicated is a "strong suggestion" and not a requirement. |  | accepted. Resolved by comment #141. |  | 2004-01-13
Fischer, Matthew | 9.9.2.3 | T | Y | 4th paragraph, new language regarding allowing associations of QACK-capable devices - great new language to include, but does this sentence need a shall in order to make it useable? Does it need to replace "do not force" with "shall not force"? | change "do not force" to "shall not force" - or just leave it alone - does the absence of an explicit requirement to do something imply that the action is optional? |  | alternate resolution. Replace, ".. do not force the QAP to then be required ...", with "… do not require the QAP ..." |  | 2004-01-13
Fischer, Matthew | 9.9.3.1 | T | Y | What is the required setting of the TID field in frames that are sent in a lower AC as a result of the QSTA's lack of support for signaling a TSPEC (or decision not to signal one, even though it may be capable!) - should the TID contain the true priority, or should it contain the value of the transmitted priority (AC)? | Explicitly indicate what the value of the TID field should be in the cited case. |  | Accept. Alternate resolution per comment 3. |  | 2004-01-13
Fischer, Matthew | 9.9.3.1 | T | Y | What is the required setting of the TID field in frames that are sent in a lower AC as a result of the QAP lowering the AC value due to the lack of an admitted TSPEC for a downlink flow? | Explicitly indicate what the value of the TID field should be in the cited case. |  | Accept. Alternate resolution per comment 3. |  | 2004-01-13
Moreton, Mike | 9.10.4 | T | Y | Comment resubmitted with additional explanation: "It's really important not to resequence frames relative to each other (as otherwise TGi security protocols will delete them all, and you may trigger attack warnings), so this section should make it clear that the buffering and resequencing requirements apply equally to normal ACK frames as to Block ACK frames (once Block ACK has been turned on) - the problem is that if you get an out of sequence frame you can't tell if the missing one was a normal ACK or not. From a practical perspective this makes NoACK counter-productive once BlockACK is turned on, and it would be wise to explicitly exclude it in the previous section." | See comment. Note that it's not acceptable to just say "well reordering doesn't matter that much" as the last comment resolution team did, as this contradicts 6.1.3 that explicitly states it won't happen. |  | Comment declined. Reading the architecture figure in the Tgi draft 7.0 and the architecture figure in Tge draft, it appears that the decryption is done above re-ordering and assembly and does not appear to be the problem. |  | 2004-01-14
Moreton, Mike | 7.2.1.8 | T | Y | The new requirement that the starting sequence number in the BlockAck frame be the same as that of the preceding BlockAckreq makes implementation of the receiver more complex, as it makes it more difficult for the receiver to construct the BlockAck ahead of time. If you're going to have this rule, you must also define what the recipient of the BlockAck should do if the rule isn't followed - adding gratuitous restrictions to the spec is a really bad idea unless they serve a very clear purpose. | Remove this restriction, and explicitly state that there is no such restriction. |  | Comment declined. The complexity introduced by the mechanism is not substantial and will avoid any possible interoperability problems. |  | 1/15/2004
Moreton, Mike | 6.1.1 | T | Y | One of the security assumptions of TGi is that group addressed frames are only sent via the AP. It seems TGe are proposing to allow anyone to send them. As TGi are already in sponsor ballot, this is something that TGe must fix. | Either delete this change, or add a security fix for it. Given the potential state explosion this calls, many legacy STAs will not be able to support reception of such frames securely, so there should be a mechanism wherby a STA can decline to receive such frames. |  | Comment declined. The harmonization of Tgi can only occur after at least one of them have been approved. |  | 2004-01-13
Kuehnel, Thomas | 7.2.3.1 | T | Y | The presence of the QBSSLoadElement is not clear. The table states that it shall be present if dot11QoSOptionsImplemented and dot11QBSSLoadImplemented are both true. The next sentence states that it shall be always present in Beacons. As there is a fast roaming study group, which will define its own requirements and presumably information elements to facilitate roaming this is out of the scope of 802.11e. | remove the QBSS load element |  | Alternate resolution. Delete the second sentence in the notes. |  | 2004-01-13
Kuehnel, Thomas | 7.3.2.13 | T | Y | The QBSS Load Element is out of scope of the QoS enhancements working group. There is an fast roaming study group that will address the required protocols, information elements across multipe standards. | remove the QBSS load element |  | declined. It is within the scope of QoS enhancements as a QSTA may choose which QBSS to associate with based on this element. Furthermore, the fast roaming study group is not constituted into a TG yet. |  | 2004-01-13
Kuehnel, Thomas | 7.3.2.13 | T | Y | The behavior upon reception is not defined, i.e. what should or shall a station do if for instance the channel utilization indicates full utilization, or/and Available admission capacity is exceeded. | define the behavior upon reception by an STA |  | declined. The information may be provided to a potentially associating QSTA. How the QSTA uses this information to make a decision is dependent on the implementation. |  | 2004-01-13
Kuehnel, Thomas | 7.3.2.15 | T | Y | Table 20.6 the behavior of APSD and Schedule for EDCF mode, i.e. uplink polling for Power Save is not clear. | define a single bit (schedule bit) that if set indicates uplink polling for powersaving for EDCF. If acknowledged by the AP, the AP will queue frames. |  | Table 20.6 has a combination of bits available for this and no justification has been provided why a unique bit should be provided. |  | 2004-01-13
Kuehnel, Thomas | 9.9.3.1 | T | Y | "shall use an AC that corresponds…" prescribes a certain implementation | "shall use parameters of an AC that corresponds to a lower priority" |  | accepted with "of" replaced by "associated with". |  | 2004-01-13
Kuehnel, Thomas | 7.3.1.4 | T | Y | As APSD is part of the QoS extensions and is tightly related to it, it shall not be signalled inpependent in the Capapbility inofmation element. Otherwise it is possible that an AP (QAP?) does not support QoS but APSD which is contradictory to the scope of the standard. APSD is negotiated during TSPEC setup (admission control) which is suffcient. | remove APSD bit from Capability Information field (Figure 27) |  | declined. While signaling is needed for a setup, a QSTA may decide which channel to associate with depending on the support of this capability. |  | 2004-01-13
Kuehnel, Thomas | 7.3.1.4 | T | Y | The BlockAck mechansims is integral part of the QoS mechansims and the capability shall not be signalled independently. | remove BlockAck bit from Capability Information field (Figure 27) |  | declined. Block Ack mechanism is an optional mechanism and signaling in the capability information field provides some efficiency. |  | 2004-01-13
Adachi, Tomoko | 6.1.1.2 | T | Y | In the fifth paragraph, it is described that QSTAs will act as a non-QoS STA when it is associated in an nQBSS. Does this mean that also management frames will be sent in a non-QoS manner? A QSTA may know it will associate in a QBSS or an nQBSS at the time when it sends a Probe Request frame. | Add to an appropriate clause that management frames will be treated in a QoS manner even if a QSTA is not associated in an nQBSS. |  | alternate resolution. Instruct the editor to indicate that the management frames are to be sent using the default parameter values for AC_VO in EDCA before association in a BSS. |  | 2004-01-13
Adachi, Tomoko | 7.2.3.1 | T | Y | These parameters should not be contained in Beacon frames sent by a QSTA in a QIBSS. | Change the notes for these parameters that these are only and always present within Beacon frames generated by QAPs. |  | accepted. |  | 2004-01-13
Adachi, Tomoko | 7.3.2.17 | T | Y | How will the TS Delay be set when sending an ADDTS Response frame with result code "success"? | Have the TS Delay set to zero when the result code is "success". The requesting QSTA will ignore the TS Delay field when the result code of ADDTS Response frame is "success". |  | alternate resolution. Resolved by resolution to comment 163. |  | 2004-01-13
Adachi, Tomoko | 7.3.2.17 | T | Y | When the result code of ADDTS Response frame is "reject with suggested changes", the TS Delay shall not be set to zero. | Prohibit the TS Delay field set to zero when the result code of ADDTS Response frame is "rejected with suggested changes." |  | alternate resolution. Resolved by resolution to comment 163. |  | 2004-01-13
Adachi, Tomoko | 7.5 | T | Y | The resolution to my comment (no.249) in LB59 is not applied completely. Data(+CF-Poll)+CF-Ack frame to a different STA must not be sent to QSTAs which are not capable with Q-Ack. The comment no.249 in LB59 was as follows: "The description of Q-Ack in 9.1.3.2 is not limited to QoS data but in Annex D, dot11QAckOptionImplemented limits to QoS data. There is no difference in capability of recognizing +CF-Ack whether it is QoS or not." And the recommended change was: "Delete the word QoS from the description of dot11QAckOptionImplemented. Also change the usage descriptions for (Data+)CF-Ack of QoS CFP in Table 20.19 (provided in clause 7.5) to use Rda and Tda. " And the recommended disposition written was: "alternate resolution. The first part of the recommended change is resolved by comment 272. For the second part of the recommended change, create a new designation which indicates that a receiver accepts only the CF-Ack portion of the frame and apply it to all of the non-QoS +CF-Ack frames for QoS CFP except for CF-End+CF-Ack." | Reflect the comment in Table 20.21. |  | Comment declined. We believe is already reflected in table 20.21 through the creation of Rq. |  | 2004-01-13
Adachi, Tomoko | 9.9 | T | Y | There is a sentence "A TXOP shall not extend across a TBTT or exceed dot11MaxDwellTime (if using an FH PHY)." How about if backoff counted down to zero and now ready to transmit but the frame will exceed TBTT so transmission was suspended. After receiving a Beacon frame and waited AIFS idle time, will the QSTA transmit the frame? Then collision will occur between other ACs and QSTAs that suspended their transmission by TBTT. Does the case in clause 9.9.1.5 a) cover this situation and backoff is invoked after AIFS? | Add the description that when backoff counted down to zero but did not start TXOP due to lack of time before TBTT, backoff shall be invoked again. |  | Accept, alternate resolution per comment 164. |  | 2004-01-13
Adachi, Tomoko | 9.9.1.2 | T | Y | Comment to the second paragraph. When TXOP limit value is zero, can an MSDU or an MMPDU fragmented and all of those fragments transmitted? | Clarify. |  | Reject. The text states MSDU, which could be fragmented. |  | 2004-01-13
Adachi, Tomoko | 9.9.1.2 | T | Y | In the last paragraph, it is said that somewhat protection mechanism is explained in clause 9.10. But in 9.10, there is only a similar description with HCCA case added to it (clause 9.10.3). In concrete, what is the protection mechanism which was to be described in clause 9.10? | Clarify the protection mechanism which should be applied to the transfer of Block Ack policy data. |  | 9.10 refers to the subclause in IEEE 802.11g, 2003. Comment accepted with the instruction that the editor harmonizes subclause numbers with IEEE 802.11g, 2003 |  | 2004-01-13
Adachi, Tomoko | 9.9.1.3 | T | Y | Does the AIFSN=3 case in EDCA become the same with the legacy DCF manner? Since UP=0 is categorized to AC_BE whose default AIFSN value for non-AP QSTAs is 3 (= DIFS + SLOT) and can be no smaller than 2 (= DIFS), don't 11e non-AP QSTAs have less advantage to legacy STAs? | Clarify. |  | Reject. See resolution for comment 175. |  | 2004-01-13
Adachi, Tomoko | 9.9.1.4 | T | Y | Does the third paragraph from the end saying that while the Duration/ID is set for continuation of TXOP, recovery may perform without the backoff explained in clause 9.9.1.5 c)? | Clarify. |  | Reject. The group thinks that the text is clear and that the observation made by the commenter is correct. |  | 2004-01-13
Adachi, Tomoko | 9.9.1.5 | T | Y | As the comment for clause 9.9, does a) include the case when there is not enough time to send a frame before TBTT? Also how about the case when suspending TXOP due to TBTT? | Clarify that backoff will take place when TXOP is suspended due to TBTT and taking the next TXOP. Also, clarify that backoff is invoked when once the counter counted down to zero but the TBTT was approaching and couldn't acquire that TXOP. |  | Accept. Alternate resolution per comment 324. |  | 2004-01-13
Adachi, Tomoko | 9.9.2.2 | T | Y | How can the separation be defined between CAPs? There is a sentence "A TXOP or transmission within a TXOP shall not extend across … dot11CAPLimit." But the definition to separate CAPs is not clear and it is difficult to say that these TXOPs are a single CAP and do not exceed the dot11CAPLimit. TXOPs are separated by PIFS or SIFS and CAP will start after PIFS idle time. | Provide clear definition of how to judge a single CAP. Or delete the CAP limit. |  | comment accepted. Instruct the editor to incorporate the text in 9.9.2.1.2, "A CAP ends when the HC does not reclaim the channel after a duration of PIFS after the end of a TXOP." |  | 2004-01-14
Adachi, Tomoko | 9.10.3 | T | Y | The second paragraph is explaining the protection mechanism in Block Ack policy transfer. It is saying that "A protection mechanism (such as transmitting using HCCA, using RTS/CTS or the mechanism described in 9.10) should be used ..." What kind of protection is intended to be described in 9.10? Where is it? | Clarify. |  | 9.10 refers to the subclause in IEEE 802.11g, 2003. Comment accepted with the instruction that the editor harmonizes subclause numbers with IEEE 802.11g, 2003 |  | 2004-01-13
Adachi, Tomoko | 9.10.4 | T | Y | In the second paragraph, it says "If a BlockAckReq is received, all complete MSDUs with lower sequence numbers than the starting sequence number contained in the BlockAckReq shall be indicated to the MAC client using the MA-UNIDATA.indication primitive." Then when will the completed MSDUs for the last burst be indicated by MA-UNITDATA.indication? Also, there is a typo in the cited sentence. MA-UNIDATA.indication is MA-UNITDATA.indication. | Clarify the timing to indicate the complete MSDUs of the last burst by MA-UNITDATA.indication. And correct the typo. |  | Comment accepted. Instruct the editor to incorporate the text, "Upon arrival of a BlockAckReq frame, the originator shall indicate the MSDUs starting with the Starting Sequence number sequentially until there is an incomplete MSDU in the buffer." |  | 2004-01-14
Adachi, Tomoko | 9.11 | T | Y | The last sentence says "A protective mechanism (such as transmitting using HCCA, using RTS/CTS or the mechanism described in 9.10) …" What is described in 9.10? | Clarify. |  | 9.10 refers to the subclause in IEEE 802.11g, 2003. Comment accepted with the instruction that the editor harmonizes subclause numbers with IEEE 802.11g, 2003 |  | 2004-01-13
Adachi, Tomoko | 10.3.6.1.2 | T | Y | Does QoSAction need to be always present? It seems not necessary for all cases. | Correct as follows. "QoSAction may be present only if …" |  | accepted. |  | 2004-01-13
Adachi, Tomoko | 11.4.8 | T | Y | In Figure 68.5, QoS Data is responded with QoS CF-Ack. But in the fourth paragraph in clause 9.9.2.3, in Table 22.3, and in Figure 62.16, it is ACK. What is the condition to use QoS CF-Ack (not piggyback case)? | Clarify. |  | Comment accepted. Replace QoS CF-Ack with Ack. |  | 2004-01-13
Adachi, Tomoko | 11.7.4 | T | Y | Figure 68.8 is unclear to understand how the DLP inactivity timer is reset. | Clarify. |  | Accepted. The figure number is duplicated and the arrows are not properly aligned in the figure. Instruct the editor to fix to figure. |  | 2004-01-13
Adachi, Tomoko | H.2.1 | T | Y | When ACM bits for both AC_VI and AC_VO are set to one, then at least either of the ACM bit for AC_BE or AC_BK shall be set to zero. | Change as described in comment. |  | Comment declined. While the indicated setting in the comment is recommended by the draft, it is felt that there should not be such restriction written in the draft. |  | 2004-01-14
Adachi, Tomoko | 7.3.2.16 | T | Y | The two most significant bits of DSCP field are assigned to Addition of Explicit Congestion Notification (ECN) bits by RFC 3168 and those are irrelevant to 802.11e QoS. These bits shall be ignored to classify the frames. | Specify that the most significant 2 bits of DSCP field shall be ignored for frame classification. |  | comment accepted. |  | 2004-01-13
Adachi, Tomoko | 9.12 | T | Y | For broadcast/multicast sequence, there is only a case sent by a QAP. A non-AP QSTA can also send those frames by QoSLocalMulticast. | Add the bc/mc sequence sent from non-AP QSTAs. |  | accepted. |  | 2004-01-13