## LB_Comments
ID | Name | Clause | E/T | Y/N | Comment/Explanation | Recommended Change | Ad-Hoc Group Responsible | Recommended Disposition | Draft Incorporating Resolution | Date Resolved (Based on Pacific Time) | Miscellaneous Comments | Comment accepted/rejected/other resolution | Status
1 | Housley, Russell | 7.3.1.4 | T | N | How does the QSTA requesting a direct link request the use of 802.11i (as oppend to WEP)? A single bit to signal the desire for encryption does not see sufficient since the choices include WEP, TKIP, and CCMP. At this point, it is pretty clear that TGi is going to finish before TGe, so I do not see any reason to avoid references to 802.11i. | Specify a manner for the selection of TKIP or CCMP for the encryption of direct link traffic. |  | The mechanism that can be used in the current framework is outlined in 03/657r0. However, as Tgi is not an approved standard, this information cannot be added to the draft at this time.
2 | Housley, Russell | 10.3.12.2 | T | N | If a direct link is refused because the worng type of encryption was requested (which assumes that a solution to my previous comment is adopted), then a means of rejecting the request for a direct link is needed that tells the requesting QSTA that different encryption is needed. | Include the capability to tell the requesting QSTA the type of encryption (None, WEP, TKIP, or CCMP) that is needed for the direct link request to be acceptable. |  | Comment declined. The commenter is indeed correct regarding the necessity of providing the reasons for these refusals. However, as Tgi is not yet an approved standard, the task group can not take any action at this time.
3 | Lanzl, Colin | 9.9.1.2 | E | N | On page 71, line 34, the sentence: "In a QIBSS, for broadcast/multicast frames belonging to QoSLocalMulticast service shall be sent one at a time and perform backoff." does not make sense. It does make sense if the word "for" is removed. | Remove the first "for" in the sentence on line 34, page 71, assuming the sense of the sentence with the "for" removed was intended. If not, reword the sentence appropriately.
4 | Lanzl, Colin | 9.9.2.3.1 | E | N | On page 82, the collections of words at lines 5-8 and 9-11 are not sentences. These words are utterly unclear about what is required. Even the sense of what they are attempting to communicate is missing. The only meaning I can extract is that the HC will continue to poll according to the negotiated schedule under some conditions that are a mystery to me. It appears that this text is a victim of multiple edits. | Sadly, I cannot suggest changes to this text as I'm comletely unclear about what behavior it is trying to define. Please re-word this text so that it makes sense and is clear about the normative behavior.
5 | Bray, Jennifer | 6.2.1.3.2 | T | Y | part “f)” of the list in 6.2.1.3.2 says: “Undeliverable. Unsupported service class (for service classes other than ReorderableMulticast or StrictlyOrdered) for non-QoS STAs and service classes other than QoSAck, QoSNoAck or QoSLocalMulticast for QSTAs;” This implies that QoSLocalMulticast is a supported service class in all QSTAs, but 6.1.3 (line 17) contradicts this by saying: “In a QAP, QoSAck and QoSNoAck are the only service classes available” | Change part 6.2.1.3.2 “f)” to: “Undeliverable. Unsupported service class (for service classes other than ReorderableMulticast or StrictlyOrdered) for non-QoS STAs; for service classes other than QoSAck, QoSNoAck or QoSLocalMulticast for non-AP QSTAs and for service classes other than QoSAck or QoSNoAck for QAPs; Generally the explanation of QoSLocalMulticast seems unclear and could benefit from review. |  | Resubmitted comment. Comment declined. See Comment #5 of 04/0181r6 for details.
6 | Bray, Jennifer | 7.1.3.1.2 Table 1 | E | Y | I can find no use for a QoS (no data) + CF-Ack Table 3.2 in clause 7.1.3.5.3 and Table 20.5 in clause 7.3.2.15 say: “The addressed recipient returns an ACK or QoS (+) CF-ACK frame after a SIFS period, according to the procedures defined in 9.2.8, 9.3.3 and 9.9.2.3.” However looking specifically at the QoS (no Data) + CF-Ack, clause 9.9.2.1.3 clarifies that a polled non-AP QSTA shall send a QoS (+) Null frame if it has no data to send: “If a polled non-AP QSTA has no queued traffic to send, or if the MPDUs available to send are all too long to transmit within the specified TXOP limit, the non-AP QSTA shall send a QoS (+) Null frame.” (text begins at line 20 on page 77). So it seems that only an AP QSTA would send a QoS (no data) + CF-Ack. But looking at section 9.12 Table 22.2 there are no sequences allowed that use QoS (no data) + CF-Ack), In all allowable frame sequences non-piggybacked ack's seem to always be normal ack's. Implementers will waste resources supporting reception of this packet type which cannot be sent, so it should be removed. In LB65 the editor agreed this type was not useful, but declined removing it because it could not be assigned to anything else. Whether it can be assigned elsewhere is not relevant, it should still be removed as it has no purpose. | Remove the frame type CF-Ack(no Data) from clause 7.1.3.1.2 Table 1 and indicate this Type Value as “Reserved”
7 | Bray, Jennifer | 7.2.1.3 | T | Y | line19-21 says: ‘In all other frames, the duration value is the value obtained from the duration field of the immediately previous data, or management frame, BlockAckReq frame, or BlockAck frame minus the time, in microseconds, required to transmit the ACK frame and its SIFS interval." The text does not say how Duration/Id should be calculated in QoS stations when they are ACK-ing Ps-Poll frames. This is also not explained in the base standard. It is within the scope of the group to explain this, and it is required information for a complete implementation of the standard | Provide an explanation of how Duration/ID should be calculated in QoS stations when ACK-ing PS-Poll frames |  | Resubmitted comment. Comment declined. See Comment #9 of 04/0181r6 for details.
8 | Bray, Jennifer | 9.9.1.3 | T | Y | The rule defining slot times, rule c)1), do not quite make sense to me. Below is the formulation of 802.11e Draft 7.0 beginning at page 71 line 23: >1) the latter of > i) the end of the ACK-Timeout interval plus AIFSN[AC] × aSlotTime – > aTxRxTurnaroundTime of IDLE time after the PHY-TXEND.confirm, and > ii) the end of the first AIFSN[AC] × aSlotTime – aTxRxTurnaroundTime of IDLE time > following the PHY-TXEND.confirm This makes no sense because (i) would never apply. This is because ii) is always earlier than i), because i) is ii) plus a non-negative quantity [ACK-Timeout]: The slot boundary algorithm was rewritten in 802.11e D6.0 in response to a comment about the effect of noise during the SIFS period after a transmission. The current definition appears to be incorrect; the definition in 802.11e D5.2 made more sense. | Revert to the slot bloundary algorithm in draft 5.2 |  | Resubmitted comment. Comment declined. See Comment #12 of 04/0181r6 for details.
9 | Bray, Jennifer | 9.9.1.3 | T | Y | rule c part 2) beginning at line 28 of page 71 says: 2) at the end of the first AIFSN[AC] × aSlotTime – aRxTxTurnaroundTime of IDLE medium after the PHY-RXEND.indication when a PHY-RXSTART.indication occurs as specified in subclause 9.2.8, This makes the timing of slots relative to the PHY-RXEND.indication. But surely the PHY-RXEND.indication is implementation dependent, so the slot timing under this rule would vary between implementations? Further, this rule seems to cover the same scenario as rule a), assuming the ACK is received correctly. Yet a) specifies a different timing, with slots refered to the last busy medium, and delayed by a further SIFS interval. Part 2) of rule c should be changed for consistency within the rules, and for consistency between implementations. | Replace rule c part 2 with a similar formula to rule a) |  | Resubmitted comment. Comment declined. See Comment #13 of 04/0181r6 for details.
10 | Bray, Jennifer | 9.9.1.3 | T | Y | Rule e) beginning at line 35 of page 71 states: "Following AIFSN[AC] * aSlotTime of medium idle time indication after the last indicated idle medium as indicated by the CS mechanism that is not covered by a) through d) " The STA should wait an additional SIFS. Otherwise stations that fail to receive a burst, but detect it with their CS mechanism, could start transmitting earlier than stations that do receive it and wait an extra SIFS [rule a)]. | Change rule e) beginning at line 35 of page 71 to: "Following AIFSN[AC] * aSlotTime plus one SIFS interval of medium idle time indication after the last indicated idle medium as indicated by the CS mechanism that is not covered by a) through d) " |  | Resubmitted comment. Comment declined. See Comment #14 of 04/0181r6 for details.
11 | Bray, Jennifer | 9.9.1.3 | T | Y | Rules for determining slot times after transmissions requiring acknowledgement by other Access Categories are stated at c), but there is no rule for determining slot times after transmissions requiring acknowledgement by the same Access Category allowing special timing of transmissions in this case. For instance, the same Access Category may initiate recovery before the end of a TXOP after say a PIFS interval, if no acknowledgement is detected, etc. Normally the ‘CS mechanism’ determines the busy or idle state of the medium due to the transmissions of OTHER stations, in the case of competing channel access functions within a station this will not apply. A statement on how the channel access function for an AC behaves after Tx’s by the same AC is required. There are several options: (1) State that the behaviour is the same for the same access category as for other Access Categories (2) State how the behaviour should be different (3) Clearly state any other rules which should be used as the default | State that the behaviour is the same for the same access category as for other access categries. Note that rule d) does not differentiate between the same/other access categories, so this choice would be consistent with the other rules. To accomplish this simply delete the limitation to ‘any other channel access function’ on page 71, line 21 |  | Resubmitted comment. Comment declined. See Comment #15 of 04/0181r6 for details.
12 | Bray, Jennifer | 9.9.1.3 | T | Y | The slot rules seem to allow an AC that does not get an acknowledgement to a transmission requiring acknowledgement to give up transmitting during an TXOP, before the expiry of the NAV that its transmissions may have set. In this circumstance other STAs are not allowed to transmit until this NAV expires. However I could not find a specific rule prohibiting other ACs at the same STA from transmitting during this time. However I could not find a specific rule prohibiting other ACs at the same STA from transmitting during this time. Both rule c) (page 71 line 21) and rule b) (Page 73 line 28) seem to allow this. It would be better to require all ACs to perform a backoff at the expiry of the NAV set by the frame that resulted in a transmission failure. | After page 73/line 8-10: "However, at the expiry of the NAV set by the frame that resulted in a transmission failure, the channel access function shall invoke backoff procedure." Add: "No other AC at the STA shall transmit before the expiry of the NAV set by the frame that resulted in a transmission failure. All other ACs at the STA shall treat the medium as busy until the expiry of the NAV set by the frame that resulted in a transmission failure, just as they would if they had received that transmission from another STA." |  | Resubmitted comment. Comment declined. See Comment #16 of 04/0181r6 for details.
13 | Bray, Jennifer | 9.9.1.4 | T | Y | “If the Duration/ID is set for continuation of TXOP, if there is a transmission failure, the corresponding channel access function may recover before the expiry of the NAV setting due to the setting of the Duration/ID field in the frame that resulted in a transmission failure. However, at the expiry of the NAV set by the frame that resulted in a transmission failure, the channel access function shall invoke backoff procedure.” The last sentence seems to imply that backoff procedures shall be invoked regardless of whether there has already been a successful recovery. In fact, recovery within the TXOP does not require the backoff procedure to be used because there is no contention. | Change the last sentence to: “However, at the expiry of the NAV set by the frame that resulted in a transmission failure, if the channel access function has not recovered then the channel access function shall invoke backoff procedure.” |  | Resubmitted comment. Comment declined. See Comment #17 of 04/0181r6 for details.
14 | Bray, Jennifer | 9.9.2.2.1 | T | Y | A QAP may create a CFP using a beacon CF Parameter Set, and give polled TXOP’s to non-AP QSTAs during this CFP (1st paragraph 9.9.2.1.1). If these stations transmit RTS frames, they should be responded to regardless of the state of the NAV. (2nd paragraph of 9.9.2.2.1 "If an RTS frame is received with the RA address matching the MAC address of the QSTA and the MAC address in the TA field in the RTS frame matches the saved TXOP holder address, then the QSTA shall send the CTS frame after SIFS, without regard for, and without resetting, its NAV." However 2nd paragraph of 9.9.2.2.1 begins with "When a QSTA sets a NAV value using the duration value from a QoS (+)CF-Poll containing the BSSID of a QBSS, that QSTA shall also save the TXOP holder address," and this seems to be the only situation in which the TXOP holder address is updated. So if the the DurationId from the CF-Poll corresponds to a NAV that is less than the NAV from the beacon then the TXOP holder will not be updated, and there will be no CTS response to the RTS. | The solution seems to be to always update the TXOP holder regardless of whether the NAV is updated. A change to the opening of the 2nd paragraph of 9.9.2.2.1 could do this. Change from: "When a QSTA sets a NAV value using the duration value from a QoS (+)CF-Poll containing the BSSID of a 1 QBSS, that QSTA shall also save the TXOP holder address, " to: "When a QSTA receives a QoS (+)CF-Poll containing the BSSID of a QBSS, that QSTA shall update the NAV of that QBSS if necessary and shall save the TXOP holder address for that QBSS, " This is a complex area and may have side effects I have not foreseen, but it is the best solution I can see at present. An alternative might be to require a CTS regardless of whether the TA in the RTS matches the saved TXOP holder address, but this seems inelegant. |  | Resubmitted comment. Comment declined. See Comment #23 of 04/0181r6 for details.
15 | Moreton, Mike | 9.9.2.1.1 | T | N | reference to figure 63, that doesn't exist. | correct the reference. |  | Comment declined. It refers to the figure in 9.3.1 which is numbered as figure 63 in "IEEE Wireless LAN Edition Standards Information Network, IEEE Press. A compilation based on IEEE Std 802.11-1999 (R2003) and its amendments
16 | Moreton, Mike | 9.12 | T | N | Figure 62.12 on line 2 of the flow diagram there are two entries for TX:Data(dir)+CF-Poll(+CF-Ack). [Paul Newton] | Shouldn't the second be TX:CF-Poll(+CF-Ack) as the next process in the flow diagram doesn't return a piggyback ack. |  | Comment declined. The comment is out of order as it is not based on changes from Draft 7.0 to Draft 8.0. |  |  | Comment is correct though.
17 | Moreton, Mike | 9.9.1.2 | T | N | The new text has two "may"s in the first sentence, which from later context should probably be "shall"s. | Change both to "shall". |  | Comment declined. Since there are two clear options, "may" is appropriate.
18 | Moreton, Mike | 9.9.1.2 | E | N | The new text has a number of grammatical errors. | Correct them.
19 | Moreton, Mike | 9.9.1.4 | T | N | The new text is written in an unclear way, and appears to be describing behaviour when there isn't a continuation TXOP, so is in the wrong section. | Rewrite, and move to a more appropriate section. |  | Comment declined. The commenter did not indicate what is unclear. While the behavior is not strictly continuation TXOP, it is allowing QAP to piggyback a new TXOP. This place is appropriate as any other section. |  |  | One option could be to add a new subclause.
20 | Moreton, Mike | 9.9.2.3 | T | N | First block of text says to use a SIFS if the STA set the Q-ACK subfield, but doesn't say what IFS to send a QoS Data+CF-Ack after if it didn't. | This is a poorly phrased sentence. I can guess you probably mean something else than what you wrote, but I'd like you to rewrite this sentence so that it doesn't have multiple possible meanings. |  | Comment declined. This behavior is already described in 9.9.2.1.2
21 | Moreton, Mike | 9.9.2.3 | T | N | The second block of new text shares similar weird phrasing to the first block, and is again open to different interpretations. Some of the phrases chosen don't sound like the normal sort of thing you find in a spec e.g. "are also useful if" | Rewite to make more easilly understandable. |  | Comment declined. The newly added text is merely indicating what the HC can do with the available features and is more of a clarification.
22 | Moreton, Mike | 9.9.3.1.2 | T | N | How does an AP respond to a TSPEC in a (re)association request frame? | Allow it to send the response in the Association response? |  | Comment declined. The comment is out of order as it is not based on changes from D7.0 to D8.0
23 | Moreton, Mike | 9.9.3.1.2 | E | N | Change "in a (re)association request" to "in a (Re)Association Request frame". | See comment.
24 | Moreton, Mike | 9.10.6 | T | N | Sorry, but I can't parse the new text. | Please rewrite. |  | Comment declined. The sentence is perfectly parsable.
25 | Moreton, Mike | 11.2.1.5 | E | N | "it shall automatically wake up" - I don't think there's any need to specify how the STA should wake up, simply that it should. | Delete "automatically".
26 | Lim, Wei Lih | 9.9.3.2 | T | N | The service start time in ADDTS Response frame shall not exceed the requested Service Start Time, if specified in ADDTS request frame, by more than one Maximum Service Interval instead of Minimum Service Interval. Agree that this is not a changes from draft 6.0 to draft 7.0/8.0. But it is still a mistake that need to be rectified. | As suggested |  | Comment declined. See Comment #61 of 03/181r5
27 | Lim, Wei Lih | 11.4.8 | T | N | Second sentence of bullet b) is misleading. How can having TSID in an QoS Null frame being used to ensure that the non-AP QSTA is actually using the assigned TXOP for the given TSID. On the other hand, how can the non-AP QSTA is being ensured that it is not using thea ssigned TXOP for the given TSID, if Qos Null frame is not being received within the TXOP. | Please clarify or remove it |  | Comment declined. The comment is out of order as it is not based on changes from D7.0 to D8.0
28 | Lim, Wei Lih | H4.1 | T | N | Second paragraph is misleading. If there are no downlink, then what is the reserve polling for. Poll for QoS Null frame? So, unscheduled APSD is only usefull is there exist bi-directional streams. | Please clarify or remove it |  | Comment declined. The comment is out of order as it is not based on changes from D7.0 to D8.0
29 | Kuehnel, Thomas | 7.3.2.21 | T | N | The action element format provides for the possibility of embedded Ies, like multiple TCLASS elements and a single TSPECS. This creates a unecessary complication as those elements can be included separately in a association/reassocaition request. It furthermore allows only to have a single TSPEC (for one connection to be conveyed). This seems wrong. | Change the action IE to only carry the action code, like ADDTS request/response, DELTS. This way the IE has a constant length, decoding is simplified and no limititations on the number of TSPEcs carried in the association/reassociation is imposed |  | Comment declined. The comment is out of order as it is not based on changes from D7.0 to D8.0. Furthermore this change will make changes to Tgh and if there are any Tgh devices before this becomes a standard they become non-compliant.
30 | Kuehnel, Thomas | 11.2.1.7 | T | N | the additions to clause e) are confusing as a non- AP QSTA shall never expect a QoS + CF ACK from its QAP duing a CP. Repetetion of earlier comment - alternative resolution is not accepted | remove additions made in D7 and reinstate the original text |  | Comment declined. The addition of +Cf-Ack improves efficiency of the usage of the channel.
31 | Kuehnel, Thomas | 9 | T | N | Alternate resolution. Resolved by the addition of text into clause 9 allowing +Cf-Ack in EDCA. | remove additional text that allows +CF Ack in EDCA |  | Comment declined. The addition of +Cf-Ack improves efficiency of the usage of the channel.
32 | Kuehnel, Thomas | 9.6 | T | N | All data frames of subtype CF-Poll sent in the CP shall be transmitted at one of the rates in the BSS basic rate set so that they will be understood by all STAs in the BSS, unless an RTS-CTS exchange has already been 11 performed before the transmission of the data frame of subtype CF-Poll and the duration field in the RTS 12 frame covers the entire TXOP. 13 | remove as there shall never be CF-Poll in CP |  | Comment declined. The addition of +Cf-Ack improves efficiency of the usage of the channel.
33 | Kuehnel, Thomas | 9.9.14 | T | N | Upon receiving an MPDU with the BSSID in the address 1 field of the frame and the duration/ID field in the frame covers no more than the ACK frame, the QAP (i.e., the HC) may send the QoS +CF-Ack to the same 25 non-AP QSTA a SIFS after receiving the MPDU. Upon receiving an MPDU with the BSSID in the address 1 26 field of the frame and the duration/ID field in the frame covers no more than the ACK frame and if the non- 27 AP QSTA has set the Q-Ack subfield in QoS Capability Information Element in the (re)association request 28 frame to 1, the QAP (i.e., the HC) may send the QoS +CF-Ack to another non-AP QSTA a SIFS after 29 receiving the MPDU. | remove added section as there shall never be CF-Poll in CP , frames should not be mixed up as the rules for CFP and CP are associated with the frame formats. Implementations will be more difficult. |  | Comment declined. The addition of +Cf-Ack improves efficiency of the usage of the channel.
34 | Kuehnel, Thomas | 7.2.3.1 | T | N | The presence of the QBSSLoadElement is not clear. The table states that it shall be present if dot11QoSOptionsImplemented and dot11QBSSLoadImplemented are both true. The next sentence states that it shall be always present in Beacons. As there is a fast roaming study group, which will define its own requirements and presumably information elements to facilitate roaming this is out of the scope of 802.11e. repetition from previous ballots | remove QBSSLoadElement repetition from LB63 |  | Comment declined. Refer to resolution to comment #111 in 04/181r5
35 | Kuehnel, Thomas | 7.3.2.13 | T | N | The QBSS Load Element is out of scope of the QoS enhancements working group. There is an fast roaming study group that will address the required protocols, information elements across multipe standards. Repetition | remove QBSSLoadElement repetition from LB63 |  | Comment declined. Refer to resolution to comment #112 in 04/181r5
36 | Kuehnel, Thomas | 7.3.2.13 | T | N | The behavior upon reception is not defined, i.e. what should or shall a station do if for instance the channel utilization indicates full utilization, or/and Available admission capacity is exceeded. | define the behavior upon reception by an STA repetition from LB 63 |  | Comment declined. Refer to resolution to comment #113 in 04/181r5
37 | Kuehnel, Thomas | 7.3.1.4 | T | N | The BlockAck mechansim is integral part of the QoS mechansims and the capability shall not be signalled independently. | remove BlockAck bit from Capability Information field (Figure 27) repetition from LB63, LB65 |  | Comment declined. Refer to resolution to comment #116 in 04/181r5
38 | Kuehnel, Thomas | 7.1.3.5.2 | T | N | "..to end a scheduled/unscheduled service period after…otherwise" it is redundent if this is the final frame of the service period; repetition from LB65 | replace with" The End of Service Period (EOSP) field is set to 1 at the end of a triggered service period (SP), and is set to 0 otherwise." |  | Comment declined. Refer to resolution to comment #118 in 04/181r5
39 | Kuehnel, Thomas | 9.9.3.1.2 | T | N | DELTS shall not be used for renegotiation repetition from LB65 | If an explicit admission is torn down, the STA shall disable the use of the AC. |  | Comment declined. Refer to resolution to comment #121 in 04/181r5
40 | Kuehnel, Thomas | 9.9.3.1.2 | T | N | DELTS shall not be used for renegotiation repetition from LB65 | remove the additions (subtract associated medium time value from the admitted time variable" made to D7 and resinstate the original text. Add the following text to 9.9.3.1: "A Setup request for a flow (TID) that has an established explicit admission shall be regarded as a request for a change to the existing admitted flow. If a request for a change to an admitted flow is refused, the previously accepted admission for the same flow remains valid. Admitted time for each channel access function is the sum of the admitted times for all admitted flows which map into that AC. A STA may choose to police admitted time and used time on a per-TID basis, with the rules for not transmitting when admitted time is exceeded applying per TID as well. A STA shall not be required to support any more than one admitted TSPEC per AC. A AP shall not be required to support any more than one admitted TSPEC per AC per STA. |  | Comment declined. Refer to resolution to comment #122 in 04/181r5
41 | Kuehnel, Thomas | 11.2.1.4 | T | N | The text is unclear, repetition from LB65 | replace the text with the following: "The procedures defined in this section apply to unicast QoS-Data and QoS-Null frames that are to be delivered to a nonAP QSTA when the STA is in PS-mode. The power-save procedures during CP are based on the legacy procedures defined in [spec 1999], but an option for triggered power-save delivery is added. A non AP QSTA chooses legacy versus triggered behavior on a per-AC basis. A non AP QSTA causes an AC to be “trigger-enabled” by setting APSD=1 in at least one admitted downlink TSPEC that maps to the AC. (Note: throughout this section, a bi-directional TSPEC is equivalent to an uplink and a downlink TSPEC with identical characteristics). If, for a particular STA, an AC is not trigger-enabled, then all downlink frames destined to that STA that map to that AC are buffered and delivered using the procedures described in [spec 1999]. The buffer used to hold these frames will be referred to as the legacy PS buffer. The QAP uses the TIM and the More Data bit carried in Frame Control Field to indicate the status of the legacy buffer as specified in [spec 1999]. If, for a particular STA, an AC is trigger-enabled, then all downlink frames destined to that STA that map to that AC are temporarily held by the QAP in a “triggered PS buffer”. Conceptually, there is one triggered PS buffer per trigger-enabled AC and PS-mode STA (this conceptual model does not, of course, constrain the implementation). The QAP shall not use the TIM bits or the More Data bits to indicate the status of any triggered PS buffer. Downlink frames are released from a triggered PS buffer by a trigger frame. A trigger frame is defined as a QoS-Data or QoS-Null frame, sent uplink by a PS-mode STA, in which the UP maps to a trigger-enabled AC. (Note: transmission of trigger frames is not implicitly allowed by admission of a downlink flow. If the trigger frame maps to an AC that has ACM=1, then the STA must establish a suitable uplink flow before sending triggers.) The combination of sending STA and UP uniquely identifies a triggered PS buffer; the trigger frame causes all frames to be released from that buffer. The released frames are delivered during a triggered service period. The triggered service period begins after the QAP acknowledges the trigger frame transmitted by the station. The frames released from the triggered PS buffer shall be delivered using the access parameters of the corresponding AC. The QAP uses the EOSP bit that is carried in the QoS Control field to indicate the end of the triggered service period. It should be clear that, for a particular STA, the triggered PS buffer, the trigger frame, and the triggered service period are all per-AC. Therefore, if a non AP QSTA establishes flows that result in more than one trigger-enabled AC, the STA must initiate triggered service periods separately for each such AC in order to retrieve all the buffered frames. The non AP QSTA must remain awake as long as there is at least one triggered service period still in progress. " An AC shall be considered trigger-enabled, for a particular STA, if there exists at least one admitted downlink or bi-directional TSPEC with APSD=1 that maps to that AC. Downlink unicast QoS-Data frames associated with a trigger-enabled AC shall be temporarily held in the AC’s triggered PS buffer. |  | Comment declined. Refer to resolution to comment #124 in 04/181r5
42 | Kuehnel, Thomas | 7.3.2.15 | T | N | The Aggregation subfield is valid only when access method is HCCA or when the access method is EDCA and the schedule subfield is set to 1. This extended function of the aggreation bit is not clear in EDCA - reinstate with the original sentence. | When the access policy is set to EDCA and the APSD subfield is set to 0, then the aggregation subfield is reserved. |  | Comment declined. The original text does not cover all cases where as the added text does.
43 | Kuehnel, Thomas | 7.3.2.2.1 | T | N | The action frame format should be limited to the action (ADDTS, DELTS) and not carry TCLASS and TSPEC. The latter one would mean that IE is carried in an IE which is generally not the case in the spec. In addition, it limits the flexibility | redfine action frajme format to only carry the action rather than the action and parameters. |  | Comment declined. The comment is out of order as it is not based on changes from D7.0 to D8.0. Furthermore, the way Tge is using is not in anyway different from what is already there in IEEE 802.11h standard.
44 | Kuehnel, Thomas | 9.9.3.1.2 | T | N | "the inclusion of or in a (re)association request" seems unreasonable as the admission can only be obtained for a single flow. The rejection of the TSPEC does not necessarily result in the rejection of the admission. This should be addressed by fast roaming stury group | remove "or in a (re)association request" as it adds a new feature and is not fully specified. Should be addressed by fast roaming stufy group. |  | Comment declined. The mechanism improves efficiency even for one TSPEC and is especially useful for application specific devices.
45 | Kuehnel, Thomas | 7.2.3.4 | T | N | The current format of the Association request frame allows for one TSPEC to be conveyed as part of the QoS Action IE. As typically there are more than one connection (signalling, bearer) that need to be accomodated by the new AP the frame format should be changed | The QoS Action IE needs to conatin only the action, i.e. ADDTS; additionally the Association request frame may conatin zero or more Tspecs as separate Ies. This way no embedded Ies are needed. |  | Comment declined. The comment is out of order as it is not based on changes from D7.0 to D8.0. Furthermore, the way Tge is using is not in anyway different from what is already there in IEEE 802.11h standard.
46 | Kuehnel, Thomas | 7.2.3.6 | T | N | The current format of the ReAssociation request frame allows for one TSPEC to be conveyed as part of the QoS Action IE. As typically there are more than one connection (signalling, bearer) that need to be accomodated by the new AP the frame format should be | The QoS Action IE needs to conatin only the action, i.e. ADDTS; additionally the ReAssociation request frame may conatin zero or more Tspecs as separate Ies. This way no embedded Ies are needed. |  | Comment declined. The comment is out of order as it is not based on changes from D7.0 to D8.0. Furthermore, the way Tge is using is not in anyway different from what is already there in IEEE 802.11h standard.
47 | Buttar, Alistair | 7.3.2.15 | E | N | The clause "When the APSD subfield is set to 1, the aggregation is also set to 1" is inconsistant with the text defining the aggregation bit in the same clause, because it does not consider combinations of APSD, access policy and schedule type where the aggregation subfield is reserved. If such restrictions are to be placed on the aggregation subfield, then they should only apply to cases where the aggregation field is valid. | Change the text to read "When the APSD subfield is set to 1 and the access policy is HCCA, or when the APSD subfield is set to 1 and the schedule subfield is set to 1, the aggregation subfield is also set to 1".
48 | Buttar, Alistair | 7.3.2.15 | E | N | The sentence "If the APSD field values of two admitted traffic streams associated with the same QSTA differ, the QSTA is assumed to use APSD mechanism until termination of the traffic stream with a TSPEC with the APSD bit set to 1" is ambiguous and confusing. What does it mean to assume that a mechanism is used, and what actions should be taken by the QAP and non-AP QSTA as a result of this assumption? | Change the text to read "If the APSD field values of two admitted traffic streams associated with the same QSTA differ, the QAP employs the APSD mechanism for the traffic stream having the TSPEC with its APSD bit set to 1 until the termination of its TSPEC"
49 | Buttar, Alistair | 11.2.1.5 | T | Y | The sentence in bullet g) reading "The More Data bit of the directed data or management frame shall be set to 1 to indicate the presence of more frames that are destined for that non-AP QSTA" is too restrictive. The word shall should be replaced with may to allow the AP flexibility to intelligently determine if and when to notify a non-AP QSTA that data is pending. For example, there may be cases where the AP may choose to limit the number of stations eligible at a certain time to send PS-Poll frames and reduce the possibility of collisions on the channel, or there may be cases where it would be preferable for APSD stations to wait for the AP to delivery frames during next regularly occurring service period. In these cases, the QAP should have the flexibility to set the More Data bit of a frame to 0. | Change bullet g) to read "The More Data bit of the directed data or management frame may be set to 1 to indicate the presence of more frames that are destined for the non-AP QSTA". |  | Comment declined. Please see comment #72 of 03/0181r5. |  |  | Comment declined. The comment is out of order as is not based on the changes made from D6.0 to D7.0 or from D7.0 to D8.0
50 | Buttar, Alistair | 11.2.1.5 | E | N | The title of Table 26.1 does not indicate that the material presented is intended to be informative, and this could be confusing. Further, the behaviors summarized in the table are now clearly defined by the text in clause 11.2.1.4.5, and therefore the information in the table is redundant. If clarification is desired, the informative annex would be a more suitable location to provide an informative table. | Insert the text "(Informative)" in the table title
51 | Buttar, Alistair | 11.2.1.5 | E | N | When reading bullet i), it is unclear whether a directed MPDU or management frame sent with the More Data sub-field set to 0 and the EOSP set to 0 should be retransmitted to the Max Retry Limit, or to the lesser of the Max Retry Limit and the MIB attribute dot11QAPMissingAckRetryLimit. Since the non-AQ QSTA obviously remains awake after receiving a frame send with EOSP equal to 0, including this case in clause i) may unnecessarily confuse the reader. | Change the first sentence in bullet i) to read "If the QAP does not receive an acknowledgement to a directed MPDU or management frame sent with the EOSP set to 1, it shall retransmit that frame at least once within the same service period, time permitting – subject to applicable retry or lifetime limit"
52 | Buttar, Alistair | 11.2.1.5 | E | N | The sentence in bullet c) reading "At every beacon interval, the APSD-capable QAP shall assemble the partial virtual bitmap containing the buffer status per destination for non-AP QSTAs using APSD, and shall send this out in the TIM field of the beacon" opens up the possibility that the QAP must constuct the bitmap for a non-AP QSTA that has a TSPEC with APSD set to 1 but currently in active mode. The text "using APSD" without mentioning power save mode is ambiguous and confusing. | Change the text to read "At every beacon interval, the APSD-capable QAP shall assemble the partial virtual bitmap containing the buffer status per destination for non-AP QSTAs using APSD and in the PS mode, and shall send this out in the TIM field of the beacon."
53 | Buttar, Alistair | H.4.1 | E | Y | In H 4.1, second paragraph, it states " The Unscheduled APSD option is useful only if there exists, at minimum, one uplink or bi-directional traffic stream because nothing can be retrieved from the AP buffer if there is no uplink stream.". More information is needed to discuss the case when there is no uplink stream. In the absence of uplink traffic stream, the STA using unscheduled APSD can set an uplink stream sending QoS-Null to trigger unscheduled service period. Therefore, it is still useful. | Change the paragraph to "It should be evident that unscheduled service periods are useful if there exists, at minimum, one uplink and one downlink TSPEC; because if there is no downlink TSPEC the QAP will not buffer frames for unscheduled delivery, and if there is no downlink TSPEC the non-AP QSTA will be unable to issue trigger frames. A bidirectional reservation is considered to be equivalent to an uplink plus a downlink TSPEC with identical characteristics—including the setting of the APSD and schedule subfield—so a single admitted bidirectional reservation satisfies the minimal requirement. If necessary, the non-AP QSTA may establish an uplink traffic stream consisting of QoS-Null frames, and use these frames to trigger unscheduled service periods each time the QSTA is ready to receive buffered frames via unscheduled delivery.
54 | Buttar, Alistair | H 4.3 | E | Y | In H 4.3, starting from Line 4, second paragraph, it states "if there is buffered traffic not associated with an APSD TSPEC, the AP will either transmit it during the service period or notify the station by setting the More Data bit to 1 and the EOSP to 1 in the last downlink frame. ". It is inconsistent with the normative text in clause 11.2.1.5, which allows the AP to deliver frames associated with TSPECs having APSD=1 during APSD service periods. | Change the sentence to "if there is buffered traffic not associated with an APSD TSPEC, the AP will notify the station by setting the More Data bit to 1 and the EOSP to 1 in the last downlink frame".
55 | Adachi, Tomoko | 7.3.2.17 | T | Y | The comment same to which I gave in LB63 (comment no.321) and LB65 (comment no.110). When the QAP responds by ADDTS response frame with status code set to 40, the TS Delay field should never be set to zero. The resolution to comment no.110 in LB65 was that this condition does not occur. Then, add that description to make it clear! Add the description here that when QAP responds by status code 40, the TS Delay is set to a non-zero value. | Change as requested. |  | Comment declined. A value of "0" has specific meaning - never to send another ADDTS. The group thinks that this encoding is needed. Furthermore, what the commenter is seeking is not on a change between D7.0 and D8.0 and is thus out of order. |  |  | Comment declined. A value of "0" has specific meaning - never to send another ADDTS. What the commenter is seeking is not on a change between D7.0 and D8.0 and is thus out of order..
56 | Adachi, Tomoko | 9.9.2.3.1 | EorT | N | The same comment to comment no.100 in LB65. In the second and third paragraphs, there are no verbs in the "If …" phrases. What should the TXOP request and Queue request subfields be? Is the second paragraph saying the situation when the TXOP request subfield is set to one? It should be so, or the following "even if ..." phrase doesn't make sense. The third paragraph has the same problem. | Clarify.
57 | Adachi, Tomoko | 9.12 | T | Y | In the RTS-CTS-QoS Data(bc/mc) sequence for non-AP QSTAs, it should be made clear that RTS-CTS exchange is done between the QAP. Also, the RTS-CTS exchange should be limited to EDCA TXOP, since HCCA TXOPs are already protected by the QAP. | Change RTS-CTS-QoS Data(bc/mc) to {RTS-CTS-} QoS Data(bc/mc) and add the description that RTS-CTS exchange is done between the QAP and its is only requested for EDCA TXOP. |  | Resolved by resolution to comment #58.
58 | Takagi, Masahiro | 9.12 | T | N | (RTS-CTS-QoS Data(bc/mc) in Table 22.3) It should be clearly stated that the RA of RTS and SA of CTS is the QAP and this sequence is only used as EDCA TXOP sequence. There is no need to add RTS-CTS in HCCA since the TXOP has been protected by QAP. It seems me that MSDUs should be replaced by MPDU. | Usage of RTS-CTS-QosData(bc/mc) : "First broadcast or multicast MPDU sent by non-AP STAs as QoSLocalMulticast frames when they are sent in a burst of frames under EDCA. RTS/CTS shall be exchanged between non-AP STA and QAP." Usage of {CTS-} QoS Data(bc/mc) : "...MPDU sent by non-AP STAs as QoSLocalMulticast... Any broadcast or multicast MPDUs sent under HCCA or sent by QAP under EDCA." |  | Comment declined. What the commenter seeks is already there elsewhere and no update of the draft is required.
59 | Takagi, Masahiro | 6.1.1.2 | T | Y | Repetition of the commnet no.54 of LB65. "If a QSTA is associated in an nQBSS, the QSTA is functioning as a non-QoS STA, so the priority value is always Contention or ContentionFree." Does this implies that QSTA shall use DIFS (= SIFS + Slot *2) instead of default AIFS (= SIFS + Slot * 3) | Allow to use both DIFS and default AIFS. |  | Comment declined in the previous recirculation letter ballot. The commenter does not indicate why he wants to make the change he is suggesting. |  |  | Comment declined in the previous recirculation letter ballot. The commenter does not indicate why he wants to make the change he is suggesting.
60 | Mani, Mahalingam | H.4 | T | Y | The deletion of certain text in H.4 removed valuable information concerning the use of the power save features. Notwithstanding the feature being optional and text being informative, for interested implementers it is crucial. there appear to be no grounds to exclude unless there is objectionable verbiage editorially or technically. | Restore last paragraph in subclause H.4.1 as it was in D7.0. Restore subclause H.4.3 as it was in D7.0 |  | Comment declined. The last paragraph of H.4.1 is a reiteration of what is already in the normative text. Refer to comment #77 of 03/181r5. For the changes in H.4.5, the commenter is referred to comment #84, #85 and #86 of 03/0181r5 for the reasons why the changes have been made. |  |  | The comment is an invalid Technical "No" comment as it does not seek to change the behavior normatively and seeks changes to normative text. Further, the comment is declined as the original text does not contain any extra information but provides an incomplete qualitative analysis.
61 | Soomro, Amjad | 7.3.2.15 | T | Y | Applications such as video are quite tolerant to frame loss conditions and yet an HC may drop an admitted stream due to frame loss condtions. In order to ensure interoperability and better expression of traffic stream requirements, acceptable frame loss rate for the traffic stream needs to be communicated between HC and a QSTA. | Add 'Acceptable Frame Loss Rate' parameter in TSPEC. This could be an optional parameter |  | Comment declined. The functionality increases complexity. Furthermore, the proposal is incomplete. |  |  | Comment declined in the previous letter ballot. Further no new information has been provided to the group.
62 | Benveniste, Mathilde | 9.9.1.3 | T | Y | The EDCA backoff rules in the current TGe draft do not work. The EDCA backoff rules cause legacy stations to perform better than 802.11e stations when transmitting BE traffic. Part of the problem is that the new backoff rules are different from those in the existing 802.11-1999 standard. Aside from the problems the new backoff rules cause, they are confusing to understand and thus more complex to implement. The old backoff rules have been well tested and understood. More details in doc 04/244. | Use the old backoff rules in the 802.11e-compliant stations. This way, 802.11e stations will not be at a disadvantage relative to the stations following the existing 802.11-1999 backoff rules. Adopt the EDCA backoff rules proposed in doc 03/149. |  | Reject. This comment was rejected in the previous letter ballot. |  |  | Reject. This comment was rejected in the previous letter ballot.
63 | Benveniste, Mathilde | H.4.1 | T | Y | Useful text has been deleted from the second paragraph of H.4.1. The text was helpful as it contained suggestions of how the standard could be used. | Restore the text deleted in the second paragraph of H.4.1 as it was in D7.0, or add the text: "An uplink stream may consist of QoS-Null frames. Such a stream may be generated whenever the non-AP QSTA receives a TIM (or More Data bit) indication that there are buffered frames at the AP, in order to retrieve such frames from the AP." |  | Comment declined. That is the only condition when an uplink QoS-Null frames may be used to trigger. For example, the non-AP QSTA may set an uplink stream with 0 mean data rate. |  |  | The comment is an invalid Technical "No" comment as it does not seek to change the behavior normatively and seeks changes to normative text. Further, the comment is declined as the original text does not contain any extra information but provides an incomplete qualitative analysis.
64 | Benveniste, Mathilde | H.4.2.2 | T | Y | The deleted text has value as it helps the implementers undertand the possibilities of the standard.. | Restore the text deleted in the last two paragraphs of H.4.2.2 as it was in D7.0. |  | Comment declined. The commenter is referred to comment #79, #80, #81 and #87 of 03/181r5 for the reason why the text is deleted. |  |  | The comment is an invalid Technical "No" comment as it does not seek to change the behavior normatively and seeks changes to normative text. Further, the comment is declined as the original text does not contain any extra information but provides an incomplete qualitative analysis.
65 | Benveniste, Mathilde | H.4.3 | T | Y | The deleted text in the last paragraph of H.4.3 has informative value as it describes useful ways in which the available power save options may be combined. | Restore the text in the last paragraph of H.4.3 as it was in D7.0. |  | Comment declined. The commenter is referred to comment #84, #85 and #86 of 03/181r5 for the reason why the text is deleted. |  |  | The comment is an invalid Technical "No" comment as it does not seek to change the behavior normatively and seeks changes to normative text. Further, the comment is declined as the original text does not contain any extra information but provides an incomplete qualitative analysis.
66 | Benveniste, Mathilde | general | E | N | The QoS enhancement of the DCF protocol has been known as 'EDCF' for most of the time TGe has been working on this protocol. Consequently, EDCF was the name used in the TGe technical documents posted on the IEEE 802.11 server. These documents describe the mechanism, its performance, and the rationale for its specification. The subsequent change of the name to 'EDCA' deprives the reader of the 802.11e standard of the link to this technical information. While the loss caused by the name change is clear, I don't see any benefit from the name change. | Use the name EDCF in place of "EDCA', for continuity and clarity.
67 | Amann, Keith | 7.2.3.4 | T | Y | (Duplicate, Originally Comment #153 from LB#63) For an (re)association request sent with a ADDTS request QOS action, it is not clear what happens in terms of association if (1) the TSPEC is unacceptable, or (2) the QAP chooses to "suggest" a different TSPEC. In these two cases, it seems that it makes the most sense to explicitly require the QAP to refuse association until the (re)association request is sent with a mutually acceptable TSPEC. The task group responded as follows: Alternate resolution. Clause 11.4.3 already indicates that the process is repeated. It does not appear clear why the association has to be defined. The inclusion of ADDTS request is only to provide efficiency of the channel use. Instruct the editor to add, "If the original ADDTS request is sent in a (re) association request frame, the whole process can be repeated with the exception that the request is sent in an ADDTS request". First, although I agree that one purpose of including the ADDTS request in the (re)association request is for channel efficiency, the other purpose is to establish whether the QAP has the resources available before/while commiting to the association. If a QoS application is active at the time of association then it is forced to attempt to run under degraded conditions while it attempts to determine whether the QAP can support it, this seems counter intuitive to the idea of QoS. By allowing the QSTA to establish the TSPEC at association time, the QAP can reject the association, and force the QSTA to find an alternative AP. The proposed resolution attempted to clarify this point. | Provide clarifying text here, clause 11.4, and/or where ever else necessary to specify the rules that should be followed in the event that the TSPEC is rejected or modified when included within a (re)association request. It is suggested that the preferred rule would be to reject the (re)association until a mutually acceptable TSPEC can be identified. |  | Comment declined in the previous letter ballot. It is still not clear why the association request itself should be denied. If the non-AP QSTA can not use the degraded service it can always initiate disassociation. |  |  | Comment declined in the previous letter ballot. It is still not clear why the association request itself should be denied. If the non-AP QSTA can not use the degraded service it can always initiate disassociation.
68 | Amann, Keith | 9.9.3.2 | T | Y | (Duplicate, Orginally Comment #159 from LB#63) This clause contains text that specifies that the QAP may aggregate admitted HCCA TSPECs for a single non-AP QSTA through the use of the "Aggregation field". Although this type of behavior may be convenient for the scheduling algorithm, this can have an adverse impact on the applications that originally requested the TSPECs as they may have dramatically divergent requirements in terms of TSPEC scheduling. Task Group Response: Comment declined. By definition aggregation means that the aggregated TSPEC would meet individual TSPEC requirements. First, I believe the point of the original comment was missed, sorry. The original concern was over the use of the word "may" in this context. Specifically, by using this word the HC can, at it's discretion, choose to aggregate schedules without this being explicitly requested by the QSTA. The recommended change prevents this behavior, and makes the signalling and requirements for aggregation explicitly under the control of the QSTA. The second concern was over vastly divergent TSPEC requirements, and it is not clear to the commenter how, if at all, the scheduler would be able to meet ALL of the individual TSPEC requirements in one aggregated schedule. For example, if one TSPEC were established for constant bit-rate traffic (i.e. voice), with a 30ms service period requirement, and another TSPEC were dealing with variable bit-rate traffic, what schedule will be produced that can still satisfy the CBR traffic, and the VBR traffic? If the task group believes that this is possible I would be happy with some example showing how that would be made to work. | Remove the sentence "The HC may aggregate admitted HCCA TS for a single non-AP QSTA and establishes a Service Schedule for the non-AP QSTA". I believe this makes it clear that the non-AP QSTA is the controlling entity as far as aggregation is concerned. |  | Comment declined in a previous letter ballot. As indicated in the previous letter ballot resolution all the statement indicates is what the HC may do with a TSPEC. The conditions for aggregation are given elsewhere and will still be adhered to. |  |  | Comment declined in a previous letter ballot. As indicated in the previous letter ballot resolution all the statement indicates is what the HC may do with a TSPEC. The conditions for aggregation are given elsewhere and will still be adhered to.
69 | Moore, Tim | 11.7 | T | Y | There is no definition of what should happen if one of the QSTAs roams to a different QAP after a DLP is setup | There are 2 possiblities I can see: 1. There is an implict Teardown. 2: The QSTAs continue to be able to communicate. Note in this case the DLP cannot be torndown since a Teardown message cannot be sent since the QSTAs are not on the same QAP |  | Comment declined. The comment is out of order as is not based on the changes made from D7.0 to D8.0 |  |  | Comment declined. The comment is out of order as is not based on the changes made from D7.0 to D8.0
70 | Moore, Tim | 11.7 | T | Y | The QAP can reject a DLP by sending a Not allowed in the BSS but there is no SME interface that this messages flows over so the SME can reject the DLP request in the QAP nor is there a MIB variable that can be set to reject DLP requests | Add either a SME interface or a MIB varialbe that specifies whether a DLP request is rejected by the QAP |  | Comment declined. The comment is out of order as is not based on the changes made from D7.0 to D8.0 |  |  | Comment declined. The comment is out of order as is not based on the changes made from D7.0 to D8.0
71 | Moore, Tim | 11.7 | T | Y | A QSTA can can refuse a DLP request with Refused but this request does not go over a SME interface nor is there a MIB variable to configure this | Add either a SME interface or a MIB varialbe that specifies whether a DLP request is rejected by the QSTA |  | Comment declined. The comment is out of order as is not based on the changes made from D7.0 to D8.0 |  |  | Comment declined. The comment is out of order as is not based on the changes made from D7.0 to D8.0
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148

## Voting Pattern
Name | No. of comments | No. of comments that are part of No Vote | No. of "No" comments accepted | No. of "No" comments countered | No. of "No" comments declined | Remarks
Adachi, Tomoko | 3 | 0
Amann, Keith | 2 | 0
Barber, Simon |  | 0
Barr, John | 0 | 0
Benveniste, Mathilde | 5 | 0
Black, Simon |  | 0
Buttar, Alistair | 8 | 0
Bray, Jennifer | 10 |  |  |  |  | Not in the voting pool
Brennan, Jim |  | 0
Cam-Winget, Nancy | 0 | 0
Chaplin, Clint |  | 0
Chen, Hungkun |  | 0
Chesson, Greg |  | 0
Chintz, Leigh |  | 0
Choi, Sunghyun | 0 | 0
Clements, Ken | 0 | 0
Cole, Terry | 0 | 0
Conkling, Craig |  | 0
Cooklev, Tudor |  | 0
del Prado, Javier | 0 | 0
Dickman, Georg |  | 0
Dutkiewicz, Eryk | 0 | 0
Eastlake, Donald | 0 | 0
Ecclesine, Peter | 0 | 0
Euscher, Christoph | 0 | 0
Falk, Lars |  | 0
Fischer, Matthew | 0 | 0
Fujisawa, Ken |  | 0
Green, Patrick |  | 0
Haisch, Fred | 0 | 0
Hamady, Neil | 0
Hillman, Garth | 0 | 0
Hinsz, Christopher | 0 | 0
Ho, Jin-Meng |  | 0
Housley, Russell | 2 | 0
Hunter, David | 0 | 0
Inoue, Yasuhiko | 0 | 0
Jalfon, Marc | 0 | 0
Jose, Bobby | 0 | 0
Kaiser, Daryl |  | 0
Kandala, Srinivas | 0 | 0
Karcz, Kevin | 0 | 0
Kitchin, Duncan | 0 | 0
Kleindel, Gunter |  | 0
Kuehnel, Thomas | 18 | 0
Kwak, Joe |  | 0
Lanzl, Colin | 2 | 0
Lefkowitz, Martin |  | 0
Lewis, Mike | 0 | 0
Lim, Wei Lih | 3 | 0
Liu, Shawn |  | 0
Ludeman, Luke |  | 0
Maa, Yeong-Chang |  | 0
Mani, Mahalingam | 1 | 0
McCann, Justin |  | 0
Mehta, Mehul |  | 0
Meyer, Klaus | 0 | 0
Miller, Robert |  | 0
Mishra, Partho |  | 0
Montemurro, Michael |  | 0
Moore, Tim | 3 | 0
Moreton, Mike | 11 | 0
Myles, Andrew | 0 | 0
Nagai, Yukimasa | 0
Negus, Kevin |  | 0
Nelson, David |  | 0
Ngo, Chiu |  | 0
Ni, Qiang | 0 | 0
O'Hara, Bob | 0 | 0
Oakes, Ivan | 0 | 0
Raad, Raad | 0 | 0
Rios, Carlos |  | 0
Sanwalka, Anil |  | 0
Schrum, Sid | 0 | 0
Shen, Yangmin |  | 0
Sherman, Matthew | 0 | 0
Skellern, David | 0 | 0
Soomro, Amjad | 1 | 0
Spiess, Gary | 0 | 0
Stephens, Adrian | 0 | 0
Takagi, Masahiro | 2 | 0
Tan, Pek-Yew | 0 | 0
Teague, Roger |  | 0
Tsai, Allen |  | 0
Tsien, Chih | 0
Tsoulogiannis, Tom |  | 0
van Leeuwen, Richard | 0 | 0
Ware, Chris | 0 | 0
Wentink, Menzo |  | 0
Worstell, Harry |  | 0
Wright, Charles | 0 | 0
Total Comments | 71
Number of Commentors | 14
Number of Technical Comments | 56
Number of Comments that are part of a No vote | 27
Number of Editorial Comments | 14
Number of comments labelled as E or T | 1

## Rev_History
Revision | Changes
r0 | Comments received

## Progress
2026-07-29
Number of Comments addressed | 56
Number of "Technical" comments resolved | #REF!
Number of "Technical Required" comments resolved | 0
Number of "Technical" comments resolved by an ad hoc group and awaiting TG's approval | 0
Number of "Editorial" comments resolved | #REF!
As of 7/29/y
Number of comments accepted (marked with "A" in Comment accepted/declined/other resolution) | 0
Number of comments partially accepted (marked with "PA" in Comment accepted/declined/other resolution) | 0
Number of comments for which an alternate resolution has been made/proposed (marked with "O" in Comment accepted/declined/other resolution) | 0
Number of comments withdrawn (marked with "W" in Comment accepted/declined/other resolution) | 0
Number of comments declined | 0
Total | 0
Number of comments for which all issues are resolved (in the editor's opinion - marked with "C" in Status column) | 0
Number of comments that are resubmitted back to the TG for further consideration (marked with "R" in Status column) | 0
Number of comments that may be rediscussed and thus the editor has not yet taken any action (marked with "P" in Status column) | 0
Number of comments for which action is needed either by the editor or another Tg member (in terms of providing text/figures etc. - marked with "I" in Status column) | 0
Total | 0
Number of comments that have been incorporated into the draft | 0