## LB68
Name | Comment Number | Vote | Clause | Type of Comment | Part of No Vote | Comment | Proposed Change | Resolution | Accept/ Reject/ Counter | Comment Recirculated? (Y/N/NA) (for ballot resolution use only) | Editor's tally of completed actions
Andrew Myles | 1 | N | 11.1.3 | E | N | The second sentence needs rewriting to allow correct parsing | One possible rewording might be, "A STA receiving an MLME-SCAN.request shall return a ResultCode of NOT_SUPPORTED to a request for an active scan if regulatory domain information indicates an active scan is illegal." | Current text is correct, because NOT_SUPPORTED can be a valid response for multiple reasons | Reject | NA | done
Andrew Myles | 2 | N | 11.1.3 | E | N | The last sentence needs rewriting to allow correct parsing | One possible rewording might be, "A STA receiving an MLME-START.request shall return a ResultCode of NOT_SUPPORTED to the request if regulatory domain information indicates starting the BSS is illegal." | Current text is correct, because NOT_SUPPORTED can be a valid response for multiple reasons | Reject | NA | done
Andrew Myles | 3 | N | 17.1 | E | N | The text, ", the Regulatory Classes annex" is unnecessary. | Remove indicated text | Text is necessary to provide context | Reject | NA | done
Andrew Myles | 4 | N | 17.1 | T | Y | The first paragraph of the base standard mentions FCC regulations. I802.11j should make the effort to clean up Cause 17 by extracting all regulatory specifications and placing them into a single regulatory annex | Make indicated change in 17.1 and any other clause containing regulatory references | Current draft already does this. Comment is repeated from LB66. | Reject | NA | done
Peter Ecclesine | 5 | Y | 17.3.10.1 | E | N | Table 97 has erroneous values for some 10 MHz settings of modulation and coding rate | Provide correct values | Editorial error - correct typo to reflect values from 04-42r5 | Accept | NA | done
Gunnar Nitsche | 6 | Y | 17.3.10.1 | E | N | Table 97: The sensitivity for 10 MHz column is incorrect (copy/paste error?) | Sensitivity for 10 MHz should be sensitivity for 20 MHz - 3 dB | Same as Comment 5 | Accept | NA | done
Jung Yee | 7 | N | 17.3.10.1 | E | Y | Table 97 Minimum sensitivity for 10 MHz channel spacing is not correct | Add the following for 10 MHz minimum sensitivity ( BPSK r=1/2, -85dBm; BPSK r=3/4, -84dBm; QPSK r=1/2, -82dBm; QPSK r=3/4, -80dBm; 16QAM r=1/2, -77dBm; 16QAM r=3/4, -73dBm; 64QAM r=2/3, -69dBm; 64QAM r=3/4, -68dBm) | Same as Comment 5 | Accept | NA | done
Andrew Myles | 8 | N | 17.3.10.1 | E | Y | The 10MHz sensitivity column is incorrect for all but the first row | Propose reasonable sensitivities. | Same as Comment 5 | Accept | NA | done
Gunnar Nitsche | 9 | Y | 17.3.10.5 | E | N | Since the sensitivities for 10 and 20 MHz are different, the CCA sensitivities (values in brackets) should also be different. | (-82 dBm for 20 MHz, -85 dBm for 10 MHz channel spacing) ... (-62 dBm for 20 MHz, -65 dBm for 10 MHz channel spacing) | Editorial error - correct to be consistent with resolution of comment 5 | Accept | NA | done
Jung Yee | 10 | N | 17.3.10.5 | E | Y | -82dBm CCA threshold for 10 MHz channels causes missed detection | Change the value to -85dBm | Same as comment 9 | Accept | NA | done
Andrew Myles | 11 | N | 17.3.10.5 | E | Y | CCA uses a minimum power level of -82dBm, which corresponds to the minimum sensitivity for 20MHz channels at 6Mb/s. However, the minimum sensitivity for 10MHz channels is -85dBm. | Should the CCA definition change for 10MHz channels? | Same as comment 9 | Accept | NA | done
Peter Ecclesine | 12 | Y | 17.3.2.2 | E | N | both clause heading and Table 84 heading refer to rate-dependent, but are now driven by Modulation and Coding rate | Change clause heading and Table 84 heading to refer to Modulation-dependent parameters | Make recommended change for clarity given current text | Accept | NA | done
Jung Yee | 13 | N | 17.3.2.4 | E | Y | tsignal and tDATA values are referring to 20 MHz channelization | Add a qualifier that this example applies only to 20 MHz channelization | Editorial comment - will add clarifying text | Accept | NA | done
Jung Yee | 14 | N | 17.3.3 | E | Y | Figure 110 applies only to 20 MHz channelization | Either delete the figure or add a qualifier that this applies only to 20 MHz channels | Editorial comment - will add clarifying remarks to text prior to Figure 114 | Counter | NA | done
Peter Ecclesine | 15 | Y | 17.3.8.6 | E | N | Table 17.3.8.6 Coverage Class values should be extended to indicate 93 us aAirPropagationTime in increments of 3 us to cover Japanese operations | Extend Coverage Classes to 31, marking 8-255 as reserved | Add additional coverage class parameters as a reference | Accept | NA | done
Jung Yee | 16 | N | 17.3.8.6 | T | Y | aSlotTime for 10 MHz channel and coverage class 0 is 17us, assuming 1us AirPropagation time | Change 16 us to 17 us for coverage class 0 of 10 MHz channel | Has been addressed already in Mar04 plenary and 04-42r5. Add additional clarifying test only for 10MHz operation and AirPropagation time. | Reject | NA | done
Andrew Myles | 17 | N | 17.3.8.6 | T | Y | Table 17.3.8.6 specifies aSlotTime of 16us for 10MHz channels and Coverage Class = 0 Given the values in Table 99 and the formula in 9.2.10 the aSlotTime should be 1 + 8 + 4 + 4 = 17us. However, I also believe the values in Table 99 are incorrect (see another comment) and the correct value is 1 + 8 + 2 + 2 = 13us. I also note that all the other SlotTimes for 10Hz channels are similarly incorrect. I believe they should be: * CC = 0; 13us * CC = 1; 15us * CC = 2; 18us ... * CC = 7; 33us | Rethink the SlotTimes for 10MHz channels | Addressed in comment 16 | Reject | NA | done
Andrew Myles | 18 | N | 17.3.8.6 | T | Y | Table 17.3.8.6 specifies aSlotTimes for 20MHz channels and Coverage Class = 1-7 Given the values in Table 99 and the formula in 9.2.10 the aSlotTimes are incorrect. I believe they should be: * CC = 1; 11us * CC = 2; 14us ... * CC = 7; 29us | Rethink the SlotTimes for 20MHz channels | Addressed in comment 16 | Reject | NA | done
Andrew Myles | 19 | N | 17.3.8.6 | T | Y | The text says the slot time, "... shall be 9 µs for 20 MHz channel spacing, which is the sum of the RX-to- TX turnaround time, MAC processing delay, and CCA detect time …" This definition of slot time is incorrect because it does not include propagation delay as specified in 9.2.9. Various comments can be made about slot times and propagation delays: * Various PHYs are very inconsistent in their dealing with propagation delay. * The slot time definition in 17.3.8.6 of the base standard is internally inconsistent, effectively saying 8=9! * Propagation delay is defined incorrectly in the base standard as a single trip rather than a round trip | Include the propagation delay in the textual definition of slot time. Define propagation delay properly (in 10.4.3.2) as the maximum round time propagation time between STAs at the furthermost points of a BSS. Define the propagation delay for 802.11a as 1us, and not <<1us, to make the 802.11a usage consistent with the other PHYs. | Addressed in comment 16 | Reject | NA | done
Bobby Jose | 20 | N | 17.3.8.6 | T | Y | There is no need to change the definition of aSlotTime which is: aCCATime + aRxTxTurnaroundTime + aAirPropagationTime +_ + aMACProcessingDelay, Note for channel contention we just need one aAirPropagationTime ( one way delay), (Note for ACKTimeout we do need two aAirPropagationTime you only need to change that definition and leave aSlotTime intact). Thanks for providing the rational in the comment response to LB 66. "For channel contention, slot time must include two way air propagation time because slot times are synchronized to what is received locally only". This is not correct.. Consider that both STA and AP in a BSS operate with maximum transmit allowed for that coverage class, synchronization is among STA that can hear each other, (not hidden terminal), and for this the aAirPropagationTime need be one worst case propagation delay defined for that class, as defined in Table 21, why have one more table ? | Delete "which is the sum of RX_toTX turn arround time, MAC processing delay, and CCA detect time". Update the table with proper values or delete it. | Delete unnecessary text, other changes not necessary | Counter | NA | done
Bobby Jose | 21 | N | 17.3.8.6 | T | Y | it is a basic 802.11 requirement to support overlaping BSS in the same channel. These overlapping BSS could belong to different coverage class, and are required to operating using shot times that are not a multiple of each other. if proper solution to this problem is outside the current plan of Tgj then consider using only slot times that are a multiple of the base slot time (used by coverage class 0). For exampe coverage class 1 should have slot time of 18us and coverage class 2 a slot time of 27 us for the 20Mhz spacing. (Coverage class 2 has an air propagation time of 19us ?). | Solve the problem of overlapping BSS using different coverage classes. | Previously commented and rejected in 04-42r5. Current text better addresses overlapping BSS problem | Reject | NA | done
Jung Yee | 22 | N | 17.4.4 | T | Y | aSlotTime value for 10 MHz channels incorrect | Change 16us to 17us | 16us is correct, because air propagation time (as shown in table 99) is << 1us | Reject | NA | done
Andrew Myles | 23 | N | 17.4.4 | T | Y | The aRxTxTurnaroundTime for 20MHz channels is specified as <2us and for 10MHz channels is specified as <4us There appears to be no connection between channel width and turn around time | Either change the aRxTxTurnaroundTime for 10MHz channels to <2us or justify <4us | Editorial change - add clarifying text in introduction to 17.1 | Counter | NA | done
Andrew Myles | 24 | N | 17.4.4 | T | Y | The aMACProcessingDelay for 20MHz channels is specified as <2us and for 10MHz channels is specified as <4us There appears to be no connection between channel width and MAC processing time | Either change the aMACProcessingDelay for 10MHz channels to <2us or justify <4us | Editorial change - add clarifying text to justify < 4us | Accept | NA | done
Andrew Myles | 25 | N | 7.3.2.9 | E | N | The text says, "If the field does not have a positive integer value greater than 200 …" This text contains the number equivilent of a double negative. | This sentence could be better worded as, "If the field has a positive integer value less than 201 …" | Add recommended clarifying text | Accept | NA | done
Andrew Myles | 26 | N | 7.3.2.9 | E | N | In the second paragraph a "subband triplet" is defined. The paragraph also introduces the idea of a regulatory triplet However, "regulatory triplet" is not defined until the seventh paragraph | Define the term "regulatory triplet" as the same place the concept is introduced, i.e. in the second paragraph Alternative editorial solutions are also possible | Add recommended clarifying text | Accept | NA | done
Andrew Myles | 27 | N | 7.3.2.9 | E | N | The text says, "… within consecutive subband triplets." The text would read better as, "in consecutive subband triplets." | Make indicated change | Add recommended clarifying text | Accept | NA | done
Andrew Myles | 28 | N | 7.3.2.9 | E | N | The text uses "sub-element" "sub-element" is not a term that is ever used in the base standard or defined in the 802.11j draft | Remove "sub-element" | Remove the term "sub-element" only | Accept | NA | done
Andrew Myles | 29 | N | 7.3.2.9 | E | N | The text speaks of the, "… the regulatory and subband information specifying the beacon …" This does not makes sense because the information is the regulator and subband triplets do not "specify the beacon". | It appears that it is really attempting to say, " … the regulatory and subband triplets specifying information relevant to the channel in the which the Beacon is being transmitted…". Improve the language roughly along the lines indicated | Adopted proposed text as superior | Accept | NA | done
Andrew Myles | 30 | N | 7.3.2.9 | T | Y | The paragraph specifying the order of regulatory and subband triplets is almost impossible to parse in its current form, and so is not reviewable | Rewrite the paragraph as an ordered list | Current text considered best option given IEEE style guide requirements and complexity of specification | Reject | NA | done
Andrew Myles | 31 | N | 7.3.2.9.1 | T | Y | The text specifies that the Regulatory Class is an index into a set of values. The text then specifies the particular parameters. This set of parameters is too restrictive because some parameters may not be required in a particular regulatory domain and extra parameters may be required in other regulatory domains. | Change the text so that the set of paramaters specified for a regulatory domain are specific to the domain. My specific suggestions are: * Move the list of paramaters to the annex, making them domain specific * Move the general description of Regulatory Class field to 7.3.2.9 * Delete 7.3.2.9.1 If this change is accepted then: * 7.3.2.9.2 should also be incorporated into 7.3.2.9 * 7.3.2.9.2 should be deleted | Editorial change - clarifying text already exists in J.2.1, will move class field descriptions back to 7.3.2.9.1 for clarity and delete redundant radio equipment sets of rules descriptions | Counter | NA | done
Peter Ecclesine | 32 | Y | 7.3.2.9.2 | E | N | Table 21 - Coverage Class values should be extended to indicate 93 us aAirPropagationTime in increments of 3 us to cover Japanese operations | Extend Coverage Classes to 31, marking 8-255 as reserved | Add additional coverage class parameters as a reference | Accept | NA | done
Andrew Myles | 33 | N | 7.3.2.9.2 | T | Y | The text states that the aAirPropagation time for CoverageClass 0 is "<= 1" However, if CoverageClass 0 is intended to be equivilent to legacy then the aAirPropagation time for CoverageClass 0 should be "<< 1" | Change the aAirPropagation time for CoverageClass 0 to "<< 1" Alterntively, accept one of my other comments to make it "1" | Existing text is appropriate for legacy compatibility | Reject | NA | done
Andrew Myles | 34 | N | 7.3.2.9.2 | E | N | There are no values specified for CoverClasses 8-255 Are these values not allowed or are they reserved for future use? | Clarify and make appropriate changes to the text | Note values are reserved | Accept | NA | done
Andrew Myles | 35 | N | 7.3.2.9.2 | T | Y | Table 21 indicates that aAirPropagationTime = 3us is equivilent to a BSS radius of 0.45km However, slot synchronisation for STAs on opposite sides of the BSS requires the aAirPropagationTime to incorporate a round trip, which means aAirPropagationTime = 3us is equivilent to a BSS radius of 3us (aAirPropagationTime) * 0.5 (to convert diameter to radius) * 0.5 (to convert round trip to single trip) * 3 * 10^8 m/s (speed of light) = 0.225km Similar problems apply to all radii | Either halve the radii or increase the aAirPropagationTime's | Addressed in comment 16 | Reject | NA | done
Bobby Jose | 36 | N | 7.3.2.9.2 | T | Y | Coverage Class is defined based on the maximum range supported to an associated STA. Therefore all the stations of the BSS belong to the same coverage class. However it is a basic 802.11 requirement to support overlaping BSS in the same channel. What happens in cases of overlapping BSS belonging to different coverage classes, don't stations that belong to different coverage classes (and can hear each other) use different aSlotTimes? The recomendation to use dynamic aSlotTime would cause significant degradation in performance in certain conditions. The base standard has been used to successfully support products with a wide range of coverage using the basic aSlotTime which is a simple solution the relation to aAirPropagationTime is specified. Note that FCC transmit powers used by current 11b/g solutions operating using base standard at (36 dBm EIRP PMP rules, 42dbm+ EIRP is common under other FCC rules) , are larger than limits specified in J.3.2. What is special about 11j/japanese regulations that requires the coverage class?. The resolution to my comment in previous LB was that a proper soution is beyond the scope of 11j - well, then lets not provide a partial solution. It is my opinion that the coverage class concept is incomplete, introduces more problems that it solves. | remove Section 7.3.2.9.2 and coverage class related text or propose an alternative which will solve the MAC layer issues. | Slot time must be changed to accommodate larger BSS. Overlapping BSS'es are a minimal issue as 11j intended for planned, licensed indoor and outdoor networks. | Reject | NA | done
Bobby Jose | 37 | N | 9.2.8 | T | Y | The ACKTimeout is related to the aAirPropagationTime. The relationship of ACKTimeout to aAirPropagation is specified through the definition of aSlotTime. However for ACKTimeout needs to be proportional to twice airpropagation time, so considering add one aSlotTime to the current ACKTimeout as aAirPropagationTime is defined as one way propagation | If coverage class remains in the draft, then Include two air propagation delays in the defintion of ACKTimeout and CTSTimeout. | Addressed in comment 16 | Reject | NA | done
Andrew Myles | 38 | N | Annex A | T | N | I hope someone has read this stuff; I haven't and will not until the basic text is pinned down | None | Annex has been reviewed by group | Reject | NA | done
Andrew Myles | 39 | N | Annex D | T | N | I hope someone has read this stuff; I haven't and will not until the basic text is pinned down | None | Annex has been reviewed by group | Reject | NA | done
Terry Cole | 40 | Y | General | E | N | You will need to include 802.11i in your base document designation. | Your editor will have to enter all relevant text effected by 802.11i prior to publication. Any technical issues arising would require errata from TGj. Please review any issue now! | Draft has been reviewed and no issues found | Accept | NA | done
Terry Cole | 41 | Y | General | E | N | In Clause 17, we often use the instrucitons to delete a column and add two. It leaves open the possibility that we changed the mateiral in the existing column. I do not think this is the case. | The material may be better represented by instructions to relable the existing second column and add a third column as shown. The added words would be udnerlines in the new second column title, and all words underlines in the new third column. | Current format better as it is better if this is further extended | Reject | NA | done
Andrew Myles | 42 | N | General | T | Y | I strongly object to the use of 15 day letter ballots because they do not provide sufficent time to schedule a proper review of the document, which has changed substantially changed between D1.3 and D1.4 | Don't do it again! ;) | WG rules note 15 day recirc; Please note that sponsor recirc's are 10 days | Reject | NA | done
Andrew Myles | 43 | N | J.1 | E | Y | The last sentence in the first paragraph repeats information in the first sentence. | Remove the last sentence in the first paragraph | Remove redundant text | Accept | NA | done
Andrew Myles | 44 | N | J.1 | T | Y | It is unclear to what the note under Table J.1 refers | Clarify and make appropriate changes | Add clarifying text to note "in Japan" | Accept | NA | done
Yasuhiko Inoue | 45 | Y | J.2 | E | N | In the Tables J.2.1, J.2.2 and J.2.3, Emission limits set and Behavior limits set are expressed in integer valus, and the meaning of the values are described in the text. It will be preferred if there are tables (for Emission limits set and Behavior limits set) summarizing the meaning of each value. Those tables will also be useful for future revisions. | add tables for Emission limits set and Behavior limits set in J.2. | Add tables for reference | Accept | NA | done
Peter Ecclesine | 46 | Y | J.2.1 | E | N | Behavior Limits Set for Japan does not include 4 ms Carrier Sense Rule | Add a sixth behavior for Carrier Sense, and mark it required for all Japan Regulatory classes in Table J.2.3. Remove J.3.4 | Replace J.3.4 with recommended text | Accept | NA | done
Terry Cole | 47 | Y | J.2.1 | E | N | The text of J.2.1 seems to be a long list of stand-alone sentences. It might benefit from arrangment into paragraphs or from adding sub-headings. | Consdier the two options and choose one. | Replace standalone text with tabular text | Accept | NA | done
Andrew Myles | 48 | N | J.2.1 | E | Y | The text is written so that the parameters for all Regulatory Classes are fixed. However, a more general mechanism is to make the parameters a function of the regulatory domain. | Restructure text to make the paramters a function of the regulatory domain. | Per comment 45, creating tabular text indexed to regulatory domain | Counter | NA | done
Andrew Myles | 49 | N | J.2.1 | T | Y | The description of the Channel Starting Frequency limits the values to 4GHz or 5GHz This is an unneccessary restriction because: * these values are never encoded for transmission across the air interface * table J2.1-3 already define the values allowed | Remove the restriction | Restriction based on PAR of TGj | Reject | NA | done
Andrew Myles | 50 | N | J.2.1 | T | Y | The description of the Channel Spacing includes a very strange definition of a 20MHz channel that is not repeated for a 10MHz channel | Remove the strangeness or justify it | Add clarifying text | Counter | NA | done
Andrew Myles | 51 | N | J.2.1 | T | Y | The text description of the Transmit Power Limit includes a specification that the limit is expressed in dBm However, the tables express the power in mW | Remove the text specification | Editorial comment - remove reference to dBm | Accept | NA | done
Andrew Myles | 52 | N | J.3.1 | T | Y | This text merely repeats regulatory information, which is not necessary in the 802.11 standard | Delete J.3.1 | Precedent exists for this information in base standard clause 17, et. al. This text useful as original information in other language. | Reject | NA | done
Peter Ecclesine | 53 | Y | J.3.2 | E | N | Table J.3.2.1 text that is now in the base standard is shown underlined | Remove underlines | Remove underlines | Accept | NA | done
Andrew Myles | 54 | N | J.3.2 | T | Y | This text merely repeats regulatory information, which is already specified elsewhere (J.2.1) | Delete J.3.2 | As in comment 52 | Reject | NA | done
Peter Ecclesine | 55 | Y | J.3.3 | E | N | text that is now in the base standard is shown underlined | Remove underlines | Remove underlines | Accept | NA | done
Terry Cole | 56 | Y | J.3.3 | E | N | One sentence is underlined. This is not correct since it is part of an insert editing instruction. | Remove underlining. | As in comment 55 | Accept | NA | done
Andrew Myles | 57 | N | J.3.3 | T | Y | This text merely repeats regulatory information, which is not necessary in the 802.11 standard | Delete J.3.3 | As in comment 52 | Reject | NA | done
Andrew Myles | 58 | N | J.3.4. | T | Y | This section specifies the carrier sense rule in Japan This text is better placed with the Regulatory Class table for Japan (as another parameter) | Make suggested change | Resolved by resolution to comment 46 | Counter | NA | done
Jennifer Bray | 59 | Y |  | E | N | Given that a STA can support multiple frequency ranges and we now have a unified system for defining channel number ranges, it is not clear that multiple MLME scan requests are required to retrieve the full range of channels supported. A clarifying statement that dot11StartingFrequency can be used to switch between ranges would be useful. (I have classed this as an editorial comment because I believe the information can be deduced from the current standard, so this is just a minor clarification not a technical change). | At the end of 17.3.8.3.2 Channel numbering add the following: "An SME managing multiple channel sets can change the channel set being managed by changing the value of dot11StartingFrequency." | Make recommend clarifying text | Accept | NA | done