## Sheet1
ID | Source | Citation | 802.11 Ref | Assessment | Recommendation | Status | Assigned | Text written | Text approved | Text in draft | Draft Approved
1 | 03-382r0 | Page 3, left | 5.4.2.2 | Beyond PAR of 802.11m project because it would be defining new functionality | Consider for future work and PARs. 802.11 WGTE to include in a database, if desired. | Closed |  | n/a
2 | 03-382r0 | Page 3 right, bullet 1 & 2 | 5.5 | Technically correct -- possible wording changes might improve text | Change text to "Data frames in an IBSS with frame control (FC) bits To DS and From DS both false." | Editor | Brian Mathews | yes | yes 5/11/04
3 | 03-382r0 | Page 3 right, bullet 2 | 5.5 | Incorrect conclusion because bits are subject to rules in section 7. Imroved wording may be warranted. | change of ID 2 recommendation also corrects this. | Same as Item #2 | n/a | n/a | n/a | n/a | n/a
4 | 03-382r0 | Page 3 right, bullet 3 | 5.5 | We believe that the statement is not true. Research and editorial Clarification may be warranted. | This is true only in an IBSS. See rx_coord_2b in station SDL code for confirmation. No change required, unless we want to prohibit this behavior. Since authentication and association are both optional in an IBSS | Same as Item #2 | n/a | n/a | n/a | n/a | n/a
5 | 03-382r0 | Page 4 left | 5.5 | Research and editorial Clarification may be warranted. | Remove "Management frame" text, including deauthentication frame from 5.5 c) 2) and move the text "Deauthentication notification when in State 3 implies disassociation as well, changing the STAs state from 3 to 1. The STA shall become authenticated again prior to another association." to 5.5 a) 2) iv). | Editor | n/a | yes | yes 5/11/04
6 | 03-382r0 | Page 4 right | 5.6 | More research is required to determine if association/disassociation is disallowed elsewhere in the document | Association is optional in an IBSS, making state 2 and both class 2 and class 2 frames possible in an IBSS. No text changes required. | Closed | n/a | n/a | n/a | n/a | n/a
7 | 03-382r0 | Page 5 | 5.5 & 5.6 | Same as 6 | Authentication is optional and needs to be described, as it is in the standard. No text changes are required. | Closed | n/a | n/a | n/a | n/a | n/a
8 | Internal Discussion | none | Figure 8 | Text labels incorrect from state 2 to 3. Needs simple fix. | Change "Successful Authentication or Reassociation" to "Successful Association or Reassociation" | Editor | n/a | yes | yes 5/11/04
9 | Internal Discussion | None | 5 | Section 5 largely is descriptive. Review of each may and shall is warranted for section 5. |  | Needs Assignment
10 | 03-382r0 | Page 6 | 6.2.1.2.2 | Further research required. | Leave it to Tge | Needs Assignment | n/a | n/a | n/a | n/a | n/a
11 | 03-382r0 | Page 7 left | 7.2.3.10 | We feel the spec is unambigous. Title of Table 14 will be ammended by adding Element at the end. | Change title of table 14 to "Presence of challenge text information element" | Editor | n/a | yes | yes 5/11/04
12 | Internal Discussion | None | 7.3.2.1, 10.3.2.1.2, 11.1.3 & 11.1.3.2.1 | Clarify the broadcast SSID is actually the wildcard SSID. | adopt document 04/759 | Editor | 2004-05-11 | 2004-07-12 | yes 7/13/2004
13 | 03-382r0 | Page 7 right bullet 1 | 7.3.2 | Correct. Statement should be added in 17 pointing out that this is correct and OK. We should state that the DS IE should not be used for this purpose. Clarification in section 10 needed that you must fill in the PHY paramter set even though it wasn't on air. | Resolve as part of item 71 | Closed | n/a | n/a | n/a | n/a | n/a
13a | 03-382r0 | Page 8 | 7.3.2.6 | A couple of examples, especially any special cases should be developed. | Add two examples in 7.3.2.6. | Jon Rosdahl | 2004-07-13
14 | 03-382r0 | Page 9 left | 8 | Beyond PAR of 802.11m project and is within the scope of PAR for P802.11i |  | Closed | n/a | n/a | n/a | n/a | n/a
15 | 03-382r0 | Page 9 right | 8.1.1.2 | Text should be chagned to match MIB. | Change dot11AuthenticationType to dot11AuthenticationAlgorithm, in two places in 8.2 of 802.11i | Editor | 2004-07-13
16 | 03-382r0 | Page 10 | 8.3.2 | Text in MIB should be brought in line with 8.3.2 | The undecryptable counter must not be incremented, except as described in 8.3.2. There are no other frames that may validly carry the WEP bit set. | Closed | n/a | n/a | n/a | n/a | n/a
17 | 03-382r0 | Page 11 left | 9.1.4 | Research and editorial Clarification may be warranted espeically to align MIB and text. | Change the first sentence of the third paragraph of 9.1.4 to "When a directed MSDU, plus MAC header and FCS, is received from the LLC or a directed MMPDU is received from the MAC sublayer management entity (MLME) with a length greater than dot11FragmentationThreshold, ..." (two changes in this sentence!) Also change all "aFragmentationThreshold" to "dot11FragmentationThreshold"! | Editor | n/a | yes | yes 5/11/04
18 | 03-382r0 | Page 11 right | 9.2.3.3 & 9.2.3.4 | Research and editorial Clarification may be warranted. | needs investigation | Needs Assignment
19 | 03-382r0 | Page 12 left | 9.2.4 | Research and editorial Clarification may be warranted. | Not clear what needs clarification. | Andrew Myles | 2004-05-11
20 | 03-382r0 | Page 12 right | 9.2.5.4 | Research and editorial Clarification may be warranted. Perhaps look more deeply into 802.11a (and also g) | define a PHY dependent variable to replace 2*aslotTime and add to each PHY clause a spec for that variable. | More discussion needed after research.
21 | 03-382r0 | Page 13 left | 9.2.5.4 | Research and editorial Clarification may be warranted. | append to the last sentence of the first paragraph of 9.2.5.4: "for those PHYs that provide a PHY-CCARESET.request primitive." | Editor | n/a | yes | yes 5/11/04
22 | 03-382r0 | Page 13 right | 9.2.5.7 | Clarification and alignment of SDL with text may be warranted. | related to item 20 (needing PHY dependent variable) | Needs Assignment
23 | 03-382r0 | Page 14 left | 9.2.8 | Clarification and alignment of SDL with text may be warranted. | related to item 20 (needing PHY dependent variable) | Needs Assignment
24 | 03-382r0 | Page 14 right | 9.3.2.1 | Research and Clarification is desired. | wait until Tge completes | Needs Assignment | n/a | n/a | n/a | n/a | n/a
25 | 03-382r0 | Page 15 | 9.3.2.2 | SDL and text need alignment. | wait until Tge completes | Needs Assignment | n/a | n/a | n/a | n/a | n/a
26 | Internal Discussion | none | 9.3.2.2 | The special exception for timing of PCF beacon is 9.3.3.2 should be tied to the normal situations. | wait until Tge completes | Needs Assignment
27 | 03-382r0 | Page 20 | 10.3.2.1 | Research and editorial Clarification may be warranted. | Replace 11.1.3.2.2 c) with "Send a probe request to the broadcast destination address, with the SSID, and BSSID from the MLME-SCAN.request primitive" | Editor (modified 7/14/2004) | n/a | yes | yes 5/11/04
28 | 03-382r0 | Page 21 left | 11.1.2 | Clarification is warranted. |  | Andrew Myles
29 | 03-382r0 | Page 21 right | 11.1.2 | Research required on how the 4us was derrived and is anything required for OFDM? | should be clarified to reflect the use of symbol timing of some PHYs | Bob
30 | 03-382r0 | Page 22 left | 11.1.2.1 | Research and editorial Clarification may be warranted. | Change "aBeaconPeriod" to "dot11BeaconPeriod" and delete the word "basic" before "medium access". | Editor | n/a | yes | yes 5/13/04
31 | 03-382r0 | Page 22 right | 11.1.2.1 | Research and editorial Clarification may be warranted. | Delete "If the medium is determined by the CS mechanism (see 9.2.1) to be unavailable,unavailable, the AP shall delay the actual transmission of a beacon" and combine the remainder of that sentence with the previous sentence. | Editor
32 | 03-382r0 | Page 23 left | 11.1.2.2 | Perverse interaction with 11.2.2, where ATIM transmission is not clearly specified | rewrite 11.2.2 to clearly specify the rules for ATIM transmission and make them normative. | Withdrawn by Andrew (closed)
33 | 03-382r0 | Page 23 right | 11.1.3.2.2 | Text seems clear. |  | Closed | n/a | n/a | n/a | n/a | n/a
34 | 03-382r0 | Page 24 left | 11.2.1.1 | Clarification desired but text is accurate. | In the penultimate paragraph of 11.2.1.1, change "To change Power Management modes, a STA shall inform the AP through a successful frame exchange" to "To change Power Management modes, a STA shall inform the AP through a successful Data frame frame exchange". At the end of that same paragraph of 11.2.1.1, add the following text: "The Power Management bit shall not be set in any management frame." | Editor
35 | 03-382r0 | Page 24 right | 11.2.1.5 | Reserarch requried as to what the document specifies in text and/or SDL | Change 9.3.2.1 to describe SIFS timing after Beacon for buffered mcast frames and first data frame or poll following mcasts. Delete "at least" from the second paragraph. | Editor
36 | 03-382r0 | Page 25 left | 11.2.1.6 |  | Looks like it was corrected in the 2003 edition | Closed | n/a | n/a | n/a | n/a | n/a
37 | 03-382r0 | Page 25 right | 11.2.1.6 | Clarification Required to state that no back-off required if only one bit set in TIM. | In 11.2.1.6 b): delete "If more than one bit is set in the TIM," | Editor | n/a | n/a | yes 5/13/04
38 | 03-754r0 |  | 7.3.2.9 | clarification is warranted | Add to 7.3.2.9, at the end of the description of the maximum transmit power level: "As the method of measurement for maximum transmit power level differs by regulatory domain, the value in this field shall be interpreted according to the regulations applicable for the domain identified by the Country String." | Editor | n/a | n/a | yes 5/13/04
39 | Internal Discussion |  | 10 | Missing primitive in Associate sequence |  | Darwin
40 | Internal Discussion |  | Table 4 (7.2.2) | Clarify columns 1 and 2 with respect to RA and TA. |  | Editor | Darwin | yes | yes 1/04 | 11ma draft
41 | Internal Discussion |  | 7.2.2 | Validate BSSID on all receive decisions? | No, validate BSSID only on multicast. In 7.2.2, change "originated in the same BSS" to "originated in the BSS to which the station is joined" | Editor | n/a | n/a | yes 5/13/04
42 | 03-667r0 |  | 6.2.1.3 | Discuss TGe changes to the primitives | Rename unitdata-status.indication to be unitdata.confirm and keep all status values, both synchronous and asynchronous. There is no support in X.210 for separation of synchronous and asynchronous status. | Needs Assignment
43 | Internal Discussion |  | 11.2.1.6 | AP might discard frames before a STA would wake and request them | In 11.2.1.6 a), change "after" to "before". | Editor | n/a | n/a | yes 9/13/04
44 | 03-382r0 | page 26 left | 11.2.1.6 | PS-Poll priority is not stated in the standard. Text seems clear and describes intended operation where first PS-Poll is sent immediately (after random (0,Cwmin) backoff) and subsequent PS-Polls are sent at discretion of STA. |  | Closed | n/a | n/a | n/a | n/a | n/a
45 | 03-382r0 | page 26 right | 11.2.2 | IBSS power save operation could be clarified with a few notes | Add the following at the end of the first paragraph of 11.2.2.1: "To maintain correct information on the power save state of other stations in an IBSS, a station needs to remain awake. If a station changes to the PS mode, it needs to assume that all other stations are in the PS mode also." | Editor
46 | 03-382r0 | page 27 left | 11.2.2.1 | clarification is warranted | see #45 | Closed | n/a | n/a | n/a | n/a | n/a
47 | 03-382r0 | page 27 right | 11.2.2.1 | compare to SDL and clarify | Research of the original draft from 802.11/d5.0 and 802.11/d5.1 shows that aCWminx is a typo from an improper replacement of aCWmax. In 11.2.2.1, replace "aCWminx" with "aCWmin". | Editor | n/a | n/a | yes 5/13/04
48 | 03-382r0 | page 28 left | 11.2.2.2 | clarification is warranted | In 11.2.2.2, replace "BeaconInterval" with "dot11BeaconPeriod" and append "where ATIMWindow is the value of the ATIM Window parameter of the IBSSParameter Set from the MLME-Start.request or MLME-JOIN.request primitive." | Editor | n/a | n/a | yes 5/13/04
49 | 03-382r0 | page 29 left | 12.3.5.11.3 | clarification is warranted | In 12.3.5.11.3, delete "error check (HEC) CRC" | Editor | n/a | n/a | yes 5/13/04
50 | 03-382r0 | page 30 | 17.4.4 table 99 | clarification is warranted | Change value of aPreambleLength from 20us to 16us in the table. | Editor
51 | 03-382r0 | page 31 | table G.1 | determine if statement is correct and clarify if needed |  | Needs Assignment
52 | 03-382r0 | page 32 | table g.14 | research and clarify if needed |  | Needs Assignment
53 | 03-199r0 | row 2 | 7.1.3.3.2 | clarification is warranted | Delete "in the DA field" from 7.1.3.3.2 b) 2). | Editor
54 | 03-199r0 | row 3 | 8 | research whether to include a warning on the weakness of WEP | left to TGi | Closed | n/a | n/a | n/a | n/a | n/a
55 | 03-199r0 | row 4 | all | out of scope |  | Closed | n/a | n/a | n/a | n/a | n/a
56 | 03-199r0 | row 5 | 17.1 | editorial removal of "all additions" | not in 2003 edition | Closed | n/a | n/a | n/a | n/a | n/a
57 | 03-199r0 | row 6 | 15.1 | clarification is warranted | In the second sentence, delete "initially" and from "as provided" to the end of the sentence. | Editor
58 | 03-199r0 | row 7 | G.3.1 | correct equation | In the equation below Table G.3, change "1<=k<=160" to "1<=k<=159" | Editor | n/a | n/a | 2004-09-13
59 | 03-199r0 | row 7 | G.4.5 | correct equation | In the equation G.4.5, change "1<=k<=80" to "1<=k<=79" | Editor | n/a | n/a | 2004-09-13
60 | 03-199r0 | row 8 | 15.4.7.9 | correct equation | Have Carl Andren explain this | Needs Assignment
61 | 03-199r0 | row 9 | various | Handled in the individual documents |  | closed
62 | 03-199r0 | row 10 | 9.3 | STA-STA traffic in BSS needs clarification/correction | In the first paragraph of 9.3 change "a CF-Pollable STA may transmit only one MPDU, which can be to any destination (not just to the PC)," to "a CF-Pollable STA may transmit only one MPDU, which shall be sent to the PC but may have any destination," | Editor
63 | 03-199r0 | row 11 | C | "getElem" function correction |  | Needs Assignment
64 | 03-199r0 | row 12 | C | Handled in the individual documents |  | Needs Assignment
65 | 03-199r0 | row 13 | 12 | service primitives are not conformance items, but abstract definitions |  | Closed
66 | 03-199r0 | row 14 | 10.3.4 and D | clarification is warranted | Leave the definition as it is. It is clear for the function it describes. | Closed
67 | 03-199r0 | row 15 | 9.4 | clarification is warranted | Insert the following as the first sentence of the second paragraph: "A fragment is an MPDU, the payload of which carries all or a portion of an MSDU or MMPDU." Also replace "fragment MPDU" with "fragment" wherever it occurs. | editor
68 | 03-199r0 | row 16 | various | correction required | Replace the "a" prefix with "dot11" before LongRetryLimit in 6.2.1.3.2 b), 9.2.4, and 9.2.5.3. Also before MaxTransmitMSDULifetime in 6.2.1.3.2 h) and 9.4 (twice). Also before FragmentationThreshold in 9.1.4 (four times) and 9.4 (three times). | Editor
69 | 03-199r0 | row 17 | various | investigate and clarify if needed | there is differentiation between MIB attributes (prefixed with "dot11") and parameters that are defined in one layer and used in another, e.g. slot time duration, (prefixed with "a") and also to parameters in service primitives (that have no prefix). We believe this is sufficient for the purposes of the standard. | Closed
70 | 03-199r0 | row 18 | C | correct variable naming | Change "dot11MultiDomainOperationImplemented" to dot11MultiDomainCapabilityImplemented" on page sta_Start_Ibss_3d(8) and 3201_d\StationConfig(5) and 14.8.2.20 | Editor
71 | 02-092r0 |  | 10.3.2.2.2 | clarify what to do when returning BSSDescription Set for PHYs without a parameter set in the frame. | send back channel number stuff was received on | Simon Black | 2004-07-13
72 | 02-091r0 | item 1 | 14.8.2.20 | change MIB attribute name | change "operation" to "capability" | Closed (see item 70)
73 | 02-091r0 | item 2 | C | change MIB attribute name | change "operation" to "capability" | Closed (see item 70)
74 | 02-091r0 | item 3 | C | change "integer" back to "TU" | on page 3201_d\StationConfig(5), change "dot11AuthenticationResponseTimeout Integer nodelay;" to "dot11AuthenticationResponseTimeout TU nodelay;" | Editor |  |  | yes, 9/15/04
75 | 02-091r0 | item 4 | C | change "true" to "false" | In 14.8.2.20, change "dot11MultiDomainOperationImplemented" to dot11MultiDomainCapabilityImplemented" and on page 3201_d\StationConfig(5), change "dot11MultiDomainOperationImplemented Boolean = true" to "dot11MultiDomainCapabilityImplemented Boolean = false" | Editor |  |  | yes, 9/15/04
76 | 02-091r0 | item 5 | C | delete second definition | not found in current editors roll up | Closed
77 | Internal Discussion |  | C | "yBytp" should be "yBtyp" | On pages sta_Start_Ibss_3d(8) and ap_Start_Bss_2c(3), replace "yBytp" with "yBtp" in the decision symbol. | Editor |  |  | yes, 9/15/04
78 | Internal Discussion |  | C | on same page as 77, change multidomainoperation to multidomaincpability |  | Closed (see item 70)
79 | 02-091r0 | item 6 | C | described operation is as intended, IBSS of 802.11d capable device shall not be started without valid information and being enabled |  | Closed
80 | 02-091r0 | item 7 | C | correct "enabled" to be "implemented" | The intent is correct, the implementation is wrong in the SDL | Needs Assignment
81 | 02-091r0 | item 8 | C | no clarification needed |  | Closed
82 | internal discussion |  | C | In AP_Start_Bss_2c, attribute name is incorrect | In AP_Start_Bss_2c, change "operation" to "capability" | Editor |  |  | yes, 9/15/04
83 | 02-091r0 | item 9 | C | described operation is as intended, BSS of 802.11d capable device shall not be started without valid information and being enabled |  | Closed
84 | 02-091r0 | item 10 | D | The MIB attribute was misspelled in the instruction. The document has the correct spelling. | In 11.1.3.4, change dot11RegDomainsSupportEntry to dot11RegDomainsSupportedValue and add the value "Other (0)" to the "INTEGER SYNTAX" line for dot11RegDomainsSupportedValue. | Editor
85 | 02-091r0 | item 11 | D and 11.1.3.4 | needs investigation, looks like description in MIB is incorrect. The values listed in the MIB entry should be in the "value" part of the table. "Other" needs to be added to the enumeration in the value entry. | Insert "and the dot11RegDomainsSupportEntry shall be set to Other" at the end of the sentence beginning "If the dot11MultiDomainCapabilityEnabled attribute is true". See item 84 and 86 for complete resolution. | Editor
86 | 02-091r0 | item 12 | 11.1.3.4 and others | clarification is warranted, what is "adopt" | Use 04/425r1 as a template for modifying 11.1.3.4. | Terry Cole | 2004-07-15
87 | 02-091r0 | item 13 | C | correct cross reference to 7.3.2.12 on page AP_TSF_bss_3 | On page ap_TSF_bss_3c(3), replace "7.3.2.14" with "7.3.2.12" | Needs Assignment
88 | Internal Discussion |  | 7.3.2.x | 802.11d numbered IEs up to 15, but only 12 are in the 2003 edition. Investigate. | All IEs from 802.11d are incorporated into the 2003 edition | Closed
89 | 02-091r0 | item 14 | C | need to add requested information elements to probe response process |  | Needs Assignment
90 | 02-093r0 | item 1 | 7 | no clarification needed |  | Closed
91 | 02093r0 | item 2 | 17.3.8.3.2 | caught by editor in roll-up |  | Closed
92 | SDL bugs | item 1 | C | On sta_join_4, correct "start" to "confirm" | On page sta_join_4, change "MLMEStart.confirm" to "MLMEJoin.confirm" | Editor |  |  | yes, 9/15/04
93 | SDL bugs | item 2 | C | investigate and clarify if needed | investigated and comment is correct. Probe Request seems to be passed to the DS in the AP SDL. | Simon Black | 2004-07-13
94 | SDL bugs | item 3 | C | investigate and clarify if needed |  | Needs Assignment
95 | SDL bugs | item 4 | C | investigate and clarify if needed |  | Needs Assignment
96 | SDL bugs | item 5 | C | investigate and clarify if needed |  | Needs Assignment
97 | SDL bugs | item 6 | C | investigate and clarify if needed |  | Needs Assignment
98 | SDL bugs | item 7 | C | investigate and clarify if needed |  | Needs Assignment
99 | SDL bugs | item 8 | tables 2 and 22 | conflicting STA to STA in BSS | In Table 29, delete the row containing "CF-Poll(no data){+CF-Ack} – Data(dir) – ACK" | Editor
100 | PICS | internal discussion | PICS | "d" PICS is screwy |  | Needs Assignment
101 | Interp req | 04/425r1 | 11.1.4 | adoption of "all parameters" is unclear | Resolve in the same fashion as item 86. | Terry Cole
102 | internal | 04/522r1 | 7.3, 7.2 | addition of vendor-specific IE |  | closed | Bob | yes | yes 5/11/04
103 | Richard P |  | 802.11d | country-independent country code, must be orthogonal to ISO 3166, for use in trains, planes, and ships, etc. | Adopt document 04/982 | Editor |  | yes (04/982) | yes 9/13/04
104 | Peter E | 802.11h MIB | 802.11h | dot11SMTbase3 does not have dot11SpectrumManagementImplemented nor dot11SpectrumManagementRequired |  | Needs Assignment
105 | Peter E | 802.11h MIB | 802.11h | dot11SpectrumManagement is missing from the Compliance Statements optional groups |  | Needs Assignment
106 | TGk | Table 66, clause 15 |  | Column 3 of table has paste error, putting "1, 2 Mbps" in rowas it does not belong | need original source material or 11b expert to provide correct information for column 3 (Carl Andren?) | Needs Assignment
107 |  | internal discussion | 11.2.2 | aATIMwindow should be dot11ATIMwindow |  | Editor | n/a | n/a | yes 5/13/04
108 |  | internal discussion | 10.3.3.1.2, 10.3.3.1.4 | change the "BSSDescription" as a parameter name to remove ambiguity. | In 10.3.3.1.2 and 10.3.3.1.4, change "BSSDescription" in all locations, except the Type column and the first occurrence in the Description column, to "SelectedBSS". | Editor | n/a | n/a | yes 5/13/04
109 |  | internal discussion | 7.3 | need status code for "ListenInterval too large" | Add a row to Table 20, placing the next available value in the "Status Code" column and "Association denied because the ListenInterval is too large" in the "Meaning" column.
110 |  | internal discussion | 802.11-2003 figure 128 | This receive diagram indicates "PHY_TXEND" | Above the two bold arrows at the upper right of this figure, attach PHY_TXEND.request and PHY_TXEND.confirm, respectively. Also, replace "number supplied in the DSSS PHY preamble" with "number supplied in the TXVECTOR" in the second paragraph below the figure.
111 | D | internal discussion | Annex D | the default values for dot11AuthenticationAlgorithmsEnable is incorrect | In the description of dot11AuthenticationAlgorithmsEnable in the MIB, replace "The default value of this attribute shall be 1 for the Open System table entry and 2 for all other table entries." with "The default value of this attribute shall be true when the value of dot11AuthenticationAlgorithm is Open System and false otherwise."
112 |  | internal discussion |  |  | a note that describes the naming convention used ("a", "dot11", and none) to differentiate various objects might be nice to include. Where?