## Official 802.11 WG Timelines
OFFICIAL IEEE 802.11 WORKING GROUP PROJECT TIMELINES - 03/18/06
Document | Type | Activity | Task Group |  | PAR Approved | Initial WG Letter Ballot |  | Recirculation WG LB(s) |  | SB Pool Formed | Initial Sponsor Ballot |  | Recirculation SB(s) |  | Final WG / SEC Approval | RevCom / Standards Board Approval
[6 empty] | Draft | Date | Draft | Date |  | Draft | Date | Draft | Date
IEEE 802.11e | A | MAC Enhancements (QoS) | TGe | Actual | 2000-03-30 | D4.0 | 2002-11-28 | D5.0 | 2003-08-01 | 2004-06-01 | D9.0 | 2004-08-06 | D10.0 | 2004-09-23
[8 empty] | D6.0 | 2003-12-04 |  |  |  | D11.0 | 2004-10-27
[8 empty] | D7.0 | 2004-01-31 |  |  |  | D12.0 | 2004-12-08
[8 empty] | D8.0 | 2004-02-24 |  |  |  | D13.0 | 2005-02-03
|  |  |  | Predicted | [9 empty] | 2005-04-01 | 2005-07-15 | 2005-09-05
IEEE 802.11k | A | Radio Resource Measurement | TGk | Actual | 2002-12-11 | D1.0 | 2004-08-02
[6 empty] | D2.0 | 2005-02-03
|  |  |  | Predicted |  |  | 2005-05-05 |  | 2005-07-01 | 2005-09-30 |  | 2005-12-01 |  | 2006-01-15 | 2006-03-15 | 2006-06-06
IEEE 802.11REVma | STD | Standard Maintenance | TGm | Actual | 2003-03-20
|  |  |  | Predicted |  |  | 2005-04-01 |  | 2005-06-03 | 2005-07-01 |  | 2005-09-30 |  | TBA | 2006-03-01 | 2006-03-01
IEEE 802.11n | A | High Throughput | TGn | Actual | 2003-09-11
|  |  |  | Predicted |  |  | 2005-07-01 |  | 2005-11-01 | 2006-01-01 |  | 2006-03-01 |  | 2006-07-01 | 2006-11-01 | 2006-12-01
IEEE 802.11p | A | Wireless Access for the Vehicular Environment | TGp | Actual | 2004-09-23
|  |  |  | Predicted |  |  | 2005-05-01 |  | 2005-09-01 | 2005-11-01 |  | 2006-01-01 |  | 2006-03-01 | 2006-07-01 | 2006-09-01
IEEE 802.11r | A | Fast Roaming | TGr | Actual | 2004-05-13
|  |  |  | Predicted |  |  | 2005-07-01 |  | 2005-09-01 | 2005-11-01 |  | 2006-01-01 |  | 2006-03-01 | 2006-07-01 | 2006-09-01
IEEE 802.11s | A | ESS Mesh Networking | TGs | Actual | 2004-05-13
|  |  |  | Predicted |  |  | 2006-07-01 |  | 2006-11-01 | 2007-05-01 |  | 2007-07-15 |  | 2007-09-15 | 2008-03-01 | 2008-06-15
IEEE 802.11.2 | RP | Wireless Performance | TGT | Actual | 2004-08-12
|  |  |  | Predicted |  |  | 2006-01-01 |  | 2006-05-01 | 2007-01-01 |  | 2007-03-01 |  | 2007-09-01 | 2007-11-01 | 2007-12-01
IEEE 802.11u | A | InterWorking with External Networks | TGu | Actual | 2004-12-08
|  |  |  | Predicted |  |  | 2006-03-01 |  | 2006-06-01 | 2006-07-01 |  | 2006-09-01 |  | 2007-05-01 | 2007-07-01 | 2007-09-01
IEEE 802.11v | A | Wireless Network Management | TGv | Actual | 2004-12-08
|  |  |  | Predicted |  |  | 2006-01-01 |  | 2006-04-01 | 2006-11-01 |  | 2007-01-01 |  | 2007-04-01 | 2007-07-01 | 2007-09-01
Timeline Chart Notes:
| A | = Amendment |  |  | RP | = Recommended Practice |  |  |  |  | WG/SEC | = Approval at 802.11 WG / 802 SEC Plenary Session
| Predicted | = Current Date Estimate |  |  | SB | = Sponsor Ballot |  |  |  | RevCom/Stds. |  | = Approval at RevCom / Stds.Board Normal Session
| Date | = Actual or Start Date |  |  | STD | = Standard and/or Revision
| LB | = Letter Ballot |  |  | TG | = Task Group