## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-06/0687r4
Venue Date: | May 2006
First Author: | Naveen Kakani
Subject: | Resolution of comments received during IEEE 802.11 Letter Ballot 84
Full Date: | 2006-05-16
Author(s): | Naveen Kakani
Nokia Inc
6021 Connection Dr, Irving TX 75039
Phone: +1 972 894 6024
email: naveen.kakani@nokia.com
Abstract:
Letter Ballot 84 was a vote to submit the contents of document IEEE 802.11 TGn Draft 1.0 to Sponsor Ballot.
This document contains the comments received during Letter Ballot 84, and their resolutions.
Status of this document: This document should be considered preliminary as the comment list has not been officially verified.
Organisation of this document: The spreadsheet contains multiple tabs along the bottom. The green tabs contains the comments compiled from the commenter responses to LB84. The "Editorial" tab includes unique editorial comments. The "Technical" tab includes unique technical comments.
The yellow tabs contain lookup tables used to help classify comments (preliminary, pending discussion at the May 13th meeting).
Also, see the Revision History tab.
Notice: This document has been prepared to assist IEEE 802.11. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.11.
Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures <http:// ieee802.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <stuart.kerry@philips.com> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.11 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## Revision History
Revision History
Revision | Date | Summary of Changes
r1 | 2006-05-16 | Updated During May 16th Morning session of PSMP Ad-hoc
r2 | 2006-05-16 | Update: May 16th PM2 resolutions
r3 | 2006-05-16 | Update: May 16th EVE resolutions, copied resolutions from column X to resolution section
r4 | 2006-05-16 | Updated the revision No. (from 2 to 4)

## Sheet1
Count of Name of Commenter(Ed) | Type E/HE/T/ST/DT(Ed)
Resn Status | DT | ST | T | (blank) | Grand Total
A | 2 | 3 | 10 |  | 15
D | 11 | 4 | 7 |  | 22
R | 1 |  | 2 |  | 3
T | 1 | 1 | 2 |  | 4
(blank) | 51 | 46 | 106 |  | 203
C | 3 | 3 | 5 |  | 11
W |  |  | 1 |  | 1
Grand Total | 69 | 57 | 133 |  | 259

## PSMP
CID | Name of Commenter(Ed) | Clause Number(C) | Page(C) | Line(C) | Type of Comment T/E(C) | Part of No Vote(Y/N) | Page(Ed) | Line(Ed) | Clause Title(Ed) | Clause(Ed) | Type E/HE/T/ST/DT(Ed) | Duplicate of CID | Resn Status | Assignee | Submission | TGn approval | Comment | Proposed Change | Resolution | Edited in draft | Topic lookup | Topic Group Lookup
4528 | Loc, Peter | 9.9.4 | 25 | 1 | T | Y | 25 | 1 |  | 9.9.4 | DT |  | A |  |  |  | Contradicting statements regarding updating NAV during ULT and DLT periods. | Remove the part in red : During DLT and ULT periods the NAV value continues to count down and it cannot be reset or suspended. Additionally NAV updates may occur due to the reception of other frames not directed toward the receiving STA during the DLT and ULT periods. | Accept - The comment is a valid comment and the proposed solution: Delete the text "and it cannot be reset or suspended" from line 27, page 91. The proposed soliution doesn't add any new issues. (OBSS is a known problem). Accpeted - U |  |  |  | Accept - The comment is a valid comment and the proposed solution: Delete the text "and it cannot be reset or suspended" from line 27, page 91. The proposed soliution doesn't add any new issues. (OBSS is a known problem). Accpeted - U
6912 | Nanda, Sanjiv | 7.4.7.10 | 76 | 5 | T | N | 76 | 5 |  | 7.4.7.10 | DT |  | R |  |  |  | PSMP is a Management Action frame which may require a STA to respond with frames within DLT2ULT time. STA may be unable to respond with Data frames within this short duration | Add "STA may respond with QoS Null frame in ULT" | Reject the comment. STAs typically respond in SIFS (immediate ACK). In cases where you need to move up the stack (to service multiple queues) the time it takes some time but 16 us should be okay. In cases where it is not possible the current spec does allow the transmission of QoS null frame. |  |  |  | Reject the comment. STAs typically respond in SIFS (immediate ACK). In cases where you need to move up the stack (to service multiple queues) the time it takes some time but 16 us should be okay. In cases where it is not possible the current spec does allow the transmission of QoS null frame.
12218 | Cheng, Hong | 7.4.7.10 | 76 | 5 | T | N | 76 | 5 |  | 7.4.7.10 | DT |  | D |  |  |  | The use of Management Action frame to serve PSMP is unreliable, since some receiver implementation may not respond immediately to a management frame. | Use a control frame to for PSMP. | Straw poll to change: Yes 2 , No 3. Defer - U |  |  |  | Straw poll to change: Yes 2 , No 3. Defer - U
2354 | Ji, Lusheng | 7.4.7.10 | 76 | 13 | T | Y | 76 | 13 |  | 7.4.7.10 | T |  | A |  |  |  | size of each is not given. | State the size (and units) for each | Accept the comment. Instruct the editor to add the size field and if required change the figure to be consistent with the base spec. Accepted - U |  |  |  | Accept the comment. Instruct the editor to add the size field and if required change the figure to be consistent with the base spec. Accepted - U
7816 | SURINENI, SHRAVAN | 7.4.7.10 | 76 | 13 | E/T | Y | 76 | 13 |  | 7.4.7.10 | ST |  | T |  |  |  | Missing entries in table in Figure n28 | Fill in missing entries for name and value | It is better to modify the Figure to a frame format. Transferred to frame format group for consistency. |  |  | Frame Format | It is better to modify the Figure to a frame format. Transferred to frame format group for consistency.
10165 | Zaks, Artur | 7.4.7.10 | 76 | 13 | T |  | 76 | 13 |  | 7.4.7.10 | T |  | T |  |  |  | Define TBD in Figure n28 |  | Transferred to Frame Format group to be consistent with resolution to CID 7816. Transferred - U |  |  | Frame Format | Transferred to Frame Format group to be consistent with resolution to CID 7816. Transferred - U
774 | Durand, Roger | 7.4.7.10 |  |  | T | Y | 76 |  |  | 7.4.7.10 | ST |  | D |  |  |  | missing detail | how is PSMP used in the presence of legacy clients and overlapping RF covergae zones | Defer - Need submission at TGn to describe the behaviour. Defer - U |  |  |  | Defer - Need submission at TGn to describe the behaviour. Defer - U
1211 | Fischer, Matthew | 7.4.7.10 |  |  | T | Y | 76 |  |  | 7.4.7.10 | T |  | D |  |  |  | All of the information fields in this MA frame need to have definitions within 7.3.1 | Move the definitions of all information fields of this MA Frame as new subclauses beneath 7.3.1 and provide definitions for those fields that lack one | Defer - Suggest to make a PSMP element and define in 7.3.1. Defer - U |  |  |  | Defer - Suggest to make a PSMP element and define in 7.3.1. Defer - U
1212 | Fischer, Matthew | 7.4.7.10 |  |  | T | Y | 76 |  |  | 7.4.7.10 | T |  | T |  |  |  | There is a TBD | Replace the TBD with a category ID from ANA | Transferred to Frame Format group to be consistent with resolution to CID 7816. Defer - U |  |  | Frame Format | Transferred to Frame Format group to be consistent with resolution to CID 7816. Defer - U
1213 | Fischer, Matthew | 7.4.7.10 |  |  | T | Y | 76 |  |  | 7.4.7.10 | DT |  | D |  |  |  | DA of PSMP frame should be allowed to be other than BCAST - MCAST should also be allowed. Use of MCAST would allow a STA to avoid having to parse the remainder of the frame to look for its address in the STA INFO. | Change text to allow DA to be either BCAST or MCAST. | Defer - Need more information and possible submission. Defer - U |  |  |  | Defer - Need more information and possible submission. Defer - U
1215 | Fischer, Matthew | 7.4.7.10 | 76 |  | T | Y | 76 |  |  | 7.4.7.10 | ST |  | C |  |  |  | It is noted that the PSMP frame transmission is somehow related to a "Service period" - how clearly defined is this relationship? | Define the relationship between a service period and a set of PSMP and sub-PSMP frames. | C - Modify the text in line 18,19 to "When set to 0 it indicates that there is no PSMP following the current PSMP sequence. - U |  |  |  | C - Modify the text in line 18,19 to "When set to 0 it indicates that there is no PSMP following the current PSMP sequence. - U
3790 | Kandala, Srinivas | 7.4.7.10 |  |  | T | Y | 76 |  |  | 7.4.7.10 | ST |  | A |  |  |  | Define all fields - who is the SA of this frame? AP or anyone else? | Clarify | Accept - Add the following text after line 7 "SA is the source address of the STA that initiates the PSMP frame" |  |  |  | Accept - Add the following text after line 7 "SA is the source address of the STA that initiates the PSMP frame"
7361 | Scarpa, Vincenzo | 7.4.7.10 |  |  | T |  | 76 |  |  | 7.4.7.10 | DT |  | D |  |  |  | "Multicast data is transmitted using PSMP by setting STA_ID in the STA_INFO field to a specific value 0. The ULT startoffset and ULT duration fields of the STA_INFO field shall be set to the Least Significant Bits of the multicast address." Multicast addressing is not adequately served in this draft. | Modify the PSMP format/mechanism. | Defer - Need additional information in the form of submission - U |  |  |  | Defer - Need additional information in the form of submission - U
7593 | Stephens, Adrian | 7.4.7.10 |  |  | T | Y | 76 |  |  | 7.4.7.10 | ST |  | D | Adrian S |  |  | "Multicast data is transmitted using PSMP by setting STA_ID in the STA_INFO field to a specific value 0. The ULT startoffset and ULT duration fields of the STA_INFO field shall be set to the Least Significant Bits of the multicast address." The whole area of multicast is not adequately described or served in this draft. | Modify the PSMP mechanism to achieve reliable multicast. | Defer - Assigned volunteer to bring a submission - U |  |  |  | Defer - Assigned volunteer to bring a submission - U
7594 | Stephens, Adrian | 7.4.7.10 |  |  | T | Y | 76 |  |  | 7.4.7.10 | DT |  | D | Adrian S |  |  | It needs to be stated that only a single STA Info record for a particular STA ID may be present. Failure to do this could significantly complicate the PSMP STA. | Add the following in this subclause: The STA Info fields within a PSMP frame all have distinct STA ID values (i.e. any particular STA ID value may occur at most once). | Defer - The current text has STA ID = 0 to indicate multiple multicast addresses. Need a submission and additional changes as appropriate. - U |  |  |  | Defer - The current text has STA ID = 0 to indicate multiple multicast addresses. Need a submission and additional changes as appropriate. - U
7595 | Stephens, Adrian | 7.4.7.10 |  |  | T | N | 76 |  |  | 7.4.7.10 | ST |  | D | Adrian S |  |  | "The TSIDs set field presents the AP recommendation to the STA containing the TSIDs for which data can be transmitted in the ULT resources. Each bit in this field represents a TSID, where the bit position is equal to TSID - 8. For example bit2 represents TSID=10. If one more bits are set, the AP is recommending that the STA use the ULT for the indicated TSIDs. " This doesn't say how to set this field when delivering TIDs0-7 for unscheduled APSD. | Consider whether it is necessary to modify the definition or interpretation of this field for U-PSMP. | Defer - Need additional information in the form of submission - U |  |  |  | Defer - Need additional information in the form of submission - U
1214 | Fischer, Matthew | 7.4.7.10 | 77 | 1 | T | Y | 77 | 1 |  | 7.4.7.10 | ST |  | C |  |  |  | Is "PSMP exchange" defined anywhere? | Provide a definition for PSMP exchange. | Counter - Change occurance of PSMP Exchange to PSMP Sequence. Edit section 9.12 to be aligned with the terminology used in the rest of the text (PSMP period). Add a definition of PSMP Sequence in the definitions section (3): "A sequence of frames where the first frame is a PSMP frame which is followed by Down Link transmissions and then by uplink transmissions. The schedule of the Downlink and Uplink transmissions is indicated in the PSMP frame" - U |  |  |  | Counter - Change occurance of PSMP Exchange to PSMP Sequence. Edit section 9.12 to be aligned with the terminology used in the rest of the text (PSMP period). Add a definition of PSMP Sequence in the definitions section (3): "A sequence of frames where the first frame is a PSMP frame which is followed by Down Link transmissions and then by uplink transmissions. The schedule of the Downlink and Uplink transmissions is indicated in the PSMP frame" - U
658 | CYPHER, DAVID | 7.4.7.10 | 77 | 3 | T | Y | 77 | 3 |  | 7.4.7.10 | ST |  | C |  |  |  | If the sequence duration field has ten bit then it can represent (2**10)-1 values (i.e. 1023) and if each value is equal to 8 us, then 8 us times 1023 equals 8.148 ms. Why then does the text state 8 ms? | Fix either the text or the value | Counter - The comment and edit the text to indicate the exact value 8.184 ms - U |  |  |  | Counter - The comment and edit the text to indicate the exact value 8.184 ms - U
3793 | Kandala, Srinivas | 7.4.7.10 | 77 | 3 | T | Y | 77 | 3 |  | 7.4.7.10 | T |  | C |  |  |  | From my quick calculation the PSMP Sequence Duration allows a value of up to 8192 microseconds. | Replace 8 ms with 8192 microseconds or 8 Tus. | Counter - Resolution CID 658 - U |  |  |  | Counter - Resolution CID 658 - U
4554 | Lojko, Peter | 7.4.7.10 | 77 | 7 | T | Y | 77 | 7 |  | 7.4.7.10 | ST |  | D | Naveen K |  |  | "IBSS mode of operation" for PSMP is not defined | Define it some where | Defer - Need submission at TGn to describe the behaviour. Defer - U |  |  |  | Defer - Need submission at TGn to describe the behaviour. Defer - U
3591 | Kakani, Naveen | 7.4.7.10 | 77 | 9 | T | Y | 77 | 9 |  | 7.4.7.10 | T |  | D | Adrian S, Naveen K |  |  | Separate Broadcast and Multicast transmissions | STA_ID = ALL 1's indicates broadcast transmission | Defer - Need to address Multicast/Broadcast signalling. - U |  |  |  | Defer - Need to address Multicast/Broadcast signalling. - U
1225 | Fischer, Matthew | 7.4.7.10 | 77 | 12 | T | Y | 77 | 12 |  | 7.4.7.10 | T |  | A |  |  |  | "DLT Duration" is probably incorrect in this sentence | "DLT Duration" --> "DLT Start Offset" | Accept - U Make changes as suggested. |  |  |  | Accept - U Make changes as suggested.
3794 | Kandala, Srinivas | 7.4.7.10 | 77 | 13 | T | Y | 77 | 13 |  | 7.4.7.10 | T |  | A |  |  |  | A PSDU does not contain the preamble which needs to be accounted for. | Replace PSDU with PPDU | Accept - U Make changes as suggested. |  |  |  | Accept - U Make changes as suggested.
6847 | Myles, Andrew | 7.4.7.10 | 77 | 13-15 | T | Y | 77 | 13 |  | 7.4.7.10 | T |  | A |  |  |  | The text appears to confuse its ULT's and DLT's by mentioning ULT Duration in a paragraph on DLT Durations | Fix | Accept - Change the text in line 14, 15 "If no ULT …. " to "If no DLT is scheduled for a STA, but a ULT is scheduled for that STA, then the DLT Duration is set to null (0)." - U |  |  |  | Accept - Change the text in line 14, 15 "If no ULT …. " to "If no DLT is scheduled for a STA, but a ULT is scheduled for that STA, then the DLT Duration is set to null (0)." - U
659 | CYPHER, DAVID | 7.4.7.10 | 77 | 14&25 | T | Y | 77 | 14 |  | 7.4.7.10 | ST |  | A |  |  |  | Is there a reason for the difference in units for DLT 16us and ULT 4us? |  | Accept - Add text "Note: The DLT granularity effects power save and ULT granularity effects medium access period so it is important to get the medium access time precisely" Editor can reword the text to align with the spec languge. - U |  |  |  | Accept - Add text "Note: The DLT granularity effects power save and ULT granularity effects medium access period so it is important to get the medium access time precisely" Editor can reword the text to align with the spec languge. - U
851 | Emeott, Stephen | 7.4.7.10 | 77 | 14-15 | T | Y | 77 | 14 |  | 7.4.7.10 | T | 6847 | A |  |  |  | The current draft reads " If no ULT is scheduled for a STA, but a DLT is scheduled for that STA, then the ULT Duration is set to null (0)" from line 14-15, which is the same as text from line 22-23. Should line 14-15 be changed to "If no DLT is scheduled for a STA, but a ULT is scheduled for that STA, then the DLT Duration is set to null (0)" | Make the recommeded change | Accept - U Use resolution from CID 6847 |  | Duplicate |  | Accept - U Use resolution from CID 6847
1226 | Fischer, Matthew | 7.4.7.10 | 77 | 14-15 | T | Y | 77 | 14 |  | 7.4.7.10 | T | 6847 | A |  |  |  | Discussion of ULT seems very strange at the end of the sentence? | Was this really supposed to be about DLT Duration? | Accept - U Use resolution from CID 6847 |  | Duplicate |  | Accept - U Use resolution from CID 6847
1227 | Fischer, Matthew | 7.4.7.10 | 77 | 20 | T | Y | 77 | 20 |  | 7.4.7.10 | DT |  | D |  |  |  | Are all DLT supposed to finish before any ULT begin? This seems inefficient per STA in that the radio chain would need to be turned on and off twice | Isn't it more efficient to have DLT and ULT for a given station be adjacent? | Defer - Need additional information - U |  |  |  | Defer - Need additional information - U
1228 | Fischer, Matthew | 7.4.7.10 | 77 | 25 | T | Y | 77 | 25 |  | 7.4.7.10 | T |  | R |  |  |  | DLT Duration hould be irrelevant to the ULT Duration, so why is it included in the middle of this sentence? | Delete "but a DLT is scheduled for that STA," | Reject - The text addresses the scenario and the setting of the ULT duration field where there is no ULT but there is a DLT - U |  |  |  | Reject - The text addresses the scenario and the setting of the ULT duration field where there is no ULT but there is a DLT - U
1217 | Fischer, Matthew | 7.4.7.10 | 77 | 28 | T | Y | 77 | 28 |  | 7.4.7.10 | DT |  | D |  |  |  | wrong word choice | Change "can" to "should" | Defer: The text is in line with the fact that the TSID field is a "recommendation". Not sure if the field is required at all. - U |  |  |  | Defer: The text is in line with the fact that the TSID field is a "recommendation". Not sure if the field is required at all. - U
3418 | Jokela, Jari | 7.4.7.10 | 77 | 28-31 | T | Y | 77 | 28 |  | 7.4.7.10 | ST | 7595 | A |  |  |  | Usage/encoding of TSIDs set field is not clear. | Clarify. Table may help to clarify TSID <=> TSIDs set field mapping. | Accept - U Use resolution from CID 7495 |  | Duplicate |  | Accept - U Use resolution from CID 7495
1218 | Fischer, Matthew | 7.4.7.10 | 77 | 29 | T | Y | 77 | 29 |  | 7.4.7.10 | T |  | A |  |  |  | wrong word choice | Change "in the ULT resources" to "during the ULT assigned to that STA." | Accept - Change as suggested. - U |  |  |  | Accept - Change as suggested. - U
657 | CYPHER, DAVID | 7.4.7.10 | 77 | 30 | T | Y | 77 | 30 |  | 7.4.7.10 | T |  | A |  |  |  | Does not read right | Add "or" to make "If one or more bits …" | Accept - Change as suggested. - U |  |  |  | Accept - Change as suggested. - U
1219 | Fischer, Matthew | 7.4.7.10 | 77 | 30 | T | Y | 77 | 30 |  | 7.4.7.10 | T | 657 | C |  |  |  | wrong word choice | Change "If one more bits are set, the AP is recommending that the STA use the ULT for the indicated TSIDs" to "If more than one bit is set, the AP is recommending that the STA should use the ULT for any, some or all of the indicated TSIDs." | Counter - Use resolution for CID 657 - U |  | Duplicate |  | Counter - Use resolution for CID 657 - U
1229 | Fischer, Matthew | 7.4.7.10 | 77 | 30 | T | Y | 77 | 30 |  | 7.4.7.10 | T | 657 | C |  |  |  | Grammar/Unclear | Clarify "If one more bits are set," is it "If more than one bits are set,the AP is recommending that the STA use the ULT for the MULTIPLE indicated TSIDs | Counter - Use resolution for CID 657 - U |  | Duplicate |  | Counter - Use resolution for CID 657 - U
1220 | Fischer, Matthew | 7.4.7.10 | 77 | 32 | T | Y | 77 | 32 |  | 7.4.7.10 | T |  | R |  |  |  | clumsy wording | Combine the note on line 34 with the previous sentence -- e.g. begin the sentence on line 32 as follows: "All frames (including control frames)" | Reject - Take resolution for CID 6911 |  |  |  | Reject - Take resolution for CID 6911
3419 | Jokela, Jari | 7.4.7.10 | 77 | 32-33 | T | Y | 77 | 32 |  | 7.4.7.10 | T |  | D |  |  |  | In 7.3.1.2 it is said that in A-MPDU all the MPDUs carry the same Duration/Id value. So if A-MPDU is sent with PSMP, all the MPDUs in A-MPDU carry the same Duration/Id value and not the remaining duration (i.e., MPDUn+1 is not having smaller value than MPDUn). | Clarify. | Defer - The setting of Duration/ID field of MPDU's with in A-MPDU is clear. However, the value to which the Duration/ID needs to be set is not clear as PSMP TXOP is not defined. The submission will address what is PSMP TXOP, what does the Duration/ID field of 1) PSMP Frame carry, 2) frames transmitted during DLT/ULT period |  |  |  | Defer - The setting of Duration/ID field of MPDU's with in A-MPDU is clear. However, the value to which the Duration/ID needs to be set is not clear as PSMP TXOP is not defined. The submission will address what is PSMP TXOP, what does the Duration/ID field of 1) PSMP Frame carry, 2) frames transmitted during DLT/ULT period
6911 | Nanda, Sanjiv | 7.4.7.10 | 77 | 32 | E | N | 77 | 32 |  | 7.4.7.10 | T |  | A |  |  |  | Discussion of Duration/ID field does not belong in this section | Delete lines 32-34 | Accept - U |  |  |  | Accept - U
1221 | Fischer, Matthew | 7.4.7.10 | 77 | 35 | T | Y | 77 | 35 |  | 7.4.7.10 | T |  | D |  |  |  | clumsy wording | Change "to a specific value 0" to "to the value 0" | Defer - Take resolution from CID's 7593, 3591 - U |  |  |  | Defer - Take resolution from CID's 7593, 3591 - U
7248 | Raissinia, Ali | 7.4.7.10 | 77 | 35-37 | T | Y | 77 | 35 |  | 7.4.7.10 | DT |  | D |  |  |  | The text implies that AP would need to have multiple multicast queues since the PSMP exchange would have to schedule them at different times so that appropriate ULT offset and ULT duration can contain the multicast address | Remove this burden since it adds unnecessary complexities. | Defer - Take resolution from CID's 7593, 3591 - U |  |  |  | Defer - Take resolution from CID's 7593, 3591 - U
9981 | Xhafa, Ariton | 7.4.7.10 | 77 | 35 | T | Y | 77 | 35 |  | 7.4.7.10 | T |  | W |  |  |  | "Multicast data is transmitted using PSMP by setting STA_ID in the STA_INFO Field to a specific valye 0. The ULT startoffset and ULT duration fields of the STA_INFO field shall be set to the Least Significant Bits of the multicast address" | Remove the sentence in lines 35-37 | Withdrawn |  |  |  | Withdrawn
11881 | Tsien, Chih | 7.4.7.10 | 77 | 35 | T | Y | 77 | 35 |  | 7.4.7.10 | DT |  | D |  |  |  | ULT Start Offset and ULT Duration set to LSBs of Multi-Cast Address is inconsistent with Unicast usage. Setting to zero is better because it is less complex. | ULT Start Offset and ULT Duration set to zero | Defer - Take resolution from CID's 7593, 3591 - U |  |  |  | Defer - Take resolution from CID's 7593, 3591 - U
1222 | Fischer, Matthew | 7.4.7.10 | 77 | 36 | T | Y | 77 | 36 |  | 7.4.7.10 | T |  | D |  |  |  | Which bits of the LSBs of the MCAST Address will appear in which positions of the fields ULT Start offset and ULT duration? | Define the exact bits of the LSBs of the MCAST Address and the exact locations within ULT start offset and ULT duration where these bits will appear. | Defer - Take resolution from CID's 7593, 3591 - U |  |  |  | Defer - Take resolution from CID's 7593, 3591 - U
2364 | Ji, Lusheng | 7.4.7.10 | 77 | 36 | T | Y | 77 | 36 |  | 7.4.7.10 | T |  | D |  |  |  | Procedure specifications don't belong in 7 | Move this text to a more appropriate clause | Defer - Take resolution from CID's 7593, 3591 - U |  |  |  | Defer - Take resolution from CID's 7593, 3591 - U
1216 | Fischer, Matthew | 7.4.7.10 | 77 |  | T | Y | 77 |  |  | 7.4.7.10 | T |  | C |  |  |  | clumsy wording | Replace the following text: "NOTE—The STA does not expect transmissions directed to this STA PPDU which start after the DLT Duration expiration. The STA completes receiving any PPDU directed to this STA which starts before the end of the DLT. If no frames directed toward a STA begin within DLT Duration from the DLT start offset time for that STA, then the STA assumes that no frame directed toward it is forthcoming during this DLT." with this text: "NOTE—A STA does not expect transmissions directed to itself to start after the DLT Duration expiration. A STA completes receiving any PPDU directed to itself which starts before the end of a DLT for that STA. If no frames directed toward a STA begin within DLT Duration from the DLT start offset time for that STA, then the STA assumes that no frame directed toward it is forthcoming during this DLT." | Counter : Add the following text - "NOTE—A STA does not expect transmissions directed to itself to start after the DLT Duration expiration. A STA completes receiving any PPDU directed to itself which starts before the end of a DLT for that STA. If no frames that are directed toward a STA begin within DLT Duration from the DLT start offset time for that STA, then the STA assumes that no frame directed toward it is forthcoming during this DLT." - U |  |  |  | Counter : Add the following text - "NOTE—A STA does not expect transmissions directed to itself to start after the DLT Duration expiration. A STA completes receiving any PPDU directed to itself which starts before the end of a DLT for that STA. If no frames that are directed toward a STA begin within DLT Duration from the DLT start offset time for that STA, then the STA assumes that no frame directed toward it is forthcoming during this DLT." - U
1763 | Jang, KyungHun | 7.4.7.10 | 77 |  | T | Y | 77 |  |  | 7.4.7.10 | T |  | A |  |  |  | The unit of DLT duration and that of ULT duration are different, 16us and 4us respectively. Need explanation for this difference. | Add informative text to explain why different time units are used for DLT/ULT durations. | Accept - Take resolution from CID 659 |  |  |  | Accept - Take resolution from CID 659
3800 | Kandala, Srinivas | 7.4.7.10 | 78 |  | T | Y | 78 |  |  | 7.4.7.10 | DT |  | T |  |  |  | Is the pad really needed or it was put in because someone thought it is cool. The MSDU can still be of any length and the FCS needs to be added. So, whatever supposed gains we may have in decoding the frame are offset by having to determine and insert the pad - both of them affect the data path; one has the advantage of making the frame slightly longer. :) | Delete the pad field. | Transfer to Frame format Ad-hoc - U |  |  | Frame Format | Transfer to Frame format Ad-hoc - U
7311 | Ramesh, Sridhar | 9.9.4 (PSMP NAV operation) | 91 | 23,24 | T | Y | 91 | 23 |  | 9.9.4 | DT |  | D |  |  |  | "...PSMP TXOP with duration of the value of the Duration/ID field of the transmitted PSMP frame." TXOP duration is a SIFS shorter than the Duration/ID field of the transmitted PSMP frame. | "...PSMP TXOP with duration of the value of the Duration/ID field of the transmitted PSMP frame, less a SIFS interval." | Defer - Need clarification on the comment - U |  |  |  | Defer - Need clarification on the comment - U
10026 | Xhafa, Ariton | 9.9.4 | 91 | 23 | T | Y | 91 | 23 |  | 9.9.4 | T |  | D |  |  |  | "The STA (including AP) …" This is not clear either. Does this imply that the STA may send a PSMP frame? | Text needs clarification. | Defer - Use the resolution from CID 4554 to explicitly indicate the use of PSMP in BSS and IBSS mode of operation. - U |  |  |  | Defer - Use the resolution from CID 4554 to explicitly indicate the use of PSMP in BSS and IBSS mode of operation. - U
1480 | Fischer, Matthew | 9.9.4 | 91 | 27 | T | Y | 91 | 27 |  | 9.9.4 | DT |  | C |  |  |  | The no-reset NAV policy here has a couple of problems - this line contradicts the language of 9.3.2.2 where a CF-END reception resets the NAV without qualification, and this line creates a problem for non-HT devices which are unaware of this new protocol and the rule just stated. | Resolve the contradiction in this draft by deciding in favor of one rule or the other and making it clear which one has precedence by explicitly naming that precendence somewhere (here or in the CF-end rules). Allow non-HT STA to be compliant by allowing them to follow the existing CF-end NAV reset rule - i.e. explicitly note the precedence rule for non-HT STA as CF-end SHALL reset the NAV. Clearly, it would be least confusing for the set of rules to allow CF-end to reset NAV in case of any type of STA. And when the language is resolved, the word "cannot" shall not be present. | A - Accept the resolution from CID 4528 - U |  |  |  | A - Accept the resolution from CID 4528 - U
3900 | Kandala, Srinivas | 9.9.4 | 91 | 27 | T | Y | 91 | 27 |  | 9.9.4 | DT |  | C |  |  |  | If the station receives a CF-end, does it reset its NAV? | Describe the behavior | A - Accept the resolution from CID 4528 - U |  |  |  | A - Accept the resolution from CID 4528 - U
7290 | Raissinia, Ali | 9.9.4 | 91 | 28 | T | N | 91 | 28 |  | 9.9.4 | DT |  | C |  |  |  | Add the phrase "(except CF-End frame)" after "of other frames". | The statement should be "Additionally NAV updates may occur due to the reception of other frames (except CF-End frame) not directed toward the receiving STA during the DLT and ULT periods. | A - Accept the resolution from CID 4528 - U |  |  |  | A - Accept the resolution from CID 4528 - U
1481 | Fischer, Matthew | 9.9.4 | 91 | 29 | T | Y | 91 | 29 |  | 9.9.4 | T |  | C |  |  |  | The term "PSMP exchange" is introduced here without definition. | Define "PSMP exchange" | Counter - Use resolution from CID 1214 - U |  |  |  | Counter - Use resolution from CID 1214 - U
3901 | Kandala, Srinivas | 9.9.4 | 91 |  | T | Y | 91 |  |  | 9.9.4 | DT |  | A |  |  |  | Describe how NAVs should be managed if two PSMP frames from two different APs are received - the PSMP station should not transmit until its NAV (set by either AP) expires. | Add the suggested behavior | Accept - Use the resolution as suggested because this is in confirmance with base spec - U |  |  |  | Accept - Use the resolution as suggested because this is in confirmance with base spec - U
3902 | Kandala, Srinivas | 9.9.4 | 91 |  | T | Y | 91 |  |  | 9.9.4 | DT |  | D |  |  |  | Given the lack of guarantee that all legacy stations will not adhere to a set Long NAV and nodes that are hidden can not receive all the frames, they might end up transmit and collide with PSMP transmissions. | Disallow the use of Long NAV within PAMP. | Defer - Need additional information that would be provided by the resolution from CID 3419 - U |  |  |  | Defer - Need additional information that would be provided by the resolution from CID 3419 - U
7291 | Raissinia, Ali | 9.9.4 | 91 |  | T | N | 91 |  |  | 9.9.4 | DT |  | D |  |  |  | Add a statement that use of LongNAV within PSMP shall not be used. Protection maybe provided before PSMP management action frame. | Add an "equivalent statement" to the spec. | Defer - Need additional information that would be provided by the resolution from CID 3419 - U |  |  |  | Defer - Need additional information that would be provided by the resolution from CID 3419 - U
10025 | Xhafa, Ariton | 9.9.4 | 91 |  | T | Y | 91 |  |  | 9.9.4 | T | [5 empty] | Lines 22 is not clear. First, a PSMP sequence may start with a CTS-2-Self frame, followed by a PSMP frame PIFS times later. CTS-2-Self frame shall protect PSMP phase. | Include CTS-2-Self transmission for NAV operation during PSMP
1646 | Hillman, Garth | 9.18 | 111 | 14 | T | Y | 111 | 14 |  | 9.18 | T | [5 empty] | Needs informative introduction like clause 9.19, 9.20 and 9.21 | Add informative introduction talking about applicability to VoIP and the like
2603 | Ji, Lusheng | 9.18 | 111 | 14 | T | Y | 111 | 14 |  | 9.18 | DT | [5 empty] | PSMP may conflict with CFP/CP partition in PCF/HCCA. | Either specify that PSMP only applies to EDCA BSSs or provide specifcation text for how PSMP should not violate PCF/HCCA CFP/CP boundries.
1351 | Fischer, Matthew | 9.18.1.1 | 111 | 17 | T | Y | 111 | 17 |  | 9.18.1.1 | T | [5 empty] | imprecise language | change "using" to "specifying the use of"
1352 | Fischer, Matthew | 9.18.1.1 | 111 | 17 | T | Y | 111 | 17 |  | 9.18.1.1 | T | [5 empty] | need a shall | change "periodically initiates" to "shall periodically initiate"
1353 | Fischer, Matthew | 9.18.1.1 | 111 | 17 | T | Y | 111 | 17 |  | 9.18.1.1 | T | [5 empty] | imprecise language | change "created" to "had a TSPEC accepted which establishes" and "the AP" to "the associated AP"
4772 | McCann, Stephen | 9.18.1.1 | 111 | 17 | T | Y | 111 | 17 |  | 9.18.1.1 | DT | [5 empty] | I think it should be remembered that an AP is also an STA (see my comment 43 above). Hence I think that this sections requires some re-writing | Clarify when an AP differs from an STA.
1354 | Fischer, Matthew | 9.18.1.1 | 111 | 20 | T | Y | 111 | 20 |  | 9.18.1.1 | T | [5 empty] | imprecise language | change "S-APSD" to "an S-APSD Service Period."
1348 | Fischer, Matthew | 9.18 |  |  | T | Y | 111 |  |  | 9.18 | DT | [5 empty] | DA of PSMP frame should be allowed to be other than BCAST - MCAST should also be allowed. Use of MCAST would allow a STA to avoid having to parse the remainder of the frame to look for its address in the STA INFO. | Change description to allow STA not matching an MCAST address to not have to parse remainder of frame, and add text requiring that STA generating MCAST PSMP frame to not include STA INFO for STA which is not part of MCAST group.
1349 | Fischer, Matthew | 9.18 |  |  | T | Y | 111 |  |  | 9.18 | ST | [5 empty] | It is not clear if this entire section should really be in clause 11 or not. Or maybe only portions of it should be here and the rest in clause 11? I am not certain of what determines whether text should appear in 9 or 11. | Appropriately divide the various subfunctions of PSMP and locate them per precedent in either clause 9 or 11.
1350 | Fischer, Matthew | 9.18 |  |  | T | Y | 111 |  |  | 9.18 | T | [5 empty] | Because PSMP STA use AID values, is there any implication with respect to the PSMP protocol and the legacy PS protocol which employs the legacy bitmap? | Explicitly indicate whether or not a relationship exists between the legacy PS bitmap and the fact that PSMP STA must have an assigned AID value.
3855 | Kandala, Srinivas | 9.18 |  |  | T | Y | 111 |  |  | 9.18 | ST | [5 empty] | No introduction, no motivation to the reader as to what the heck it is? | please provide one
3856 | Kandala, Srinivas | 9.18.1 |  |  | T | Y | 111 |  |  | 9.18.1 | DT | [5 empty] | OBSS problem would be a nightmare when schedule PSMP stations are associated - HCCA has a similar problem, but the problem is exacerbated in this case because there are no immediate response frames and a collision will not be known to the transmitter for a long duration. Once the collision happens it is not clear how any kind of recovery can happen until the next schedule starts - this means the mechanism is not particularly efficient either. | Discuss the issues with OBSS in the draft and provide a solution to overcome it.
6848 | Myles, Andrew | 9.18 |  |  | T | Y | 111 |  |  | 9.18 | DT | [5 empty] | It appears that PSMP that was created to overcome some of the overheads of regular EDCA However, it is replaces a relatively simple but overhead laden system with massve complexity and its own overheads. The complexity is related the specificaton and implemenation of the infrastructure required and the scheduler required. The overheads ae related to new management frames, new protocol and inefficiencies from poor schedulers. 802.11 suceeded where Hyperlan2 failed because it was simple and worked! Why are we redesigning 802.11 to be a new Hyperlan2? | Either prove the efficiency and usefulness of PSMP in a working implemenation or remove it from the specification. I suspect similar comments apply to other parts of the specification, but I have rn out of time to review the rest.
7014 | O'Hara, Bob | 9.18 |  |  | T | Y | 111 |  |  | 9.18 | DT | [5 empty] | It appears that PSMP that was created to overcome some of the overheads of EDCA. It is replaces a simple system with a different system built on undue complexity and its own overheads. The complexity is related to the infrastructure required to implement the specification. The overhead is related to the new management frames, new protocol, and inefficiencies from poor schedulers. 802.11 suceeded where Hyperlan2 failed because it was simple and worked! Why are we redesigning 802.11 to be a new Hyperlan2? | Prove the efficiency and usefulness of PSMP or remove it from the specification.
7625 | Stephens, Adrian | 9.18.1.1 |  |  | T | Y | 111 |  |  | 9.18.1.1 | DT | [5 empty] | "The time between the downlink and the delayed uplink may be protected using one or more CTS-to-self transmissions." This is misleading. The minimum delay is 32us, and there is not time to transmit a CTS-to-self within 32us (-SIFS - RIFS). | Remove the quoted sentence.
7626 | Stephens, Adrian | 9.18.1.1 |  |  | T | Y | 111 |  |  | 9.18.1.1 | ST | [5 empty] | The Min DLT2ULT parameter needs to be a read-only parameter of the MIB. It should also include some measure of propagation time and thinking time. | Recommend that this parameter is replaced with SIFS+ a new MAC read-only MIB parameter with value 16us of name PSMP_MinDLT2ULT
7627 | Stephens, Adrian | 9.18.1.1 |  |  | T | Y | 111 |  |  | 9.18.1.1 | DT | [5 empty] | "The PSMP frame shall be sent at a non-HT basic rate". This and similar statements are repeated in different sections. It is not extensible to future PHYs or future .11n-only networks. | Extend the concept of "basic rate" so that it encompasses any other necessary PHY attributes - for example PPDU format, channel width. Then all that is necessary with any control frame is to say "basic rate". That way we localize the definition in one place, and therefore make it consistent.
7628 | Stephens, Adrian | 9.18.1.1 |  |  | T | Y | 111 |  |  | 9.18.1.1 | DT | [5 empty] | It is necessary to state which acknowlegement policies may be used in PSMP data frames - i.e. there's nothing that says you can't transmit non-QoS data, or normal ack. | Add the following: "Data frames transmitted with an individual receiver address within an A-MPDU shall be a QoS Data subtype and shall have one of the following AckPolicy values: BlockAck, Normal Ack (meaning implicit MTBAR) or No Ack. Data frames transmitted with an individual receiver address as a non-aggregate shall be a QoS data subtype and shall have one of the following AckPolicy values: BlockAck or No Ack."
7261 | Raissinia, Ali | 9.18.1.1 | 112 | Fig n38 | T | Y | 112 | 1 |  | 9.18.1.1 | DT | [5 empty] | Modify the figure to show MTBA (and MTBAR if any) is transmitted as separate PPDUs since control/response frame are supposed to be transmitted in the non-HT legacy PPDU format and non-HT rate. Otherwise, this creates fairness issue for legacy STAs due to the EIFS timeout. | Fix it.
6917 | Nanda, Sanjiv | 9.18.1.1 | 112 | 6 | E | N | 112 | 6 |  | 9.18.1.1 | ST | [5 empty] | No description is provided for Figures n38 and n39 | Add text description
6919 | Nanda, Sanjiv | 9.18.1.1 | 112 | 8 | T | N | 112 | 8 |  | 9.18.1.1 | T | [5 empty] | CTS-to-self may be sent before each PSMP | Replace with "CTS-to-self may be sent at the start of a PSMP sequence"
1355 | Fischer, Matthew | 9.18.1.1 | 112 | 9 | T | Y | 112 | 9 |  | 9.18.1.1 | T | [5 empty] | missing word | change "basic" to "BSS Basic"
7262 | Raissinia, Ali | 9.18.1.1 | 112 | 9 | T | N | 112 | 9 |  | 9.18.1.1 | T | [5 empty] | The phrase "non-HT basic rate" should be replaced by "non-HT PPDU transmission at one of the basic rates". | Modify the text.
3858 | Kandala, Srinivas | 9.18.1.1 | 112 | 10 | T | Y | 112 | 10 |  | 9.18.1.1 | T | [5 empty] | Is Minimal DLT2ULT Delay same as Minimum DLT2ULT Delay in figure 38? | Clarify - regardless, add one or both of them to Definitions in clause 3.
3859 | Kandala, Srinivas | 9.18.1.1 | 112 | 10 | T | Y | 112 | 10 |  | 9.18.1.1 | ST | [5 empty] | Assuming Minimal DLT2ULT Delay and Minimum DLT2ULT Delay are identical, it appears to me that its value is longer than 32 microseconds | Harmonize the two.
3860 | Kandala, Srinivas | 9.18.1.1 | 112 | 10 | T | Y | 112 | 10 |  | 9.18.1.1 | DT | [5 empty] | Is there any reason why Minimal DLT2ULT Delay should be 32 microseconds? Why isnt a SIFS duration sufficient. | Set the Minimal DLT2ULT Delay value to 16 microseconds.
6918 | Nanda, Sanjiv | 9.18.1.1 | 112 | 11 | E | N | 112 | 11 |  | 9.18.1.1 | T | [5 empty] | 32 us is a parameter | Replace with dot11DLT2ULTTime
1359 | Fischer, Matthew | 9.18.1.1 | 112 | 12 | T | Y | 112 | 12 |  | 9.18.1.1 | T | [5 empty] | sentence beginning "Within a PSMP" is confusing - I do not know what it means. | Rewrite sentence to clarify intent.
3861 | Kandala, Srinivas | 9.18.1.1 | 112 | 12 | T | Y | 112 | 12 |  | 9.18.1.1 | T | [5 empty] | There is something wrong with this phrasing, "… if the number of STAs that are involved can not ensure this required delay …" The required delay can not be met because of the number of stations - don’t think that is quite right. | Correct the sentence.
1360 | Fischer, Matthew | 9.18.1.1 | 112 | 16 | T | Y | 112 | 16 |  | 9.18.1.1 | T | [5 empty] | If there are multiple PSMP frames within a single PSMP sequence, then do all MCAST have to appear after the first PSMP, before any UCAST, or can the MCAST appear before the UCAST of any PSMP within the whole set? I assume that it is the latter case. | Add language to create a distinction between PSMP sequence and PSMP frame, so that the intent of placing MCAST before UCAST per PSMP frame transmitted is clearly reflected in the text.
3593 | Kakani, Naveen | 9.18.1.1 | 112 |  | T | Y | 112 |  |  | 9.18.1.1 | T | [5 empty] | Use of RIFS in Figure n38 is an unnecessary constraint | Delete the text RIFS in Figure n38
7263 | Raissinia, Ali | 9.18.1.1 | 112 |  | T | N | 112 |  |  | 9.18.1.1 | ST | [5 empty] | Specify under this section whether or not during PSMP exchange following MAC HT enhancements can be used: Reverse direction during DLT and ULT TXOP truncation using CF-End L-SIG TXOP protection, if so will there be a CF-End frame transmitted PCO transmission 40MHz transmission with duplicated control frames Use of other control frames during DLT and ULT such as RTS/CTS, etc. | Specify the requirements in this section.
747 | Durand, Chris | 9.18.1.1 | 113 | 1-2 | T | Y | 113 | 1 |  | 9.18.1.1 | T | [5 empty] | This sentance is nonsensical. The requirement is unclear. | Reword or remove sentance.
1361 | Fischer, Matthew | 9.18.1.1 | 113 | 1 | T | Y | 113 | 1 |  | 9.18.1.1 | T | [5 empty] | do you mean "during?" | change "transmitted" to "transmitted during"
1363 | Fischer, Matthew | 9.18.1.1.1 | 113 | 4 | T | Y | 113 | 4 |  | 9.18.1.1.1 | T | [5 empty] | the sentence needs a shall and an offsetting sentence to clearly delineate the behavior so that other STA/AP may be able to accurately predict the sleep/wake state of the STA | replace "During a PSMP sequence, a STA is only required to be able to receive during its scheduled DLT." with "During a PSMP sequence, a STA shall be in an active receive state during its scheduled DLT and may not be in an active receive state at other times."
1364 | Fischer, Matthew | 9.18.1.1.1 | 113 | 6 | T | Y | 113 | 6 |  | 9.18.1.1.1 | T | [5 empty] | "its" has three or four possible antecedents | change "its" to a more explicit reference - I believe it is referring to "that STA's"
1366 | Fischer, Matthew | 9.18.1.1.1 | 113 | 11 | T | Y | 113 | 11 |  | 9.18.1.1.1 | T | [5 empty] | this sentence is not clear - it mentions multiple RA, but it does not mention whether the context is the entire PSMP exchange, or just one DLT | add language to clarify that the multiple RA discussion is with respect to a multiplicity of DLT within a single PSMP exchange, and not multiple RA within a single DLT
1367 | Fischer, Matthew | 9.18.1.1.2 | 113 | 18 | T | Y | 113 | 18 |  | 9.18.1.1.2 | T | [5 empty] | Needs a shall or maybe a MAY? | add a shall to make the behavior normative - or actually, do we want a MAY here?
1368 | Fischer, Matthew | 9.18.1.1.2 | 113 | 20 | T | Y | 113 | 20 |  | 9.18.1.1.2 | T | [5 empty] | not specific enough | change "duration" to "ULT duration"
1369 | Fischer, Matthew | 9.18.1.1.2 | 113 | 21 | T | Y | 113 | 21 |  | 9.18.1.1.2 | T | [5 empty] | do not understand the meaning or reason for this sentence | strike lines 21, 22
6922 | Nanda, Sanjiv | 9.18.1.1.2 | 113 | 23 | T | N | 113 | 23 |  | 9.18.1.1.2 | DT | [5 empty] | "TSID set" subfield is advisory in PSMP | Remove
785 | Durand, Roger | 9.18.1.1.2 | 113 | 25 | T | Y | 113 | 25 |  | 9.18.1.1.2 | ST | [5 empty] | This is just wrong and bandwidth wasteful, put real rules in or take it all out. | elimnate the last two sentences
1370 | Fischer, Matthew | 9.18.1.1.2 |  |  | T | Y | 113 |  |  | 9.18.1.1.2 | T | [5 empty] | what about provision for DLS within PSMP? | add appropriate language to allow DLS behavior within PSMP
1770 | Jang, KyungHun | 9.18.1.1.2 | 113 |  | T | Y | 113 |  |  | 9.18.1.1.2 | T | [5 empty] | When nothing is transmitted by QSTA during its scheduled Uplink transmission time, there is no way for an QAP to determine whether QSTA does not have anything to transmit or QSTA did not receive PSMP frame correctly. | Provide more detailed behaviors of STA and AP when STA does not have any frames to be transmitted during its ULT. QSTA should transmit NULL frame when it does not have anything to transmit. If AP receives the NULL frame from the STA, it may schedule a 'reverse-direction' traffic to STA as far as the remaining ULT for the corresponding STA allows. On the other hand, if AP senses the medium idle for the duration of a NULL frame, it resends the PSMP frame based on the interpretation that the initial PSMP delivery was not successful.
7629 | Stephens, Adrian | 9.18.1.1.1 |  |  | T | Y | 113 |  |  | 9.18.1.1.1 | T | [5 empty] | "Additional Information Elements" - does not exist | Replace with "Additional HT Information Elements"
7630 | Stephens, Adrian | 9.18.1.1.1 |  |  | T | N | 113 |  |  | 9.18.1.1.1 | T | [5 empty] | "The DLT transmission may contain one or several A-MPDUs and/or MPDUs containing payload and MTBA" This mixes concepts and is awkward. | Replace with: "The DLT transmission may contain one or more PPDUs each of which may contain an A-MPDU or single MPDU. The MPDUs contained within the DLT transmission may be Data or MTBA".
7631 | Stephens, Adrian | 9.18.1.1.1 |  |  | T | N | 113 |  |  | 9.18.1.1.1 | T | [5 empty] | "Multiple RA are supported by separate PPDUs separated by RIFS or SIFS as described above. This is shown in Figure n40 below." As this follows a description of what goes into a DLT, it may mislead the reader into believing a DLT contains more than one RA. | Replace with: "Each DLT contains frames addressed to a single receiver address. Adjacent DLT may be separated by RIFS or SIFS as specified above. This means that PPDUs to different RA may be separated by RIFS or SIFS. This is shown in Figure n40 below."
7634 | Stephens, Adrian | 9.18.1.1.2 |  |  | T | Y | 113 |  |  | 9.18.1.1.2 | DT | [5 empty] | "The AP may reuse any unused ULT in scheduled or unscheduled PSMP." It is not clear if this statement was superceded by the following para, which is certainly a subset of the quoted sentence. | Remove the quoted sentence.
8086 | Trainin, Solomon | 9.18.1.1.1 | 113 |  | T | Y | 113 |  |  | 9.18.1.1.1 | DT | [5 empty] | AP transmission of management frames in PSMP sequence. Append to the section | If the AP contains management frames for the station what is already PSMP scheduled it shall transmit them during DLT time of this station. The station shall acknowledge the management frame immediately with regular ACK. After transmitting a management MPDU the AP shall wait for an ACKTimeout interval. If a PHY-RXSTART.indication does not occur during the ACKTimeout interval, the AP concludes that the transmission of the MPDU has failed and may retransmit the failed MPDU or transmit any another frame. The AP shall wait SIFS after getting ACK before continuing transmitting frames to this particular station.
1371 | Fischer, Matthew | 9.18.1.1.2 | 114 | 1 | T | Y | 114 | 1 |  | 9.18.1.1.2 | T | [5 empty] | missing word | change "TSID field" to "TSID set field"
1372 | Fischer, Matthew | 9.18.1.1.2 | 114 | 3 | T | Y | 114 | 3 |  | 9.18.1.1.2 | T | [5 empty] | wrong word choice | change "over" to "using"
4773 | McCann, Stephen | 9.18.1.1.2 | 114 | 3 | T | Y | 114 | 3 |  | 9.18.1.1.2 | DT | [5 empty] | Since an AP is also an STA, the statement 'STA's AP' is meaningless | Clarify when an AP differs from an STA.
2607 | Ji, Lusheng | 9.18.1.1.2 | 114 | 4 | T | Y | 114 | 4 |  | 9.18.1.1.2 | T | [5 empty] | "Additional Information Element" is not a valid name | Replace with the correct name of the IE that has this field
8087 | Trainin, Solomon | 9.18.1.1.2 | 114 | 4 | T | Y | 114 | 4 |  | 9.18.1.1.2 | DT | [5 empty] | STA transmission of management frames in PSMP sequence. Insert the following | Non AP STA may transmit management frames directed to AP during ULT time of the related station. The AP shall acknowledge the management frame immediately with regular ACK. After transmitting a management MPDU the non AP STA shall wait for an ACKTimeout interval. If a PHY-RXSTART.indication does not occur during the ACKTimeout interval, the non AP STA concludes that the transmission of the MPDU has failed and may retransmit the failed MPDU or transmit any another frame. The non AP STA shall wait SIFS after getting ACK before continuing transmitting frames to AP.
3427 | Jokela, Jari | 9.18.1.1.2 | 114 | 6-16 | T | Y | 114 | 6 |  | 9.18.1.1.2 | T | [5 empty] | Concept of PSMP-recovery frame is unclear. | Add more explanation and figure to explain the operation of PSMP-recovery frame.
1373 | Fischer, Matthew | 9.18.1.1.2 | 114 | 7 | T | Y | 114 | 7 |  | 9.18.1.1.2 | T | [5 empty] | define "PSMP-recovery frame" | define "PSMP-recovery frame"
6921 | Nanda, Sanjiv | 9.18.1.1.2 | 114 | 7 | E | N | 114 | 7 |  | 9.18.1.1.2 | ST | [5 empty] | PSMP-recovery frame is not defined. | Clarify the difference between a PSMP frame and a PSMP-recovery frame
7264 | Raissinia, Ali | 9.18.1.1.2 | 114 | 7 | T | N | 114 | 7 |  | 9.18.1.1.2 | DT | [5 empty] | Add "and no other frame" after "PSMP-recovery frame". This will ensure AP will not send any other frames beside PSMP management action frame. | Fix it.
10005 | Xhafa, Ariton | 9.18.1.1.2 | 114 | 7 | T | Y | 114 | 7 |  | 9.18.1.1.2 | DT | [5 empty] | "The AP may transmit a PSMP-recovery frame if the currently scheduled ULT duration is longer than the total time of PSMP recovery frame plus PIFS." Sending the PSMP recovery frame should not be the only option and could result in un-necessary increase in complexity. CTS-2-Self should also be an option to recover unused ULTs. | Change to "The AP may transmit a PSMP-recovery frame or non-HT CTS-2-Self frame (with its MAC duration protecting till the end of PSMP phase) if the currently scheduled ULT duration is longer than the total time of PSMP recovery frame or CTS-2-Self frame plus PIFS."
1375 | Fischer, Matthew | 9.18.1.1.2 | 114 | 8 | T | Y | 114 | 8 |  | 9.18.1.1.2 | T | [5 empty] | will shall be "shall" | change "will" to "shall"
1374 | Fischer, Matthew | 9.18.1.1.2 | 114 | 9 | T | Y | 114 | 9 |  | 9.18.1.1.2 | T | [5 empty] | ambiguous terminology - every STA listed in the original PSMP frame is a "Currently scheduled STA" | define "currently scheduled STA"
1376 | Fischer, Matthew | 9.18.1.1.2 | 114 | 12 | T | Y | 114 | 12 |  | 9.18.1.1.2 | T | [5 empty] | wrong tense | change "being" to "were"
1377 | Fischer, Matthew | 9.18.1.1.2 | 114 | 12 | T | Y | 114 | 12 |  | 9.18.1.1.2 | T | [5 empty] | need a shall | change "is" to "shall be"
681 | CYPHER, DAVID | 9.18.1.1.2.1 | 114 | 19 | T | Y | 114 | 19 |  | 9.18.1.1.2.1 | ST | [5 empty] | IUS should be added to clasue 3 and/or clause 4
786 | Durand, Roger | 9.18.1.1.2.1 | 114 | 20 | T | Y | 114 | 20 |  | 9.18.1.1.2.1 | ST | [5 empty] | confusion | across diferent stations some HT some not is the 1US always a SIFS? If yes then please clearly state this
6923 | Nanda, Sanjiv | 9.18.1.1.2.1 | 114 | 20 | E | N | 114 | 20 |  | 9.18.1.1.2.1 | T | [5 empty] | 8 us should be a parameter | Replace with dot11IUSTime
3862 | Kandala, Srinivas | 9.18.2 | 114 | 26 | T | Y | 114 | 26 |  | 9.18.2 | ST | [5 empty] | Define "precisely" - since a precise value is desired, the formula for getting to that precision should be provided. | As suggested.
3863 | Kandala, Srinivas | 9.18.2 | 114 | 30 | T | Y | 114 | 30 |  | 9.18.2 | DT | [5 empty] | Since the draft seeks precise settings of durations, the draft should provide the description of a scheduler that achieves this precision - failing that establish some reasonable constraints that an implementer can hope to meet. | As suggested.
7136 | Perahia, Eldad | 9.18.2 | 114 | 33 | T | N | 114 | 33 |  | 9.18.2 | DT | [5 empty] | In order to allocate the minimum amount of time to each STA, the AP should use the Peak Data Rate not the Minimum Data Rate. | in line 33, change Minimum Data Rate to Peak Data Rate
1380 | Fischer, Matthew | 9.18.2 | 114 | 37 | T | Y | 114 | 37 |  | 9.18.2 | T | [5 empty] | use proper terminology | change "also transmits" to "may also transmit"
1381 | Fischer, Matthew | 9.18.2 | 114 | 37 | T | Y | 114 | 37 |  | 9.18.2 | T | [5 empty] | the wording of the procedure for the transmission of the RR makes it sound like it is allowed to transmit the RR AFTER the ULT has been filled with DATA - this needs to be fixed to avoid having someone interpret the text in such manner | change "the STA transmits only the part of the queued data that fits within the allocated ULT Duration and also transmits an additional Resource Request (RR) to the AP." to "the STA may transmit part of the queued data and may also transmit an additional Resource Request (RR) to the AP. All transmissions by the STA shall begin and end within the allocated ULT Duration for that STA."
3864 | Kandala, Srinivas | 9.18.2 | 114 | 37 | T | Y | 114 | 37 |  | 9.18.2 | DT | [5 empty] | Couldn’t find the frame "Resource Request (RR)" | Define such a frame. If you meant something else please state clearly.
682 | CYPHER, DAVID | 9.18.2 | 114 | 38 | T | Y | 114 | 38 |  | 9.18.2 | ST | [5 empty] | RR should be added to clasue 3 and/or clause 4
1772 | Jang, KyungHun | 9.18.2 | 114 |  | T | Y | 114 |  |  | 9.18.2 | T | [5 empty] | In 802.11e amendment, the resource request using Quese Size Field or the TXOP Duration Request field of QoS Control Field is optional. But in PSMP, resource request mechanism based on these parameters is crucial to the effectiveness of multi-phase PSMP operation in its power saving capability. The usage of these QoS parameters in the resource request being optional within the PSMP exchange would keep the participating STA's from saving its power to the fullest potential that PSMP mechanism provides. | Resource Request using Quese Size Field or the TXOP Duration Request field of QoS Control Field in multi-phase PSMP shall be mandatory when PSMP is used.
7635 | Stephens, Adrian | 9.18.1.1.2.1 |  |  | T | Y | 114 |  |  | 9.18.1.1.2.1 | ST | [5 empty] | We have a "magic number" of 8us appearing in the spec. This should be a PHY attribute or derived by formula from PHY attributes.
1382 | Fischer, Matthew | 9.18.2 | 115 | 1 | T | Y | 115 | 1 |  | 9.18.2 | T | [5 empty] | let's just be clear about the fact that we are not really trying to fool anyone | change "an exact ULT Duration" to "a new ULT with a Duration"
10007 | Xhafa, Ariton | 9.18.2 | 115 | 5 | T | Y | 115 | 5 |  | 9.18.2 | DT | [5 empty] | "The frames transmitted in ULT may be acknowledged by MTBA in DLT phase within the following Sub-PSMP." This imposes tight requirements for the AP and we should relax the sending of the MTBA. | "The frames transmitted in ULT may be acknowledged by MTBA in DLT phase of the next SP or within the following Sub-PSMP ."
1383 | Fischer, Matthew | 9.18.2 | 115 | 7 | T | Y | 115 | 7 |  | 9.18.2 | T | [5 empty] | use the plural form | change period to periods change sequence to sequences
875 | Emeott, Stephen | 9.18.2.1 | 116 | 4 | T | Y | 116 | 4 |  | 9.18.2.1 | ST | [5 empty] | It is not obvious why the PSMP power management text should be located in clause 9 apart from the other power management text in clause 11.2. It would be helpful to extend clause 11.2 to include some information about AP and station operation for PSMP stations. | Make the recommended change
1384 | Fischer, Matthew | 9.18.2.1 | 116 | 4 | T | Y | 116 | 4 |  | 9.18.2.1 | T | [5 empty] | incomplete description | Change "Power is" to "Device power usage can be"
7265 | Raissinia, Ali | 9.18.2.1 | 116 | 4 | T | N | 116 | 4 |  | 9.18.2.1 | DT | [5 empty] | Change the verb "will" to "shall" as AP expects all STAs sharing the same service interval to be awake. | Fix it.
8035 | Thrasher, Jerry | 9.18.2.1 | 116 | 5 | E | N | 116 | 5 |  | 9.18.2.1 | T | [5 empty] | use of the word "will" in the sentence is wrong | Reword to …., the STA shall stay active at least until…" | Ed: reclassified as technical because the change introduces a normative requirement.
7266 | Raissinia, Ali | 9.18.2.1 | 116 | 8 | T | Y | 116 | 8 |  | 9.18.2.1 | DT | [5 empty] | Remove the CF-End as a means to end PSMP sequence. This adds unnecessary complexity to the receiver since the use of CF-End is to reset the NAV. Having only one scheme i.e. use of "more PSMP" bit would be sufficient and thus reduces interoperability issues. | Fix it.
3865 | Kandala, Srinivas | 9.18.2.1 | 116 | 9 | T | Y | 116 | 9 |  | 9.18.2.1 | T | [5 empty] | The use of EOSP field is not clearly mentioned. | Replace the first sentence of the paragraph with, "The AP may also signal the end of a service period on a per-STA basis using the EOSP bit set in the QoS Control field.
3866 | Kandala, Srinivas | 9.18.2.1 | 116 | 9 | T | Y | 116 | 9 |  | 9.18.2.1 | DT | [5 empty] | Settings for More Data and TIM bit are not specified. | Clarify the setting of the More Data and TIM bit settings? It may make sense to have similar settings as for APSD.
1386 | Fischer, Matthew | 9.18.2.1 | 116 | 11 | T | Y | 116 | 11 |  | 9.18.2.1 | T | [5 empty] | incomplete description | add "following the successful transmission of the EOSP bit." to the end of the sentence
1387 | Fischer, Matthew | 9.18.2.1 | 116 | 13 | T | Y | 116 | 13 |  | 9.18.2.1 | T | [5 empty] | potentially contradictory instructions - make precedence explicit | change "has been permitted to return to sleep" to "has been permitted to return to sleep through the reception of an EOSP bit within a frame addressed to it"
6927 | Nanda, Sanjiv | 9.18.3 | 116 | 14 | T | Y | 116 | 14 |  | 9.18.3 | DT | [5 empty] | MTBA is used only within PSMP | Either MTBA is useful and must be permitted to be used outside PSMP as well, or it is not, and should be completely removed.
1389 | Fischer, Matthew | 9.18.3 | 116 | 16 | T | Y | 116 | 16 |  | 9.18.3 | T | [5 empty] | additional qualifier won't hurt | change "by a STA" to "by a STA within a PSMP sequence"
3857 | Kandala, Srinivas | 9.18.1.1 | 116 | 17 | T | Y | 116 | 17 |  | 9.18.1.1 | ST | [5 empty] | How does a station create a traffic stream for Scheduled PSMP. | Indicate the sequence of steps that need to be taken for this. If it is indicated elsewhere, provide a reference.
1388 | Fischer, Matthew | 9.18.3 | 116 | 19 | T | Y | 116 | 19 |  | 9.18.3 | T | [5 empty] | There is some potential confusion here - while it does say that everything is acked with MTBA, then it goes on to say that normal ack policy is used to signal the request for an MTBA, which only implies that those frames were part of an A-MPDU. And an MTBAR can be used, which suggests that block ack policy setting can be indicated in transmitted frames, which potentially then, are not part of an A-MPDU. So there is no explicit restriction that all data must be sent within an A-MPDU inside of PSMP. So, what needs to be stated is that normal ack policy setting shall not be used in non-A-MPDU aggregated frames. | Add a sentence: Non-aggregated frames transmitted during DLT or ULT shall not have ack policy set to normal.
1390 | Fischer, Matthew | 9.18.3 | 116 | 22 | T | Y | 116 | 22 |  | 9.18.3 | T | [5 empty] | need more adjectives | change "DLT" to "previous DLT(s)"
1398 | Fischer, Matthew | 9.18.3 | 116 | 22 | T | Y | 116 | 22 |  | 9.18.3 | T | [5 empty] | allow AP to determine its scheduling | change "next PSMP sequence" to "a subsequent PSMP sequence"
1391 | Fischer, Matthew | 9.18.3 | 116 | 23 | T | Y | 116 | 23 |  | 9.18.3 | T | [5 empty] | Wrong article. | change "the ULT" to "a ULT"
1392 | Fischer, Matthew | 9.18.3 | 116 | 24 | T | Y | 116 | 24 |  | 9.18.3 | T | [5 empty] | clumsy wording | change "locally limited" to "determined"
1393 | Fischer, Matthew | 9.18.3 | 116 | 25 | T | Y | 116 | 25 |  | 9.18.3 | T | [5 empty] | what does "related TSPEC" mean? | cannot provide suggested remedy, since I cannot guess at the meaning
1394 | Fischer, Matthew | 9.18.3 | 116 | 25 | T | Y | 116 | 25 |  | 9.18.3 | T | [5 empty] | really cannot make any sense from these lines (25-26) | rewrite to provide some clear meaning, or delete lines 25-26
1395 | Fischer, Matthew | 9.18.3 | 116 | 27 | T | Y | 116 | 27 |  | 9.18.3 | T | [5 empty] | first sentence does not make sense | please rewrite to provide some clear meaning
1400 | Fischer, Matthew | 9.18.3.1 | 116 | 32 | T | Y | 116 | 32 |  | 9.18.3.1 | T | [5 empty] | use standard terminology to communicate specific rules | change "receives" to "may receive", change "the next PSMP" to "subsequent PSMPs"
1401 | Fischer, Matthew | 9.18.3.1 | 116 | 33 | T | Y | 116 | 33 |  | 9.18.3.1 | DT | [5 empty] | allow AP to determine its scheduling | change "In the Sub-PSMP of the same Service Interval the AP may reserve ULT to allow STA retransmission of failed frames." to "The AP may reserve subsequent ULTs to allow STA retransmissions of failed frames."
1402 | Fischer, Matthew | 9.18.3.1 | 116 | 35 | T | Y | 116 | 35 |  | 9.18.3.1 | DT | [5 empty] | allow STA to determine its scheduling | change "the first PSMP in the next" to "subsequent"
1403 | Fischer, Matthew | 9.18.3.1 | 116 | 35 | T | Y | 116 | 35 |  | 9.18.3.1 | DT | [5 empty] | allow STA to determine its scheduling - this is what the next paragraph is doing anyway | add "or during the contention period between PSMP sequences." to the end of the paragraph
7267 | Raissinia, Ali | 9.18.3.1 | 116 | 35 | T | N | 116 | 35 |  | 9.18.3.1 | DT | [5 empty] | Replace "or in the first PSMP" with "one of the PSMP exchanges". The change provides flexibility that AP does NOT need to schedule it in the first PSMP exchange. | Make the modification.
11616 | Shao, Huai-Rong | 9.18.3.1 | 116 | 36 | T | N | 116 | 36 |  | 9.18.3.1 | DT | [5 empty] | A STA that cannot complete retransmissions in the last Sub-PSMP of the current Service Interval may transmit the data outside the PSMP sequence. However, frames transmitted outside the scheduled SP under EDCA are subject to the AC prioritization. | Since PSMP-enabled STAs can use MTBA within the PSMP sequence, the PSMP-enabled STAs should be allowed to retransmit data outside the scheduled PSMP using MTBA. This helps in further improving
1385 | Fischer, Matthew | 9.18.2.1 |  |  | T | Y | 116 |  |  | 9.18.2.1 | T | [5 empty] | will shall be "shall" | change "will" to "shall" multiple occurrences
7638 | Stephens, Adrian | 9.18.2.1 |  |  | T | N | 116 |  |  | 9.18.2.1 | T | [5 empty] | "unless the STA has been permitted to return to sleep " hides what permits it. | Replace with: "unless the STA has been permitted to return to sleep (using the EOSP protocol)"
7642 | Stephens, Adrian | 9.18.3 |  |  | T | N | 116 |  |  | 9.18.3 | DT | [5 empty] | "Retry (and possibly lifetime) limits are independent per TSID." - while true, this is behaviour defined elsewhere. Same comment in Note2 of 9.18.3.1 | Remove quoted sentence.
10008 | Xhafa, Ariton | 9.18.3 | 116 |  | T | Y | 116 |  |  | 9.18.3 | T | [5 empty] | I am a little confused with different notations used for MTBA and AMPDU acknowledging /carrying different TID/TSID during PSMP phase. | TID/TSID needs to be fixed.
1404 | Fischer, Matthew | 9.18.3.1 | 117 | 1 | T | Y | 117 | 1 |  | 9.18.3.1 | T | [5 empty] | which case? | Remove the text "Note-1" and merge this paragraph with the previous one to make the reference clear.
7268 | Raissinia, Ali | 9.18.3.1 | 117 | 1 | T | Y | 117 | 1 |  | 9.18.3.1 | ST | [5 empty] | if note-1 refers to the STA transmitting outside of PSMP, then it might be incorrect. Note that outside PSMP, the STA can simply do EDCA frame exchange sequence and get its responses BA, ACK without needing to wait for the next PSMP. | Please clarify note-1.
3868 | Kandala, Srinivas | 9.18.3.1 | 117 | 3 | T | Y | 117 | 3 |  | 9.18.3.1 | ST | [5 empty] | The note appears to indicate that there exist retrylimits per TID. This is not true. | Determine the need for such retry limits. If needed, add appropriate MIB attributes
5159 | Meylan, Arnaud | 9.18.4 | 117 | 4 | T | Y | 117 | 4 |  | 9.18.4 | DT | [5 empty] | U-PSMP operation is not clearly defined and its technical merits have not been demonstrated | Remove U-PSMP from draft
1406 | Fischer, Matthew | 9.18.4 | 117 | 5 | T | Y | 117 | 5 |  | 9.18.4 | ST | [5 empty] | need a reference to trigger frames | add a reference to the definition and description of trigger frames and their use in whatever clause it is that they are defined (11.x?)
4081 | Kerry, Stuart | 9.18.4 | 117 | 5-7 | T | Y | 117 | 5 |  | 9.18.4 | DT | [5 empty] | When the trigger frame is sent by the non_AP_QSTA, and the STA supports both APSD and PSMP, how is it decided whether a PSMP duration will be started or a U-APSD. | It may be necessary to indicate that the non_AP_QSTA that sent the trigger frame preferrs to use the U-APSD, and cannot tolerate the latency involved in the PSMP setup. Hence we may need a dynamic method to switch the access policy between U-APSD and U-PSMP, without having to do a TSPEC negotiation.
1407 | Fischer, Matthew | 9.18.4 | 117 | 6 | T | Y | 117 | 6 |  | 9.18.4 | ST | [5 empty] | do not like the wording regarding the PS-Poll frame as a trigger frame -just not "specky" enough - also, there is a problem in that the PS-Poll frame does not have a QOS Control field/TID, so for which AC/TID is it a trigger? Also, distinguish legacy vs HT STA sending a PS-Poll and even then, HT with and without PSMP advertised. | make an explicit statement regarding just exactly how a PS-POLL frame can be used as a trigger frame - how does the AP react with respect to TID/AC? Suggest: AP can send frames from an TID/AC. And presumably, this only works if the STA sending the PS-Poll has also advertised itself as PSMP, but not for legacy STA. Write it as such.
12254 | Kumar, Rajneesh | 9.18.4 | 117 | 10 | T | Y | 117 | 10 |  | 9.18.4 | ST | [5 empty] | Why cant an A-MSDU be transmitted on a trigger ? | Please specify A-MSDU as a candidate for delivery on a trigger
1526 | Grandhi, Sudheer | 9.18.4 | 117 | 21-24 | T | Y | 117 | 21 |  | 9.18.4 | ST | [5 empty] | The Section “9.18.4 Unscheduled PSMP lines 21-24” (P802.11n-D1.0) is inconsistent with Section “11.4.4B Management of Unscheduled PSMP lines 32-36” (P802.11n-D1.0) which allows only ACK/MTBA in ULT and no data. This inconsistency in the specification has to be rectified. | Remove lines 21-24 in Section "9.18.4 Unscheduled PSMP" on page 117
10258 | Zuniga, Juan Carlos | 9.18.4 | 117 | 21-24 | T | Y | 117 | 21 |  | 9.18.4 | ST | [5 empty] | There is an inconsistency between section “9.18.4 Unscheduled PSMP lines 21-24” and section “11.4.4B Management of Unscheduled PSMP lines 32-36” which allows only ACK/MTBA in ULT and no data. This inconsistency in the specification has to be rectified. | Remove lines 21-24 in Section "9.18.4 Unscheduled PSMP" on page 117
87 | Amann, Keith | 9.18.4 | 117 | 26-28 | T | Y | 117 | 26 |  | 9.18.4 | T | [5 empty] | This paragraph has a sentance fragment at the end. It is unclear as to whether it is meant to modify the "may" clause at the start of the paragraph. | Reword.
6930 | Nanda, Sanjiv | 9.18.4 | 117 | 26 | T | Y | 117 | 26 |  | 9.18.4 | DT | [5 empty] | MTBA is used only within PSMP even for TS that use PSMP | Either MTBA is useful and must be permitted to be used outside PSMP as well, or it is not, and should be completely removed.
8036 | Thrasher, Jerry | 9.18.4 | 117 | 26-28 | E | N | 117 | 26 |  | 9.18.4 | ST | [5 empty] | This paragraph has at least one extra sentence in it… | Remove the last sentence. | Ed: reclassified as technical.
4626 | Malinen, Jouni | 9.18.4 | 117 | 27 | T | Y | 117 | 27 |  | 9.18.4 | ST | [5 empty] | Incomplete sentence “Under the regular Ack and immediate BlockAck.” Is that sentence supposed to continue with some additional information like the first sentence of this paragraph? | Clarify.
6851 | Myles, Andrew | 9.18.4 | 117 | 27 | T | Y | 117 | 27 |  | 9.18.4 | T | [5 empty] | "Under the regular Ack and immediate BlockAck." is an incompele sentence | Fix
6931 | Nanda, Sanjiv | 9.18.4 | 117 | 31 | T | Y | 117 | 31 |  | 9.18.4 | DT | [5 empty] | Use of delayed BA with MTBA. Does this require and ACK? | Complex rule. Disallow this use of MTBA with delayed BA
876 | Emeott, Stephen | 9.18.4 | 117 |  | T | Y | 117 |  |  | 9.18.4 | T | [5 empty] | Clause 9.18.1.1 contains the text "The Minimual DLT2ULT delay is the … Within a PSMP sequence, if the number of STAs that are involved cannot insure this required delay, the AP shall delay the start of the entire ULT phase to meet this constraint …" Clause 9.18.4 should include the same text | Make the recommended change
3869 | Kandala, Srinivas | 9.18.4 | 117 |  | T | Y | 117 |  |  | 9.18.4 | DT | [5 empty] | Not sure what exactly is an unscheduled PSMP and why it is needed and what problems it is solving that are not solved by U-APSD (note that even with U-APSD, you can use HT rates, A-MPDUs and BAR/BAs - yes, and you can even combine data in multiple ACs depending on how you enable them) | Provide a clear functionality that is useful or delete the subclause.
4082 | Kerry, Stuart | 9.18.4 | 117 |  | T | Y | 117 |  |  | 9.18.4 | DT | [5 empty] | When a non-AP-QSTA does not have any traffic to send and yet is given a ULT phase, how does the non-AP-QSTA give up its claim to the ULT duration, without the QAP sending a recovery PSMP frame | Clarify.
7269 | Raissinia, Ali | 9.18.4 | 117 |  | T | N | 117 |  |  | 9.18.4 | ST | [5 empty] | If STA transmits an A-MPDU as a trigger frame, will AP send a BA frame, or wait to send an MTBA frame during PSMP exchange? | This condition is not specified.
7645 | Stephens, Adrian | 9.18.4 |  |  | T | Y | 117 |  |  | 9.18.4 | T | [5 empty] | "Under the regular Ack and immediate BlockAck. " is opaque. | The note that follows seems to say everything that's necessary, so delete the quoted phrase.
7646 | Stephens, Adrian | 9.18.4 |  |  | T | N | 117 |  |  | 9.18.4 | ST | [5 empty] | "The RIFS interval is subject to the same limitation as in DLT of scheduled PSMP" is not definitive enough. | Put the RIFS limitation into its own subclause and reference from here and its original location.
7647 | Stephens, Adrian | 9.18.4 |  |  | T | N | 117 |  |  | 9.18.4 | DT | [5 empty] | "If a BlockAck agreement exists for frames transmitted within the DLT then an MTBA shall be used for acknowledgements transmitted in the ULT" - it is not exactly clear what, if any, other acknowledgement mechanisms may be used. | Add the following: "Data frames transmitted with an individual receiver address within an A-MPDU shall be a QoS Data subtype and shall have one of the following AckPolicy values: BlockAck, Normal Ack (meaning implicit MTBAR) or No Ack. Data frames transmitted with an individual receiver address as a non-aggregate shall be a QoS data subtype and shall have one of the following AckPolicy values: BlockAck or No Ack."
4523 | Loc, Peter | 9.18.1.1 | 121 | 12 | T | Y | 121 | 12 |  | 9.18.1.1 | T | [5 empty] | HT-STAs have no way of communicating to the AP if it can or can not meet the minimum DLT2ULT delay of 32us | Make ULT2DLT a negotiated parameter from the AP (which may be an overkill) or jut remove "if the number of STAs that are involved cannot ensure this required delay" from the sentence.
513 | Cole, Terry | 11.4.4A | 146 | 17 | T | Y | 146 | 17 |  | 11.4.4A | T | [5 empty] | There is no editing instruction proceeding sub-clause | Add editing instruction or remove material.
7198 | Raissinia, Ali | 11.4.4A.1 | 146-147 | 18 | T | N | 146 | 18 |  | 11.4.4A.1 | DT | [5 empty] | This section is referred as "informative" although there are statements that suggests normative behavior such as "It is always the responsibility of the non-AP STA to initiate the creation of PSMP regardless of the TSPEC direction." | Remove the "informative" text.
1029 | Fischer, Matthew | 11.4.4A.1 | 146 |  | T | Y | 146 |  |  | 11.4.4A.1 | T | [5 empty] | change to normative, now that there is a shall | remove the word "informative" from the title of the clause
3607 | Kandala, Srinivas | 11.4.4A.1 | 146 |  | T | Y | 146 |  |  | 11.4.4A.1 | T | [5 empty] | There are quite a few normative statements - either make them informative and move the entire subclause to an informational annex (as specified by the IEEE editors) or delete "(Informative)" in the title and carefully ensure that the subclause provides the correct details. | As suggested.
6874 | Nanda, Sanjiv | 11.4.4A.1 | 147 | 8 | T | Y | 147 | 8 |  | 11.4.4A.1 | T | [5 empty] | Lines 8-14 are not informative | Move normative text to a separate section
1028 | Fischer, Matthew | 11.4.4A.1 | 147 | 10 | T | Y | 147 | 10 |  | 11.4.4A.1 | ST | [5 empty] | modify to clarify and add a shall | change "The lifecycle rules of PSMP are the rules of last TSPEC associated with this particular PSMP." to "The last successfully exchanged TSPEC associated with a particular flow for a PSMP STA shall be the only valid TSPEC for that flow."
1030 | Fischer, Matthew | 11.4.4A.1 | 147 | 12 | T | Y | 147 | 12 |  | 11.4.4A.1 | ST | [5 empty] | it is not clear that a requesting STA can actually knowingly request addition of its TSPEC to an existing PSMP service, there is no part of the TSPEC that would allow it to request to be attached to any given PSMP instance - | reword this section to indicate that a STA may request PSMP service, but it is up to the AP to determine if the new TSPEC will be added to an existing instance or if a new instance will be created
3608 | Kandala, Srinivas | 11.4.4A.1 | 147 | 12 | T | Y | 147 | 12 |  | 11.4.4A.1 | T | [5 empty] | "the already existent PSMP" sounds clunky | Replace with "an already existing PSMP agreement"
1031 | Fischer, Matthew | 11.4.4A.1 | 147 | 13 | T | Y | 147 | 13 |  | 11.4.4A.1 | T | [5 empty] | the word "cannot" is an attempt to be normative | change "cannot" to "shall not" twice in the sentence
7504 | Stephens, Adrian | 11.4.4a.2 |  |  | T | Y | 147 |  |  | 11.4.4a.2 | DT | [5 empty] | "The STA may add another TSPEC under TBD conditions. " - contains a TBD. "In this case the AP shall use the Start Service Interval of already established service" - the AP may have multiple established service periods. | Replace with: "A STA with a current PSMP TS may attempt to add a new PSMP TS using a TSPEC that carries the same scheduling parameters as the current TS service period. If the AP admits this TS, it shall return the same scheduling parameters."
7505 | Stephens, Adrian | 11.4.4a.2 |  |  | T | N | 147 |  |  | 11.4.4a.2 | DT | [5 empty] | "If a STA reserves a separate TSPEC for each direction the TSID for both should be the same." - why? I can see no valid reason. | Remove the quoted sentence.
7506 | Stephens, Adrian | 11.4.4a.2 |  |  | T | N | 147 |  |  | 11.4.4a.2 | T | [5 empty] | "may not be negotiated " - not the right verb according to the following phrase. | Replace may with should
1032 | Fischer, Matthew | 11.4.4A.2 | 148 | 1 | T | Y | 148 | 1 |  | 11.4.4A.2 | ST | [5 empty] | confusing language - what does "under PSMP" mean? | please clarify by providing a different description
1033 | Fischer, Matthew | 11.4.4A.2 | 148 | 1 | T | Y | 148 | 1 |  | 11.4.4A.2 | ST | [5 empty] | need to note when PSMP is legal - maybe this goes into 11.4.4A.1 instead, and then covers both S-PSMP and U-PSMP? Maybe not? | add a sentence or two that describes the situation when a STA and AP are both aware of the fact that PSMP is the appropriate delivery method - i.e. that if and only if an AP had the PSMP bit set and if and only if the STA had the bit set in the appropriate frames, then a TSPEC shall ALWAYS be interpreted from that STA as setting up a PSMP, as opposed to sometimes or through some other magical means, determined to be so
3377 | Jokela, Jari | 11.4.4A.2 | 148 | 1 | T | Y | 148 | 1 |  | 11.4.4A.2 | ST | [5 empty] | Why Aggregation subfield shall be set to 0? Allowing to set it to 1 would be aligned with text in lines 28-29. | Clarify
3609 | Kandala, Srinivas | 11.4.4A.2 | 148 | 2 | T | Y | 148 | 2 |  | 11.4.4A.2 | T | [5 empty] | Define resource reservation | As suggested
6873 | Nanda, Sanjiv | 11.4.4A.1 | 148 | 5 | T | N | 148 | 5 |  | 11.4.4A.1 | DT | [5 empty] | Why should the TSID in the two directions be the same? | Delete this sentence
1034 | Fischer, Matthew | 11.4.4A.2 | 148 | 6 | T | Y | 148 | 6 |  | 11.4.4A.2 | ST | [5 empty] | do not limit "joining" PSMP | change the text to allow a STA to "join PSMP" at any time - if there is no PSMP which currently includes the STA, then the STA MUST of course, use a non-ULT in order to send a TSPEC, so this need not be stated, and if the STA is already part of a PSMP, the STA should be allowed to send the TSPEC whenever deemed appropriate - for example, if the TID set bits allow the TSPEC to be sent within the ULT of an existing PSMP instance, then so be it - which brings up another question, see next comment
1035 | Fischer, Matthew | 11.4.4A.2 | 148 | 13 | T | Y | 148 | 13 |  | 11.4.4A.2 | T | [5 empty] | the STA deserves to be able to expect the courtesy of a response | change "and transmits" to "and shall transmit"
1036 | Fischer, Matthew | 11.4.4A.2 | 148 | 13 | T | Y | 148 | 13 |  | 11.4.4A.2 | T | [5 empty] | ambiguous antecedent | change "this TSPEC" to "a TSPEC"
555 | CYPHER, DAVID | 11.4.4A.2 | 148 | 14 | T | Y | 148 | 14 |  | 11.4.4A.2 | T | [5 empty] | Table 26.6 is referenced | Correct reference
1037 | Fischer, Matthew | 11.4.4A.2 | 148 | 14 | T | Y | 148 | 14 |  | 11.4.4A.2 | T | [5 empty] | not sure how to make this normative | change "encoding" to "allowed encodings" - need to also add something in the sentence of the sort: "the AP shall respond with one of the result codes from the table"
1038 | Fischer, Matthew | 11.4.4A.2 | 148 | 17 | T | Y | 148 | 17 |  | 11.4.4A.2 | T | [5 empty] | attach is not the right word | change the phrase beginning with "attach" to something more like "include the requesting STA in the list of STA which are part of an existing PSMP instance"
1039 | Fischer, Matthew | 11.4.4A.2 | 148 | 23 | T | Y | 148 | 23 |  | 11.4.4A.2 | T | [5 empty] | this TSPEC re-submission was already discussed in the previous paragraph - the two descriptions contradict each other, and the second description contradicts itself, in saying that a STA "may not" negotiate, but then saying an AP is "unlikely" to negotiate, leaving some hope for the STA | resolve the contradictions between the two descriptions - STA should be allowed to attempt a resubmission with or without altered parameters - the world is a dynamic place
107 | Audeh, Malik | 11.4.4A.1 | 148 | 28 | T | Y | 148 | 28 |  | 11.4.4A.1 | ST | [5 empty] | STA may add a TSPEC under TBD conditions. | Describe those conditions.
442 | Chaplin, Clint | 11.4.4A | 148 | 28 | T | Y | 148 | 28 |  | 11.4.4A | T | [5 empty] | TBD needs to be Determined | Technically complete drafts don't have TBDs in them. Should never have gone to ballot as per IEEE SA rules
556 | CYPHER, DAVID | 11.4.4A.2 | 148 | 28 | T | Y | 148 | 28 |  | 11.4.4A.2 | T | [5 empty] | TBD is used and it has nothing to do with ANA numbering allocation. Instead it is something that has not been specified. This TBD violates the 802.11 P&P and thus invalidates this draft as a letter ballot.
825 | Ecclesine, Peter | 11.4.4A.2 | 148 | 28 | T | Y | 148 | 28 |  | 11.4.4A.2 | ST | [5 empty] | The STA may add another TSPEC under TBD conditions' - but TBD is not defined | Define the conditions where an STA may add another TSPEC.
842 | Emeott, Stephen | 11.4.4A.2 | 148 | 28 | T | Y | 148 | 28 |  | 11.4.4A.2 | ST | [5 empty] | Sentence states "The STA may add another TSPEC under TBD conditions." | Replace sentence containing TBD with text describing conditions under which STA may add a TSPEC.
1040 | Fischer, Matthew | 11.4.4A.2 | 148 | 28 | T | Y | 148 | 28 |  | 11.4.4A.2 | T | [5 empty] | why would there need to be any conditions? | let the STA decide if it would like to try to submit a new TSPEC - it might get accepted and it might get refused - there is only one way to find out - there need be no conditions, unless someone wants to describe a new piece of information that the AP sends, such as a command indicating a moratorium on new requests
1041 | Fischer, Matthew | 11.4.4A.2 | 148 | 28 | T | Y | 148 | 28 |  | 11.4.4A.2 | T | [5 empty] | the second and third sentences of this paragraph serve no purpose | delete the second and third sentences of the paragraph
1581 | Heubaum, Karl | 11.4.4A.2 | 148 | 28 | T | Y | 148 | 28 |  | 11.4.4A.2 | T | [5 empty] | “TBD” shouldn’t be here. | I don’t know what was intended for this sentence, so I can’t suggest a correction.
1660 | Hinsz, Christopher | 11.4.4A.2 | 148 | 28 | T | Y | 148 | 28 |  | 11.4.4A.2 | ST | [5 empty] | "The STA may add another TSPEC under TBD conditions." What? This is a specification, again I can understand the ANA may have caused some TBD listings, but this is standards text! This draft should NOT have gone out to ballot with TBD in it. | Define the situation in which a STA may add another TSPEC
1730 | Inoue, Yasuhiko | 11.4.4A.2 | 148 | 28 | T | Y | 148 | 28 |  | 11.4.4A.2 | T | [5 empty] | "The STA may add another TSPEC under TBD conditions." | Resolve TBD
2805 | Ji, Lusheng | 11.4.4A.2 | 148 | 28 | T | Y | 148 | 28 |  | 11.4.4A.2 | T | [5 empty] | Sponsor Ballot draft can't contain TBDs | Make change indicated in comment
4590 | Malinen, Jouni | 11.4.4A.2 | 148 | 28 | T | Y | 148 | 28 |  | 11.4.4A.2 | DT | [5 empty] | Unspecified conditions: “The STA may add another TSPEC under TBD conditions.” When will this be decided? | Describe the conditions under which another TSPEC can be added.
4800 | McNamara, Darren | 11.4.4A.2 | 148 | 28 | T | Y | 148 | 28 |  | 11.4.4A.2 | ST | [5 empty] | Presence of a 'TBD' | Replace TBD with appropriate text
7349 | Sanwalka, Anil | 11.4.4a.2 | 148 | 28 | t | Y | 148 | 28 |  | 11.4.4a.2 | DT | [5 empty] | The conditions under which an STA many send another TSPEC are not specified. | Remove paragraph
10683 | Marshall, Bill | 11.4.4A.2 | 148 | 28 | T | Y | 148 | 28 |  | 11.4.4A.2 | T | [5 empty] | Sponsor Ballot draft can't contain TBDs | Define the conditions under which a STA may add another TSPEC
557 | CYPHER, DAVID | 11.4.4A.2 | 148 | 30 | T | Y | 148 | 30 |  | 11.4.4A.2 | T | [5 empty] | Where is Figure n39 | Correct reference
5126 | Meylan, Arnaud | 11.4.4B | 148 | 31 | T | Y | 148 | 31 |  | 11.4.4B | DT | [5 empty] | U-PSMP operation is not clearly defined and its technical merits have not been demonstrated | Remove U-PSMP from draft
6876 | Nanda, Sanjiv | 11.4.4B | 148 | 31 | T | Y | 148 | 31 |  | 11.4.4B | DT | [5 empty] | Unscheduled PSMP is likely to be less efficient for power save than U-APSD! So, why are we introducing a less efficient power save procedure? | Remove U-PSMP.
1042 | Fischer, Matthew | 11.4.4B | 148 | 32 | T | Y | 148 | 32 |  | 11.4.4B | T | [5 empty] | define U-PSMP | define U-PSMP
1046 | Fischer, Matthew | 11.4.4B | 148 | 32 | T | Y | 148 | 32 |  | 11.4.4B | T | [5 empty] | need to note when PSMP is legal | add a sentence or two that describes the situation when a STA and AP are both aware of the fact that PSMP is the appropriate delivery method - i.e. that if and only if an AP had the PSMP bit set and if and only if the STA had the bit set in the appropriate frames, then a TSPEC shall ALWAYS be interpreted from that STA as setting up a PSMP, as opposed to sometimes or through some other magical means, determined to be so
1048 | Fischer, Matthew | 11.4.4B | 148 | 32 | T | Y | 148 | 32 |  | 11.4.4B | T | [5 empty] | missing a qualifying sentence | need to add a sentence noting that the AP may choose to not send data in the U-PSMP sequence DLT even though both AP and STA are PSMP capable and that the AP may choose to sometimes use PSMP and sometimes not, for data from a given AC
2808 | Ji, Lusheng | 11.4.4B | 148 | 32 | T | Y | 148 | 32 |  | 11.4.4B | ST | [5 empty] | An EDCA or U-PSMP transmission may not overwrite a beacon. If the transmission plus the expected ACK would conflict with TBTT, then the transmission must be truncated with the remainder deferred to the next TXOP after the beacon, or the transmission duration must be reduced so as not to overlay the start of TBTT. | Scheduled delivery and power save in CFP depend on disciplined timing. EDCA and U-PSMP cannot be allowed to "slip" superframe timing.
2809 | Ji, Lusheng | 11.4.4B | 148 | 32 | T | Y | 148 | 32 |  | 11.4.4B | ST | [5 empty] | Institution of a U-PSMP by an STA may not conflict with the scheduled beginning of a CFP from the serving AP if EDCA and HCCA mixed mode service is being provided. | Similar to above.
10685 | Marshall, Bill | 11.4.4B | 148 | 32 | T | Y | 148 | 32 |  | 11.4.4B | ST | [5 empty] | An EDCA or U-PSMP transmission may not overwrite a beacon. If the transmission plus the expected ACK would conflict with TBTT, then the transmission must be truncated with the remainder deferred to the next TXOP after the beacon, or the transmission duration must be reduced so as not to overlay the start of TBTT. | Scheduled delivery and power save in CFP depend on disciplined timing. U-PSMP cannot be allowed to alter the superframe timing.
10686 | Marshall, Bill | 11.4.4B | 148 | 32 | T | Y | 148 | 32 |  | 11.4.4B | ST | [5 empty] | Institution of a U-PSMP by an STA may not conflict with the scheduled beginning of a CFP from the serving AP if EDCA and HCCA mixed mode service is being provided. | Scheduled delivery and power save in CFP depend on disciplined timing. U-PSMP cannot be allowed to alter the superframe timing.
7713 | Stolpman, Victor | 11.4.4B | 148 | 33-35 | T | Y | 148 | 33 |  | 11.4.4B | DT | [5 empty] | No need to limit the use of ULT in U-PSMP mode of operation | Add the following text: “The ULT can be used by STA to signal the amount of data queued at the STA and AP can allocate required resources in the sub-PSMP or the following PSMP frame to STA to transmit its queued data."
1043 | Fischer, Matthew | 11.4.4B | 148 | 34 | T | Y | 148 | 34 |  | 11.4.4B | T | [5 empty] | confusing language | change "the same" to "a single"
1047 | Fischer, Matthew | 11.4.4B | 148 | 34 | T | Y | 148 | 34 |  | 11.4.4B | T | [5 empty] | wrong term | change "SP" to "PSMP sequence"
1044 | Fischer, Matthew | 11.4.4B | 148 | 35 | T | Y | 148 | 35 |  | 11.4.4B | T | [5 empty] | antecedent confusion | change "acknowledgement. This ACK/MTBA" to "acknowledgement, which"
9897 | Xhafa, Ariton | 11.4.4B | 148 | 35 | T | Y | 148 | 35 |  | 11.4.4B | T | [5 empty] | "This ACK/MTBA shall be transmitted at a basic rate / MCS…" MTBA is the only form of BlockAck used during PSMP; hence, only MTBA should be mentioned. | Change to: "This MTBA shall …"
1045 | Fischer, Matthew | 11.4.4B | 148 | 36 | T | Y | 148 | 36 |  | 11.4.4B | T | [5 empty] | who are you kidding? | change "precise" to "to more accurately estimate the"
7199 | Raissinia, Ali | 11.4.4B | 148 | 36 | T | Y | 148 | 36 |  | 11.4.4B | DT | [5 empty] | Add a phrase "non-HT" right before "basic rate MCS". The intent is to make sure that all control response frame communicate the NAV to OBSS and non-HT STAs. | The new statement would be "This ACK/MTBA shall be transmitted using non-HT PPDU at a non-HT basic rate/MCS (thus allowing AP precise reservation of the ULT per STA)."
3612 | Kandala, Srinivas | 11.4.4B |  |  | T | Y | 148 |  |  | 11.4.4B | T | [5 empty] | Delete unscheduled PSMP and the subclause - it doesn’t add much to the already existing unscheduled APSD. | As suggested
7507 | Stephens, Adrian | 11.4.4B |  |  | T | N | 148 |  |  | 11.4.4B | DT | [5 empty] | "The ULT shall only used by the STA for acknowledgement. " - why? The AP may be aware of the state of the STA queue from its trigger frame (QoS Control field acting as RR). It may be aware of the STA's adapted rate (it could measure the MCS from the trigger frame and indicate the MFB in its DLT). | Remove the sentence.
7508 | Stephens, Adrian | 11.4.4B |  |  | T | N | 148 |  |  | 11.4.4B | DT | [5 empty] | "This ACK/MTBA shall be transmitted at a basic rate/MCS (thus allowing AP precise reservation of the ULT per STA)." - this is neither necessary or sufficient. It is not necessary because the AP should be able to track the STA's transmit rate, or recommend a rate based on the received trigger frame. It is not sufficient because any imbalance in Tx power or Rx sensitivity makes the determination of which basic rate to use imprecise. The STA may have to use a lower basic rate to send the ULT than implied using the "next lower basic rate than the received data rate" rule. There is no such rule for S-PSMP, where it was not considered necessary. Also the use of ACK/MTBA implies Acks are permitted in the ULT of an U-PSMP. Previous statements imply only an MTBA is permitted. | Remove the sentence.
9896 | Xhafa, Ariton | 11.4.4A.2 | 148 |  | T | Y | 148 |  |  | 11.4.4A.2 | ST | [5 empty] | "The STA may add another TSPEC under TBD conditions" | TBD needs to be defined.
1055 | Fischer, Matthew | 11.5.2.1 | 149 | 6 | T | Y | 149 | 6 |  | 11.5.2.1 | T | [5 empty] | not enough specificity | change "the related TSPEC" to in general, a successul or accepted TSPEC sent by a STA which advertised PSMP support in a BSS where the AP advertised PSMP support
1056 | Fischer, Matthew | 11.5.2.1 | 149 | 6 | T | Y | 149 | 6 |  | 11.5.2.1 | T | [5 empty] | not clear - reorder the text of the paragraph to make it more clear up front that the BA agreement is explicitly set up - currently, it almost reads as though the setup is implicit | reorder the text as stated
1057 | Fischer, Matthew | 11.5.2.1 | 149 | 7 | T | Y | 149 | 7 |  | 11.5.2.1 | ST | [5 empty] | was it a requirement that a TSPEC for PSMP agreement in the 11.4.4A.1 clause shall have PSMP ack policy set to a specific value? If not, then this needs to change. | explicitly indicate the complete set of requirements for all fields in the TSPEC that sets up a PSMP session
1058 | Fischer, Matthew | 11.5.2.1 | 149 | 8 | T | Y | 149 | 8 |  | 11.5.2.1 | ST | [5 empty] | it says that the AP is an originator of a DLT - but 11.4.4A.1 says that only the STA can originate any PSMP session | clarify who really set up the PSMP session and whether this makes any difference in determining who is supposed to set up the BA agreement
1059 | Fischer, Matthew | 11.5.2.1 | 149 | 9 | T | Y | 149 | 9 |  | 11.5.2.1 | T | [5 empty] | not necessary to restrict the use of ULT for BA setup - if the new rule of PSMP session is not established until BA is setup anyway - for added TSPECs (when PSMP session is already in place) there should be no restriction | strike the restriction on session establishment - there are already features in place which will cause a restriction if the AP wants there to be a restriction
7714 | Stolpman, Victor | 11.5.2.2 | 149 | 15 | T | Y | 149 | 15 |  | 11.5.2.2 | T | [5 empty] | There is no MTBA/PSMP ACK policy | Modify the text "any data under MTBA/PSMP ack policy" to "any MTBA"
7509 | Stephens, Adrian | 11.5.2.1 |  |  | T | N | 149 |  |  | 11.5.2.1 | T | [5 empty] | "after the related TSPEC has been established" - not clear. | Replace with "after a TSPEC with a PSMP access policy has been established"
7510 | Stephens, Adrian | 11.5.2.1 |  |  | T | N | 149 |  |  | 11.5.2.1 | ST | [5 empty] | There is an implicit sequence: set up TS, set up BA agreement, use it, … Because the TS and BA are independent processes, it is not stated what is permitted while the TS is in the "waiting for BA agreement phase". | Perhaps this state should be formalised in the TS lifecycle description with a "waiting for BA agreement" for PSMP channel access TS. Regardless of this state: "A STA shall not transmit data for a TS with PSMP access policy until the related BA aggreement has completed successfully"
8269 | Wells, Bryan | 11.4.4A.2 | 155 | 14 | T | Y | 155 | 14 |  | 11.4.4A.2 | T | [5 empty] | Unable to find Table n26.6 | Is the correct reference Table n56? Resolve the reference.
8270 | Wells, Bryan | 11.4.4A.2 | 155 | 28 | T | Y | 155 | 28 |  | 11.4.4A.2 | ST | [5 empty] | TBD should be resolved. "The STA may add another TSPEC under TBD conditions." | Define the conditions under which a STA may add another TSPEC.
Note on B1: Adrian Stephens: Ed = provided by editor
Note on C1: Adrian Stephens: C = provided by commenter
Note on F1: Adrian Stephens: T = Technical E = Editorial
Note on H1: Adrian Stephens: Note: yellow shading shows that the ( C ) and ( Ed ) values differ.
Note on I1: Adrian Stephens: Note: yellow shading shows that the ( C ) and ( Ed ) values differ.
Note on K1: Adrian Stephens: Note: yellow shading shows that the ( C ) and ( Ed ) values differ.
Note on L1: Adrian Stephens: E = Editorial HE = Hard Editorial T = Technical ST=Technical requiring submission DT=Disputed Technical (no clear consensus)
Note on N1: Adrian Stephens: Resolution Status: R - rejected A - accepted L - alternate
Note on P1: Adrian Stephens: Document number of any related submission provided by comment (accept) or Assignee (alternate).
Note on Q1: 11-06-0358r4: (blank) - not brought Y - approved by motion in TGn N - rejected by motion in TGn
Note on U1: Adrian Stephens: Working version of draft containing change. Editor use only.