## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-07-2959r1
Venue Date: | Dec 2007
First Author: | Joe Kwak (InterDigital)
Subject: | TGk Sponsor Ballot Resolutions
Full Date: | 2007-12-13
Author(s): | Richard Paine (Boeing), Joe Kwak (InterDigital)
InterDigital
Bolingbrook, IL 60440
| Phone: | +1 630 739 4159
Fax:
| email: | joekwak@sbcglobal.net
Abstract:
This spreadsheet holds the resolutions drafted by the CR group for all the 2nd Recirculation Sponsor Ballot comments. These proposed resolutions have been approved by the CR group. This file is updated to post progress as decsions are made by the CRGroup.

## 11-07-2959-01-000k-11k_SB_Recir
Comment ID | Date | Comment # | Name | Email | Phone | Style | Index # | Classification | Vote | Category | Page | Subclause | Line | Comment | File | Must Be Satisfied | Proposed Change | Resolution Status | Resolution Detail | Other1 | Other2 | Other3
3469400023 | 12/04/2007 05:54:35 EST | 1 | Emmelmann, Marc | emmelmann@ieee.org | +49 -- 30 -- 314 24580 | Individual | 1 | Academic | Approve | Editorial | 2 | 3.89a | 43 | Include "set" between "service" and "transition" |  | No |  |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3473300023 | 12/05/2007 22:45:50 EST | 2 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 1 | Producer | Disapprove | Technical | 109 | 11.10.3 | 6 | "If dot11RRMNonOperatingChannelMaxMeasurementDuration is set to 0, the STA does not support RRM measurements on non-operating channels. On receipt of a measurement request frame requesting a measurement on non-operating channels, the STA shall reject the measurement request by returning a Measurement Report with the Incapable bit set in the Measurement Report Mode field" |  | Yes | "If dot11RRMNonOperatingChannelMaxMeasurementDuration is set to 0, the STA does not support RRM measurements on non-operating channels; on receipt of a measurement request frame requesting a measurement on non-operating channels, the STA shall reject the measurement request by returning a Measurement Report with the Incapable bit set in the Measurement Report Mode field" |  | PROPOSED ACCEPT IN PRINCIPLE. Change sentence structure as recommended. | Ganesh
3473400023 | 12/05/2007 22:45:50 EST | 3 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 2 | Producer | Disapprove | Technical | 111 | 11.10.5 | 29 | "A STA shall accept a Measurement Request with the parallel bit field enabled if and only if dot11RRMParallelMeasurenmentEnabled is true. Otherwise, the STA shall reject the Measurement Request by returning a Measurement Report with the Incapable bit set in the Measurement Report Mode field." Using a period between these two phrases decouples the two conditions, which is not what is meant here. Use a comma. |  | Yes | "A STA shall accept a Measurement Request with the parallel bit field enabled if and only if dot11RRMParallelMeasurenmentEnabled is true, otherwise, the STA shall reject the Measurement Request by returning a Measurement Report with the Incapable bit set in the Measurement Report Mode field." Using a period between these two phrases decouples the two conditions, which is not what is meant here. Use a comma. |  | PROPOSED ACCEPT IN PRINCIPLE. Use a semi-colon instead of a comma. | Ganesh
3473500023 | 12/05/2007 22:45:50 EST | 4 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 3 | Producer | Disapprove | Technical | 113 | 11.10.6 | 6 | There are two separate paragraphs (p127 L49 and p128 L15) that specify what to do under certain conditions. Unfortunately, the conditions are identical for both paragraphs, but the specified result is different. |  | Yes | Combine the two paragraphs into one, and harmonize the result. |  | PROPOSED ACCEPT IN PRINCIPLE. The second paragraph is not correct. Delete paragraph at P113L20. | Kwak
3473600023 | 12/05/2007 22:45:50 EST | 5 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 4 | Producer | Disapprove | Editorial | 144 | 11.10.15 | 5 | "domaine" |  | Yes | "domain" |  | PROPOSED ACCEPT. | Kwak
3474000023 | 12/06/2007 19:52:31 EST | 6 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 1 | Producer | Approve | Editorial | 2 | 3 | 37 | ", includes" |  | No | ": includes" |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3474100023 | 12/06/2007 19:52:31 EST | 7 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 2 | Producer | Approve | Editorial | 72 | 7.4.6.3 | 6 | "Transmit Power Used element" |  | No | "Transmit Power Used field" |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3474200023 | 12/06/2007 19:52:31 EST | 8 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 3 | Producer | Approve | Technical | 8 | 7.2.3.1 | 34 | MIB variables missing in qualifiers of what appears in the beacon and probe response |  | No | Add RRM enabled capabilities MIB variables ANDed with dot11RMEnabled to enable these. It may be possible to simplify the "is/otherwise can" language in this case. Apply to beacon report and probe response |  | PROPOSED ACCEPT IN PRINCIPLE. Modify MIB variable descriptions to indicate that dot11RRMxxxEnabled = TRUE also requires dot11RadioMeasurementEnabled to be TRUE. P153L7, P153L14, P153L22, P153L29, P153L37, P153L44, P154L3, P154L10, P154L18, P154L26, P1 | Kwak
3474300023 | 12/06/2007 19:52:31 EST | 9 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 4 | Producer | Approve | Editorial | 126 | 11.10.12.1 | 40 | Fontsize (continuation of note so should be note fontsize) |  | No | Fix |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3474400023 | 12/06/2007 19:52:31 EST | 10 | Hart, Brian D | brianh@cisco.com | 4085253346 | Individual | 5 | Producer | Approve | Technical | 104 | 11.1.3 | 41 | In the industry, the Request element is deprecated except for FH parameters since the extra computation slows down probe responses & it is insecure. Its application to NeighRep is undefined since that is many IEs not just 1. |  | No | Remove reference to Neighbor Report (What is the use case for this? Didn't we agree to remove the reference to it?) Change to "NOTE--MLME-SCAN.request primitives and resulting Probe Request frames may include a Request information element which can be used to request information, such as the FH Parameters and/or FH Pattern Table elements, from the scanned BSSs. Requested information from the scanned BSSs will be included in the Probe Response frames and in the MLME-SCAN.confirm primitive." |  | PROPOSED ACCEPT IN PRINCIPLE. Remove "such as Neighbor Report etc.," from P104L43. | Ganesh
3482900023 | 12/07/2007 18:53:26 EST | 11 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 5 | Producer | Disapprove | Editorial | 7 | 7 | 50 | formatting of the top-level heading "Frame formats" is lost |  | No | fix formatting of "7 Frame formats" |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3483000023 | 12/07/2007 18:53:26 EST | 12 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 6 | Producer | Disapprove | Editorial | 8 | 7.1.1 | 14 | the dash list in this clause has double dashes |  | No | remove the extra dashes from the list |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3483100023 | 12/07/2007 18:53:26 EST | 13 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 7 | Producer | Disapprove | Editorial | 8 | 7.1.1 | 15 | bad cross reference |  | No | change 7.4.7a.2 to 7.4.7.2 |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3483200023 | 12/07/2007 18:53:26 EST | 14 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 8 | Producer | Disapprove | Technical | 7 | 7.1.1 | 44 | This paragraph is introducing a new concept to 802.11, called "extensible parsing". This is using Dijkstra's canon to swat a fly. The frames listed already are defined in terms of information elements (with only two exceptions), and the definition of information elements is already extensible. The frames already include sub-elements, and an extensible mechanism to add new sub-elements to the frame definition. Since the "known length" can be infinite, "all octets in the frame beyond the known length" just don't exist. |  | No | Delete the change in 7.1.1. Change the definition of the Link Measurement Request frame (7.4.6.3) and Link Measurement Report Frame (7.4.6.4) to include optional sub-elements, matching the definition of all the other RRM frames. |  | Editor to implement 07/2690r2 | Hart
3483300023 | 12/07/2007 18:53:26 EST | 15 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 9 | Producer | Disapprove | Editorial | 15 | 7.3.1.11 | 10 | bad cross reference |  | No | change 7.4.7a to 7.4.7 |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3483400023 | 12/07/2007 18:53:26 EST | 16 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 10 | Producer | Disapprove | Technical | 15 | 7.3.2 | 44 | Since this is the first amendment to 802.11 that defines sub-elements, it is not necessary to condition the statements in the first dash list on "dot11RadioMeasurementEnabled is true". However, the first dash list item does need to be conditional. |  | No | Change the second and third dash list items to be normal statements (not part of a dash list), and make them into a separate paragraph in 7.3.2. |  | See resolution detail for comment# 14 | Hart
3483500023 | 12/07/2007 18:53:26 EST | 17 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 11 | Producer | Disapprove | Technical | 15 | 7.3.2 | 44 | Extensible parsing just doesn't make sense for information elements that already end with a variable number of optional sub-elements. |  | No | delete Measurement Request elements and Measurement Report elements from the dash list of elements subject to extensible parsing. |  | See resolution detail for comment# 14 | Hart
3483600023 | 12/07/2007 18:53:26 EST | 18 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 12 | Producer | Disapprove | Editorial | 18 | 7.3.2 | 9 | the dash list entry for Measurement Report elements is broken across two list entries |  | No | move text from the third dash list item to the end of the second item. |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Ganesh
3483700023 | 12/07/2007 18:53:26 EST | 19 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 13 | Producer | Disapprove | Technical | 16 | 7.3.2 | 10 | Extensibility of the AP Channel Report element can't be determined. Since the length of the Channel List depends on Regulatory Class (which can be extended), it is not possible for a STA receiving an AP Channel Report to perform the extensible parsing required. |  | No | Remove AP Channel Report from list of information elements subject to extensible parsing. |  | See resolution detail for comment# 14 | Hart
3483800023 | 12/07/2007 18:53:26 EST | 20 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 14 | Producer | Disapprove | Technical | 16 | 7.3.2 | 10 | Neighbor Report element already ends with a variable number of optiona sub-elements. Therefore extensible parsing doesn't apply to it. |  | No | Remove Neighbor Report from list of information elements subject to extensible parsing |  | See resolution detail for comment# 14 | Hart
3483900023 | 12/07/2007 18:53:26 EST | 21 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 15 | Producer | Disapprove | Technical | 16 | 7.3.2 | 10 | Measurement Pilot Transmission Information element already ends with a variable number of optiona sub-elements. Therefore extensible parsing doesn't apply to it. |  | No | Remove Measurement Pilot Transmission Information from list of information elements subject to extensible parsing |  | See resolution detail for comment# 14 | Hart
3484000023 | 12/07/2007 18:53:26 EST | 22 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 16 | Producer | Disapprove | Technical | 16 | 7.3.2 | 10 | Multiple BSSID element already ends with a variable number of optiona sub-elements. Therefore extensible parsing doesn't apply to it. |  | No | Remove Multiple BSSID element from list of information elements subject to extensible parsing |  | See resolution detail for comment# 14 | Hart
3484100023 | 12/07/2007 18:53:26 EST | 23 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 17 | Producer | Disapprove | Technical | 45 | 7.3.2.22.8 | 7 | Addition of optional sub-elements to the STA Statistics Report is unparseable. The length of the Statistics Group Data is variable, and depends on the value of the Group Identity. Whenever a new Group Identity is defined, the length of the Statistics Group Data will not be known to the receiving STA. |  | No | Insert a one-octet length in the IE, between Group Identity and Statistics Group Data, that contains the length of the Statistics Group Data. |  | PROPOSED ACCEPT IN PRINCIPLE. Figure 7-68h is misleading in labelling the length of the Statistics Group Date field as variable. In fact the length of this field is always fixed to the length defined in Table 7-31f for each Group Identity. Modify table | Kwak
3484200023 | 12/07/2007 18:53:26 EST | 24 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 18 | Producer | Disapprove | Editorial | 49 | 7.3.2.22.8 | 8 | Some of these statistics are defined in Annex Q, not in Annex D |  | No | change cross references (2) to include Annex Q for the definition of these statistics |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3484300023 | 12/07/2007 18:53:26 EST | 25 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 19 | Producer | Disapprove | Editorial | 76 | 7.3.2.44a | 32 | 7.3.2.44a is not an appropriate subclause number. |  | No | follow the IEEE Style Guide |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3484400023 | 12/07/2007 18:53:26 EST | 26 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 20 | Producer | Disapprove | Technical | 67 | 7.3.2.44a | 11 | Length field in octets should be set to 5, not 7. The previous draft was correct is stating that it is set to 4, with the RRM Capability bitmask being 32 bits. Extensing the Capability bitmask to 5 octets should only increase the length of the information element by one, not by 3. |  | No | change "is set to 7" to "is set to 5" |  | PROPOSED ACCEPT IN PRINCIPLE. Change P67L11 to "The Length field in octets is set to 5." | Ganesh
3484500023 | 12/07/2007 18:53:26 EST | 27 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 21 | Producer | Disapprove | Editorial | 81 | 7.3.2.44b | 38 | 7.3.2.44b is not an appropriate subclause number |  | No | follow the IEEE Style Guide |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3484600023 | 12/07/2007 18:53:26 EST | 28 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 22 | Producer | Disapprove | Technical | 72 | 7.4.6.3 | 42 | Link Measurement Request frame should include the Optional Sub-elements, as do all of the other RRM frames |  | No | add Optional Sub-elements at the end of the Link Measurement Request frame |  | PROPOSED ACCEPT IN PRINCIPLE. Add variable length field for Optional Subelements to Figure 7-101c. Add text to end of clause consistent with other instances in the draft. | Kwak
3484700023 | 12/07/2007 18:53:26 EST | 29 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 23 | Producer | Disapprove | Technical | 73 | 7.4.6.4 | 25 | Link Measurement Report frame should include the Optional Sub-elements, as do all of the other RRM frames |  | No | add Optional Sub-elements at the end of the Link Measurement Report frame |  | PROPOSED ACCEPT IN PRINCIPLE. Add variable length field for Optional Subelements to Figure 7-101d. Add text to end of clause consistent with other instances in the draft. | Kwak
3484800023 | 12/07/2007 18:53:26 EST | 30 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 24 | Producer | Disapprove | Editorial | 137 | 11.10.8.8 | 18 | QOS should be QoS |  | No | change to QoS |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3484900023 | 12/07/2007 18:53:26 EST | 31 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 25 | Producer | Disapprove | Editorial | 139 | 11.10.11 | 19 | the dash list in this clause has double dashes |  | No | remove the extra dashes from the list |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3485000023 | 12/07/2007 18:53:26 EST | 32 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 26 | Producer | Disapprove | Editorial | 140 | 11.10.12 | 1 | The line weights on the borders of this table are inconsistent |  | No | use same line weight for entire table |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3485100023 | 12/07/2007 18:53:26 EST | 33 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 27 | Producer | Disapprove | Editorial | 142 | 11.10.12.1 | 1 | something is wrong with placement of this figure |  | No | place figure inside normal boundary of page |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3485200023 | 12/07/2007 18:53:26 EST | 34 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 28 | Producer | Disapprove | Editorial | 145 | 12.3.5.9.1 | 26 | Editor's instructions should be italic |  | No | make italic |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3485300023 | 12/07/2007 18:53:26 EST | 35 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 29 | Producer | Disapprove | Editorial | 146 | 12.3.5.11.2 | 29 | Editor's instructions should be italic |  | No | make italic |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3485400023 | 12/07/2007 18:53:26 EST | 36 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 30 | Producer | Disapprove | Editorial | 148 | 15.2.7 | 1 | something is wrong with placement of this figure |  | No | place figure inside normal boundary of page |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3485500023 | 12/07/2007 18:53:26 EST | 37 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 31 | Producer | Disapprove | Technical | 203 | Annex Q | 40 | extraneous information in the MIB "SEQUENCE" entry for Dot11RRMNeighborReportEntry" |  | No | remove "(SIZE (6))" from dot11RRMNeighborReportNeighborTSKInfo, and remove "(0..65535)" from dot11RRMNeighborReportBeaconInterval |  | PROPOSED ACCEPT. | Kwak
3485600023 | 12/07/2007 18:55:39 EST | 38 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 32 | Producer | Disapprove | Editorial | 7 | 7 | 50 | (wtm) formatting of the top-level heading "Frame formats" is lost |  | Yes | fix formatting of "7 Frame formats" |  | PROPOSED ACCEPT. P7L35: Restore H1 formatting. | Kwak
3485700023 | 12/07/2007 18:55:39 EST | 39 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 33 | Producer | Disapprove | Editorial | 8 | 7.1.1 | 14 | (wtm) the dash list in this clause has double dashes |  | Yes | remove the extra dashes from the list |  | PROPOSED ACCEPT. P7L35: Correct formatting. | Kwak
3485800023 | 12/07/2007 18:55:39 EST | 40 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 34 | Producer | Disapprove | Editorial | 8 | 7.1.1 | 15 | (wtm) bad cross reference |  | Yes | change 7.4.7a.2 to 7.4.7.2 |  | PROPOSED ACCEPT. | Kwak
3485900023 | 12/07/2007 18:55:39 EST | 41 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 35 | Producer | Disapprove | Technical | 7 | 7.1.1 | 44 | (wtm) This paragraph is introducing a new concept to 802.11, called "extensible parsing". This is using Dijkstra's canon to swat a fly. The frames listed already are defined in terms of information elements (with only two exceptions), and the definition of information elements is already extensible. The frames already include sub-elements, and an extensible mechanism to add new sub-elements to the frame definition. Since the "known length" can be infinite, "all octets in the frame beyond the known length" just don't exist. |  | Yes | Delete the change in 7.1.1. Change the definition of the Link Measurement Request frame (7.4.6.3) and Link Measurement Report Frame (7.4.6.4) to include optional sub-elements, matching the definition of all the other RRM frames. |  | See resolution detail for comment# 14 | Hart
3486000023 | 12/07/2007 18:55:39 EST | 42 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 36 | Producer | Disapprove | Editorial | 15 | 7.3.1.11 | 10 | (wtm) bad cross reference |  | Yes | change 7.4.7a to 7.4.7 |  | PROPOSED ACCEPT. | Kwak
3486100023 | 12/07/2007 18:55:39 EST | 43 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 37 | Producer | Disapprove | Technical | 15 | 7.3.2 | 44 | (wtm) Since this is the first amendment to 802.11 that defines sub-elements, it is not necessary to condition the statements in the first dash list on "dot11RadioMeasurementEnabled is true". However, the first dash list item does need to be conditional. |  | Yes | Change the second and third dash list items to be normal statements (not part of a dash list), and make them into a separate paragraph in 7.3.2. |  | See resolution detail for comment# 14 | Hart
3486200023 | 12/07/2007 18:55:39 EST | 44 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 38 | Producer | Disapprove | Technical | 16 | 7.3.2 | 6 | (wtm) Extensible parsing just doesn't make sense for information elements that already end with a variable number of optional sub-elements. |  | Yes | delete Measurement Request elements and Measurement Report elements from the dash list of elements subject to extensible parsing. |  | See resolution detail for comment# 14 | Hart
3486300023 | 12/07/2007 18:55:39 EST | 45 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 39 | Producer | Disapprove | Editorial | 18 | 7.3.2 | 9 | (wtm) the dash list entry for Measurement Report elements is broken across two list entries |  | Yes | move text from the third dash list item to the end of the second item. |  | PROPOSED ACCEPT. | Kwak
3486400023 | 12/07/2007 18:55:39 EST | 46 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 40 | Producer | Disapprove | Technical | 16 | 7.3.2 | 10 | (wtm) Extensibility of the AP Channel Report element can't be determined. Since the length of the Channel List depends on Regulatory Class (which can be extended), it is not possible for a STA receiving an AP Channel Report to perform the extensible parsing required. |  | Yes | Remove AP Channel Report from list of information elements subject to extensible parsing. |  | See resolution detail for comment# 14 | Hart
3486500023 | 12/07/2007 18:55:39 EST | 47 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 41 | Producer | Disapprove | Technical | 16 | 7.3.2 | 10 | (wtm) Neighbor Report element already ends with a variable number of optional sub-elements. Therefore extensible parsing doesn't apply to it. |  | Yes | Remove Neighbor Report from list of information elements subject to extensible parsing |  | See resolution detail for comment# 14 | Hart
3486600023 | 12/07/2007 18:55:39 EST | 48 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 42 | Producer | Disapprove | Technical | 16 | 7.3.2 | 10 | (wtm) Measurement Pilot Transmission Information element already ends with a variable number of optiona sub-elements. Therefore extensible parsing doesn't apply to it. |  | Yes | Remove Measurement Pilot Transmission Information from list of information elements subject to extensible parsing |  | See resolution detail for comment# 14 | Hart
3486700023 | 12/07/2007 18:55:39 EST | 49 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 43 | Producer | Disapprove | Technical | 18 | 7.3.2 | 10 | (wtm) Multiple BSSID element already ends with a variable number of optiona sub-elements. Therefore extensible parsing doesn't apply to it. |  | Yes | Remove Multiple BSSID element from list of information elements subject to extensible parsing |  | See resolution detail for comment# 14 | Hart
3486800023 | 12/07/2007 18:55:39 EST | 50 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 44 | Producer | Disapprove | Technical | 45 | 7.3.2.22.8 | 6 | (wtm) Addition of optional sub-elements to the STA Statistics Report is unparseable. The length of the Statistics Group Data is variable, and depends on the value of the Group Identity. Whenever a new Group Identity is defined, the length of the Statistics Group Data will not be known to the receiving STA. |  | Yes | Insert a one-octet length in the IE, between Group Identity and Statistics Group Data, that contains the length of the Statistics Group Data. |  | PROPOSED ACCEPT IN PRINCIPLE. Figure 7-68h is misleading in labelling the length of the Statistics Group Date field as variable. In fact the length of this field is always fixed to the length defined in Table 7-31f for each Group Identity. Modify table | Kwak
3486900023 | 12/07/2007 18:55:39 EST | 51 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 45 | Producer | Disapprove | Editorial | 49 | 7.3.2.22.8 | 8 | (wtm) Some of these statistics are defined in Annex Q, not in Annex D |  | Yes | change cross references (2) to include Annex Q for the definition of these statistics |  | PROPOSED ACCEPT IN PRINCIPLE. P45L23&25: CHANGE "Annex D" to "Annex D or Annex Q". | Kwak
3487000023 | 12/07/2007 18:55:39 EST | 52 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 46 | Producer | Disapprove | Editorial | 76 | 7.3.2.44a | 32 | (wtm) 7.3.2.44a is not an appropriate subclause number. |  | Yes | follow the IEEE Style Guide |  | PROPOSED ACCEPT IN PRINCIPLE. Change "7.3.2.44a" to "7.3.2.45" in ALL PLACES. | Kwak
3487100023 | 12/07/2007 18:55:39 EST | 53 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 47 | Producer | Disapprove | Technical | 67 | 7.3.2.44a | 11 | (wtm) Length field in octets should be set to 5, not 7. The previous draft was correct is stating that it is set to 4, with the RRM Capability bitmask being 32 bits. Extensing the Capability bitmask to 5 octets should only increase the length of the information element by one, not by 3. |  | Yes | change "is set to 7" to "is set to 5" |  | same as CID #26 | Ganesh
3487200023 | 12/07/2007 18:55:39 EST | 54 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 48 | Producer | Disapprove | Editorial | 81 | 7.3.2.44b | 38 | (wtm) 7.3.2.44b is not an appropriate subclause number |  | Yes | follow the IEEE Style Guide |  | PROPOSED ACCEPT IN PRINCIPLE. Change "7.3.2.44b" to "7.3.2.46" in ALL PLACES. | Kwak
3487300023 | 12/07/2007 18:55:39 EST | 55 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 49 | Producer | Disapprove | Technical | 72 | 7.4.6.3 | 43 | (wtm) Link Measurement Request frame should include the Optional Sub-elements, as do all of the other RRM frames |  | Yes | add Optional Sub-elements at the end of the Link Measurement Request frame |  | PROPOSED ACCEPT IN PRINCIPLE. Add variable length field for Optional Subelements to Figure 7-101c. Add text to end of clause consistent with other instances in the draft. | Kwak
3487400023 | 12/07/2007 18:55:39 EST | 56 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 50 | Producer | Disapprove | Technical | 73 | 7.4.6.4 | 25 | (wtm) Link Measurement Report frame should include the Optional Sub-elements, as do all of the other RRM frames |  | Yes | add Optional Sub-elements at the end of the Link Measurement Report frame |  | PROPOSED ACCEPT IN PRINCIPLE. Add variable length field for Optional Subelements to Figure 7-101d. Add text to end of clause consistent with other instances in the draft. | Kwak
3487500023 | 12/07/2007 18:55:39 EST | 57 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 51 | Producer | Disapprove | Editorial | 137 | 11.10.8.8 | 18 | (wtm) QOS should be QoS |  | Yes | change to QoS |  | PROPOSED ACCEPT IN PRINCIPLE. Change "QOS" to "QoS" in ALL PLACES. | Kwak
3487600023 | 12/07/2007 18:55:39 EST | 58 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 52 | Producer | Disapprove | Editorial | 139 | 11.10.11 | 19 | (wtm) the dash list in this clause has double dashes |  | Yes | remove the extra dashes from the list |  | PROPOSED ACCEPT. | Kwak
3487700023 | 12/07/2007 18:55:39 EST | 59 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 53 | Producer | Disapprove | Editorial | 140 | 11.10.12 | 1 | (wtm) The line weights on the borders of this table are inconsistent |  | Yes | use same line weight for entire table |  | PROPOSED ACCEPT IN PRINCIPLE. Editor will attempt to change. Anomaly in Frame may not permit such a change. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE st | Kwak
3487800023 | 12/07/2007 18:55:39 EST | 60 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 54 | Producer | Disapprove | Editorial | 142 | 11.10.12.1 | 1 | (wtm) something is wrong with placement of this figure |  | Yes | place figure inside normal boundary of page |  | PROPOSED ACCEPT IN PRINCIPLE. The PDF of the draft does not seem to have a problem. The perceived problem may be limited to the redlined document. This comment is deemed editorial and delegated to the document editor for consideration in developing futur | Kwak
3487900023 | 12/07/2007 18:55:39 EST | 61 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 55 | Producer | Disapprove | Editorial | 145 | 12.3.5.9.1 | 26 | (wtm) Editor's instructions should be italic |  | Yes | make italic |  | PROPOSED ACCEPT. | Kwak
3488000023 | 12/07/2007 18:55:39 EST | 62 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 56 | Producer | Disapprove | Editorial | 146 | 12.3.5.11.2 | 29 | (wtm) Editor's instructions should be italic |  | Yes | make italic |  | PROPOSED ACCEPT. | Kwak
3488100023 | 12/07/2007 18:55:39 EST | 63 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 57 | Producer | Disapprove | Editorial | 148 | 15.2.7 | 1 | (wtm) something is wrong with placement of this figure |  | Yes | place figure inside normal boundary of page |  | PROPOSED ACCEPT IN PRINCIPLE. The PDF of the draft does not seem to have a problem. The perceived problem may be limited to the redlined document. This comment is deemed editorial and delegated to the document editor for consideration in developing futur | Kwak
3488200023 | 12/07/2007 18:55:39 EST | 64 | Chaplin, Clint | clint.chaplin@gmail.com | +1(408)239-3348 | Individual | 58 | Producer | Disapprove | Technical | 203 | Annex Q | 40 | (wtm) extraneous information in the MIB "SEQUENCE" entry for Dot11RRMNeighborReportEntry" |  | Yes | remove "(SIZE (6))" from dot11RRMNeighborReportNeighborTSKInfo, and remove "(0..65535)" from dot11RRMNeighborReportBeaconInterval |  | PROPOSED ACCEPT. | Kwak
3489200023 | 12/08/2007 20:53:10 EST | 65 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 1 | User | Approve | Technical | 22 | 7.3.2.21.6 | 37 | The new Optional Sub-elements should contain the optional fileds in the frame format, including the Reporting Information, Threshold/Offset and SSID element. |  | No | Modify Figure 7-62d deleting the 3 fields: Reporting Information, Threshold/Offset and SSID element. These will be included in the Optional Sub-elements table. |  | PROPOSED ACCEPT IN PRINCIPLE. Modify Figure 7-62d deleting the 3 fields: Reporting Information, Threshold/Offset and SSID element. These will be included in the Optional Sub-elements table. | Kwak
3489300023 | 12/08/2007 20:53:10 EST | 66 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 2 | User | Approve | Technical | 25 | 7.3.2.21.6 | 27 | The new Optional Sub-elements should contain the optional fileds in the frame format, including the Reporting Information, Threshold/Offset and SSID element. |  | No | Add Reporting Information as ID#11 in Table 7-29f. Move descriptive text fromP23L43 to an appropriate place following Table 7-29f. Add sentence indicating that "When Reportiong Information is not included in a Beacon Request, the Reporting Condition is 0 (default) and the Reporting Detail is 2 (default)." |  | PROPOSED ACCEPT IN PRINCIPLE. Add Reporting Information as ID#01 in Table 7-29f. Move descriptive text fromP23L43 to an appropriate place following Table 7-29f. Modify Figure 7-62e to replace Reporting Detail with Threshold/Offset. Add sentence indicating | Kwak
3489400023 | 12/08/2007 20:53:10 EST | 67 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 3 | User | Approve | Technical | 25 | 7.3.2.21.6 | 27 | The new Optional Sub-elements should contain the optional fileds in the frame format, including the Reporting Information, Threshold/Offset and SSID element. |  | No | Add Threshold/Offset as ID#12 in Table 7-29f. Move descriptive text fromP25L1 to an appropriate place following Table 7-29f. |  | PROPOSED ACCEPT IN PRINCIPLE. Add Reporting Detail as ID#02 in Table 7-29f. Move descriptive text fromP23L49 to an appropriate place following Table 7-29f. Add sentence indicating that "When Reporting Detail is not included in a Beacon Request, the Report | Kwak
3489500023 | 12/08/2007 20:53:10 EST | 68 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 4 | User | Approve | Technical | 25 | 7.3.2.21.6 | 27 | The new Optional Sub-elements should contain the optional fileds in the frame format, including the Reporting Information, Threshold/Offset and SSID element. |  | No | Add SSID as ID#13 in Table 7-29f. Move descriptive text fromP25L7 to an appropriate place following Table 7-29f. Add sentence indicating that "When SSID is not included in a Beacon Request, the SSID is the wildcard SSID (default)." |  | PROPOSED ACCEPT IN PRINCIPLE. Add SSID as ID#00 in Table 7-29f. Move descriptive text fromP25L7 to an appropriate place following Table 7-29f. Add sentence indicating that "When SSID is not included in a Beacon Request, the SSID is the wildcard SSID (defa | Kwak
3489600023 | 12/08/2007 20:53:10 EST | 69 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 5 | User | Approve | Technical | 41 | 7.3.2.22.6 | 14 | The Beacon Report cannot be parsed as diagrammed in Figure 7-68c. Need to know the length of the Reported Frame Body in order to parse. |  | No | Delete Reported Frame Body filed from Figure 7-68c. Add Reported Frame Body as ID#1 in Table 7-31d. Move descriptive text fromP42L20 to an appropriate place following Table 7-31d. |  | PROPOSED ACCEPT IN PRINCIPLE. Delete Length and Reported Frame Body fields from Figure 7-68c. Add Reported Frame Body as ID#1 in Table 7-31d. Move descriptive text fromP42L20 to an appropriate place following Table 7-31d. | Kwak
3489700023 | 12/08/2007 20:53:10 EST | 70 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 6 | User | Approve | Technical | 21 | 7.3.2.21.4 | 22 | The new Optional Sub-elements are not complete and should contain a Reporting Condition sub-element. |  | No | Add Channel Load Reporting Condition as ID#1 in Table 7-29a. Add descrtiptive text and table:"Channel Load Reporting Condition contains a one octet Reporting Condition subfield and a one octet Channel Load Reference value field. The Reporting Condition is described in Table XX. The Channel Load Reference value is a Channel Load value as defined in 11.10.8.3 and is the reference value for the indicated Reporting Condition." Add Table showing conditon values: 0 == Channel Load Report to be reported when measured Channel Load is equal to the Reference value; 1 == Channel Load Report to be reported when measured Channel Load is equal to or greater than the Reference value; 2 == Channel Load Report to be reported when measured Channel Load is equal to or less than the Reference value. Other table values are reserved. Add new paragraph to Channel Load Report procedure at P118L36, "If dot11RRMChannelLoadMeasurementEndabled is true and if a Channel Load Reporting Condition is included in a Channel Load Request, the STA shall respond with a Channel Load Report only if the indicated Channel Load Reporting Condition is true." |  | PROPOSED ACCEPT IN PRINCIPLE. Add Channel Load Reporting Condition as ID#1 in Table 7-29a. Add descrtiptive text and table:"Channel Load Reporting Condition contains a one octet Reporting Condition subfield and a one octet Channel Load Reference value fie | Kwak
3489800023 | 12/08/2007 20:53:10 EST | 71 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 7 | User | Approve | Technical | 22 | 7.3.2.21.5 | 13 | The new Optional Sub-elements are not complete and should contain a Reporting Condition sub-element. |  | No | Add Noise Histogram Reporting Condition as ID#1 in Table 7-29b. Add descrtiptive text and table:"Noise Histogram Reporting Condition contains a one octet Reporting Condition subfield and a one octet ANPI Reference value field. The Reporting Condition is described in Table XX. The ANPI Reference value is an ANPI value as defined in 11.10.8.4 and is the reference value for the indicated Reporting Condition." Add Table showing conditon values: 0 == Noise Histogram Report to be reported when measured ANPI is equal to the Reference value; 1 == Noise Histogram Report to be reported when measured ANPI is equal to or greater than the Reference value; 2 == Noise Histogram Report to be reported when measured ANPI is equal to or less than the Reference value. Other table values are reserved. Add new paragraph to Noise Histogram Report procedure at P118L43, "If dot11RRMNoiseHistogramMeasurementEndabled is true and if a Noise Histogram Reporting Condition is included in a Noise Histogram Request, the STA shall respond with a Noise Histogram Report only if the indicated Noise Histogram Reporting Condition is true." |  | PROPOSED ACCEPT IN PRINCIPLE. Add Noise Histogram Reporting Condition as ID#1 in Table 7-29b. Add descrtiptive text and table:"Noise Histogram Reporting Condition contains a one octet Reporting Condition subfield and a one octet ANPI Reference value fiel | Kwak
3489900023 | 12/08/2007 20:53:10 EST | 72 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 8 | User | Approve | Editorial | 149 | Annex D | 1 | Update all MIB descriptions to align with spec text. |  | No | Update all descriptions. |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3490000023 | 12/08/2007 20:53:10 EST | 73 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 9 | User | Approve | Editorial | 165 | Annex Q | 1 | Update all MIB descriptions to align with spec text. |  | No | Update all descriptions. |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3490100023 | 12/08/2007 20:53:10 EST | 74 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 10 | User | Approve | Technical | 67 | 7.3.2.44a | 11 | Length field description is incorrect. |  | No | Change 7 to 5. |  | same as CID #26 | Ganesh
3490200023 | 12/08/2007 20:53:10 EST | 75 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 11 | User | Approve | Editorial | 73 | 7.4.6.3 | 7 | Reference is incorrect. |  | No | Change 7.3.2.19 to 7.3.1.20 |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak
3490300023 | 12/08/2007 20:53:10 EST | 76 | Kwak, Joseph A | joekwak@sbcglobal.net | 630-739-4159 | Individual | 12 | User | Approve | Editorial | 73 | 7.4.6.3 | 11 | Reference is incorrect. |  | No | Change 7.3.1.20 to 7.3.1.19 |  | PROPOSED ACCEPT IN PRINCIPLE. This comment is deemed editorial and delegated to the document editor for consideration in developing future drafts. Please note that the IEEE standards are edited professionally prior to publication. | Kwak