## Slide 1: IEEE 802.11ah Timeline Projection
Date: 2011-03-3
Authors:

## Slide 2: Abstract
Initial IEEE 802.11ah timeline was created by mapping IEEE 802.11y actual timeline onto IEEE 802.11ah. Current discussions involve more than a rebanding effort. This submission presents an updated timeline.
The projected timeline is non binding. If we can do better, great!

## Slide 3: Current projected IEEE 802.11ah timeline
Initial Letter Ballot : July 2011
Initial Sponsor Ballot : July 2012
EC Approval : May 2013
Revcom Approval : July 2013

## Slide 4: Proposed update
First letter ballot process is similar to TGac.
Create new timeline to First letter ballot by reviewing TGac timeline and creating expectation for TGah.
Expect TGah timeline to be shorter than TGac.

## Slide 5: Use TGac as guide to internal task group ballot
First/Last motion
Use Cases
Chnl Mdls
Func Req
Spec Frm
Use Cases
Chnl Mdls
Func Req
Spec Frm
JAN
MAR
MAY
JUL
SEP
NOV
JAN
MAR
MAY
JUL
SEP
NOV
JAN
TGac
TGah
Sub groups formed

## Slide 6: Proposed IEEE 802.11ah timeline
Internal Task Group Ballot : March 2012
Initial Letter Ballot : July 2012
Initial Sponsor Ballot : July 2013
EC Approval : May 2014
Revcom Approval : July 2014