## Slide 1: IEEE 802.11ah Timeline Projection
Date: 2012-11-14
Authors:

## Slide 2: History
May 2012 – Move out 2 months
November 2012 – Suggest move out internal task group letter ballot and enlarging time between letter ballot to sponsor ballot.

## Slide 3: Abstract
IEEE 802.11ah timeline. This document gets updated as milestones are met.

## Slide 4: Discussion for November 2012
While we have an initial draft text submission for the PHY, achieving internal task group letter ballot in January 2013 appears unlikely.
  Suggest moving Internal Task Group ballot from Jan. 2012 to March 2013
Initially envisioned draft to be mostly PHY. However, we have a significant amount of MAC functionality in the specification framework document. Currently have one year from initial letter ballot to initial sponsor ballot.
  Suggest enlarging Initial LB to Initial SB from one year to 1.5 years.

## Slide 5: Suggested update to IEEE 802.11ah timeline
Internal Task Group Ballot : Jan. 2013 → March 2013
Initial Letter Ballot : May 2013 → July 2013
Initial Sponsor Ballot : May 2014 → Jan. 2015
EC Approval : March 2015 → November 2015
Revcom Approval : May 2015 → Jan. 2016