## Slide 1: IEEE 802.11ah Timeline Projection
Date: 2015-11-12
Authors:

## Slide 2: History
May 2012 – Move out 2 months
November 2012 – Suggest move out internal task group letter ballot and enlarging time between letter ballot to sponsor ballot
March 2013 – Move out 2 months
July 2015 – Move out 4 months because a sponsor ballot plan is postponed to a next plenary meeting
November 2015 – Update a pre-completed sponsor ballot on October and move in 2 months for an initial Recirculation Sponsor Ballot
March 2016 – Update Revcom approval to be inline with REVmc

## Slide 3: Abstract
IEEE 802.11ah timeline. This document gets updated as milestones are met.

## Slide 4: Current projected IEEE 802.11ah timeline
Internal Task Group Ballot : May 2013
Initial Letter Ballot : September 2013
Initial Recirculation Letter Ballot : September 2014
Initial Sponsor Ballot : November 2015 October 2015
Initial Recirculation Sponsor Ballot : March 2016 January 2016
EC Approval : July 2016
Revcom Approval : July September 2016