## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-12/0985
Venue Date: | July 2012
First Author: | Carlos Cordeiro, Intel Corporation
Subject: | Comments on D9.0
Full Date: | 2012-07-30
Author(s): | Carlos Cordeiro
Intel Corporation
Address
Phone:
Fax:
email: carlos.cordeiro@intel.com
Abstract:
This document contains comments submitted by the sponsor ballot members as part of SB005 on D9. This document is periodically updated to reflect the status of those comments.

## Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
10001 | Cordeiro, Carlos | 1004 | 9 |  |  |  | E | No |  |  |  |  | V |  |  |  | 1) In P425, insert line break between L12 and L13 2) Table 21-1: remove double spacing between bullets 3) Figures 21-23 and 21-24: adjust to window size 4) Capitalization. Replace "Destination" by "destination" in P306L41 | As noted. | REVISED (SB05: 2012-07-31 22:42:08Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:43 | SB05
10002 | Hunter, David | 1004 | 9 | 4.3.4.4 | 47 | 29 | T | Yes | 47 | 29 | 4.3.4.4 |  | J |  |  |  | "New architectural entities are introduced" is talking about CCSR and CCSS, But document 11-12-0233-01, which is a CRC-approved response to CRC ballot comments, specifies that the operations of CCSR and CCSS are out of scope of 802.11. How can these entities be architectural entities in 802.11 if they are out of scope of 802.11? | Replace "New architectural entities are introduced" with "Entities external to 802.11 are described". | REJECTED (SB05: 2012-07-30 23:05:40Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10003 | Hunter, David | 1004 | 9 | 4.3.7 | 50 | 4 | T | Yes | 50 | 4 | 4.3.7 |  | J |  |  |  | "The request [for SPs or SPR] is initiated by the SME": where are the primitives to do this. I cant find either an MLME to transmit an SPR frame, nor any 6.3 discussion of SMEs invoking SP-related elements to extend SPs. | Create in clause 6 (or reference here) the MLMEs that are used to transmit SPRs, extend SPs, etc. | REJECTED (SB05: 2012-07-30 23:05:53Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10004 | Hunter, David | 1004 | 9 | 4.3.7 | 50 | 12 | E | Yes | 50 | 12 | 4.3.7 |  | V |  |  |  | What does "on top of" mean here? | If it ony means "in addition to", then say that: replace "on top of the service period and contention-based access period." with "in addition to the service period and contention-based access period mechanisms.". | REVISED (SB05: 2012-07-30 21:00:48Z) 1) Replace "on top of" by "during". 2) The WG will request that IEEE-SA Editorial Staff review the resolution above prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:44 | SB05
10006 | Hunter, David | 1004 | 9 | 4.9.3 | 56 | 24 | E | Yes | 56 | 24 | 4.9.3 |  | V |  |  |  | "multi-band reference model applies across different physical layers." is an odd way of talking. How does a model apply across multiple PHYs? | Replace "across" with "to". | REVISED (SB05: 2012-07-31 22:43:43Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:44 | SB05
10005 | Hunter, David | 1004 | 9 | 4.9.3 | 56 | 29 | T | Yes | 56 | 29 | 4.9.3 |  | J |  |  |  | "multiple MAC reference model applies within each physical layer entity": how can a multiple MAC model be inside a PHY? | Replace "within" with "to". | REJECTED (SB05: 2012-07-30 23:05:57Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10008 | Hunter, David | 1004 | 9 | 4.9.4 | 58 | 23 | E | Yes | 58 | 23 | 4.9.4 |  | V |  |  |  | "between each other" is incorrect English. | Replace "between" with "with". | REVISED (SB05: 2012-07-31 22:43:52Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:44 | SB05
10007 | Hunter, David | 1004 | 9 | 4.9.4 | 58 | 7 | E | Yes | 58 | 7 | 4.9.4 |  | V |  |  |  | "multiple sublayers and it is coordinated by by an MM-SME in this case." is incorrect English. | Replace "multiple sublayers and it is coordinated by an MM-SME in this case" with "multiple sublayers; in this case it is coordinated by an MM-SME." | REVISED (SB05: 2012-07-31 22:43:59Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:44 | SB05
10009 | Hunter, David | 1004 | 9 | 8.4.2.131 | 188 | 5 | E | Yes | 188 | 5 | 8.4.2.131 |  | V |  |  |  | This is the first mention of TDDTI in the text, so needs to be defined. | Replace "TDDTI" with "time division data transfer interval (TDDTI)". | REVISED (SB05: 2012-07-31 22:44:05Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:44 | SB05
10010 | Hunter, David | 1004 | 9 | 8.4.2.131 | 188 | 5 | T | Yes | 188 | 5 | 8.4.2.131 |  | J |  |  |  | This statement is that TDDTI == 1 indicates scheduled DTI like 9.33.6, but the text in 9.33.6 never even mentions TDDTI. | In 9.33.6 refer to the relationship to TDDTI. | REJECTED (SB05: 2012-07-30 23:06:01Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10011 | Hunter, David | 1004 | 9 | 8.4.2.133 | 193 | 22 | T | Yes | 193 | 22 | 8.4.2.133 |  | J |  |  |  | What are an "awake beacon interval" and a "doze beacon interval"? Where are these defined? | Define these concepts in the draft. What might be taken to be 'definitions' in 10.2.5.1 are self-referential and inadequate; if those are replaced with adequate definitions, then include other explanations before the text in 8.4.2.133. | REJECTED (SB05: 2012-07-30 23:06:06Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10012 | Hunter, David | 1004 | 9 | 8.4.2.157 | 211 | 8 | T | Yes | 211 | 8 | 8.4.2.157 |  | J |  |  |  | The CCSR ID is 6 octets long. Obviously this can't be required, since CCSRs are outside the scope of 802.11. | Add a statement to the description of the CCSR ID field: "It is assumed that a CCSR has a 6 octet ID, whose definition is specified elsewhere." | REJECTED (SB05: 2012-07-30 23:06:10Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10013 | Hunter, David | 1004 | 9 | 8.4a.6 | 230 | 17 | T | Yes | 230 | 17 | 8.4a.6 |  | J |  |  |  | "An undefined value of the dot1... indicates that the STA does not participate in". Huh? What kind of engineering uses the lack of a definition as a trigger? How does the decisionmaker know that the dot11... MIB variable is undefined -- maybe it is defined but just returns an arbitrary value, or 0 (depending on the response algorithm)? What happens when this standard is amended and other values are added to the enum that makes up the values of the dot11... variable -- such as "dot11... is set to 23 when the STA participates in ..."? But then earlier STAs do not know the value 23, so they judge the MIB variable to be 'undefined'. | Instead, specify a value that indicates that the STA does not participate in .... | REJECTED (SB05: 2012-07-30 23:06:20Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10014 | Hunter, David | 1004 | 9 | 8.4a.6 | 230 | 28 | T | Yes | 230 | 28 | 8.4a.6 |  | J |  |  |  | In this table what happens if the first two columns take the values "0, 1"? Perhaps the referents of the first two columns are ANY two STAs. See the NOTE. | Explicitly state the consequences of the values "0, 1", even if those are "undefined". | REJECTED (SB05: 2012-07-30 23:06:16Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10015 | Hunter, David | 1004 | 9 | 9.33.6.2 | 305 | 10 | E | Yes | 305 | 10 | 9.33.6.2 |  | V |  |  |  | There is no such thing as an Extended Scheduled element. | Replace "Scheduled" with "Schedule". | REVISED (SB05: 2012-07-31 22:44:11Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:44 | SB05
10016 | Hunter, David | 1004 | 9 | 9.33.7.1 | 315 | 8 | T | Yes | 315 | 8 | 9.33.7.1 |  | J |  |  |  | This statement is really confused: "Any STA coordinated by an MM-SME that belongs to an MMSL cluster identified by the Source AID and Destination AID..." MM-SMEs do not belong to MMSL clusters. Is a whole MMSL cluster really identified by a Source AID and Destination AID? (Since I don't know what else the Source and Destination AIDs identify, I've left that claim in my proposed solution). And it is confusing which other components belong to what. | Replace: "Any STA coordinated by an MM-SME that belongs to an MMSL cluster identified by the Source AID and Destination AID of the Dynamic Allocation Info field in the Grant frame may transmit during the allocation, if the STA sent an MMS element to the peer STA and the BeamLinkCluster field within the MMS element is 1." with: "An MM-SME coordinated STA may transmit during an allocation if all of the following are true: " - The STA belongs to an MMSL cluster " - That MMSL cluster is identified by a source AID and destination AID that are equal to, respectively, the values of the Source AID and Destination AID subfields of the Dynamic Allocation Info field in the Grant frame that set up the allocation. " - The STA previously transmitted an MMS element to the peer STA " - The BeamLink Cluster field in that MMS element is 1." | REJECTED (SB05: 2012-07-30 23:06:24Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10017 | Hunter, David | 1004 | 9 | 9.34.2.2 | 327 | 33 | T | Yes | 327 | 33 | 9.34.2.2 |  | J |  |  |  | This paragraph formally requires (in a "shall" statement) specific operations in a CCSR, operations which are out of scope of 80211. Where are the operations "process of exclusion by a CCSR" and "configuration of values by a CCSR" specified in this standard? | Replace "In order to become an S-AP in a centralized PCP/AP cluster, a centralized clustering enabled STA shall:" with "To become an S-AP in a centralized PCP/AP cluster, a centralized clustering enabled STA:" And replace "have" with "has", "start" with "starts", and "include" with "includes". | REJECTED (SB05: 2012-07-30 23:06:32Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10018 | Hunter, David | 1004 | 9 | 9.35.1 | 337 | 4 | E | Yes | 337 | 4 | 9.35.1 |  | V |  |  |  | "Control PHY" is not the name of a defined object (unlike frames, fields, primitives, etc.). | Replace "Control PHY" with "control PHY" throughout the draft" -- including 21.1.1 (see 523.8, 523.24). | REVISED (SB05: 2012-07-31 22:44:17Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:44 | SB05
10020 | Hunter, David | 1004 | 9 | 9.35.1 | 338 | 3 | E | Yes | 338 | 3 | 9.35.1 |  | V |  |  |  | The commas on lines 3 and 5 separate prepositional phrases from their subjects. | Delete the commas on lines 3 and 5. | REVISED (SB05: 2012-07-31 22:44:29Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:45 | SB05
10019 | Hunter, David | 1004 | 9 | 9.35.1 | 338 | 2 | E | Yes | 338 | 2 | 9.35.1 |  | V |  |  |  | "betweew" | Run spellcheck. | REVISED (SB05: 2012-07-31 22:44:23Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:44 | SB05
10021 | Hunter, David | 1004 | 9 | 9.35.1 | 338 | 26 | T | Yes | 338 | 26 | 9.35.1 |  | J |  |  |  | This specifies that, if an MMS element has been transmitted, then the MACs shall use the same beamformed link when transmitting to the same peer. So does "link" in MMSL really mean "beamformed link"? If so, why not just include that in the definition of "MMSL"? | Replace "sublayers link" with "sublayers beamformed link". Also need to specify a reference to the subclause that specifies the setup of a beamformed link (in clause 21?). | REJECTED (SB05: 2012-07-30 23:06:37Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10022 | Hunter, David | 1004 | 9 | 10.1.1 | 397 | 8 | E | Yes | 397 | 8 | 10.1.1 |  | V |  |  |  | Extra space before the closing parens of "(10.32 Multi-band}". | Delete the extra space. | REVISED (SB05: 2012-07-31 22:44:40Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:45 | SB05
10023 | Hunter, David | 1004 | 9 | 10.1.1 | 397 | 8 | T | Yes | 397 | 8 | 10.1.1 |  | J |  |  |  | A multi-band capable device contains multiple STAs, so which one is required to contain a TSF timer? This requirement is on a device, not a MAC-PHY. The statement does not state "TSF fimer per STA" , so is one TSF timer sufficient for all active STAs? Finally, if "shall maintain a local TSF timer for each channel" means that every dualband 802.11 device shall have separate TSF timers, then what about today's 2.4/5 dualband APs? | Replace this complete sentence with "Each STA in a multi-band device that contains a DMG STA (10.32 Multi-band) shall maintain a local TSF timer.". (Assuming, of course, that a single PHY still can't operate simultaneously on two channels, right?) | REJECTED (SB05: 2012-07-30 23:06:41Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10024 | Hunter, David | 1004 | 9 | 10.1.2.1 | 397 | 40 | E | No | 397 | 40 | 10.1.2.1 |  | V |  |  |  | "AT I" on this line includes a space. | Replace "AT I" with "ATI". | REVISED (SB05: 2012-07-31 22:44:34Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:45 | SB05
10025 | Hunter, David | 1004 | 9 | 10.1.4.3.2 | 407 | 28 | E | Yes | 407 | 28 | 10.1.4.3.2 |  | V |  |  |  | The original list in 802.11-2012 is a set of separate directive sentences -- each ends with a period. Since several of those sentences remain, then keep the 802.11-2012 (and IEEE Style Manual) style and change the new text to follow the same style. By the way, changing style also requires change bars to notify the 11mc editor, so each of those semicolons should have been marked as changes. | Retain the 802.11-2012 list style on all items in the list. Change the new 11ad items in the list to complete directive sentences, with a period (instead of semicolon) at the end of each. In addition: Line 29: replace "STA;" with "STA." Line 30: replace "DMG STAs only:" with "If the STA is a DMG STA:". Line 35: replace "perform beamforming training with the peer DMG STA as defined in 9.35.5;" with "perform the beamforming training defined in 9.35.5." Line 37: replace the whole line with: "e) If the STA is a DMG STA, perform the basic access procedure defined in 9.3.4.2." Line 38: replace the item with: "f) If the STA is a non-DMG STA, transmit a probe request to the broadcast destinaton address." Line 38: create a new item: "g) If the STA is a DMG STA: " a. After transmission of an SSW-Feedback frame transmit a probe request to the MAC address of the DMG STA addressed by the SSW-Feedback frame. " b. Optionally, after reception of an SSW-Feedback frame transmit a probe request to the transmitter of the SSW-Feedback frame." Replace the remainder of f) with a new item: "h) In each of these cases the probe request is transmitted using the SSID and BSSID from the MLME-SCAN. request primitive. If the transmitter is a DMG STA, the probe request includes the DMG Capabilities element. If the SSID list is present in the MLME-SCAN. request primitive, transmit one or more probe requests, each with an SSID indicated in its SSID List field and the BSSID from the MLME-SCAN.request primitive." 408.3: Replace "g)" with "i)" and the semicolon with a period. 408.4: Replace the whole h) item with: "j) If the PHY-CCA.indication (busy) has not been detected before the ProbeTimer reaches MinChannelTime, then: " a. If the STA is a non-DMG STA, set the NAV to 0 and scan the next channel. " b. Otherwise, when the ProbeTimer reaches MaxChannelTime, process all received probe responses." 408.7: Replace "i)" with "k)". | REVISED (SB05: 2012-07-30 21:11:46Z) 1) Change the format of the noted paragraph to match the baseline 802.11-2012 format. Make no changes to wording. 2) The WG will request that IEEE-SA Editorial Staff review the resolution above prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:46 | SB05
10026 | Hunter, David | 1004 | 9 | 10.1.4.3.2 | 407 | 39 | T | Yes | 407 | 39 | 10.1.4.3.2 |  | J |  |  |  | Putting an "a)", "b)" inside an "a)", "b)" list violates the intended hierarchy. | Use a different index indicator -- probably check with Arian. Also, use the same index indicator on lines 31 and 34 above. In addition reformat to match the indented style sub-items under c) above, replacing "or, in the case of a DMG STA only," with "or, for DMG STAs only:" and indenting the sub-items below. | REJECTED (SB05: 2012-07-30 22:07:52Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10027 | Hunter, David | 1004 | 9 | 10.1.4.3.2 | 407 | 39 | T | Yes | 407 | 39 | 10.1.4.3.2 |  | J |  |  |  | Some of the logic of the list is now confused: does "in all these cases" apply to a) , b), etc, or only to the other cases in f)? In h) does the "else" apply only to DMG STAs, or to the rest of h)? | See the changes included in the comment above on line 39. Are these what was intended? | REJECTED (SB05: 2012-07-30 22:22:11Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10029 | Hunter, David | 1004 | 9 | 10.2.5.1 | 412 | 36 | E | Yes | 412 | 36 | 10.2.5.1 |  | V |  |  |  | There is no such thing as a Wakeup Scheduled element. | Replace "Scheduled" with "Schedule". | REVISED (SB05: 2012-07-31 22:45:42Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:46 | SB05
10028 | Hunter, David | 1004 | 9 | 10.2.1.2 | 412 | 12 | E | Yes | 412 | 12 | 10.2.1.2 |  | V |  |  |  | Number mistake. | Replace "any of the MMSL" with "any of the MMSLs". | REVISED (SB05: 2012-07-31 22:45:36Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:46 | SB05
10030 | Hunter, David | 1004 | 9 | 10.3.3 | 425 | 13 | T | Yes | 425 | 13 | 10.3.3 |  | J |  |  |  | This is a requirement on a device. | Replace "A multi-band capable device" with "A STA in a multi-band capable device" and delete "transmitting" on line 14. | REJECTED (SB05: 2012-07-30 22:27:08Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10031 | Hunter, David | 1004 | 9 | 10.24.3.1.2 | 458 | 11 | E | Yes | 458 | 11 | 10.24.3.1.2 |  | V |  |  |  | "where" is used for location, but does not indicate the extent of the location. | Replace "where" with "in which" to indicate that the limitation is that frequncy band. | REVISED (SB05: 2012-07-31 22:45:49Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:46 | SB05
10032 | Hunter, David | 1004 | 9 | 10.24.3.1.2 | 458 | 13 | E | Yes | 458 | 13 | 10.24.3.1.2 |  | V |  |  |  | "with" here is vague. | Replace "with the Band ID, Operating Class and Channel Number fields" with "an the Band ID, Operating Class and Channel Number fields of that frame shall be" and replace "with other fields within" with "with the other fields in". Also, "being reserved" is not something that can be done in a specific invocation of an element (it is something that is done in the definition of the element, perhaps for specific applications). So that part of this sentence needs to be a reference to the subclause in which such reservations of those fields are defined. | REVISED (SB05: 2012-07-30 21:14:30Z) 1) Replace "with the Band ID, Operating Class and Channel Number fields" with "and the Band ID, Operating Class and Channel Number fields of that frame shall be" and replace "with other fields within" with "with the other fields in" 2) The WG will request that IEEE-SA Editorial Staff review the resolution above prior to publication and implement changes as required by their editorial guidelines | SB05 |  |  | As for the question on "reserved," there is no problem in doing that. This is a protocol behavior issue. The "reserved" that the commenter is referring to is a frame format issue, which is different than the protocol behavior. |  |  |  | 2012-07-31 22:47 | SB05
10033 | Hunter, David | 1004 | 9 | 10.24.3.1.2 | 458 | 15 | E | Yes | 458 | 15 | 10.24.3.1.2 |  | V |  |  |  | "Otherwise" here is ambiguous. | Replace "Otherwise," with "If the frame requests information relative to the band in which it is transmitted," | REVISED (SB05: 2012-07-31 22:47:05Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:47 | SB05
10034 | Hunter, David | 1004 | 9 | 10.30.5 | 469 | 7 | E | Yes | 469 | 7 | 10.30.5 |  | V |  |  |  | It is not clear what the subject of the verb "uses" is. | Replace "uses" with "shall use". | REVISED (SB05: 2012-07-31 22:47:23Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:47 | SB05
10035 | Hunter, David | 1004 | 9 | 10.32.1 | 473 | 18 | T | Yes | 473 | 18 | 10.32.1 |  | J |  |  |  | "A device is ... if its local MIB variable dot11MultibandImplemented is true." But devices don't have MIB variables, as far as 802.11 knows, and an 802.11 STA doesn't know how to change the values of a device's MIB variables, if the device does have some. (Similar problems in the following sentences have been corrected, but this one was missed.) | Replace: "A device is multi-band capable if the value of its local MIB variable dot11MultibandImplemented is true." with "A STA is part of a multi-band capable device if its local MIB variable dot11MultibandImplemented is true." | REJECTED (SB05: 2012-07-30 22:32:33Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10036 | Hunter, David | 1004 | 9 | 10.32.1 | 473 | 41 | T | Yes | 473 | 41 | 10.32.1 |  | J |  |  |  | This is a requirement on a device. | Replace "A multi-band capable device" with "A STA in a multi-band capable device". And also replace the beginning of the next sentence: "If the multi-band capable device" with "If a STA in a multi-band capable device". | REJECTED (SB05: 2012-07-30 22:31:35Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10042 | Hunter, David | 1004 | 9 | 10.32.1 | 474 | 42 | T | Yes | 474 | 42 | 10.32.1 |  | J |  |  |  | This is a requirement on a device. | Replace "A multi-band capable device should" with "A STA in a multi-band capable device should". | REJECTED (SB05: 2012-07-30 22:45:02Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10043 | Hunter, David | 1004 | 9 | 10.32.1 | 474 | 45 | T | Yes | 474 | 45 | 10.32.1 |  | J |  |  |  | This is a requirement on a device. | Replace "A multi-band capable device shall" with "A STA in a multi-band capable device shall". | REJECTED (SB05: 2012-07-30 22:45:10Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10041 | Hunter, David | 1004 | 9 | 10.32.1 | 474 | 25 | T | Yes | 474 | 25 | 10.32.1 |  | J |  |  |  | This is a requirement on a device. | Replace "a multi-band capable device may" with "the STAs in a multi-band capable device may". Or does this really mean that any of the STAs may operate in each band/channel? Or, if each MAC retains its unique MAC address, then replace "a multi-band capable device" with "any of the STAs in a multi-band capable device". | REJECTED (SB05: 2012-07-30 23:07:23Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10039 | Hunter, David | 1004 | 9 | 10.32.1 | 474 | 8 | T | Yes | 474 | 8 | 10.32.1 |  | J |  |  |  | This is a description of device operations. | Replace "A multi-band" with "A STA in a multi-band". | REJECTED (SB05: 2012-07-30 22:34:51Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10038 | Hunter, David | 1004 | 9 | 10.32.1 | 474 | 3 | T | Yes | 474 | 3 | 10.32.1 |  | J |  |  |  | What does "to the difference between the TSF of the BSS the STA is member on the channel indicated in" mean? Something is missing or misplaced. | Please add whatever is missing or change whatever is misplaced to make this a clear sentence. | REJECTED (SB05: 2012-07-30 22:33:12Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10037 | Hunter, David | 1004 | 9 | 10.32.1 | 474 | 2 | T | Yes | 474 | 2 | 10.32.1 |  | J |  |  |  | This is a requirement on a device. | Replace: "The multi-band capable device shall set" with: "Each STA in a multi-band capable device shall set". | REJECTED (SB05: 2012-07-30 22:45:15Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10040 | Hunter, David | 1004 | 9 | 10.32.1 | 474 | 14 | T | Yes | 474 | 14 | 10.32.1 |  | J |  |  |  | "the STA may use" -- which STA is this? | Replace "the STA may use" with "any STA in the multi-band capable device may use" | REJECTED (SB05: 2012-07-30 22:35:18Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10044 | Hunter, David | 1004 | 9 | 10.32.2.1 | 475 | 29 | T | Yes | 475 | 29 | 10.32.2.1 |  | J |  |  |  | Need parens around the reference to the subclause. | Actually need a Word / FrameMaker reference to that suclause. | REJECTED (SB05: 2012-07-30 22:45:34Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10045 | Hunter, David | 1004 | 9 | 10.32.2.1 | 476 | 7 | T | Yes | 476 | 7 | 10.32.2.1 |  | J |  |  |  | The first sentence describes a case in which the FST Setup Request is rejected. The second sentence states "In that case, ..., the rsponder may include a Timeout Interval element in the FST Setup Response frame to indicate the period in Tus before which it initiates a FST Setup" Huh? Which is "this case" -- the rejection of the request or the acceptence of the request? This, by the way, is the problem behind the old CID 6412. | Perhaps replace "In this case," with "If the FST Setup Request is being accepted,". | REJECTED (SB05: 2012-07-30 23:07:44Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10046 | Hunter, David | 1004 | 9 | 10.32.2.1 | 476 | 11 | E | Yes | 476 | 11 | 10.32.2.1 |  | V |  |  |  | Something is missing in "the frequency band/channel the FST Ack Request and FST Ack Response frames, if any, are sent". | I suggest inserting "about which" after "channel" and replacing "sent" with "transmitted". | REVISED (SB05: 2012-07-31 22:47:34Z) The WG will request that IEEE-SA Editorial Staff review this comment prior to publication and implement changes as required by their editorial guidelines | SB05 | [6 empty] | 2012-07-31 22:48 | SB05
10047 | Hunter, David | 1004 | 9 | 10.33 | 488 | 40 | T | Yes | 488 | 40 | 10.33 |  | J |  |  |  | This subclause specifies the set up of an MMSL cluster. But where is the set up of an MMSL specified? | If the transmission/receopt of an MMS element are sufficient for the MMSL setup, then specify that here. Elset specify what are the necessary and sufficient condtions for setting up an MMSL. | REJECTED (SB05: 2012-07-30 23:07:48Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10048 | Hunter, David | 1004 | 9 | 11.5.19.1 | 515 | 42 | T | Yes | 515 | 42 | 11.5.19.1 |  | J |  |  |  | This is a description of device operations. | Replace "A multi-band capable device" with "A STA in a multi-band capable device". | REJECTED (SB05: 2012-07-30 23:07:52Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10049 | Hunter, David | 1004 | 9 | 11.5.19.1 | 516 | 4 | T | Yes | 516 | 4 | 11.5.19.1 |  | J |  |  |  | 802.11 STAs create cipher suites. | On line 4 replace "by a pair of" with "by the STAs in a pair of". On line 6 replace "devices" by "STAs". | REJECTED (SB05: 2012-07-30 23:08:00Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10050 | Hunter, David | 1004 | 9 | 11.5.19.1 | 516 | 8 | T | Yes | 516 | 8 | 11.5.19.1 |  | J |  |  |  | "(see 11.5.19)" either is an incorrect pointer (11.5.19 itself has no content), or self-referential, since 11.5.19.1 is part of 11.5.19. | Either delete this reference or change it to what was intended. | REJECTED (SB05: 2012-07-30 23:07:56Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10051 | Hunter, David | 1004 | 9 | 11.5.19.4 | 517 | 38 | T | Yes | 517 | 38 | 11.5.19.4 |  | J |  |  |  | Devices don't set up TDLS links. | Replace "When two" with "When STAs in two". This also works better with the "supported by both STAs" on line 40. | REJECTED (SB05: 2012-07-30 23:08:05Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10052 | Hunter, David | 1004 | 9 | 21.1.1 | 526 | 0 | E | Yes | 526 | 0 | 21.1.1 |  | J |  |  |  | What is a packet. Is that a frame, or something else. Define it, if is not a frame. | Replace "packet" with "frame". | REJECTED (SB05: 2012-07-30 21:09:28Z) - The term "packet" is widely used in the baseline 802.11-2012 spec in PHY clauses. It is understood as referring to a PHY packet (preamble+PLCL+..) | SB05 | [6 empty] | 2012-07-30 21:09 | SB05
10053 | Hunter, David | 1004 | 9 | 21.3.2 | 527 | 24 | T | Yes | 527 | 24 | 21.3.2 |  | J |  |  |  | Devices don't transmit. | Replace "device" with either "STA" or "PHY". | REJECTED (SB05: 2012-07-30 23:08:09Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10054 | Hunter, David | 1004 | 9 | 21.5.3.1.2 | 547 | 2 | T | Yes | 547 | 2 | 21.5.3.1.2 |  | J |  |  |  | Replace "device" with "PHY". | Replace "device" with "PHY". | REJECTED (SB05: 2012-07-30 22:46:23Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10055 | Hunter, David | 1004 | 9 | 21.6.3.1.2 | 560 | 2 | T | Yes | 560 | 2 | 21.6.3.1.2 |  | J |  |  |  | Replace "device" with "PHY". | Replace "device" with "PHY". | REJECTED (SB05: 2012-07-30 22:48:07Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10056 | Hunter, David | 1004 | 9 | 21.10.2.2.1 | 577 | 20 | T | Yes | 577 | 20 | 21.10.2.2.1 |  | J |  |  |  | "both devices" does not indicate which devices these are. | Replace "both devices" with "both transmit and receive STAs". | REJECTED (SB05: 2012-07-30 22:48:44Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05
10057 | Hunter, David | 1004 | 9 | B.4.3 | 592 | 1 | T | Yes | 592 | 1 | B.4.3 |  | J |  |  |  | The fourth column of the CF26 line specifies optional multi-band operation in which the two or more STAs are 2.4 GHz and/or 5 GHz. This specification is outside of 11ad's scope (which is limited to functions that enable 60 GHz operation -- a pair of 2.4/5 GHz STAs does not enable 60 GHz operation.) | Replace the contents of the foruth column with: "At least one of CF25 and at least one of CF4, CF6, CF15, CF17 or CF25:O". | REJECTED (SB05: 2012-07-30 23:08:27Z) Withdrawn by commenter. | SB05 | [6 empty] | 2012-07-30 23:10 | SB05