## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-13/0036r07
Venue Date: | Jan 2013
First Author: | Marc Emmelmann
Subject: | TGai D0.2 combined comments
Full Date: | 2013-01-13
Author(s): | Marc Emmelmann
| Company: | Fraunhofer FOKUS
Address
Phone:
Fax:
| email: | emmelmann@ieee.org
Abstract:
Combined comments received during the (editorial) review of TGai D0.2.
Export from comment database

## Revision History
Revision | Date | Description
0 | 2013-01-07 | Initial version
1 | 2013-01-09 | Rev.01 Update with changes from contribution 13/17r1, add two new collumns of "Comment ID" and "Similar to Comment", Similar to Comment is used to indicate comments that might point to the same or similar issues.
2 | 2013-01-13 | XL File as exported from comment database. Same as Rev.01
3 | 2013-01-13 | Corrected DCN on title page
4 | 2013-01-15 | Added Tabs for catergoriing comments.
5 | 2013-01-15 | Assign comments to volunteers and Ad-Hocs to come up with resolutions
6 | 2013-01-16 | Editor Motion Group 2 created
7 | 2013-01-16 | Removed commetn form ED Motion Grp 2 per group request and make it technical; created SEC Motion Grp 1 and GEN Motion Grp1 based on agreed resolutions
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29

## SEC Motion Grp 1
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
277 | David Goodall(11-13-0016r0) | 0 | 2 | 11.11.2.2.1 | 58 | 36 | T | Y | 58.36 | 36 | 11.11.2.2.1 |  | V | Dan Harkins |  |  | I cannot see in the draft where it is explained how to create FILS Wrapped Data and how to unwrap it on receipt. | Provide an explanation of how to create FILS Wrapped Data and how to unwrap it on receipt. | REVISED (Security: 2013-01-16 21:52:02Z) - accept: Change "shall be encoded as FILS Wrapped Data (see 8.4.1.42a)." to "shall be copied into the FILS Wrapped Data field (see 8.4.1.53)." Then on 58.41 change "the AP shall forward the STA's EAP-Initiate/Re-auth packet to the TTP" to "the AP shall extract the EAP-Initiate/Re-auth data from the FILS Wrapped Data field (see 8.4.1.53) and shall forward it to the TTP". | Security | SEC Motion Grp 1 | Rdy 4 Motion | TGai General: 2013-01-14 23:54:05Z - null edit to force export. TGai General: 2013-01-14 23:53:57Z - null edit to force export. |  |  |  | 2013-01-17 00:33 | Security
6 | David Goodall(11-13-0016r0) | 0 | 2 | 4.10.3.7 | 4 | 47 | E | Y | 4.47 | 47 | 4.10.3.7 |  | A | Dan Harkins |  |  | Typo: "with a trusted third party" should be "without an online trusted third party" | As per comment | ACCEPTED (Security: 2013-01-16 21:53:06Z) - accept: change "when FILS authentication is used with a trusted third party:" to "when FILS authentication does not use an online trusted third party." | Security | SEC Motion Grp 1 | Rdy 4 Motion | TGai General: 2013-01-14 23:54:05Z - null edit to force export. TGai General: 2013-01-14 23:53:57Z - null edit to force export. EDITOR2: 2013-01-14 17:35:49Z - Changing "with" to "without" is technical, not editorial. Will require vote to approve change. |  |  |  | 2013-01-17 00:33 | Security

## GEN Motion Grp 1
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
72 | Jarkko Kneckt (11-13-0018r0) | 0 | 2 | 8.5.8.34 | 32 | 22 | E | Y | 32.22 | 22 | 8.5.8.34 |  | J |  |  |  | The name: "FD Frame Control field" is confusing. The "Frame" and the field very closely may confuse the reader. Also the FD Capability and Control are quite close to each other. The FD Control field indicates the presence of the fields and the sizes of h | Change the name to "FD Presence field" | REJECTED (TGai General: 2013-01-15 21:59:08Z) - The group does not agree that the used name causes confusion. | TGai General | GEN Motion Grp 1 | Rdy 4 Motion | TGai General: 2013-01-15 21:59:28Z - discussed with commenter Tgai General: 2013-01-14 23:54:05Z - null edit to force export. Tgai General: 2013-01-14 23:53:57Z - null edit to force export. EDITOR2: 2013-01-14 18:51:30Z -- Think this counts as technical. |  |  |  | 2013-01-17 00:53 | TGai General
51 | Yunsong Yang (11-13-0019r0) | 0 | 2 | 6.3.3.3.2 | PDF 23 | 37 | E | Y | 0.37 | 37 | 6.3.3.3.2 |  | A |  |  |  | The term is inaccurate since the definition is about a time offset to the next TBTT | Change "Neighbor AP Next TBTT" to "Neighbor AP's Next TBTT Offset" | ACCEPTED (TGai General: 2013-01-15 21:48:31Z) | TGai General | GEN Motion Grp 1 | Rdy 4 Motion | TGai General: 2013-01-15 21:48:02Z - Group agrees to make the change and consider it as editorial Tgai General: 2013-01-14 23:54:05Z - null edit to force export. Tgai General: 2013-01-14 23:53:57Z - null edit to force export. EDITOR2: 2013-01-14 18:34:42Z -- is this really an editorial change. Pls. Confirm. |  |  |  | 2013-01-17 00:53 | TGai General
3 | David Goodall(11-13-0016r0) | 0 | 2 | 4.5.4.2 | 1 | 62 | E | Y | 1.62 | 62 | 4.5.4.2 |  | J |  |  |  | FILS authentication is stated as applying to an IBSS. | Rewrite the paragraph to separate the authentication algorithms that are applicable to BSS and IBSS respectively. | REJECTED (TGai General: 2013-01-15 20:30:56Z) There is no technical reason to prohibit FILS solutions to be used in FILS mode, though we do not actively advertise using FILS for IBSS since our focus per PAR is on BSS mode. Commenter agrees to leave text as is. | TGai General | GEN Motion Grp 1 | Rdy 4 Motion | TGai General: 2013-01-14 23:54:05Z - null edit to force export. TGai General: 2013-01-14 23:53:57Z - null edit to force export. EDITOR2: 2013-01-14 17:28:44Z - Not considered strictly editorial as it would make changes to the base-line document. |  |  |  | 2013-01-17 00:53 | TGai General

## EDITOR Motion Grp 2
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
207 | Jarkko Kneckt (11-13-0018r0) | 0 | 2 | 10.1.4.3 |  |  | E | Y |  |  | 10.1.4.3 |  | V |  |  |  | The style of showing the additions and deletions is unclear. Especially the blue color the showing the newly placed old text is new and members of the 802.11 are not used to such a notation. | Write the active scanning clauses and show only deletions and additions. | REVISED (EDITOR: 2013-01-16 22:27:52Z) - no action required. Reply from editor: Knew that the color would be an issue (was an artifact of cut/paste from the original submission), but felt that it was unimportant when compared to the big issue of just what should be in this clause and the ordering of the paragraphs. See comments at start of the clause and those copied from the submissions in the middle of the clause. | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | Knew that the color would be an issue (was an artifact of cut/paste from the original submission), but felt that it was unimportant when compared to the big issue of just what should be in this clause and the ordering of the paragraphs. See comments at start of the clause and those copied from the submissions in the middle of the clause. |  |  |  | 2013-01-16 22:41 | EDITOR
23 | Jarkko Kneckt (11-13-0018r0) | 0 | 2 | 8.3.3.10 | 15 | 12 | E | Y | 15.12 | 12 | 8.3.3.10 |  | A |  |  |  | The content of the frames are not used to describe the normative behaviour, i.e. These clauses must not contain:"may, should or shall words". | Change:" ...number may be present..." to "... number is optionally present". | ACCEPTED (EDITOR: 2013-01-16 01:24:51Z) | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | EDITOR2: 2013-01-14 18:38:33Z - Lee: Please revisit and check the satus of those comments.. |  |  |  | 2013-01-16 22:41 | EDITOR
27 | David Goodall(11-13-0016r0) | 0 | 2 | 8.3.3.11 | 16 | 8 | E | Y | 16.08 | 8 | 8.3.3.11 |  | V |  |  |  | The various FILS elements and fields don't need to be explained in the Authentication frame body, rather there should be an indication of when they are included. The FILS nonce is a field not an element. | Rewrite the notes to include a reference to Table 8-29, which indicates when the various FILS elements and fields are present in Authentication frames. | REVISED (EDITOR: 2013-01-16 16:18:54Z) Used text provided by David | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | EDITOR2: 2013-01-14 18:38:33Z - Lee: Please revisit and check the satus of those comments.. Need a specific input, not clear exactly what should be changed and what the new wording should be. |  |  |  | 2013-01-16 22:41 | EDITOR
30 | Yunsong Yang (11-13-0019r0) | 0 | 2 | n/a | PDF 17 | footer | E | Y | 0 | 0 | n/a |  | A |  |  |  | Page number in the footer section should be "11" | Page number in the footer section should continue from the previous page number | EDITOR: 2013-01-16 01:13:23Z - ACCEPTED (EDITOR: 2013-01-16 01:12:43Z) finally found the cure for this problem, it will show up in D0.4 | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | EDITOR2: 2013-01-14 18:38:33Z - Lee: Please revisit and check the satus of those comments.. |  |  |  | 2013-01-16 22:41 | EDITOR
37 | Lei Wang (11-13-008r0) | 0 | 2 | 8.4.2.175 | 20 | 54 | E | Y | 20.54 | 54 | 8.4.2.175 |  | A |  |  |  | The organization of the description of the Neighbor AP Information field does not comply with the convention of 802.11 standard spec, because subsections in 8.4.2.nnn are information elements, not information fields. The descriptions of information fields | make the following changes: 1. delete line 54 to 60 on page 20, i.e., The format of Neighbor AP Information field is described in 8.4.2.176. 8.4.2.176 Neighbor AP Information Field 2. change the subsection numbers after 8.4.2.176 accordingly. | ACCEPTED (EDITOR: 2013-01-16 01:37:32Z) will be in D0.4 | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | EDITOR2: 2013-01-14 18:38:33Z - Lee: Please revisit and check the satus of those comments.. |  |  |  | 2013-01-16 22:41 | EDITOR
40 | Jarkko Kneckt (11-13-0018r0) | 0 | 2 | 8.4.2.175 | 21 | 51 | E | Y | 21.51 | 51 | 8.4.2.175 |  | A |  |  |  | A line is missing from TBTT Offset field of the figure. | Add the line to figure. | EDITOR: 2013-01-16 01:36:28Z - ACCEPTED (EDITOR: 2013-01-16 01:36:02Z) will be in D0.4 | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | TGai General: 2013-01-15 20:02:50Z - Graph not correctly drawn. Line missing. Tgai General: 2013-01-14 23:54:05Z - null edit to force export. Tgai General: 2013-01-14 23:53:57Z - null edit to force export. |  |  |  | 2013-01-16 22:41 | EDITOR
43 | Jarkko Kneckt (11-13-0018r0) | 0 | 2 | 8.4.2.177 | 22 | 38 | E | Y | 22.38 | 38 | 8.4.2.177 |  | A |  |  |  | The element descriptions are not used to describe the normative behaviour, i.e. These clauses must not contain:"may, should or shall words". | Change" The reporting STA shall monotically increase..." to "The reporting STA monotonically increases..." | ACCEPTED (EDITOR: 2013-01-16 01:39:25Z) is already in D0.3 | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | EDITOR2: 2013-01-14 18:03:04Z - Lee, please check status. Accepted, revised, or rejected. Did you make changes? EDITOR2: 2013-01-14 18:02:44Z -- Text in draft and original submission uses the term "increment" instead of "increase" |  |  |  | 2013-01-16 22:41 | EDITOR
52 | Yunsong Yang (11-13-0019r0) | 0 | 2 | 6.3.3.3.2 | PDF 23 | 40 | E | Y | 0.4 | 40 | 6.3.3.3.2 |  | A |  |  |  | The GAS Configuration Sequence Number should not be added in the table of the BSSDescriptionFromFDSet. Instead, it should be added to the table of the BSSDescriptionSet, as it is transmitted in the Beacon or Probe Response frame, not in the FD frame. | Move the added GAS Configuration Sequence Number row to the table of the BSSDescriptionSet | ACCEPTED (EDITOR: 2013-01-16 16:37:58Z) - EDITOR: 2013-01-16 16:37:52Z - Actually, there is no "BSSDescriptionSet" table, the table that describes the BSSDescriptionSet is called the BSSDescription table. Perhaps a minor technicality but such detail is why this was added to the wrong table to begin with. The table provided in the submission did not contain a "IBSS adoption" column, so such a column was added but left blank. It is left to future comment process to propose wording for this blank cell. | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | EDITOR2: 2013-01-14 18:38:33Z - Lee: Please revisit and check the satus of those comments.. Same as CID 217, needs text to go into the "IBSS adoption" column before this can be resolved. |  |  |  | 2013-01-16 22:41 | EDITOR
57 | David Goodall(11-13-0016r0) | 0 | 2 | 8.4.2.180 | 25 | 21 | E | Y | 25.21 | 21 | 8.4.2.180 |  | V | Dan Harkins |  |  | Reference to a non-exisiting section 11.9a. | Provide correct section number. | REVISED (EDITOR: 2013-01-16 21:59:11Z) - accept: make it 11.11.2 | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | TGai General: 2013-01-15 20:07:26Z - Dan to provide correct Ref. To Editor Tgai General: 2013-01-15 20:05:32Z - need to very correct cls. Number to reference. Editor thinks it should be 11.11.2 Tgai General: 2013-01-14 23:54:05Z - null edit to force export. Tgai General: 2013-01-14 23:53:57Z - null edit to force export. EDITOR2: 2013-01-14 18:41:16Z -- what number? Only one with such a title is 11.11.2. |  |  |  | 2013-01-16 22:41 | EDITOR
93 | Jarkko Kneckt (11-13-0018r0) | 0 | 2 | 8.5.8.34 | 34 | Figure 8-460p | E | Y | 34 | 0 | 8.5.8.34 |  | A |  |  |  | The shortened format is typically after the long text, the size of the fields is not present. | Change to: " Number of Spatial Streams (NSS)" and remove 2 instances of (4 bits). | ACCEPTED (EDITOR: 2013-01-16 16:57:05Z) | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | TGai General: 2013-01-15 20:12:49Z - clarification: delete (4bits) as it is redundant information. Use "Number of Spatial Streams (NSS)" in the graphic Tgai General: 2013-01-14 23:54:05Z - null edit to force export. Tgai General: 2013-01-14 23:53:57Z - null edit to force export. EDITOR2: 2013-01-14 18:59:21Z -- ? Don't understand, 4 bits doesn't have anything to do with number of spatial streams. |  |  |  | 2013-01-16 22:41 | EDITOR
139 | Jarkko Kneckt (11-13-0018r0) | 0 | 2 | 10.1.4.3.8 | 46 | 39 | E | Y | 46.39 | 39 | 10.1.4.3.8 |  | J |  |  |  | The comparison should be based on value of the field. | Change the text to read: "... Compare the value of the received..." | REJECTED (EDITOR: 2013-01-16 17:15:44Z) | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | Seems so self-evident that it shouldn't have to be stated that it is the values that are compared. What is possible to compare other than the values? |  |  |  | 2013-01-16 22:41 | EDITOR
141 | Lei Wang (11-13-008r0) | 0 | 2 | 10.3.1 | 46 | 61 | E | Y | 46.61 | 61 | 10.3.1 |  | J |  |  |  | The first 3 paragraphs in Section 10.3.1. are exactly the same as those in the baseline standard, 802.11-2012. Why does 11ai spec have to include them? | Delete the text from line 61 page 46 to line 9 page 47. | REJECTED (EDITOR: 2013-01-16 17:16:30Z) | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | The note before the clause indicates that this is a change, these paragraphs are not changed as noted by the absence of strikethrough or underlining. The are kept in to provide easy recognition of what is being changed, where, and to assist in providing context. Such paragraphs are usually deleted when there is a large amount of such text but in this case it was felt that they could be included. |  |  |  | 2013-01-16 22:41 | EDITOR
19 | Lei Wang (11-13-008r0) | 0 | 2 | 3 and 4 | 10 | 1 | E | Y | 10.01 | 1 | 3 and 4 |  | A |  |  |  | page number reset to 1 after page 10 between Section 3 and 4 | correct the page number (between Section 3 and Secction 4) | ACCEPTED (EDITOR: 2013-01-16 00:29:03Z) | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | EDITOR2: 2013-01-14 18:38:33Z - Lee: Please revisit and check the satus of those comments.. |  |  |  | 2013-01-16 22:41 | EDITOR
157 | David Goodall(11-13-0016r0) | 0 | 2 | 11,11 | 57 | 13 | E | Y | 57.13 | 13 | 11,11 |  | A |  |  |  | Duplicate sentence "When a TTP is not used , PFS shall be used" | Remove duplicate sentence | ACCEPTED (EDITOR: 2013-01-16 18:00:59Z) - ACCEPTED (EDITOR: 2013-01-16 18:00:36Z) - Deleted the second instance. | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | Any preference as to which one is deleted? |  |  |  | 2013-01-16 22:41 | EDITOR
293 | Jarkko Kneckt (11-13-0018r0) | 0 | 2 | 8.4.2.184 |  |  | T | Y |  |  | 8.4.2.184 |  | J |  |  |  | Definition of Element ID and Length field use is missing. | Specify use of the Element ID field and Length field. | REJECTED (EDITOR: 2013-01-16 22:02:04Z)These are standard fields and terms in the standard and do not require specification/definition here. | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion |  |  |  |  | 2013-01-16 22:41 | EDITOR
212 | Jarkko Kneckt (11-13-0018r0) | 0 | 2 | 10.1.4.3.2 | 38 |  | E | Y | 38 |  | 10.1.4.3.2 |  | J |  |  |  | The 802.11ai should include text that includes the 802.11ad active scanning additions to generate the full text for the active scanning to 802.11-reaff 2014 version. | Write a submission that combines both the 802.11ad additions to active scanning and hte 802.11ai additions to active scanning. | REJECTED (EDITOR: 2013-01-16 17:38:21Z) The proposed change is a request for a submission, not an actual change proposal. Yes, please, write such a submission so we can do something about it. | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | Yes, someone please write such a submission. |  |  |  | 2013-01-16 22:41 | EDITOR
213 | Giwon Park (11-13-0017r0) | 0 | 2 | 6.3.3.2.2 | 6 | 10 | T | Y | 6.1 | 10 | 6.3.3.2.2 |  | J |  |  |  | It's not clear ReportingOption of MLME-SCAN.request. | Clarify the each Reporting mode (i.e., IMMEDIATE, CHANNEL_SPECIFIC, AT_END) in the description of the table. | REJECTED (EDITOR: 2013-01-16 17:43:38Z)This exactly matches style/contents for the Valid range and Description cells for similar entries in all base standard tables. In addition, no specific proposed text is provided that would indicate a need for change. | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion |  |  |  |  | 2013-01-16 22:41 | EDITOR
217 | Lei Wang (11-13-008r0) | 0 | 2 | 6.3.3.3.2 | 7 | 40 | T | Y | 7.4 | 40 | 6.3.3.3.2 |  | A |  |  |  | The GAS configuration sequence number is added in a wrong table, because based on the passed motion regarding the GAS configuration sequence number as proposed in 12/1046r3, it is proposed to be added in the BSSDescriptionSet, no the BSSDescriptionFromFDS | Make the following changes: 1. remove the row in line 40 on page 7; 2. in line 1 page 7: add the editor instruction and proposed Table row as proposed in 12/1046r3, page 2, the first proposed change. | ACCEPTED (EDITOR: 2013-01-16 16:38:32Z) - Actually, there is no "BSSDescriptionSet" table, the table that describes the BSSDescriptionSet is called the BSSDescription table. Perhaps a minor technicality but such detail is why this was added to the wrong table to begin with. The table provided in the submission did not contain a "IBSS adoption" column, so such a column was added but left blank. It is left to future comment process to propose wording for this blank cell. | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | Now understand this row to be added to "BSSDescription" table. Confusion was that the submission left out the right-most column "IBSS Adoption" so assumed that the submission error was in the table title rather than the table format. Before moving row to the other table, what should be the contents of "IBSS Adoption" cell? (same as CID 52) |  |  |  | 2013-01-16 22:41 | EDITOR
258 | Yunsong Yang (11-13-0019r0) | 0 | 2 | 8.4.2.178 | PDF 39 | 54 | T | Y | 0.54 | 54 | 8.4.2.178 |  | A |  |  |  | "are to be included" is not consistent with the request nature of this field. | Change "are to be included" to "are requested to be included" | ACCEPTED (EDITOR: 2013-01-16 19:06:42Z) | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion |  |  |  |  | 2013-01-16 22:41 | EDITOR
259 | Yunsong Yang (11-13-0019r0) | 0 | 2 | 8.4.2.178 | PDF 39 | 55 | T | Y | 0.55 | 55 | 8.4.2.178 |  | A |  |  |  | This subclause is about Probe Request frame format. It is better to move the description of how Neighbor Report element is included in the Probe Response frame in subclause 10.1.4.3.7. A reference can be added for clarity. | Replace the second sentence of this paragraph with "The detailed descriptions of the information of other BSSs are provided in subcluase 10.1.4.3.7.". And move the orignal second sentence to Subclause 10.1.4.3.7, P802.11ai D0.2 PDF Page 62, Line 3, after | ACCEPTED (EDITOR: 2013-01-16 19:15:56Z)Please verify that the changes were done correctly, especially the insertion in clause 10. | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion |  |  |  |  | 2013-01-16 22:41 | EDITOR
260 | Yunsong Yang (11-13-0019r0) | 0 | 2 | 8.4.2.178 | PDF 39 | 57 | T | Y | 0.57 | 57 | 8.4.2.178 |  | A |  |  |  | "is not to be included" is not consistent with the request nature of this field. | Change "is not to be included" to "is not requested". | ACCEPTED (EDITOR: 2013-01-16 19:19:59Z) | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion |  |  |  |  | 2013-01-16 22:41 | EDITOR
266 | Giwon Park (11-13-0017r0) | 0 | 2 | 10.1.4.3.6 | 45 | 22 | T | Y | 45.22 | 22 | 10.1.4.3.6 |  | A |  |  |  | Following description is the condition of the Probe Request omission. "The responding STA that is about to transmit a probe response receives an acknowledged Probe Response addressed to the requesting STA containing information of the BSS of the respondin | Modify the text as follow: STAs with dot11FILSActivated equal to true should respond to one or more Probe Request frames addressed to broadcast address with a Beacon frame if the criteria below are is met: The responding STA that is about to transmit a pr | ACCEPTED (EDITOR: 2013-01-16 21:43:51Z) Need to check results. In D0.3, this was a hyphenated list (a change from D0.2), this modification results in only a single item which does not justify a list format. In pondering the options, made it a continuation of the paragraph ending in "criteria below is met:" Please comment if there is a better way of doing this. | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | TGai General: 2013-01-15 17:20:07Z - Commenter clarified comment and proposed resolution. @EDITOR: please revisit comment and resolution: Dear Marc I replaced the strikeout text to <start/End of the deletion>. And, I replace the underlined text to the <start/End of the addition>. Please check the following: 2. CID 266 Comment: Following description is the condition of the Probe Response Broadcasting not Beacon transmission. "The responding STA that is about to transmit a probe response receives an acknowledged Probe Response addressed to the requesting STA containing information of the BSS of the responding STA." Thus, I suggest the deleting the above sentence. Proposal: Modify the text as follow: STAs with dot11FILSActivated equal to true should respond to one or more Probe Request frames addressed to broadcast address with a Beacon frame if the criteria below <Start of the deletion> are <End of the Deletion> <Start of the addition>is<End of the addition> met: <Start of the deletion>The responding STA that is about to transmit a probe response receives an acknowledged Probe Response addressed to the requesting STA containing information of the BSS of the responding STA.<End of the deletion> The next TBTT of the responding STA is within dot11BeaconResponseDuration and is no later than any deadline of Probe Response Reception Time, if the Probe Response Reception Time element is present in any Probe Request frame. Thanks Giwon Tgai General: 2013-01-14 23:54:05Z - null edit to force export. Tgai General: 2013-01-14 23:53:57Z - null edit to force export. |  |  |  | 2013-01-16 22:41 | EDITOR
268 | Yunsong Yang (11-13-0019r0) | 0 | 2 | 8.5.8.34 | PDF 50 | 10 | T | Y | 0.1 | 10 | 8.5.8.34 |  | J |  |  |  | A general comment: there are too many bits (9 in total) equivalently reserved in this 24-bit field. We can try to save one byte. |  | REJECTED (EDITOR: 2013-01-16 21:47:48Z) No Proposed Change. | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion |  |  |  |  | 2013-01-16 22:41 | EDITOR
290 | Jarkko Kneckt (11-13-0018r0) | 0 | 2 | 8.4.2.180 |  |  | T | Y |  |  | 8.4.2.180 |  | J |  |  |  | Definition of Element ID and Length field use is missing. | Specify use of the Element ID field and Length field. | REJECTED (EDITOR: 2013-01-16 22:00:50Z)These are standard fields and terms in the standard and do not require specification/definition here. | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion |  |  |  |  | 2013-01-16 22:41 | EDITOR
291 | Jarkko Kneckt (11-13-0018r0) | 0 | 2 | 8.4.2.181 |  |  | T | Y |  |  | 8.4.2.181 |  | J |  |  |  | Definition of Element ID and Length field use is missing. | Specify use of the Element ID field and Length field. | REJECTED (EDITOR: 2013-01-16 22:01:36Z)These are standard fields and terms in the standard and do not require specification/definition here. | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion |  |  |  |  | 2013-01-16 22:41 | EDITOR
292 | Jarkko Kneckt (11-13-0018r0) | 0 | 2 | 8.4.2.183 |  |  | T | Y |  |  | 8.4.2.183 |  | J |  |  |  | Definition of Element ID and Length field use is missing. | Specify use of the Element ID field and Length field. | REJECTED (EDITOR: 2013-01-16 22:01:52Z)These are standard fields and terms in the standard and do not require specification/definition here. | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion |  |  |  |  | 2013-01-16 22:41 | EDITOR
144 | David Goodall(11-13-0016r0) | 0 | 2 | 10.3.4.2 | 49 | 31 | E | Y | 49.31 | 31 | 10.3.4.2 |  | J |  |  |  | If authentication was successful for FILS then the next state will be state 5 according to Figure 10-6. | Update part c of 10.3.4.2 to be consistent with Figure 10-6. | REJECTED (EDITOR: 2013-01-16 17:20:44Z) | EDITOR | EDITOR Motion Grp 2 | Rdy 4 Motion | This is true and a change is needed, but since it is outside the original submission and constitutes a new revision of the base standard, a new submission is required to make this change. |  |  |  | 2013-01-16 22:41 | EDITOR