## Slide 1: 802.11REVmc Editor’s Report – Oct 2015
Date: 2015-10-07
Authors:

## Slide 2: Acknowledgement
The following people have kindly aided the technical editor in one way or another during the development of REVmc:
  Dorothy Stanley, Jon Rosdahl, Mark Hamilton, Mark Rison, Peter Ecclesine, Mike Montemurro, Liwen Chu, Eldad Perahia, Brian Hart, Sai Shankar, James {Yee|Wang|P.K. Gilb}, Assaf Kasher, Carlos Cordeiro, Edward Au, Kaberi Banerjee, Rich Kennedy, Yongho Seok, Carlos Aldana, Gabor Bajko
And thank you to Edward Au and Emily Qi, who are sub-editors.

## Slide 3: Status of Draft

## Slide 4: Reference Documents
Draft: P802.11REVmc D4.2 (members’ area)
WG Ballot composite comments
  11-15/0532
    LB193 comments start at CID 1000
    LB199 comments start at CID 2000
    LB202 comments start at CID 3000
    LB206 comments start at CID 4000
    SB0 is shown as “LB1000”, comments start at CID 5001
    Includes pre-ballot comments
MAC comment resolutions
  11-15/0565
GEN comment resolutions
  11-15/0665
MAC/GEN sheets usually used for motioning tech resolutions.
Composite SS may lag contents of these sheets during a session, but is the eventual resting place of approved resolutions.

## Slide 5: Comments by commenter
 | N |  |  | N Total | Y |  |  | Y Total | Grand Total
Owning Ad-hoc | E | G | T |  | E | G | T |  | 
RISON, Mark |  |  |  |  | 317 | 16 | 324 | 657 | 657
Hunter, David | 1 |  |  | 1 | 561 |  | 58 | 619 | 620
Stephens, Adrian | 15 | 23 | 4 | 42 | 14 | 39 | 50 | 103 | 145
Schelstraete, Sigurd | 17 |  | 73 | 90 |  |  |  |  | 90
Hamilton, Mark | 7 |  | 3 | 10 | 7 |  | 40 | 47 | 57
Fischer, Michael | 38 |  |  | 38 | 2 |  | 2 | 4 | 42
Hiertz, Guido | 9 |  |  | 9 | 21 | 1 | 1 | 23 | 32
Stanley, Dorothy | 9 |  |  | 9 | 21 |  | 1 | 22 | 31
Thomas, Angela |  |  |  |  |  |  | 29 | 29 | 29
Eastlake 3rd, Donald | 24 |  | 2 | 26 |  |  |  |  | 26
Bahr, Michael | 13 |  | 7 | 20 |  |  |  |  | 20
Aldana, Carlos | 3 |  | 15 | 18 |  |  |  |  | 18
TorabJahromi, Payam |  |  |  |  | 2 |  | 15 | 17 | 17
Trainin, Solomon |  |  |  |  |  |  | 12 | 12 | 12
Yang, Yunsong | 8 |  | 4 | 12 |  |  |  |  | 12
Fischer, Matthew |  |  |  |  |  |  | 11 | 11 | 11
Cordeiro, Carlos |  |  |  |  | 2 |  | 9 | 11 | 11
Seok, Yongho |  |  |  |  | 2 |  | 9 | 11 | 11
Gwynne, Gloria | 5 |  | 1 | 6 | 2 | 1 |  | 3 | 9
Ecclesine, Peter |  |  | 1 | 1 |  |  | 5 | 5 | 6
Bajko, Gabor |  |  |  |  | 1 |  | 5 | 6 | 6
Adachi, Tomoko | 3 |  | 3 | 6 |  |  |  |  | 6
Malinen, Jouni |  |  | 2 | 2 | 1 |  | 3 | 4 | 6
Qi, Emily | 2 |  | 3 | 5 |  |  |  |  | 5
Wentink, Menzo |  |  |  |  |  |  | 4 | 4 | 4
Yee, James | 3 |  |  | 3 |  |  |  |  | 3
McCann, Stephen |  |  | 3 | 3 |  |  |  |  | 3
Smith, Graham |  |  |  |  |  |  | 3 | 3 | 3
Sakoda, Kazuyuki |  |  | 2 | 2 |  |  |  |  | 2
Kasher, Assaf |  |  |  |  |  |  | 2 | 2 | 2
Hach, Rainer |  |  |  |  |  | 1 |  | 1 | 1
Eitan, Alecsander |  |  | 1 | 1 |  |  |  |  | 1
Grow, Robert |  |  |  |  |  |  | 1 | 1 | 1
Grand Total | 157 | 23 | 124 | 304 | 953 | 58 | 584 | 1595 | 1899

## Slide 6: Partition by ad-hoc
Owning Ad-hoc | Unassigned | Assigned | Discuss | Resolution Drafted | Ready for Motion | Approved | Duplicate | Grand Total
EDITOR |  | 71 |  | 8 | 1 | 1243 | 29 | 1352
GEN | 24 | 108 | 1 |  | 25 |  |  | 158
MAC | 2 | 357 |  | 4 | 26 |  |  | 389
Grand Total | 26 | 536 | 1 | 12 | 52 | 1243 | 29 | 1899

## Slide 7: Rate of Progress
We have approved 263 technical comments (May:46, June 71, July 50, Aug 49, Sept 49).
We approved these 263 technical comments in 5 months, or ~53 comments a month or about 2.5 comments per meeting hour.
  FWIW, 802.11n resolved about 7 comments per meeting hour
There are 789-263 technical comments remaining, which implies a further 10 months of comment resolution.
Based on this, my best estimate for completion of SB0 comment resolution is August 2016.
(FWIW - In May 2015, based on WG LB performance, I predicted a completion date of June 2016 for this round of comment resolution.)

## Slide 8: A brief selectrion from IEEE SASB OM
Voting in the ballot (5.4.3.2) (my highlight)
  a) Approve (Affirmative). This vote may be accompanied by comments suggesting corrections and improvements. All comments shall be considered; making a change to the proposed standard as a result of the comments is left to the discretion of the Sponsor
  Do Not Approve (Negative with comment). This vote must be accompanied by one or more specific objections with proposed resolution in sufficient detail so that the specific wording of the changes that will cause the Do Not Approve voter to change his or her vote to Approve can readily be determined. The Sponsor shall encourage the submission of comments with all Do Not Approve ballots.

## Slide 9: 5.4.3.3 & 5.4.3.5
The Sponsor shall make a reasonable attempt to resolve all Do Not Approve votes that are accompanied by comments. Comments that advocate changes in the proposed standard, whether technical or editorial, may be accepted, revised, or rejected.
Once all required recirculations have been completed and 75% approval has been achieved, the IEEE requirements for consensus have been met. Efforts to resolve Do Not Approve votes may continue for a brief period; however, if such resolution is not possible in a timely manner, the Sponsor should forward the submittal to RevCom because the IEEE has an obligation to the majority to review and publish the proposed standard quickly.

## Slide 10: Editorial Comment resolution
Owning Ad-hoc | Assigned | Ready for Motion | Approved | Duplicate | Grand Total
EDITOR | 69 | 1 | 980 | 29 | 1079
201505 approved |  |  | 1 |  | 1
201506 approved |  |  | 25 |  | 25
201507 approved |  |  | 745 | 1 | 746
201508 approved |  |  | 23 | 1 | 24
201509 approved |  |  | 176 | 1 | 177
201509 approved rework required |  |  | 10 |  | 10
Duplicates |  |  |  | 26 | 26
Editorials - assigned | 69 |  |  |  | 69
Editorials - ready for motion |  | 1 |  |  | 1
Grand Total | 69 | 1 | 980 | 29 | 1079

## Slide 11: Editorial Resolutions by Resn Status
Owning Ad-hoc | A | V | J | (blank) | Grand Total
201505 approved | 10 | 33 | 4 |  | 47
201506 approved | 29 | 55 | 11 | 1 | 96
201507 approved | 472 | 310 | 14 |  | 796
201508 approved | 7 | 53 | 11 |  | 71
201509 approved | 63 | 72 | 91 |  | 226
201509 approved rework required | 2 | 7 | 1 |  | 10
Duplicates | 9 | 8 | 6 | 3 | 26
Editorials - assigned |  |  |  | 69 | 69
Editorials - ready for motion |  | 1 |  |  | 1
General |  | 4 | 4 | 2 | 10
Grand Total | 592 | 543 | 142 | 75 | 1352

## Slide 12: Status of the editing
Owning Ad-hoc | Not edited | Edited | Grand Total
EDITOR | 5 | 1130 | 1135
201505 approved |  | 43 | 43
201506 approved |  | 84 | 84
201507 approved |  | 782 | 782
201508 approved |  | 60 | 60
201509 approved |  | 135 | 135
201509 approved rework required |  | 9 | 9
Duplicates |  | 17 | 17
Editorials - ready for motion | 1 |  | 1
General | 4 |  | 4
Grand Total | 5 | 1130 | 1135

## Slide 13: Summary of Assignees
Owning Ad-hoc | EDITOR | GEN | MAC | Grand Total
Adrian Stephens | 1 | 35 | 81 | 117
Assaf Kasher |  | 1 | 1 | 2
Carlos Cordeiro |  |  | 6 | 6
Dan Harkins |  |  | 1 | 1
Dorothy Stanley |  |  | 12 | 12
Edward Au | 7 |  |  | 7
Graham Smith |  | 4 | 33 | 37
Jon Rosdahl |  | 3 |  | 3
Mark Hamilton |  |  | 58 | 58
Mark RISON | 59 | 21 | 22 | 102
Mark Rison/Mark Hamilton |  |  | 3 | 3
Matthew Fischer |  |  | 17 | 17
Menzo Wentink |  |  | 17 | 17
Michael MONTEMURRO |  |  | 13 | 13
Peter Ecclesine |  | 1 | 3 | 4
Stephen McCann |  | 2 | 11 | 13
Vinko Erceg |  | 35 |  | 35
Ganesh Venkatesan |  |  | 1 | 1
Guido Hertz |  |  | 5 | 5
Emily Qi |  |  | 21 | 21
sigurd Schelstraete |  | 2 | 3 | 5
Payam Torab Jahroni |  | 2 | 3 | 5
Grand Total | 67 | 106 | 311 | 484

## Slide 14: Editorial Discuss/Review
Discuss = “input from TGmc needed before a resolution can be written”
Review = “resolution written, but TGmc needs to pay special attention to it”
Edit Status Review = “TGmc has approved a resolution, but editor needs to bring comment back to TGmc for further work”
CIDs 5208, 5357, 5812, 5959, 6319, 6328, 6349, 6566
These are embedded on the next slide as a spreadsheet.