## Slide 1: 802.11REVmc Editor’s Report – July 2016
Date: 2016-07-25
Authors:

## Slide 2: Acknowledgement
The following people have kindly aided the technical editor in one way or another during the development of REVmc:
  Dorothy Stanley, Jon Rosdahl, Mark Hamilton, Mark Rison, Peter Ecclesine, Mike Montemurro, Liwen Chu, Eldad Perahia, Brian Hart, Sai Shankar, James {Yee|Wang|P.K. Gilb}, Assaf Kasher, Carlos Cordeiro, Edward Au, Kaberi Banerjee, Rich Kennedy, Yongho Seok, Carlos Aldana, Gabor Bajko, Scott Marin, Graham Smith, Sigurd Schelstraete, Emily Qi
And a big thank you to Edward Au and Emily Qi, who are the sub-editors

## Slide 3: Status of Draft

## Slide 4: Reference Documents
Draft: P802.11REVmc D6.0 (members’ area)
WG & Sponsor Ballot composite comments
  11-15/0532 – currently R47
    SB0 is shown as “LB1000”, comments start at CID 5001
    SB1 is shown as “LB1001”, comments start at CID 7001
    SB2 is shown as “LB1002”, comments start at CID 8001
    Includes pre-ballot comments
MAC comment resolutions
  11-15/0565
GEN comment resolutions
  11-15/0665
MAC/GEN sheets usually used for motioning tech resolutions.
  Composite SS may lag contents of these sheets during a session, but is the eventual resting place of approved resolutions.

## Slide 5: Comments by commenter

## Slide 6: Status (2016-07-15)

## Slide 7: Detail

## Slide 8: Status of speculative editing

## Slide 9: End timing
We determined at the last meeting that we cannot meet the Aug 5th deadline for September RevCom approval, and so we have slipped our plan to a December RevCom approval.
That means we have plenty of time to resolve comments, and can take our time – doesn’t it? WRONG.
Our slip has already pushed TGah and TGai back 3 months, because they are dependent on REVmc. Worse, they have to perform potentially two recirculation ballots each to catch up with numbering & quoted text changes from REVmc, and do this after we determine that TGmc are going to make no more changes, and also hit the 17th October RevCom submission deadline. There is virtually no slack assuming we finish comment resolution in the July session.
See detailed plan to right:

## Slide 10: Implications of End Timing
If we are to avoid delaying TGah and TGai to March 2017, we have to complete SB2 comment resolution in the July session (or earlier).
We cannot afford to make any subsequent changes – i.e., D7 will the be the draft sent to RevCom.
  This means we should not make changes that are likely to carry a high risk of attracting further valid comments.
    Contentious changes
    Highly complex changes
    Partial solutions to a problem that will garner comments and suggestions for a more complete solution
  We should also put in place a more thorough editing review so that we don’t get comments of the form “you didn’t edit CID <x> correctly”.

## Slide 11: A proposed process
Reject now all comments that can validly be rejected due to “Out of Scope” or “Insufficient Detail”
Hear submissions related to unresolved comments before those related to already resolved comments.
Set a fixed time in the July session agenda to consider a motion to recirculate.
As agenda time allows, reconsider “Out of Scope” and “Insufficient Detail” comments up to the fixed time to recirculate.