## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-13/0199r0
Venue Date: | March 2013
First Author: | Adrian Stephens (Intel Corporation)
Subject: | TGac D5.0 comments
Full Date: | 2013-02-19
Author(s): | Robert Stacey
| Company: | Intel Corporation
Address
Phone:
Fax:
| email: | adrian.p.stephens@intel.com
Abstract:
This document contains working update on comments submitted for the TGac P802.11ac/D5.0 and their resolution.
There is a separate tab for each ad-hoc, plus a tab for all the comments (most comments exist in two places).
Note the tab name might be a compressed representation of the comment group name to meet Excel tab naming restrictions.

## Revision History
Revision | Date | Description
0 | 2013-01-04 | Comments from LB191 added, with initial assignements to EDITOR, MAC and PHY ad-hocs.
1 | 2013-02-19 | Withdrawn and resolved Editorial. Few MAC remaining
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29

## Withdrawn
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
8036 | Liwen Chu | 191 | 5 | 9.19.2.4 | 154 | 47 | T | N | 154.47 | 47 | 9.19.2.4 |  | J | Allan |  |  | CTS-to-Self protection is not consistant with the RTS/CTS protection when the TXOP has multiple CTS e.g. CTS-to-Self, A-MPDU, BlkAck,A-MPDU, BlkAck, RTS/CTS, A-MPDU, BlkAck. | Disallow TXOPs like "CTS-to-Self, A-MPDU, BlkAck,A-MPDU, BlkAck, RTS/CTS, A-MPDU, BlkAck" or rewrite the rule the TXOP protected for CTS-to-Self. | REJECTED (MAC: 2013-02-15 10:28:55Z): Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:29:04Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8001 | Matthew Fischer | 191 | 5 | 11.4.4.1 | 197 | 42 | T | Y | 197.42 | 42 | 11.4.4.1 |  | J | Adrian |  |  | Need to add a BIP-CMAC-256 cipher suite to allow some symmetry with CCMP-256. | Add AES-256 in CMAC mode to this introduction (11.4.4.1 BIP overview) and within the relevant descriptive and behavioral sections. E.g. 11.4.4.5 BIP transmission and 11.4.4.6 BIP reception | REJECTED (MAC: 2013-02-15 10:04:40Z): Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:12:00Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8026 | Yusuke Asai | 191 | 5 | 22.3.11.2 | 304 | 15 | T | N | 304.15 | 15 | 22.3.11.2 |  | J | Eldad |  |  | "j" in "(0 \leq j \leq N_{user})" should be revsed to u. | As in comment. | REJECTED (PHY: 2013-02-13 23:53:46Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | PHY: 2013-02-13 06:32:41Z - withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8027 | Yusuke Asai | 191 | 5 | 22.3.11.4 | 304 | 59 | T | N | 304.59 | 59 | 22.3.11.4 |  | J | Eldad |  |  | "VHT-LTF symbols in the MU transmission" should be revised to "VHT-LTF symbols in the VHT MU PPDU". | As in comment. | REJECTED (PHY: 2013-02-13 23:53:49Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | PHY: 2013-02-13 06:32:41Z - withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8029 | Yusuke Asai | 191 | 5 | B.4.23.2 | 372 | 32 | G | N | 372.32 | 32 | B.4.23.2 |  | J | Osama |  |  | Static BW operation is mandatory feature and its signaling is carried by non-HT duplicate PPDUs. This inherently suggest that transmission function of non-HT duplicate PPDUs is mandatory for a VHT STA; however, it is not clear whether a VHT STA shall support to transmit non-HT duplicate PPDUs or not. | Add a corresponding row for non-HT duplicate format to PICS (in B.4.23.2) as well as "VHTP2: VHT format". | REJECTED (MAC: 2013-02-15 10:45:57Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:46:13Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8031 | Liwen Chu | 191 | 5 | 8.2.4.6.3 | 39 | 36 | T | N | 39.36 | 36 | 8.2.4.6.3 |  | J | Adrian |  |  | "If the unsolicited MFB is estimated from an SU PPDU, the MFSI/GID-L subfield is set to all 1s" If "MFSI/GID-L" indicates SU PPDU sequence number, the receiver will know which frame is used to estimate the feedback information. | Change to "If the unsolicited MFB is estimated from an SU PPDU, the MFSI/GID-L subfield is set to b2 to b0 of the frame sequence number used for feedback extimation". A hash function may also be used to hash sequence number to 6 bits. And the MFSI/GID-L subfield is set to b2 to b0 of the hash result. | REJECTED (MAC: 2013-02-15 10:24:56Z): Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:25:03Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8032 | Liwen Chu | 191 | 5 | 8.2..4.6.3 | 39 | 60 | T | N | 39.6 | 60 | 8.2..4.6.3 |  | J | Adrian |  |  | "If the unsolicited MFB is estimated from an SU PPDU, the GID-H subfield is set to all 1s" If "GID-H" indicates SU PPDU sequence number, the receiver will know which frame is used to estimate the feedback information. | Change to "If the unsolicited MFB is estimated from an SU PPDU, the GID-H subfield is set to b5 to b3 of the frame sequence number used for feedback extimation" A hash function may also be used to hash sequence number to 6 bits. And the GID-H subfield is set to b5 to b3 of the hash result. | REJECTED (MAC: 2013-02-15 10:26:06Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:26:20Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8022 | Yusuke Asai | 191 | 5 | 22.3.8.3.3 | 265 | 39 | T | N | 265.39 | 39 | 22.3.8.3.3 |  | J | Eldad |  |  | "SU and MU PPDUs" should be revised to "VHT SU and MU PPDUs" | As in comment. | REJECTED (PHY: 2013-02-13 23:53:39Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | PHY: 2013-02-13 06:32:41Z - withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8034 | Liwen Chu | 191 | 5 | 8.4.2.160.2 | 98 | 32 | E | N | 98.32 | 32 | 8.4.2.160.2 |  | J | Matt |  |  | Change Encoding part to "Set to 0 if the AP does not support TXOP Power Save Mode. Set to 1 if the AP supports TXOP Power Save Mode. Set to 0 if the STA does not enable TXOP Power Save Mode. Set to 1 if the STA enables TXOP Power Save Mode." | Change Encoding part to "Set to 0 if the AP does not support TXOP Power Save Mode. Set to 1 if the AP supports TXOP Power Save Mode. Set to 0 if the STA does not enable TXOP Power Save Mode. Set to 1 if the STA enables TXOP Power Save Mode." | REJECTED (MAC: 2013-02-15 10:27:37Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | EDITOR: 2013-02-04 09:53:16Z - It looks like this is asking for a technical change. Assigning to MAC. MAC: 2013-02-15 10:28:11Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8021 | Yusuke Asai | 191 | 5 | 22.3.8.3.2 | 264 | 53 | T | N | 264.53 | 53 | 22.3.8.3.2 |  | J | Eldad |  |  | M_u is already defined in Table 22-6 (P252L12). | Delete the equation and refer to Table 22-6. | REJECTED (PHY: 2013-02-13 23:53:34Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | PHY: 2013-02-13 06:32:41Z - withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8037 | Liwen Chu | 191 | 5 | 9.7.11.3 | 140 | 17 | T | N | 140.17 | 17 | 9.7.11.3 |  | J | Allan |  |  | Additional rate selection constraints for VHT PPDUs should also inlcudes additional restriction of VHT Basic MCS set. Further if Supported VHT MCS Set and VHT Basic MCS Set are reqefined by the current MCS definition and removing the MCS restricted by 9.7.11.3, less changes qre required in other parts of 11ac draft e.g. rate selection in 9.7. | As proposed. | REJECTED (MAC: 2013-02-15 10:30:14Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:30:24Z -Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8061 | David Goodall | 191 | 5 | 11.4 | 196 |  | T | Y | 196 |  | 11.4 |  | J | Adrian |  |  | There is no top secret level BIP based on CMAC. This means that implementations of BIP are forced to implement GCMP-256 to achieve top secret level security. | Define a BIP-CMAC-256 cipher suite that may allow implementations of BIP to make use of the same hardware or software that is required for CCMP-256. | REJECTED (MAC: 2013-02-15 10:17:47Z): Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:17:54Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8072 | Wei Shi | 191 | 5 | 9.12.6 | 145 | 6 | T | Y | 145.06 | 6 | 9.12.6 |  | J | Jae Seung |  |  | "Have 0 in the MPDU Length field" is not sufficient, because you cannot (see line 33) add a zero-length subframe with EOF = 0 after one with EOF = 1. | Add text "and 0 in the EOF field" or "and 1 in the EOF field" or, if you really want to, something like "and 1 in the EOF field if A-MPDU subframes with 0 in the MPDU Length field and 1 in the EOF field are already present in the A-MPDU" (Is it ok to have VHT single MPDU followed by EOF = 0, MPDU length = 0?) | REJECTED (MAC: 2013-02-15 10:13:37Z): Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:15:55Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8073 | Wei Shi | 191 | 5 | 9.31.5.2 | 172 | 42 | T | Y | 172.42 | 42 | 9.31.5.2 |  | J | Allan |  |  | If a BFer does not receive a VHT Compressed Beamforming frame correctly from the BFee then it could send a BF report poll to retrieve it again. In this case does the BFee need to set the retry bit high in the "retried" VHT Compressed Beamforming frame that it sends? | Retry bit in a VHT Compressed Beamforming frame shall always be set to zero. | REJECTED (MAC: 2013-02-15 10:15:05Z): Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:15:20Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8074 | Mark RISON | 191 | 5 | 9.3.2.6 | 125 | 39 | T | Y | 125.39 | 39 | 9.3.2.6 |  | J | Allan |  |  | "The CTS frame's TXVECTOR parameters CH_BANDWIDTH and CH_BANDWIDTH_IN_NON_HT may be set to any channel width for which [...]" -- this is mandatory, not optional, behaviour | Change to "[...] shall be set to a channel width for which [...]" | REJECTED (MAC: 2013-02-15 09:53:05Z) - Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 09:31:23Z - Withdrawn by commenter. |  |  |  | 2013-02-18 14:59 | MAC
8076 | Mark RISON | 191 | 5 | 22.3.19.5.2 | 318 | 48 | T | Y | 318.48 | 48 | 22.3.19.5.2 |  | J | Youhan |  |  | This subclause starts "For the operating classes requiring CCA-Energy Detect (CCA-ED)" but examination of Annex E shows that the only operating classes requiring CCA-ED are in the 3G band and the maximum channel width is 20 MHz, so this subclause seems otiose at best and misleading at worst | Delete this subclause | REJECTED (PHY: 2013-02-14 15:55:46Z) - Withdrawn by commenter. | EDITOR | Withdrawn |  | Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8077 | Mark RISON | 191 | 5 | 9.12.6 | 144 | 44 | T | Y | 144.44 | 44 | 9.12.6 |  | J | Jae Seung |  |  | The second bullet appears to allow a VHT single MPDU (i.e. one with EOF = 1) to be followed by null subframes with EOF = 0. Once EOF has been signalled, it makes no sense to unsignal it (cf. 145.33) | Change "0 in the EOF field" to "the same value in the EOF field as the preceding A-MPDU subframe" | REJECTED (MAC: 2013-02-15 09:55:12Z): Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 09:31:23Z - Withdrawn by commenter. |  |  |  | 2013-02-18 14:59 | MAC
8033 | Liwen Chu | 191 | 5 | 8.2.4.7.1 | 43 | 4 | T | N | 43.04 | 4 | 8.2.4.7.1 |  | J | Adrian |  |  | The unit of size and duration is missing. | Add them. | REJECTED (MAC: 2013-02-15 10:26:57Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:27:09Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8010 | Yusuke Asai | 191 | 5 | 8.4.1.48 | 60 | 24 | T | N | 60.24 | 24 | 8.4.1.48 |  | J | Adrian |  |  | The possible values of N_{STS,NDP} are not clear. | Add the sentence: N_{STS,NDP} may take values from 1 to 8. | REJECTED (MAC: 2013-02-15 10:43:12Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:43:23Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8002 | Matthew Fischer | 191 | 5 | 8.3.1.1 | 45 | 22 | T | Y | 45.22 | 22 | 8.3.1.1 |  | J | Adrian |  |  | MOREDATA bit in control frames should be ignored by receivers. Currently, the requirement is that the bit is set to "0" in all Control frames. But this might contradict the value in Data frames that are transmitted in the same TXOP. | Either change the MOREDATA bit in Control frames to reserved, in which case, it will be ignored at receivers, but there needs to be an exception for the ACK frame when dot11moredataackoptionimplemented is true (although that exception should already be in the standard, but it is NOT!) - OR - create a line of behavioral text somewhere that explicitly instructs recipients to ignore the bit, with the moredataACK exception. | REJECTED (MAC: 2013-02-15 10:10:36Z): Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:11:07Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8003 | Yongho Seok | 191 | 5 | 8.4.2.88 | 95 | 65 | T | N | 95.65 | 65 | 8.4.2.88 |  | J | Adrian |  |  | If the channel usage element supports 80MHz/160MHz/80+80MHz channel bandwidth, the Channel Usage Response frame should also include the VHT Transmit Power Envelope element as an optional feature. Because the Power Constraint element couldn't indicate the local maximum transmit power for 80MHz/160MHz/80+80MHz. | Include th VHT Transmit Power Envelope element in Figure 8-495 Channel Usage Response frame format as an optional IE. | REJECTED (MAC: 2013-02-15 10:57:55Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:58:44Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8004 | Yongho Seok | 191 | 5 | 10.2.1.17 | 1004 |  | T | N | 1004 |  | 10.2.1.17 |  | J | Menzo |  |  | In the TIM Broadcast, some 11ac specific events shall be considered as critical updates for increasing the value of the Check Beacon field. | In the TIM Broadcast, add the following event as a critical update: - Inclusion of a Wide Bandwidth Channel Switch element - Inclusion of a Channel Switch Wrapper element - Inclusion of a Operating Mode Notification element - Inclusion of a Quiet Channel element - Modification of the VHT Operating element | REJECTED (MAC: 2013-02-15 10:59:26Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:59:39Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8005 | Yongho Seok | 191 | 5 | 8.4.2.164 | 104 | 25 | T | N | 104.25 | 25 | 8.4.2.164 |  | J | Menzo |  |  | For the backward compatibility, the length field of IE shall be set to the number of octets of the remaining fields. | The Length field of the VHT Transmit Power Envelope element varies between 1 and 5, not 1 and 4. | REJECTED (MAC: 2013-02-15 11:00:15Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 11:00:31Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8006 | Yongho Seok | 191 | 5 | 8.4.2.165 | 105 | 64 | T | N | 105.64 | 64 | 8.4.2.165 |  | J | Menzo |  |  | The length of the Channel Switch Wrapper element can be set to a value greater than 3. | Correct the range of value of the length field. | REJECTED (MAC: 2013-02-15 11:00:56Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 11:01:08Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8007 | Yusuke Asai | 191 | 5 | 3.2 | 4 | 24 | T | N | 4.24 | 24 | 3.2 |  | J | Yusuke |  |  | "where the two frequency segments of channels are not adjacent." is not needed because it is defined in P306L57 that the two frequency segments in 80+80 MHz transmission are always non-adjacent with each other. | Dele the phrase. | REJECTED (MAC: 2013-02-15 10:40:12Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:40:22Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8025 | Yusuke Asai | 191 | 5 | 22.3.11.1 | 303 | 39 | T | N | 303.39 | 39 | 22.3.11.1 |  | J | Eldad |  |  | N_{STS,u} is not used but referred in Equation (22-101). | Detele P303L39. Instead, add the reference for N_{TX} as follows: "N_{TX} is defined in Table 22-6 (Frequently used parameters). | REJECTED (PHY: 2013-02-13 23:53:42Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | PHY: 2013-02-13 06:32:41Z - withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8009 | Yusuke Asai | 191 | 5 | 13 | 7 | 13 | T | N | 7.13 | 13 | 13 |  | J | Edward |  |  | "MU PPDU" is not defined in TGac Draft. | Replace "MU PPDU" with "VHT MU PPDU" throughout the draft. Ditto P126L35, P127L4, P167L4, P192L56, P193L28, P265L39, P280L9, P280L46, P280L62, P321L1, P385L32, P385L46, P385L59, P399L13, P399L16, P399L20, P399L33, P399L37, P399L43 and P400L12. Otherwise, define the term of "MU PPDU". | REJECTED (MAC: 2013-02-15 10:42:20Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:42:36Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8080 | Mark RISON | 191 | 5 | 8.4.2.164 | 104 | 54 | T | Y | 104.54 | 54 | 8.4.2.164 |  | J | Menzo |  |  | The VHT Transmit Power Envelope is described as being about the power limit for a "transmission bandwidth" but this term is not defined either here or in the baseline. Specifically, is this referring to the PPDU width, the PPDU mask, or the channel width? Note also the use of "PPDU bandwidth" in one other place, which too is ambiguous as to whether it's the PPDU or the mask | Change "transmission bandwidth" and "PPDU bandwidth" to "mask bandwidth" | REJECTED (MAC: 2013-02-15 09:58:40Z): Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 09:31:23Z - Withdrawn by commenter. |  |  |  | 2013-02-18 14:59 | MAC
8012 | Yusuke Asai | 191 | 5 | 9.3.2.9a | 126 | 34 | T | N | 126.34 | 34 | 9.3.2.9a |  | J | Allan |  |  | According to the title of the Figure 9-9a, "MU PPDU" transmitted by AP should be replaced with "VHT MU PPDU". Ditto Figure 9-9b. | As in comment. | REJECTED (MAC: 2013-02-15 10:43:57Z) - Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:44:07Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8013 | Yusuke Asai | 191 | 5 | 18.3.5.5 | 214 | 18 | T | N | 214.18 | 18 | 18.3.5.5 |  | J | Edward |  |  | CBW_IN_NON_HT_TEMP should be replaced with CbwInNonHtTemp according to Table 18-6a. | As in comment. | REJECTED (MAC: 2013-02-15 10:44:39Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:44:50Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8015 | Yusuke Asai | 191 | 5 | 22.2.2 | 230 | 15 | E | N | 230.15 | 15 | 22.2.2 |  | J | Yusuke |  |  | The cells for TXVECTOR and RXVECTOR are blank. | Add "N" to these cells. | REJECTED (PHY: 2013-02-14 15:47:34Z) - Withdrawn by commenter. | EDITOR | Withdrawn |  | EDITOR: 2013-02-04 10:00:26Z - Requires technical interpretation. Assigning to PHY. Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8016 | Yusuke Asai | 191 | 5 | 22.2.4.3 | 234 | 40 | T | N | 234.4 | 40 | 22.2.4.3 |  | J | Yusuke |  |  | Reference subclause of "18.3.9.3 (Transmit spectrum mask)" is for non-HT PPDUs. "20.3.20.1 (Transmit spectrum mask)" is suitable reference for the spectrum mask for HT PPDUs. | Replace "18.3.9.3 (Transmit spectrum mask)" with "20.3.20.1 (Transmit spectrum mask)". | REJECTED (PHY: 2013-02-14 15:47:55Z) - Withdrawn by commenter. | EDITOR | Withdrawn |  | Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8017 | Yusuke Asai | 191 | 5 | 22.3.3 | 241 | 1 | T | N | 241.01 | 1 | 22.3.3 |  | J | Yusuke |  |  | Figure 22-10 does not have STBC block after LDPC tone mapper and Constellation mapper blocks in each user. | Replace the Figure 22-10 with that embedded in 11-12/1438r3. | REJECTED (PHY: 2013-02-14 15:48:08Z) - Withdrawn by commenter. | EDITOR | Withdrawn |  | Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8018 | Yusuke Asai | 191 | 5 | 22.3.7.4 | 254 | 64 | T | N | 254.64 | 64 | 22.3.7.4 |  | J | Eldad |  |  | f_{CH,start} and the corresponding equation number should also be referred. As stated on the top of Table 22-27, f^(i_{Seg})_c is the function of f_{CH,start} and f_{(i_{seg})}. | Apply the resolution to CID 7052 in 12/1438r3. | REJECTED (PHY: 2013-02-13 23:52:54Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | PHY: 2013-02-13 06:32:41Z - withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8019 | Yusuke Asai | 191 | 5 | 22.3.7.5 | 258 | 61 | T | N | 258.61 | 61 | 22.3.7.5 |  | J | Eldad |  |  | "Gamma" does not have context. It is better to change the title of this subclause to "Definition of phase rotation of tones". | As in comment. | REJECTED (PHY: 2013-02-13 23:53:28Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | PHY: 2013-02-13 06:32:41Z - withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8008 | Yusuke Asai | 191 | 5 | 3.2 | 5 | 40 | T | N | 5.4 | 40 | 3.2 |  | J | Yusuke |  |  | The definitions of 80+80 MHz mask PPDU and 80+80 MHz PPDU are exactly the same. The definition of 80+80 MHz mask PPDU is no longer needed for TGac Draft. | The changes are as follows: (P5L40) Delete the definition of 80+80 mask PPDU. (P124L40) Change "before transmitting a 40, 80, 160 or 80+80 MHz mask PPDU" to "before transmitting a 40, 80 or 160 MHz mask PPDU or an 80+80 MHz PPDU". (P158L11) Change "Transmit a 160 MHz or 80+80 MHz mask PPDU" to "Transmit a 160 MHz mask PPDU or an 80+80 MHz PPDU" (P310L28) Change "For an 80+80 MHz mask PPDU of non-HT duplicate or VHT format," to "For an 80+80 MHz PPDU of non-HT duplicate of VHT format," (P311L40) Change the title of the Figure 22-31 to "Example transmit spectral mask for an 80+80 MHz PPDU" | REJECTED (MAC: 2013-02-15 10:41:37Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 10:41:52Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8131 | Sigurd Schelstraete | 191 | 5 | 22.3.8.3.2 | 264 | 54 | T | N | 264.54 | 54 | 22.3.8.3.2 |  | J | Eldad |  |  | Repeated definition | M_u is already defined in Table 22-6. Moreover, it is slightly different here from Table 22-6. Propose to replace line with "Mu is defined in Table 22-6". | REJECTED (PHY: 2013-02-13 23:54:15Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | PHY: 2013-02-13 06:29:57Z - withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8122 | Sigurd Schelstraete | 191 | 5 | 22.2.2 | 225 | 57 | T | N | 225.57 | 57 | 22.2.2 |  | J | Yusuke |  |  | Make it explicit that STBC = 0 for MU | Add: "The field shall be 0 when the PPDU is an MU PPDU" | REJECTED (PHY: 2013-02-14 16:45:38Z) - Withdrawn by commenter. | EDITOR | Withdrawn |  | Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8124 | Sigurd Schelstraete | 191 | 5 | 22.2.4.2 | 230 | 65 | T | N | 230.65 | 65 | 22.2.4.2 |  | J | Yusuke |  |  | Wrong reference | Replace 20.3.20.1 (Transmit spectrum mask) with 18.3.9.3 (Transmit spectrum mask) | REJECTED (PHY: 2013-02-14 16:45:52Z) - Withdrawn by commenter. | EDITOR | Withdrawn |  | Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8125 | Sigurd Schelstraete | 191 | 5 | 22.2.4.2 | 232 | 41 | T | N | 232.41 | 41 | 22.2.4.2 |  | J | Yusuke |  |  | Improve notation in Figure 22-1 | In the box "Clause 20 Transmit procedure", the notation +22.3.18.1-20.3.20.1 is used, presumably to indicate that section 20.3.20.1 is to be replaced with section 22.3.18.1. For clarity, it is proposed to use " +22.3.18.1 instead of 20.3.20.1" Similar comment for "Clause 18 transmit procedure" in same figure | REJECTED (PHY: 2013-02-14 16:46:04Z) - Withdrawn by commenter. | EDITOR | Withdrawn |  | Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8126 | Sigurd Schelstraete | 191 | 5 | 22.2.4.3 | 234 | 40 | T | N | 234.4 | 40 | 22.2.4.3 |  | J | Eldad |  |  | Wrong reference | Replace 18.3.9.3 (Transmit spectrum mask) with 20.3.20.1 (Transmit spectrum mask) | REJECTED (PHY: 2013-02-13 23:53:55Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | PHY: 2013-02-13 06:29:57Z - withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8127 | Sigurd Schelstraete | 191 | 5 | 22.3.4.2 | 238 | 54 | T | N | 238.54 | 54 | 22.3.4.2 |  | J | Minho |  |  | Use consistent reference when mentioning windowing | When applying windowing, sometimes the referenced section is 22.3.7.4 (see e.g. p238.54 , p239.62, p 241.50), sometimes 18.3.2.5 (see e.g. p242.60, p243.52, p244.60, p246.16, ...) 18.3.2.5 looks like the better reference. Propose to consistently use this in the places listed above | REJECTED (PHY: 2013-02-13 23:53:59Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8128 | Sigurd Schelstraete | 191 | 5 | 22.3.4.4 | 240 | 52 | T | N | 240.52 | 52 | 22.3.4.4 |  | J | Minho |  |  | Last sentence of bullet a) is redundant | The last sentence reads "Add calculated one bit parity and Ntail tails bits into the L-SIG symbol". The previous sentence already covers both parity and tail bits. Proposal: remove last sentence of bullet a) | REJECTED (PHY: 2013-02-13 23:54:05Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8078 | Mark RISON | 191 | 5 | 8.6.1 | 116 | 62 | T | Y | 116.62 | 62 | 8.6.1 |  | J | Jae Seung |  |  | During D4.0 comment resolution it was stated that "EOF pad" and "EOF padding" are two quite distinct things. While it is true that "EOF pad" is clearly defined as the 0-3 octets you might get at the end of an A-MPDU, "EOF padding" is never clearly defined, even though it is used twice (pages 98 and 322). It would be desirable to clarify what "EOF padding" is, exactly | Add something after the definition of "A-MPDU pre-EOF padding" like "EOF padding is the portion of the A-MPDU after the A-MPDU pre-EOF padding." | REJECTED (MAC: 2013-02-15 09:56:50Z): Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 09:31:23Z - Withdrawn by commenter. |  |  |  | 2013-02-18 14:59 | MAC
8130 | Sigurd Schelstraete | 191 | 5 | 22.3.7.4 | 258 | 17 | T | N | 258.17 | 17 | 22.3.7.4 |  | J | Eldad |  |  | Redundant definition | The notation [X]a.b for matrix elements has already been introduced in section 22.3.7.1 and doesn't need to be repeated here. Propose to delete. | REJECTED (PHY: 2013-02-13 23:54:12Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | PHY: 2013-02-13 06:29:57Z - withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8106 | Sigurd Schelstraete | 191 | 5 | 8.4.1.50 | 72 | 41 | T | N | 72.41 | 41 | 8.4.1.50 |  | J | Adrian |  |  | It looks like the coding for Rx NSS is only defined for the case where the Rx NSS Type subfield is 1 | There is no format described for Rx NSS under the first paragraph "If the Rx NSS Type subfield is 0, ...". Either repeat the coding ("Set to 0 for NSS=1, ..." below the first paragraph or decouple the coding from the second paragraph and make it explicit that it doesn't depend on the value of the Rx NSS Type subfield. | REJECTED (MAC: 2013-02-18 14:49:24Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-18 14:49:33Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8132 | Sigurd Schelstraete | 191 | 5 | 22.3.8.3.3 | 268 | 268 | T | N | 270.68 | 268 | 22.3.8.3.3 |  | J | Eldad |  |  | Confusing caption title | Caption reads "Data constellation in the VHT PPDU". What is shown is not data. Change to "Data tone constellation in VHT PPDU pre-VHT modulated fields" (See Clause 20 for similar wording in HT-SIG) | REJECTED (PHY: 2013-02-13 23:54:18Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | PHY: 2013-02-13 06:29:57Z - withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8133 | Sigurd Schelstraete | 191 | 5 | 22.3.8.3.4 | 270 | 40 | T | N | 270.4 | 40 | 22.3.8.3.4 |  | J | Eldad |  |  | Unclear references | It's not clear why references to Eqs (22-12) and (22-33) are needed here. Neither one has anything to say about the length of VHT-STF. Replace last sentence of this subclause with "The duration of the VHT-STF field is T_VHT-STF." | REJECTED (PHY: 2013-02-13 23:54:21Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | PHY: 2013-02-13 06:29:57Z - withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8135 | Sigurd Schelstraete | 191 | 5 | 22.3.8.3.5 | 274 | 43 | T | N | 274.43 | 43 | 22.3.8.3.5 |  | J | Eldad |  |  | Unclear references | It's not clear why references to Eqs (22-12) and (22-43) are needed here. Neither one has anything to say about the length of VHT-LTF. Replace last sentence of this subclause with "The duration of each VHT-LTF symbol is T_VHT-STF." | REJECTED (PHY: 2013-02-13 23:54:24Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | PHY: 2013-02-13 06:29:57Z - withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8136 | Sigurd Schelstraete | 191 | 5 | 22.3.8.3.6 | 277 | 8 | T | N | 277.08 | 8 | 22.3.8.3.6 |  | J | Eldad |  |  | Replace definition by reference | N_STS,u is already defined in Table 22-6. Don't repeat definition here. Replace this line with "N_STS,u is defined in Table 22-6" (similar to most other parameters in this list) | REJECTED (PHY: 2013-02-13 23:54:27Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | PHY: 2013-02-13 06:29:57Z - withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8137 | Sigurd Schelstraete | 191 | 5 | 22.3.10.1 | 280 | 21 | T | N | 280.21 | 21 | 22.3.10.1 |  | J | Minho |  |  | Use clear reference for N_SYM | Replace line with "N_SYM is given by Equation (22-67) | REJECTED (PHY: 2013-02-13 23:54:30Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8138 | Sigurd Schelstraete | 191 | 5 | 22.3.10.1 | 280 | 62 | T | N | 280.62 | 62 | 22.3.10.1 |  | J | Minho |  |  | Scrambling is also on per-user basis | Replace "the encoding process shall happen on a per-user basis" with "the scrambling and encoding process shall happen on a per-user basis" | REJECTED (PHY: 2013-02-13 23:54:33Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8140 | Sigurd Schelstraete | 191 | 5 | 22.3.11.1 | 303 | 48 | E | N | 303.48 | 48 | 22.3.11.1 |  | J | Eldad |  |  | Typo | Replace "can be determined from the beamformer" with "can be determined by the beamformer" | REJECTED (PHY: 2013-02-13 23:54:36Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | PHY: 2013-02-13 06:29:57Z - withdrawn by commenter. Requires technical interpretation. Assigned to PHY. |  |  |  | 2013-02-14 21:46 | PHY
8129 | Sigurd Schelstraete | 191 | 5 | 22.3.4.4 | 240 | 55 | T | N | 240.55 | 55 | 22.3.4.4 |  | J | Minho |  |  | Improve wording | Replace "L-SIG symbol of the PHY header" with "bits of the SIGNAL field" to use wording consistent with bullet a). | REJECTED (PHY: 2013-02-13 23:54:08Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8094 | Youhan Kim | 191 | 5 | 22.3.3 | 242 | 1 | T | Y | 242.01 | 1 | 22.3.3 |  | J | Youhan |  |  | According to 22.3.4.9.1, 22.3.4.9.2 and 22.3.10.9.3, segment deparser is performed before STBC encoding. However, Figure 22-11 and 22-12 shows the segment deparser after the spatial mapping block. | Move the segment deparser block to before STBC in Figure 22-11 and 22-12. | REJECTED (PHY: 2013-02-14 15:44:39Z) - Withdrawn by commenter. | EDITOR | Withdrawn |  | Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8141 | Sigurd Schelstraete | 191 | 5 | 22.3.11.4 | 305 | 1 | T | N | 305.01 | 1 | 22.3.11.4 |  | J | Eldad |  |  | Correct field name in VHT-SIG-A | Replace "NSTS in VHT-SIG-A" with "MU NSTS field in VHT-SIG-A" | REJECTED (PHY: 2013-02-13 23:54:38Z) - withdrawn by commenter. | EDITOR | Withdrawn |  | PHY: 2013-02-13 06:29:57Z - withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8081 | Mark RISON | 191 | 5 | 3.2 | 6 | 51 | T | Y | 6.51 | 51 | 3.2 |  | J | Adrian |  |  | "There can be only one primary AC at a time." -- what does "at a time" mean here? | Change to "There is only one primary AC during a TXOP" | REJECTED (MAC: 2013-02-15 09:59:25Z) - Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 09:31:23Z - Withdrawn by commenter. |  |  |  | 2013-02-18 14:59 | MAC
8084 | Mark RISON | 191 | 5 | 8.4.2.29 | 87 | 36 | E | Y | 87.36 | 36 | 8.4.2.29 |  | J | Adrian |  |  | "Max Number Of MSDUs In A-MSDU" only applies to VHT STAs | Add "VHT" before (also at 142.6) | REJECTED (MAC: 2013-02-15 10:00:35Z) - Withdrawn by commenter | EDITOR | Withdrawn |  | EDITOR: 2013-02-04 09:51:28Z - Asking for a technical change. Assigning to MAC. MAC: 2013-02-15 09:31:23Z - Withdrawn by commenter. |  |  |  | 2013-02-18 14:59 | MAC
8085 | Mark RISON | 191 | 5 | 9.23.6 | 159 | 26 | T | Y | 159.26 | 26 | 9.23.6 |  | J | Allan |  |  | 9.23.6 says that to protect non-HT STAs a VHT STA just follows the rules for HT STAs. However, things such as Table 9-10 in the baseline allow protection by sending an HT_MF as long as this requires a non-HT response. This needs to be extended to allow sending a VHT PPDU as long as this requires a non-HT response. (There may be other places where use of HT_MF needs to be extended to allow VHT instead.) | Add something like ", where a a PPDU with the TXVECTOR FORMAT parameter set to VHT may be substituted for a PPDU with the TXVECTOR FORMAT parameter set to HT_MF" to the first sentence | REJECTED (MAC: 2013-02-15 10:02:02Z) - Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 09:31:23Z - Withdrawn by commenter. |  |  |  | 2013-02-18 14:59 | MAC
8087 | Yongho Seok | 191 | 5 | 8.4.2.162 | 102 | 10 | T | N | 102.1 | 10 | 8.4.2.162 |  | J | Adrian |  |  | "The Extended BSS Load element reported by the AP contains information on MIMO spatial stream underutilization and bandwidth utilization by MU capable STAs." Bandwidth utilization is not restricted to MU-capable STAs. | Change the sentence as as the following: "The Extended BSS Load element reported by the AP contains information on MIMO spatial stream underutilization by MU capable STAs and bandwidth utilization." | REJECTED (MAC: 2013-02-15 11:01:37Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 11:02:04Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8088 | Yongho Seok | 191 | 5 | 8.4.2.162 | 103 | 28 | T | N | 103.28 | 28 | 8.4.2.162 |  | J | Adrian |  |  | "If the AP indicates a channel width of 20 MHz, 40 MHz or 80 MHz in the STA Channel Width field in the HT Operation element and in the Channel Width field in the VHT Operation element, then the 160 MHz Utilization field is reserved." 160 MHz Utilization field was change to Observable Secondary 80 MHz Utilization | Change the sentence as the following: "If the AP indicates a channel width of 20 MHz, 40 MHz or 80 MHz in the STA Channel Width field in the HT Operation element and in the Channel Width field in the VHT Operation element, then the Observable Secondary 80MHz Utilization field is reserved." | REJECTED (MAC: 2013-02-15 11:02:36Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 11:16:45Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8089 | Yongho Seok | 191 | 5 | 8.4.2.162 | 103 | 30 | T | N | 103.3 | 30 | 8.4.2.162 |  | J | Matt |  |  | "If the AP indicates a channel width of 20 MHz or 40 MHz in the STA Channel Width field in the HT Operation element, then the 80 MHz Utilization field is reserved." The 80 MH Utilization field was changed to the Observable Secondary 40 MHz Utilization. | Change the sentence as the following: "If the AP indicates a channel width of 20 MHz or 40 MHz in the STA Channel Width field in the HT Operation element, then the Observable Secondary 40 MHz field is reserved." | REJECTED (MAC: 2013-02-15 11:17:37Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 11:17:49Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8121 | Sigurd Schelstraete | 191 | 5 | 22.2.2 | 225 | 35 | T | N | 225.35 | 35 | 22.2.2 |  | J | Yusuke |  |  | SNR parameter in RXVECTOR should only be included when the PPDU is an NDP | Add note (similar to notes in DELTA_SNR) NOTE: In the RXVECTOR this parameter is present only for VHT NDP PPDUs | REJECTED (PHY: 2013-02-14 16:45:26Z) - Withdrawn by commenter. | EDITOR | Withdrawn |  | Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8093 | Youhan Kim | 191 | 5 | 22.3.3 | 241 | 5 | E | Y | 241.05 | 5 | 22.3.3 |  | J | Yusuke |  |  | Input to the upper most "CSD per STS" block in Figure 22-10 is unconnected. | Add one more line consisting of "constellation mapper" and "LDPC tone mapper", and connect the "CSD per STS" block input to it. | REJECTED (PHY: 2013-02-14 15:43:42Z) - Withdrawn by commenter. | EDITOR | Withdrawn |  | EDITOR: 2013-02-04 09:59:08Z - Requires technical interpretation. Assigning to PHY. Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8120 | Sigurd Schelstraete | 191 | 5 | 22.1.1 | 220 | 27 | T | N | 220.27 | 27 | 22.1.1 |  | J | Yusuke |  |  | Note looks out of place | This note looks like it doesn't belong here. Propose to delete. | REJECTED (PHY: 2013-02-14 16:45:05Z) - Withdrawn by commenter. | EDITOR | Withdrawn |  | Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8096 | Youhan Kim | 191 | 5 | 22.3.20 | 321 | 19 | T | Y | 321.19 | 19 | 22.3.20 |  | J | Youhan |  |  | "Note that under some circumstances, the MAC uses the value of the PHY-CCA.indication primitive before (and if) issuing the PHYTXSTART.request primitive." This is hard to read. | Change to "Note that under some circumstances, the MAC uses the value of the PHY-CCA.indication primitive which was present before the PHYTXSTART.request primitive was issued." | REJECTED (PHY: 2013-02-14 15:44:55Z) - Withdrawn by commenter. | EDITOR | Withdrawn |  | Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8097 | Youhan Kim | 191 | 5 | 22.3.21 | 324 | 41 | T | Y | 324.41 | 41 | 22.3.21 |  | J | Youhan |  |  | Definition for the invalid L-SIG length should be updated because a) Equation (22-24) no longer has a ceiling function and b) invalid L-SIG length applies only to VHT PPDUs. | Change "An invalid L-SIG Length field value is defined as a value that does not satisfy Equation (22-24)." to "The L-SIG Length field value of a VHT PPDU is invalid if it is not divisible by 3." | REJECTED (PHY: 2013-02-14 15:45:08Z) - Withdrawn by commenter. | EDITOR | Withdrawn |  | Withdrawn by commenter. |  |  |  | 2013-02-14 21:46 | PHY
8101 | Sigurd Schelstraete | 191 | 5 | 3.2 | 6 | 26 | T | N | 6.26 | 26 | 3.2 |  | J | Adrian |  |  | Definition of non-HT isn't much of a definition | Essentially the definition states it is "something, unless it isn't". Is there really a need for the second part of the definition ("unless explicitly stated or defined otherwise")? If so, could that be captured better? | REJECTED (MAC: 2013-02-18 14:43:54Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-18 14:44:13Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8102 | Sigurd Schelstraete | 191 | 5 | 3.3 | 8 | 6 | T | N | 8.06 | 6 | 3.3 |  | J | Adrian |  |  | The modified definition for PPDU (physical layer protocol data unit) currently only applies to 802.11ac. How do we reconcile that with the fact that this definition goes into the general sections of the document, where PPDU still means "PLCP protocol data unit"? | Change definition of PPDU: PPDU: PLCP protocol data unit or physical layer protocol data unit (when used in Clause 22) | REJECTED (MAC: 2013-02-18 14:46:09Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-18 14:46:20Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8103 | Sigurd Schelstraete | 191 | 5 | 6.5.8.1 | 25 | 57 | T | N | 25.57 | 57 | 6.5.8.1 |  | J | Adrian |  |  | Not clear which TXVECTOR is meant | Replace "when the TXVECTOR parameter FORMAT is VHT" with "when the TXVECTOR parameter FORMAT in the corresponding PLME-TXTIME.request is VHT" | REJECTED (MAC: 2013-02-18 14:47:08Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-18 14:47:19Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8105 | Sigurd Schelstraete | 191 | 5 | 8.4.1.48 | 60 | 60 | T | N | 60.6 | 60 | 8.4.1.48 |  | J | Adrian |  |  | There is no definition of N_RX,BFEE | Change "Based on this NDP, the beamformee estimates the N_RX,BFEE x N_STS,NDP channel, ..." to "Based on this NDP, the beamformee estimates the N_RX,BFEE x N_STS,NDP channel, with N_RX,BFEE the number of receive antennas at the beamformee, ..." | REJECTED (MAC: 2013-02-18 14:48:28Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-18 14:48:39Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC
8079 | Mark RISON | 191 | 5 | 10.39.4 | 189 | 44 | T | Y | 189.44 | 44 | 10.39.4 |  | J | Adrian |  |  | For non-VHT STAs to be able to fully benefit from the new power/regulatory/channel switching stuff, it is necessary for them e.g. to be able to receive a unicast (Extended) Channel Switch Announcement MMPDU with e.g. a VHT Transmit Power Envelope element | Add an Extended Capability bit to allow a non-VHT STA to indicate support for the VHT power/regulatory/channel switching stuff, and ensure the text requires VHT STAs to use the VHT power/regulatory/channel switching stuff with non-VHT devices which have indicated this capability | REJECTED (MAC: 2013-02-15 09:57:49Z): Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 09:31:23Z - Withdrawn by commenter. |  |  |  | 2013-02-18 14:59 | MAC
8090 | Yongho Seok | 191 | 5 | 8.4.2.162 | 103 | 32 | T | N | 103.32 | 32 | 8.4.2.162 |  | J | Adrian |  |  | "If the AP indicates a channel width of 20 MHz in the STA Channel Width field in the HT Operation element, then the 40 MHz Utilization field is reserved." The 40 MHz Utilization field was changed to the Observable Secondary 20 MHz Utilization. | Change the sentence as the following: "If the AP indicates a channel width of 20 MHz in the STA Channel Width field in the HT Operation element, then the Observable Secondary 20 MHz is reserved." | REJECTED (MAC: 2013-02-15 11:18:27Z) : Withdrawn by commenter | EDITOR | Withdrawn |  | MAC: 2013-02-15 11:18:40Z - Withdrawn by commenter |  |  |  | 2013-02-18 14:59 | MAC

## Editorial
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
8041 | Mitsuru Iwaoka | 191 | 5 | 8.3.1.9 | 46 | 24 | E | N | 46.24 | 24 | 8.3.1.9 |  | J |  |  |  | Amended text is located in the subclause 8.3.1.9.1. | Add subsection titile "8.3.1.9.1 Overview" under the 8.3.1.9 title. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8058 | Mitsuru Iwaoka | 191 | 5 | 9.25.3 | 159 | 52 | E | N | 159.52 | 52 | 9.25.3 |  | J |  |  |  | The 3rd paragraph of subclause 9.25.3 is amended by IEEE Std 802.11ad-2012, but 802.11ac D5.0 does not refrect it. | Apply amendmend of 802.11ad-2012 to 802.11ac. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8057 | Mitsuru Iwaoka | 191 | 5 | 9.25.1 | 159 | 40 | E | N | 159.4 | 40 | 9.25.1 |  | J |  |  |  | The NOTE 1 in subclause 9.25.1 is amended by IEEE Std 802.11ad-2012, but 802.11ac D5.0 does not refrect it. | Apply amendmend of 802.11ad-2012 to 802.11ac. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8056 | Mitsuru Iwaoka | 191 | 5 | 9.19.2.7 | 157 | 27 | E | N | 157.27 | 27 | 9.19.2.7 |  | J |  |  |  | Amendment to the 4th paragraph of subclause 9.19.2.7 by IEEE Std 802.11ad-2012 is not refrected in the 802.11ac D5.0. | Add "In a non-DMG network," at the beginning of the 4th paragraph according to 802.11ad. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8054 | Mitsuru Iwaoka | 191 | 5 | 9.3.1 | 123 | 36 | E | N | 123.36 | 36 | 9.3.1 |  | J |  |  |  | The 2nd to last paragraph of 9.3.1 is amended by IEEE Std 802.11ad-2012, but 802.11ac D5.0 does not refrect 1st modification. | Modify beginning of the 3rd sentence to "All HT STAs and DMG STAs that are.." | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8053 | Mitsuru Iwaoka | 191 | 5 | 9.2.7 | 122 | 50 | E | N | 122.5 | 50 | 9.2.7 |  | J |  |  |  | Subclause index of "Fragmentation/defragmentation overview" is 9.2.7, not 9.2.6. | Correct subclause index. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8052 | Mitsuru Iwaoka | 191 | 5 | 9.2.1 | 122 | 5 | E | N | 122.05 | 5 | 9.2.1 |  | J |  |  |  | Subclause 9.2.1 is amended by IEEE Std 802.11ad-2012 and need to be amended by 802.11ac. | Modify the 1st paragraph of 9.2.1 and Figure 9-1 as following. --- proposed text ---- The MAC architecture is shown in Figure 9-1. When operating with any of the Clause 14 through 20 PHYs or Clause 22 PHY, .... ---- Figure 9-1 modification ---- Replace the text in the left lowest box by "FHSS, IR, DSSS, OFDM, HR/DSSS, ERP, HT or VHT PHY". | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8046 | Mitsuru Iwaoka | 191 | 5 | 8.5.8.16 | 111 | 6 | E | N | 111.06 | 6 | 8.5.8.16 |  | J |  |  |  | EDITORIAL NOTE says "none in 802.11ad", but IEEE Std 802.11ad-2012 insert Order 16. | Change order of VHT Capabilities to 17 in Table 8-220. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8045 | Mitsuru Iwaoka | 191 | 5 | 8.4.1.11 | 54 | 13 | E | N | 54.13 | 13 | 8.4.1.11 |  | J |  |  |  | Instruction to modify reserved value is missing. | Change instruction to "Insert a new row into Table 8-38 maintaining numerical order and adjusting the reserved values as appropriate:" | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8044 | Mitsuru Iwaoka | 191 | 5 | 8.3.3.1 | 49 | 55 | E | N | 49.55 | 55 | 8.3.3.1 |  | J |  |  |  | IEEE Std 802.11ad-2012 modifies Figure 8-34, but P802.11ac D5.0 refers old figure. | In Figure 8-34, change the octet range for Frame Body from 0-2320 to 0-2328. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8011 | Yusuke Asai | 191 | 5 | 8.4.2.10 | 76 | 2 | E | N | 76.02 | 2 | 8.4.2.10 |  | J |  |  |  | It is better to add parentheses to "1+P(m)". | As in comment. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8042 | Mitsuru Iwaoka | 191 | 5 | 8.3.1.19 | 46 | 35 | E | N | 46.35 | 35 | 8.3.1.19 |  | J |  |  |  | IEEE Std 802.11ad-2012 already incerts subclause 8.3.1.19. | Change subclause index of "VHT NDP Announcement frame format" to 8.3.1.20, and "Beamforming Report Poll frame format" to 8.3.1.21 respectively. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8062 | Juho Pirskanen | 191 | 5 | 6.3.8.3.2 | 21 | 23 | E | N | 21.23 | 23 | 6.3.8.3.2 |  | J |  |  |  | MLME-REASSOCIATE.confirm primitive's VHT capabilities description is not consistent with same field in MLME-ASSOCIATE.confirm. | Change STA to AP in text: "Specifies the parameters in the VHT Capabilities element that are supported by the STA." | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8040 | Mitsuru Iwaoka | 191 | 5 | 8.3.1.8 | 46 | 12 | E | N | 46.12 | 12 | 8.3.1.8 |  | J |  |  |  | Amended text is located in the subclause 8.3.1.8.1. | Add subsection titile "8.3.1.8.1 Overview" under the 8.3.1.8 title. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8039 | Mitsuru Iwaoka | 191 | 5 | 8.3.1.6 | 46 | 6 | E | N | 46.06 | 6 | 8.3.1.6 |  | J |  |  |  | The second paragraph of 8.3.1.6 is modified by IEEE Std 802.11ad-2012, but P802.11ac D5.0 refers old text. | Change the new fifth paragraphs inserted by 802.11ad as follows. --- proposed text ---- When transmitted by a non-DMG STA, the BSSID (TA) field is set to the address of the STA contained in the AP except that the Individual/Group bit of the BSSID (TA) field is set to 1 in a CF-End frame transmitted by a VHT STA to a VHT AP in a non-HT or non-HT duplicate format to indicate that the scrambling sequence carries the TXVECTOR parameter CH_BANDWIDTH_IN_NON_HT. When transmitted by a DMG STA, the TA field is the MAC address of the STA transmitting the frame. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8035 | Liwen Chu | 191 | 5 | 8.4.2.160.2 | 100 | 6 | E | N | 100.06 | 6 | 8.4.2.160.2 |  | J |  |  |  | The reference should be Figure 8-401bs | Change "are defined in 8.4.2.160.3" to "are defined in Figure 8-401bs" in the Table. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8030 | Yongho Seok | 191 | 5 | 8.3.3.10 | 53 | 30 | E | N | 53.3 | 30 | 8.3.3.10 |  | J |  |  |  | Order of Channel Switch Wrapper element in Probe Response frame is 64, not 63. | Change the order of Channel Switch Wrapper element from 63 to 64. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8028 | Yusuke Asai | 191 | 5 | B.4.4.1 | 353 | 6 | E | N | 353.06 | 6 | B.4.4.1 |  | J |  |  |  | Some vertical lines in the table are missed. | Add lines. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8024 | Yusuke Asai | 191 | 5 | 22.3.11.1 | 303 | 28 | E | N | 303.28 | 28 | 22.3.11.1 |  | J |  |  |  | N_u in Equation (22-101) should be replaced with N_user. | As in comment. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8023 | Yusuke Asai | 191 | 5 | 22.3.10.11 | 300 | 27 | E | N | 300.27 | 27 | 22.3.10.11 |  | J |  |  |  | "the signal from transmit chain i_{TX}" -> "the signal of data symbols from transmit chain i_{TX}" | As in comment. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8020 | Yusuke Asai | 191 | 5 | 22.3.7.5 | 259 | 17 | E | N | 259.17 | 17 | 22.3.7.5 |  | J |  |  |  | "per segment" -> "per frequency segment" | As in comment. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8014 | Yusuke Asai | 191 | 5 | 22.2.2 | 230 | 15 | E | N | 230.15 | 15 | 22.2.2 |  | J |  |  |  | The right parenthesis in "Otherwise)" should be deleted. | As in comment. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8043 | Mitsuru Iwaoka | 191 | 5 | 8.3.2.2 | 49 | 1 | E | N | 49.01 | 1 | 8.3.2.2 |  | J |  |  |  | IEEE Std 802.11ad-2012 modifies subclause 8.3.2.2, but P802.11ac D5.0 refers old text. | Change title of 8.3.2.2 to "Aggregate MSDU (A-MSDU) format", and add subclause title "8.3.2.2.1 General". Change title of Figure 8-32 to "Basic A-MSDU subframe structure". | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8082 | Mark RISON | 191 | 5 | G.4 | 402 | 15 | E | Y | 402.15 | 15 | G.4 |  | J |  |  |  | The semicolon before the "vht-bf" should be a pipe, to show alternation (and to avoid a syntax error) | Change semicolon to pipe | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8134 | Sigurd Schelstraete | 191 | 5 | 22.3.8.3.5 | 272 | 29 | E | N | 272.29 | 29 | 22.3.8.3.5 |  | J |  |  |  | Typo | Replace "is the subcarrier indices" with "are the subcarrier indices" or "is the set of subcarrier indices" | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8123 | Sigurd Schelstraete | 191 | 5 | 22.2.2 | 227 | 47 | E | N | 227.47 | 47 | 22.2.2 |  | J |  |  |  | Typo (I think) | Replace "signalled" with "signaled" Same comment for line 51 | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8117 | Sigurd Schelstraete | 191 | 5 | 11.6.1.7 | 202 | 33 | E | N | 202.33 | 33 | 11.6.1.7 |  | J |  |  |  | Typo | Change "heirarchy" to "hierarchy" | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8114 | Sigurd Schelstraete | 191 | 5 | 9.31.4 | 169 | 30 | E | N | 169.3 | 30 | 9.31.4 |  | J |  |  |  | Typo | Replace "sequences's" with "sequences" or "sequence's", I don't know ... | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8111 | Sigurd Schelstraete | 191 | 5 | 9.7.11.3 | 140 | 25 | E | N | 140.25 | 25 | 9.7.11.3 |  | J |  |  |  | In <VHT-MCS,NSS>, no subscript is used. In min(VHT-MCS,7)+8(N_SS-1), SS is in subscript | Use same notation in both places | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8100 | Sigurd Schelstraete | 191 | 5 | 3.2 | 6 | 7 | E | N | 6.07 | 7 | 3.2 |  | J |  |  |  | Typo | Replace "tTransmit" with "Transmit" | REJECTED (EDITOR: 2013-02-20 01:06:35Z) - Not a typo. These automatic crossreferences remove formating from the original text. In this case underlining of "HT t" and strikethrough on "T". | EDITOR | Editorial | [5 empty] | 2013-02-20 01:18 | EDITOR
8095 | Youhan Kim | 191 | 5 | 22.3.11.1 | 303 | 28 | E | Y | 303.28 | 28 | 22.3.11.1 |  | J |  |  |  | Nu should be Nuser. | Change "Nu" to "Nuser" in Equation (22-101). | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8092 | Youhan Kim | 191 | 5 | 8.4.2.160.3 | 100 | 16 | E | Y | 100.16 | 16 | 8.4.2.160.3 |  | J |  |  |  | "rounded down to the next integer" sounds awkward. | Change "the data rate value is rounded down to the next integer" to "the data rate value is floored to the greatest integer less than or equal to the highest long GI VHT PPDU data rate". Similar changes need to be made on P100L30, P139L38 and P140L7. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8091 | Youhan Kim | 191 | 5 | 8.4.2.160.3 | 100 | 7 | E | Y | 100.07 | 7 | 8.4.2.160.3 |  | J |  |  |  | "The format and encoding of this subfield are defined in 8.4.2.160.3." But this sentence is within 8.4.2.160.3. Reference is circular. | Change to "See Figure 8-401bs and subsequent description for the format and encoding of this subfield." | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8059 | Mitsuru Iwaoka | 191 | 5 | 9.25.4 | 160 | 6 | E | N | 160.06 | 6 | 9.25.4 |  | J |  |  |  | The 3rd paragraph of subclause 9.25.4 is amended by IEEE Std 802.11ad-2012, but 802.11ac D5.0 does not refrect it. | Apply amendmend of 802.11ad-2012 to 802.11ac. | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8083 | Mark RISON | 191 | 5 | G.4 | 402 | 23 | E | Y | 402.23 | 23 | G.4 |  | J |  |  |  | "tranmission" | "transmission" | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8060 | Mitsuru Iwaoka | 191 | 5 | 10.1.3.2 | 176 | 9 | E | N | 176.09 | 9 | 10.1.3.2 |  | J |  |  |  | The title of subclase 10.1.3.2 is modified to "Beacon generation in non-DMG infrastructure networks" by IEEE STD 802.11ad-2012. | Modify the titile of 10.1.3.2 to "Beacon generation in non-DMG infrastructure networks" | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8075 | Mark RISON | 191 | 5 | Q |  |  | E | Y |  |  | Q |  | J |  |  |  | 802.11-2012 uses "MU" for the term "mobile unit", in informative Annex Q; this conflicts with its use in 11ac to mean "multi-user" | Update Annex Q to use a different abbreviation, or put a note to the effect that MU in this Annex (and this Annex only) does not have the meaning it has elsewhere in the standard | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8071 | Edward Reuss | 191 | 5 | 9.19.2.2 | 151 | 18 | E | N | 151.18 | 18 | 9.19.2.2 |  | J |  |  |  | Garbled sentence: "If a Non-VHT STA receives an RTS frame is received with the RA address" | Remove "is received". | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8070 | Edward Reuss | 191 | 5 | 8.4.2.71.5 | 94 | 38 | E | N | 94.38 | 38 | 8.4.2.71.5 |  | J |  |  |  | Wrong verb tense in the phrase "where the first N subelements contains". | Change "contains" to "contain". | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8069 | Edward Reuss | 191 | 5 | 8.4.2.56 | 95 | 5 | E | N | 95.05 | 5 | 8.4.2.56 |  | J |  |  |  | Misspelled "ther" should be "there". | Change "ther" to "there". | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8068 | Edward Reuss | 191 | 5 | 8.4.23.5 | 79 | 9 | E | N | 79.09 | 9 | 8.4.23.5 |  | J |  |  |  | In consistent use of "subelement" versus "sub-element", even in the same sentence. This error is repeated several times in the draft. | Change all instances of "sub-element" to "subelement". | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8066 | Edward Reuss | 191 | 5 | 6.5.4.2 | 24 | 18 | E | N | 24.18 | 18 | 6.5.4.2 |  | J |  |  |  | Wrong tense: "is" should be "are". | Change "The values assigned to the parameters is as specified" to "The values assigned to the parameters are as specified". | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8065 | Edward Reuss | 191 | 5 | 6.3.8.3.2 | 19 | 46 | E | N | 19.46 | 46 | 6.3.8.3.2 |  | J |  |  |  | Misspelled FMSResponse as FMSRespone This error is repeated several places. | Change to FMSResponse | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8064 | Juho Pirskanen | 191 | 5 | 7.3.5.11.2 | 31 | 33 | E | N | 31.33 | 33 | 7.3.5.11.2 |  | J |  |  |  | Hyperlink missing in text Figure 7-2 included in chapter. | Add the hyperlink | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8063 | Juho Pirskanen | 191 | 5 | 8.4.1.9 | 55 | 6 | E | N | 55.06 | 6 | 8.4.1.9 |  | J |  |  |  | Name missing from Status Code 104 | Include name: ASSOCIATION_REJECTED_NO_VHT_SUPPORT | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8139 | Sigurd Schelstraete | 191 | 5 | 22.3.10.6 | 285 | 50 | E | N | 285.5 | 50 | 22.3.10.6 |  | J |  |  |  | Typo | Replace "in a constellation point" with "of a constellation point" | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR
8086 | Mark RISON | 191 | 5 | 9.7.11.1 | 139 | 46 | E | Y | 139.46 | 46 | 9.7.11.1 |  | J |  |  |  | "are also eliminated from the Rx Supported VHT-MCS and NSS Set those tuples" makes no sense | Delete the "those" | The comment may be valid. However, since no technical change is being made to the draft this editorial comment is rejected with the expection that the issues raised will be addressed following the first sponsor ballot. | EDITOR | Editorial | [5 empty] | 2013-02-20 01:17 | EDITOR

## Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
8107 | Sigurd Schelstraete | 191 | 5 | 8.4.2.162 | 102 | 11 | T | N | 102.11 | 11 | 8.4.2.162 |  |  | Matt |  |  | The introduction of 8.4.12.162 indicates that the extended BSS load element is strictly about MU capable STAs. That restriction seems to be lost later in the subclause (specifically for the bandwidth utilization). | Confirm that the measurements involve MU-capable STAs only and make this explicit in the definitions of bandwidth utilization parameters. If this was not the intention, correct the introductory paragraph. |  | MAC | [6 empty] | 2013-02-08 14:29 | MAC
8047 | Mitsuru Iwaoka | 191 | 5 | 8.6.1 | 117 | 10 | E | N | 117.1 | 10 | 8.6.1 |  |  | Matt |  |  | Modified text losts a description about A-MPDU maximum length for a DMG STA. | Change the paragraph before Figure 8-504 as following. --- proposed text ---- The maximum length of an A-MPDU in an HT PPDU is 65 535 octets. The maximum length of an A-MPDU pre-EOF padding in a VHT PPDU is 1 048 575 octets. The maximum length of an A-MPDU in a DMG PPDU is 262 143 octets.The length of an A-MPDU addressed to a particular STA may be further constrained as described in 9.12.2 (A-MPDU length limit rules). |  | MAC |  |  | EDITOR: 2013-02-04 09:55:15Z - Adding new text that may be normative. Assigned to MAC. |  |  |  | 2013-02-08 14:29 | MAC
8048 | Mitsuru Iwaoka | 191 | 5 | 8.6.1 | 117 | 31 | T | N | 117.31 | 31 | 8.6.1 |  |  | Matt |  |  | According to IEEE Std 802.11ad-2012, field MPDU length filed in MPDU delimiter is 13bit long for DMG STA. Definition of MPDU length field in Figure 8-505a1 and equation (8-4) does not describe MPDU length filed in a DMG PPDU. | Change the title of Figure 8-505 to "MPDU delimiter" (Delete "(non-DMG)"), and add instruction as "Remove the Figure 8-505a and Table 8-282a". Change the description of MPDU Length field as following (line 1 to 32 of p.118). --- proposed text --- The format of the MPDU Length field is shown in Figure 8-505a1. The MPDU Length Low subfield contains the 12 low order bits of the MPDU length. In a VHT or DMG PPDU, the MPDU Length High subfield contains the two high order bits of the MPDU length. In an HT PPDU, the MPDU Length High subfield is reserved. The MPDU length value is derived from the MPDU Length field subfields as follows: LMPDU = Llow + Lhigh x 4096, VHT or DMG PPDU Llow, HT PPDU (8-4) where Llow is the value of the MPDU Length Low subfield Lhigh is the value of the MPDU Length High subfield NOTE--The format of the MPDU Length field maintains a common encoding structure for VHT, HT and DMG PPDUs. For HT PPDUs only the MPDU Length Low subfield is used, while for VHT or DMG PPDUs both subfields are used. For DMG PPDUs the highest bit is allways set to 0. |  | MAC | [6 empty] | 2013-02-08 14:29 | MAC
8049 | Mitsuru Iwaoka | 191 | 5 | 8.6.3 | 118 | 51 | T | N | 118.51 | 51 | 8.6.3 |  |  | Matt |  |  | The modified first paragraph of 8.6.3 does not describle A-MPDU use in a DMG PPDU. | Change the first paragraph of 8.6.3 as following. --- proposed text --- In a non-DMG PPDU, an A-MPDU is a sequence of A-MPDU subframes carried in a single PPDU with one of the following combinations of RXVECTOR or TXVECTOR parameter values: -- The FORMAT parameter set to VHT -- The FORMAT parameter set to HT_MF or HT_GF and the AGGREGATION parameter set to 1 In a DMG PPDU, An A-MPDU is a sequence of MPDUs carried in a single PPDU with the TXVECTOR/RXVECTOR AGGREGATION parameter set to 1. |  | MAC | [6 empty] | 2013-02-08 14:29 | MAC
8050 | Mitsuru Iwaoka | 191 | 5 | 8.6.3 | 119 | 9 | T | N | 119.09 | 9 | 8.6.3 |  |  | Matt |  |  | Definition of "user" and description in 4.3.10a (p.10, line 58-60) imply that a VHT MU PPDU contains only individually addressed MPDUs. Though, there is no explicit description to inhibit transmission of group addressed MPDUs in VHT MU PPDU. | Add following condition to 8.6.3 A-MPDU contents (after p.119 line. 9). --- proposed text --- A VHT MU PPDU does not carry an A-MPDU containing an MPDU with a group addressed RA. |  | MAC | [6 empty] | 2013-02-08 14:29 | MAC
8051 | Mitsuru Iwaoka | 191 | 5 | 8.6.3 | 119 | 17 | E | N | 119.17 | 17 | 8.6.3 |  |  | Matt |  |  | NOTE 2 in subclause 8.6.3 lackes description about MPDU length limit in a DMG PPDU. | Change the second sentence of NOTE 2 as "The 4095 octet MPDU length limit does not apply to A-MPDUs carried in VHT or DMG PPDUs.". |  | MAC |  |  | EDITOR: 2013-02-04 09:55:41Z - Requesting a technical change. Assigning to MAC. |  |  |  | 2013-02-08 14:29 | MAC
8055 | Mitsuru Iwaoka | 191 | 5 | 9.7.1 | 129 | 39 | E | N | 129.39 | 39 | 9.7.1 |  |  | Allan |  |  | The last paragraph of 9.7.1 need to mention to Clause 22 PHY. | Modify the last paragraph of 9.7.1 as following. --- proposed text --- For the Clause 18, Clause 17, Clause 19, Clause 20, Clause 21 and Clause 22 PHYs, the time required to transmit a frame for use in calculating the value for the Duration/ID field is determined using the PLME-TXTIME.request primitive (see 6.5.7) and the PLME-TXTIME.confirm primitive (see 6.5.8), both defined in 18.4.3, 17.3.4, 19.8.3.2, 19.8.3.3, 19.8.3.4, 20.4.3, 21.12.3 or 22.4.3 depending on the PHY options. In QoS STAs, the Duration/ID field may cover multiple frames and may involve using the PLMETXTIME.request primitive several times. |  | MAC |  |  | EDITOR: 2013-02-04 09:56:59Z - Makes a technical change. Assigning to MAC. |  |  |  | 2013-02-08 14:22 | MAC
8067 | Edward Reuss | 191 | 5 | 8.4.2.10 | 77 | 5 | E | N | 77.05 | 5 | 8.4.2.10 |  |  | Adrian |  |  | The sentence "No channel is indiacted by more than one pair of First Channel Number and Number of Channels fields within a Subband Triplet Sequence field do not have overlapping channel identifiers." does not make sense. What does this mean? | Fix this sentence. |  | MAC |  |  | EDITOR: 2013-02-04 09:50:47Z - Asking for an interpretation. Assigning to MAC. |  |  |  | 2013-02-08 14:28 | MAC
8098 | Sigurd Schelstraete | 191 | 5 | 3.2 | 5 | 1 | T | N | 5.01 | 1 | 3.2 |  |  | Yusuke |  |  | 80 MHz mask PPDUs can only be transmitted by VHT-STAs. However, some of the formats listed might be sent by non-VHT STAs. | Replace "A PPDU that is transmitted" by "A PPDU that is transmitted by a VHT STA". This would make it consistent with the e.g. 40 MHz mask, bullets 3, 7 and 9. |  | MAC | [6 empty] | 2013-02-08 14:16 | MAC
8038 | Mitsuru Iwaoka | 191 | 5 | 8.2.4.6.1 | 36 | 49 | T | N | 36.49 | 49 | 8.2.4.6.1 |  |  | Jae Seung |  |  | There is no description about VHT subfield which is defined as B0 of HT Control field in Figure 8-5. | Incert the following description of VHT subfield after p.36 line 63. ----- proposed text ----- The VHT subfield of the HT Control field indicates whether the format of the HT Control field is the HT variant or the VHT variant as defined in Table 8-6a. Table 8-6a --VHT subfield values Value Description 0 HT Control filed format is HT variant 1 HT Control filed format is VHT variant |  | MAC | [6 empty] | 2013-02-08 14:19 | MAC
8104 | Sigurd Schelstraete | 191 | 5 | 8.2.4.6.1 | 36 | 64 | T | N | 36.64 | 64 | 8.2.4.6.1 |  |  | Jae Seung |  |  | There is no description of the new VHT subfield | Add new paragraph after line 63: "The VHT subfield controls which variant of the HT Control Middle subfield is used. When the value is 1, the HT Control Middle field uses the HT variant format. Otherwise, the HT Control Middle field uses the VHT variant format." NOTE: In HT, this value was previously "reserved". I'm assuming that means value 1. If not, the above needs to change accordingly. |  | MAC | [6 empty] | 2013-02-08 14:19 | MAC
8119 | Sigurd Schelstraete | 191 | 5 | 18.3.5.5 | 215 | 27 | T | N | 215.27 | 27 | 18.3.5.5 |  |  | Edward |  |  | The example given in L.1.5.2 is for a case without BW signaling | Change "An example of scrambler output" to "An example of scrambler output (with CH_BANDWIDTH_IN_NON_HT not present)" |  | MAC | [6 empty] | 2013-02-08 14:32 | MAC
8108 | Sigurd Schelstraete | 191 | 5 | 8.4.2.165 | 105 | 63 | T | N | 105.63 | 63 | 8.4.2.165 |  |  | Menzo |  |  | The Length field of the Channel Switch Wrapper element does not indicate the correct number of bytes. | It is stated that the value of Length field is between 1 and 3, depending on the number of subelements. However, devices that are not familiar with the Channel Switch Wrapper element will interpret this number as the number of bytes in the element, rather than the number of subelements. This will cause a misalignment that will interfere with the further parsing of the element. In order to avoid the problem, the Length field would either have to be value 0, or the total length in bytes of the included subelements. Even for devices that are familiar with this element, the parsing would have to be done differently depending on the value of the Element ID. It seems better to stick with the same interpretation of Length field for all Element IDs (i.e. #bytes). |  | MAC | [6 empty] | 2013-02-08 14:24 | MAC
8109 | Sigurd Schelstraete | 191 | 5 | 9.7.10 | 139 | 3 | T | N | 139.03 | 3 | 9.7.10 |  |  | Allan |  |  | I assume that non-VHT STAs should not include CH_BANDWIDTH_IN_NON_HT and DYN_BANDWIDTH_IN_NON_HT in RXVECTOR. | Add sentence after first paragraph on page 139: "Non-VHT STAs shall not include CH_BANDWIDTH_IN_NON_HT or DYN_BANDWIDTH_IN_NON_HT in the Clause 18 RXVECTOR" |  | MAC | [6 empty] | 2013-02-08 14:22 | MAC
8110 | Sigurd Schelstraete | 191 | 5 | 9.7.11.3 | 140 | 25 | T | N | 140.25 | 25 | 9.7.11.3 |  |  | Allan |  |  | The min() operation in min(VHT-MCS,7) is redundant, since VHT-MCS is 0, 1, 2 or 3. | Remove min() operation |  | MAC | [6 empty] | 2013-02-08 14:22 | MAC
8112 | Sigurd Schelstraete | 191 | 5 | 9.7.11.3 | 140 | 31 | T | N | 140.31 | 31 | 9.7.11.3 |  |  | Allan |  |  | The min() operation in min(2(VHT-MCS),7) is redundant since VHT-MCS is 0 or 1 | Remove min() operation |  | MAC | [6 empty] | 2013-02-08 14:22 | MAC
8113 | Sigurd Schelstraete | 191 | 5 | 9.7.11.3 | 140 | 57 | T | N | 140.57 | 57 | 9.7.11.3 |  |  | Allan |  |  | Why are the last two rows of the second column blank? | If HT MCS 0 and 1 are indicated as unsupported, shouldn't VHT-MCS 0 and 1 in 40 MHz be listed as not used? Likewise, If HT MCS 2 and 3 are indicated as unsupported, shouldn't VHT-MCS 2 and 3 in 40 MHz be listed as not used? |  | MAC | [6 empty] | 2013-02-08 14:22 | MAC
8115 | Sigurd Schelstraete | 191 | 5 | 9.31.5.2 | 171 | 33 | T | N | 171.33 | 33 | 9.31.5.2 |  |  | Allan |  |  | The current sounding protocol covers cases where a non-AP VHT Bfee receives a VHT NDPA and VHT NDP from a Bfer with which it is associated or has established a (T)DLS link. Is it understood that a STA should not send feedback if the NDPA/NDP comes from any other STA? | If so, add sentence "A non-AP STA shall not respond to a VHT sounding sequence from a STA with which it is not associated or has not established a DLS or TDLS link" |  | MAC | [6 empty] | 2013-02-08 14:22 | MAC
8116 | Sigurd Schelstraete | 191 | 5 | 9.31.5.2 | 172 | 62 | T | N | 172.62 | 62 | 9.31.5.2 |  |  | Allan |  |  | There is no need for a STA that receives a NDPA with feedback type equal to MU to recalculate the value of Nc. All the constraints listed in lines 62-65 of page 172 and 1-4 of page 173 should already have been taken into account in setting the value of Nc in the NDPA (see lines 25-31 on page 171) | Delete the bullet items listed in lines 62-65 of page 172 and 1-4 of page 173 and state that the STA uses exactly the value of Nc as received in the NDPA. |  | MAC | [6 empty] | 2013-02-08 14:22 | MAC
8118 | Sigurd Schelstraete | 191 | 5 | 18.3.5.5 | 215 | 27 | T | N | 215.27 | 27 | 18.3.5.5 |  |  | Edward |  |  | Wrong reference | G.1.5.2 should be L.1.5.2 |  | MAC | [6 empty] | 2013-02-08 14:32 | MAC
8099 | Sigurd Schelstraete | 191 | 5 | 3.2 | 5 | 19 | T | N | 5.19 | 19 | 3.2 |  |  | Yusuke |  |  | 160 MHz mask PPDUs can only be transmitted by VHT-STAs. However, some of the formats listed might be sent by non-VHT STAs. | Replace "A PPDU that is transmitted" by "A PPDU that is transmitted by a VHT STA". |  | MAC | [6 empty] | 2013-02-08 14:16 | MAC