## Motion MAC-P
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
120 | Mark RISON | 193 | 2012 |  |  |  | T | N |  |  |  |  | J | Mark Rison/Mark Hamilton |  |  | The exception for the PM bit in Probe Responses sent in response to unicast Probe Requests in an IBSS makes no sense | Get rid of this special case (in 3.2, 8.2.4.1.7 and 10.2.2.4) | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | GEN: 2013-01-17 00:02:13Z move to MAC, see 119, 121, 122 |  |  |  | 2013-09-19 07:36 | MAC
11 | Adrian Stephens | 193 | 2012 | 8.4.1.9 | 446 | 10 | T | N | 446.1 | 10 | 8.4.1.9 |  | J | Mark Hamilton |  |  | (For Diane Lacey, 802.11-2012 publication editor) Ed writes: 're heading for second column: Do we want to use "ResultCode" instead of "Name" [or "Name (ResultCode)"? We refer users to this table WRT ResultCodes, e.g., the MLME-ADDTS.response primitive uses ResultCode to determine status.' Adrian writes: 'we'd need to add text to explain the relationship to parameters in Clause 6'. | Align name of Status codes Table8-37 "name" column with usage in clause 6. Perhaps add a note describing any convention we have before the table. "Status Codes that are parameters of Clause 6 primitives are often called a ResultCode." | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | [MAH] See also CID 91. This needs a submission. |  |  |  | 2013-09-19 07:36 | MAC
177 | Mark RISON | 193 | 2012 |  |  |  | T | N | 878 |  | 9.19.2.5 |  | J | Mark Rison |  |  | What exactly is "the backoff procedure" for EDCA? Is it the thing which starts with waiting for AIFS of idleness, or the thing which starts with throwing a random number and then waiting for that number of slots of idleness, or what? | Clarify and make sure all references to "the backoff procedure" do indeed refer to whatever it's deemed to mean | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:36 | MAC
157 | Mark RISON | 193 | 2012 | 9.7.6.5.4 |  |  | T | N | 861 |  | 9.7.6.5.4 |  | J | Mark Rison |  |  | My guilty secret: I've never worked out when exactly an alternate rate might be possible | Add a NOTE giving a pithy example of a rate and a possible alternate rate | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:36 | MAC
153 | Mark RISON | 193 | 2012 |  |  |  | T | N | 854 |  |  |  | J | Mark Rison |  |  | The multirate rules are an impenetrable mess. It's impossible to determine whether they are complete, let alone whether they are correct | Clean it up in some way. Good luck | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | Adrian: Amen. |  |  |  | 2013-09-19 07:36 | MAC
148 | Mark RISON | 193 | 2012 |  |  |  | T | N | 390 |  |  |  | J | Mark Hamilton |  |  | What is HEMM anyway? What does "HCCA, EDCA mixed mode" mean? Which elements of HCCA and EDCA are used in HEMM? | Clarify | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | [MAH proposal] Well, clearly it means some sort of "both" mode for a given TS. But, what exactly that means in terms of usage are not specified, agreed. Needs submission. Mark H will contact Graham Smith and Alex Ashley and see if they are willing to help. |  |  |  | 2013-09-19 07:36 | MAC
147 | Mark RISON | 193 | 2012 |  |  |  | T | N | 390 |  |  |  | J | Mark Rison |  |  | The distinctions made in the specification w.r.t. TS/TC/TSID/TID are incomprehensible | Make the definitions comprehensible. E.g. what does "UP for either TC or TS" mean? | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | [MAH] Agree this is messy and complicated, but it may not be possible to make it any more clear. Really clarifying this goes beyond just the definitions, but also to the usages. This needs a submission. |  |  |  | 2013-09-19 07:36 | MAC
145 | Mark RISON | 193 | 2012 |  |  |  | T | N | 1001 |  |  |  | J | Mark Rison |  |  | Subclause 10.2.1.16.3 states: "To terminate the use of FMS for an FMS Stream identified by FMSID, the non-AP STA shall transmit an FMS Request frame with an FMS Request element and FMS subelement with the FMSID matching the FMS stream and the delivery interval set to 0". There is no FMSID in the FMS Request element. There is however an "FMS Token" in subclause 8.4.2.78: "The FMS Token field contains a unique identifier for the FMS Stream Set that is the set of FMS subelements specified in the request. If this is a new request, then the FMS Token value is 0. Otherwise, the FMS Token value is the value assigned by the AP in the FMS Response element. The FMS Token is fixed for the lifetime of the FMS Stream Set." If the non-AP wants to terminate a particular stream (not a Stream Set), does this mean that instead of the FMS Token, it encodes the FMSID? How can you know this as these are orthogonal fields? | Clarify | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | Proposal-MAH: This appears to be correctly describing the issue. The solution will be complicated (use an (optional?) FMS Descriptor in the FMS Request, or create a new primitive and frame to support the termination, or ??). We need a detailed submission. |  |  |  | 2013-09-19 07:36 | MAC
132 | Mark RISON | 193 | 2012 |  |  |  | E | N | 116 |  |  |  | J | Mark Hamilton/Mark Rison/Brian Hart |  |  | The ProbeDelay isn't a probe delay other than in scanning | Rename it to something more generic, like NAVSyncDelay | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | See CIDs 36, 131 |  |  |  | 2013-09-19 07:36 | MAC
131 | Mark RISON | 193 | 2012 |  |  |  | T | N | 1065 |  |  |  | J |  |  |  | There should not be special probe delays for RMM and for TDLS. The SAP ProbeDelay should be used, as for everything else, since it's being used for the same purpose, viz. to decide how long to wait to try to synchronise with the NAV | Delete the dot11RMMeasurementProbeDelay and dot11TDLSProbeDelay and make all references to them just be references to the ProbeDelay instead | REJECTED (MAC: 2013-09-19 07:28:09Z): While the same purpose is being served, there could be different assumptions about the usage of the channel, which could affect the delay that should be used. The commentor has not provided evidence that the channel conditions and usage should be assumed to be the same as those assumed at SCAN time. | MAC | Motion MAC-P | Ready for motion | Proposed-MAH: Reject. While the same purpose is being served, there could be different assumptions about the usage of the channel, which could affect the delay that should be used. The commentor has not provided evidence that the channel conditions and usage should be assumed to be the same as those assumed at SCAN time. MAC: 2012-10-05 15:17:30Z - See CIDs 36, 132. MAC: 2012-10-05 15:17:30Z - Mark Rison, Brian Hart, Mark Hamilton (and someone from the "it should be zero" camp) to consider. Note that TGai will have strong interest in this discussion. |  |  |  | 2013-09-19 07:28 | MAC
200 | Mark RISON | 193 | 2012 | 9.3.4.4 | 840 |  | T | N | 840 |  | 9.3.4.4 |  | J | Mark Rison |  |  | "The AP shall attempt to deliver one MSDU to the STA that transmitted the PS-Poll, using any frame exchange sequence valid for an individually addressed MSDU." -- but an A-MSDU (typically consisting of more than one MSDU) can also be delivered in response to a PS-Poll | Update this subclause (and any other subclause which is similarly erroneous) to allow an A-MSDU in response to a PS-Poll | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | [MAH] The current text doesn't cover sending a bufferable MMPDU, either. These statements should refer to delivering one bufferable unit. Note that clause 10.2 seems to have corrected this terminology. Apparently this paragraph in clause 9 was missed. In fact, this paragraph also several times uses the phrase "data frame" when it should say BU. Scrub this entire paragraph, and make it align with clause 10.2. Needs a submission. |  |  |  | 2013-09-19 07:36 | MAC
121 | Mark RISON | 193 | 2012 |  |  |  | T | N |  |  |  |  | J | Daniel Cohn/Mark Rison/Mark Hamilton | 11-13/0131r1, 11-12/1199 |  | It's not clear enough which Control MPDUs have non-reserved PM bits and when. Note for example that 8.2.4.1.7 implies the PM bit in ACKs sent by a non-AP STA are not reserved | Make it clear | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | GEN: 2013-01-17 00:01:04Z - move to MAC after discussion on proposal in 11-13/0131r1. See 119, 120, 122 |  |  |  | 2013-09-19 07:36 | MAC
201 | Mark RISON | 193 | 2012 | 11.4.2 |  |  | T | N | 1191 |  | 11.4.2 |  | J | Mark Rison |  |  | Subclause 11.4.2.4.1 says that the TSC is checked before the MIC but subclause 11.4.2.6 says it's checked after -- which is it? | Pick one answer and stick to it. Make sure a similar problem does not afflict other cipher suites. Make sure the answer is compatible with the ordering shown in figure 5-1 and any other statements about the order things shall be done in | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:36 | MAC
119 | Mark RISON | 193 | 2012 |  |  |  | T | N |  |  |  |  | J | Mark RISON | 11-12-1199 |  | The concepts "MMDU is bufferable" and "PM bit is reserved" need to be separated. It makes no sense to say that an Action MMDU sent by a non-AP STA is bufferable, for example, just because you want to be able to say that the PM is valid in the MPDUs used to send it | Bufferability should only pertain to MMDUs sent by APs or IBSS STAs, not non-AP STAs. Separately, the MPDUs in which the PM bit is valid should be enumerated (being clear that the PM bit in PS-Polls, for example, is not valid, and also that the PM bit in the ACK sent after a data frame sent in immediate response to a PS-Poll isn't not valid either) | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | GEN: 2013-01-17 00:02:44Z - assigned to MAC, See 120, 121, 122 Gen: from 11-12-1229 Discussion: It would be nice to know what exactly is the issue by citing the text where it occurs. However, I don’t see any issue. Declaring that a particular action frame is bufferable is merely an act of classification. It doesn’t affect the behaviour of a device (such as a non-AP STA) for which no behaviour is defined that depends on the bufferability of such MMPDUs. Proposed resolution: Rejected. The commenter has not indicated a specfic issue to be resolved or specific changes that would satisfy the commenter. |  |  |  | 2013-09-19 07:36 | MAC
117 | Mark RISON | 193 | 2012 | 9.19.2.2 | 874 |  | T | N | 874 |  | 9.19.2.2 |  | J | Mark Rison |  |  | QoS Nulls should be allowed if the TXOP Limit is 0, else triggers will be awkward (some QoS Data with one octet would be needed) | Add QoS Nulls to the list of things allowed when TXOP Limit is 0. Maybe only allow one, i.e. put it in a) rather than f) | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:36 | MAC
91 | Mark Hamilton | 193 | 2012 | 8.4.1.9 | 446 | 10 | T | N | 446.1 | 10 | 8.4.1.9 |  | J | Mark Hamilton |  |  | All StatusCodes and ResultCodes should have a name | It's just easier to talk about these, if they have a name. | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | [MAH] Worse, there are two tables of Status Code values (Table 8-37 and Table 8-253), depending on where it is used. (And the spelling sometimes has a space "Status Code" and sometimes not "StatusCode".) See also CID 11. This needs a submission. |  |  |  | 2013-09-19 07:36 | MAC
89 | Mark Hamilton | 193 | 2012 | 8.2.4.1.7 | 384 | 58 | T | N | 384.58 | 58 | 8.2.4.1.7 |  | V |  |  |  | Does PM bit apply to any/all Control frames (not sent by an AP)? | Clarify PM bit on Control frames, adding to the discussion for Management and Data frames. Note, 10.2.1.2 has discussion about requiring a frame exchange that includes and ACK or BlockAck, so Control frames (today) probably can't do PM set, but that could change out from under this text (look out for TGai!) | REVISED (MAC: 2013-09-19 06:38:26Z): Change 10.2.2.2 6th paragraph, first sentence, from "To change Power Management modes, a STA shall inform the AP through a successful frame exchange as described in Annex G initiated by the STA and that includes an Ack frame or a BlockAck frame from the AP." to "To change Power Management modes, a STA shall inform the AP through a successful frame exchange as described in Annex G, that is initiated by the STA, and that includes a management, extension or data frame, and that includes an ACK or a BlockAck frame from the AP." | MAC | Motion MAC-P | Ready for motion | Change 10.2.2.2 6th paragraph, first sentence, from "To change Power Management modes, a STA shall inform the AP through a successful frame exchange as described in Annex G initiated by the STA and that includes an Ack frame or a BlockAck frame from the AP." to "…a non-AP STA shall inform the AP through a successful frame exchange described in Annex G, initiated by the non-AP STA, including a management, extension or data frame and that includes an ACK frame, or that includes a BlockAck frame from the AP." OR (Mark Hamilton to consider - ACK only from the AP does not change semantics?) "…a non-AP STA shall inform the AP through a successful frame exchange described in Annex G, initiated by the non-AP STA, including a management, extension or data frame, and that includes receiving an acknowledgment (ACK frame or BlockAck frame) from the AP." |  |  |  | 2013-09-19 06:56 | MAC
88 | Mark Hamilton | 193 | 2012 | 9.19.2 | 874 | 1 | T | N | 874.01 | 1 | 9.19.2 |  | J | Mark Hamilton |  |  | EDCAF operation needs help to improve understanding - it has not evolved well. For example, 9.19.2.3 has become a convoluted machine built from 4 separate bullet lists. 9.19.2.3 and 9.19.2.5 both discuss backoff counter decrements, and when they occur. 9.2 shows EDCA as "on top of" DCF, but EDCA TXOPs violate 9.3.4.3 (6th paragraph). Etc. | This needs off-line work, and a thought-out proposal. | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:36 | MAC
86 | Mark Hamilton | 193 | 2012 | 8.2.4.1.7 | 384 | 58 | T | N | 384.58 | 58 | 8.2.4.1.7 |  | V |  |  |  | Bufferable Management frames was intended (my opinion) to talk about frames that it made sense for an AP to buffer for a PS STA. We then mixed in allowing PM=1 only in bufferable management frames, but PM=1 is a STA tx concept, and those don't necessarily go together. For example, a DeAuth can be buffered - good. But a STA can send a DeAuth that enters PS mode? That seems wrong/odd/confusing. | Devise a better rule for which frames can set the PM subfield. These should be frames which can go from non-AP STA to AP, or to peer IBSS/MBSS STAs, and where power management mode change makes sense. Also, check P1008.30 (subclause 10.2.2.4), which restates this for the IBSS case - probably just delete this limitation here as it is redundant (or replace with text similar to 10.2.1.2's fourth paragraph). | REVISED (MAC: 2013-09-19 07:02:54Z): Change 8.2.4.1.7's lists by retaining the existing first paragraph and changing the rest to: In an infrastructure BSS, the following applies: - The Power Management field is valid only in frame exchanges as described in 10.2.1.2. In such exchanges, a value of 1 indicates that the STA will be in PS mode. A value of 0 indicates that the STA will be in active mode. - The Power Management field is reserved in all management frames transmitted by a STA to an AP with which it is not associated. - The Power Management field is reserved in all frames transmitted by the AP. In an IBSS, the Power Management field is valid only in frame exchanges as described in 10.2.2.4. In such exchanges, a value of 1 indicates that the STA will be in PS mode. A value of 0 indicates that the STA will be in active mode. In an MBSS, the Power Management field is valid only in frame exchanges as described per the mesh power mode transitions rules in 13.14. | MAC | Motion MAC-P | Ready for motion | [MAH proposal] See also CID 89. 10.2.1.2 has rules in the 4th paragraph, which are not consistent with 8.2.4.1.7. 10.2.1.2 makes more sense. Keep those rules (modified by CID 89, perhaps). Modify 8.2.4.1.7 to reference those rules (and 10.2.2.4 and 13.14). Make 10.2.2.4 align with 10.2.1.2. Note that the list of frames with PM bit, and the meaning of that bit in those frames, in 8.2.4.1.7's third bullet list is quite contradictory to 13.14. I believe 13.14 is the correct set of rules, but this should be checked with a mesh expert. Change 8.2.4.1.7's lists by retaining the existing first paragraph and changing the rest to: In an infrastructure BSS, the following applies: - The Power Management field is valid only in frame exchanges as described in 10.2.1.2. In such exchanges, a value of 1 indicates that the STA will be in PS mode. A value of 0 indicates that the STA will be in active mode. - The Power Management field is reserved in all management frames transmitted by a STA to an AP with which it is not associated. - The Power Management field is reserved in all frames transmitted by the AP. In an IBSS, the Power Management field is valid only in frame exchanges as described in 10.2.2.4. In such exchanges, a value of 1 indicates that the STA will be in PS mode. A value of 0 indicates that the STA will be in active mode. In an MBSS, the Power Management field is valid only in frame exchanges as described per the mesh power mode transitions rules in 13.14. |  |  |  | 2013-09-19 07:04 | MAC
59 | Dorothy Stanley | 193 | 2012 | 4.4.3 |  |  | G | N | 69 |  | 4.4.3 |  | J | Kazuyuki Sakoda |  |  | The new text says that Figure 4-11 shows mesh gates, but it does not. | Add a mesh gate to Figure 4-11 | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | Kaz is working on an updated Figure proposal. |  |  |  | 2013-09-19 07:36 | MAC
36 | Brian Hart | 193 | 2012 | 6.3.4.2.2 | 116 |  | T | N | 116 |  | 6.3.4.2.2 |  | J | Mark Hamilton/Mark Rison/Brian Hart |  |  | ProbeDelay is a crucial parameter in the operation of dense WiFi networks but 802.11 is silent on this topic. And by passing it from the SME, it cannot be dynamically optimized. | Add recommendations for probedelay: e.g. by default, a STA should use max TXOP duration for ProbeDelay, with relaxations only if the STA adds extra technologies: e.g. monitors all TXOP durations in last 5 min and uses the max observed TXOP duration, or 99th percentile max TXOP duration; and/or STAs with HW that can detect any PPDU at any stage (i.e. even if the preamble is missed) with high sensitivity might be able to use shorter Probe Delays. As well, describe the problems with short ProbeDelays (e.g. failure of virtual carrier sense so excess collisions) especially in high density environments like 500 students with 1500 WiFi devices in a lecture theater (if you hadn't noticed, WiFi is quite popular and pervasive) | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | See CID 131, 132. |  |  |  | 2013-09-19 07:36 | MAC
31 | Adrian Stephens | 193 | 2012 | 9.7.5.1 | 855 | 20 | T | N | 855.2 | 20 | 9.7.5.1 |  | A |  |  |  | "non-STBC PSMP frame that is not part of an FMS stream" It is surely not appropriate for a PSMP to be part of an FMS stream, which is used to deliver data, not management. PSMP is a management frame and not subject to TCLASS classification. | Remove "that is not part of an FMS stream" and remove "All non-STBC PSMP frames with a group address in the Address 1 field that are part of an FMS stream shall be transmitted using the rate chosen by the AP as described in 10.23.7." | ACCEPTED (MAC: 2013-09-19 07:24:20Z) | MAC | Motion MAC-P | Ready for motion | MAC: 2013-01-18 00:55:55Z - Assign to Qi, as an FMS expert. MAC: 2013-01-17 03:38:15Z - Yes, PSMP frames are not part of an FMS stream. But, could this be trying to say the PSMP sequence/burst started by this PSMP frame is not carrying part of an FMS stream? |  |  |  | 2013-09-19 07:25 | MAC
124 | Mark RISON | 193 | 2012 |  |  |  | T | N | 1211 |  |  |  | J | Mark Rison |  |  | What exactly does "sequential" mean? It seems to be intended to mean "increasing in steps of 1" but might be interpreted as just "increasing" | Clarify this, especially for 11.4.3.4.4.g | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:36 | MAC
1087 | Brian Hart | 193 | 1 | 8.4.4.12 | 805 | 39 | T | Y | 805.39 | 39 | 8.4.4.12 |  | J | Brian Hart |  |  | STAs can share location information in several ways (Geo, Civic etc) but this procedure is limited in that it does not take into account real-world auxiliary requirements that have arisen and led to stds work at IETF for instance (specifically, geopriv or at W3C - platform for privacy preferences, P3P). This Auxiliary requirements come up in relation to 11k/11v/11u distribution of location | Define a means to distribute location together with policy information about how the data can be used: e.g. for what purpose (L2, emergency services, higher layer purposes), can it be redistributed, & how long it is valid for. This would affect 11k/11v/11u location protocols; and ideally location could be shared via ANQP-element pre-assoc in a way that is private between TX and RX even in an open network/pre-assoc | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:36 | MAC
1526 | Mark RISON | 193 | 1 |  |  |  | T | Y |  |  |  |  | J | Mark Rison |  |  | What does "supported rate set" mean? Basic rate set? Operational rate set? | Clarify (probably operational rate set) | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | MAC: 2013-03-18 13:11:42Z - In contexts like the frame formats, it is correct, and references two different information element types (Supported Rates and Extended Supported Rates). The MLME interface talks about basic rate set and operational rate set. 8.4.3.3 and 8.4.3.12 discuss the mapping between the two concepts (with some additional information in 10.1.4.6 and 10.1.7). 9.7 uses the term "supported rate set" rather loosely, and should probably be clarified to be something like "the rates supported by a/the STA" which is a reasonable English phrasology equivalent for all this, and is used in clauses 6 and 8. (See 1136.54 for a good example, and 1135.47 for a bad example.) Nothing to do, except the clean up in 9.7. This can be done now, without logical conflict with later 9.7 clean-up work. |  |  |  | 2013-09-19 07:36 | MAC
1483 | Mark RISON | 193 | 1 | 10.2 |  |  | T | Y | 1093 | 38 | 10.2 |  | J | Mark Rison |  |  | The new stuff in 10.2.2.2 on staying in Awake when some response is expected only covers ABSSen | Add some similar blurb about staying awake if waiting for something when the device has not indicated to the IBSS (and PBSS/MBSS?) member that the device is in PS mode | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:36 | MAC
1468 | Mark RISON | 193 | 1 | 10.16 |  |  | T | Y | 1205 | 35 | 10.16 |  | J | Mark Rison |  |  | OBSS scan all messed up: ref to 10.16.5, not clear whether applies to 2G4 STAs, not clear if the dot11...Factor is a factor or a number of scans or what, ActivityFraction is zero in initial scan before BSS is started, etc. | Fix | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | “All messed up” and “fix” are not an adequate description of a problem or a resolution. |  |  |  | 2013-09-19 07:36 | MAC
1442 | Mark RISON | 193 | 1 |  |  |  | T | Y |  |  |  |  | J | Mark Rison |  |  | Can a BA receiver send a "spontaneous" BlockAck frame if it didn't get a BlockAckReq it was expecting (on the hypothesis that it's missed the said BlockAckReq or somesuch)? | Clarify (might also need tweaks to Annex G) | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | Presumably, this is not meant to include sending a BlockAck after receiving an A-MPDU with Ack Policy equal to Normal Ack (i.e., implicit Block Ack request), or after an RDG, (or maybe under PSMP?). Assuming this is talking about "simple" Block Ack (11e or 11n), then there does not appear to be text supporting such unsolicited BlockAck frames, although there are mentions that suggest it could happen (e.g. 8.2.5.2.a.4). Thus, it seems this could be considered as a behavior, but is not described currently. This comment, therefore, appears to be in effect a request for a new facility. As such, a submission is needed. |  |  |  | 2013-09-19 07:36 | MAC
1433 | Mark RISON | 193 | 1 | 8.4.2.76 |  |  | T | Y | 732 | 32 | 8.4.2.76 |  | J | Qi Wang |  |  | The whole FMS Status subelements thing is confusing; ditto TFS Status subelements | In Table 8-159 there should be a FMS Status Subelements subelement (no, really); then the FMS Status Subelements subelement is what should be stated to contain one or more FMS Status subelements, whose format is shown in Fig 8-329; similar problems for TFS Status Subelement in 8.4.2.83 | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:36 | MAC
1425 | Jon Rosdahl | 193 | 1 | 10.2.2.14 | 1107 |  | T | Y | 1107 |  | 10.2.2.14 |  | J | Jon Rosdahl |  |  | Add to the rational for responses that should be considered towards TDLS Peer Power Save Mode Keep alive status: 1.A response from a non AP-STA to an action frame be considered towards keepalive (if protected keep alive is not needed by the AP)? 2.A PS-POLL be counted towards keep alive which is sent in response to TIM bit set. (Management frames are considered but PS-POLL is not currently but keeping the spirit of the feature in mind this should be allowed. 3. Probe request from and STA with BSSID as AP MAC : This should be considered towards keepalive even if SSID is wildcard. The unmatched SSID will not be considered towards keepalive. | Add text to allow the 3 responsesto be used towards keepalive. | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:36 | MAC
1261 | David Hunter | 193 | 1 | 8.4.1.7 | 505 | 57 | T | Y | 505.57 | 57 | 8.4.1.7 |  | V |  |  |  | "SMEcancels the mesh peering instance with the reason other than reaching..." Huh? Can there be multiple instances of peering between two STAs? What does the receiver of this Management frame care about some other STA's SME? And "reason other than" doesn't indicate anything -- isn't this "for unknown reasons"? | Replace this explanation with "Mesh peering cancelled for unknown reasons." | REVISED (MAC: 2013-09-19 07:06:06Z): - In the table at 505.57, replace "SME cancels the mesh peering instance with the reason other than reaching the maximum number of peer mesh STAs" with "Mesh peering cancelled for unknown reasons". - Remove "the mesh STA has reached its capacity to set up more mesh peering," from the NOTE in 1516.31, as it conflicts with MESH-MAX-PEERS. - Relocate NOTE in 1516.31 to 1516.26, because this note gives hint to the 'internal reason' that is described in 1516.24-25. - In 1516.53, insert the following paragraph "If the Mesh Peering Confirm frame is rejected, the REQ_RJCT event shall be passed with the specified reason code to the protocol finite state machine to actively reject the mesh peering confirm." | MAC | Motion MAC-P | Ready for motion | Suggestion from Kaz: - In the table at 505.57, replace "SME cancels the mesh peering instance with the reason other than reaching the maximum number of peer mesh STAs" with "Mesh peering cancelled for unknown reasons". - Remove "the mesh STA has reached its capacity to set up more mesh peering," from the NOTE in 1516.31, as it conflicts with MESH-MAX-PEERS. - Relocate NOTE in 1516.31 to 1516.26, because this note gives hint to the 'internal reason' that is described in 1516.24-25. - In 1516.53, insert the following paragraph "If the Mesh Peering Confirm frame is rejected, the REQ_RJCT event shall be passed with the specified reason code to the protocol finite state machine to actively reject the mesh peering confirm." |  |  |  | 2013-09-19 07:07 | MAC
1157 | Qi Wang | 193 | 1 | 10.1.3.6 | 1086 |  | T | Y | 1086 |  | 10.1.3.6 |  | J | Jouni Malinen |  |  | Which BSSID (i.e., transmitted or non-transmitted BSSID) should respond to the broadcast and unicast Probe Request, respectively? | Please clarify and modify the spec accordingly. | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | MAC: 2013-07-18 04:18:27Z: Proposed Resolution: Rejected. 1086.65 states: "When a nontransmitted BSSID profile is present in the Multiple BSSID element of the Probe Response frame, the AP shall include all elements that are specific to this BSS. If any of the optional elements are not present in a nontransmitted BSSID profile, the corresponding values are the element values of the transmitted BSSID." From this it is evident that the BSSID that responds is the transmitted BSSID. Jouni was concerned with this resolution. Jouni has volunteered to research constraint on non-AP and AP. |  |  |  | 2013-09-19 07:36 | MAC
1156 | Qi Wang | 193 | 1 | 10.1.3.6 | 1086 |  | T | Y | 1086 |  | 10.1.3.6 |  | J | Jouni Malinen |  |  | Should the TA of the frames transmitted to a STA of a non-transmitted BSSID be the transmitted or non-transmitted BSSID? Should the RA of the frames transmitted to the AP be transmitted or non-transmitted BSSID? | Please clarity and modify the spec accordingly. | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | MAC: 2013-07-18 04:25:12Z: Proposed Resolution: Rejected. The commenter does not identity a problem to be resolved or a specific change to be made. This resolution was proposed due to the large number of questions in the comment, but as Jouni was assigned 1157, it would be better to group it with CID 1157. |  |  |  | 2013-09-19 07:36 | MAC
198 | Mark RISON | 193 | 2012 |  |  |  | T | N | 843 |  |  |  | J | Mark Rison |  |  | How does EIFS work if the ack timeout is a significant fraction of it? Does the EIFS start after the ack timeout? If it starts from the end of the last transmission, what happens if it's less than the ack timeout? Does backoff start immediately in that case? | Clarify | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:36 | MAC
1146 | Kazuyuki Sakoda | 193 | 1 | 8.4.2.108.1 | 772 | 46 | T | N | 772.46 | 46 | 8.4.2.108.1 |  | J |  |  |  | "Broadcast Prioeds Report" is a little misleading as this report is used for all group addressed transmissions. | Replace (rename) "Broadcast Period Report" with "Multicast Period Report" globally. Similarly, replace "Broadcast Report Present" in 8.4.2.18.2, etc, with "Multicast Report Present". Also, change the references to these fields in clause 9.20. | REJECTED (MAC: 2013-09-19 07:14:50Z): The term 'multicast' is deprecated. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:16 | MAC
1632 | Mark RISON | 193 | 1 | 8.4.2.26 | 630 | 32 | T | Y | 630.32 | 32 | 8.4.2.26 |  | J | Mark Rison |  |  | Bit 2 of the extended capabilities is not explicitly linked to dot11ExtendedChannelSwitchActivated | Link 'em, and any others | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:36 | MAC
1086 | Brian Hart | 193 | 1 |  |  |  | T | Y |  |  |  |  | J | Brian Hart |  |  | 802.11 is weak on privacy in that the TA is transmitted in the clear. This is a multidimensional problem: 1) it affects both 1a) APs and 1b) clients; 2) there is the case of 2a) class 1 traffic (sent outside the context of a BSS - no specific relationship), 2b) the traffic sent within a BSS by a non-AP STA or AP as used by the AP or non-AP STA (specific relationship), and 2c) the traffic sent within a BSS by an AP or STA as used by a third party, possibly outside the BSS (no specific relationship); and what is the purpose of the usage: 3a) pure communications, 3b) other L2 purposes such as network discovery and network mgmt, 3c) other aligned purposes such as emergency services and lawful intercept, and 3d) other higher layer functions such as a general purpose location service or analytics. | This issue also arose in the context of web traffic (with cookies) and the Platform for Privacy Preferences (P3P) v1.1 provides good leadership for 2b) and 3) here. Towards 1a) and 1b), given GOs and soft APs, therefore APs and clients should be treated the same from a privacy stds perspective (albeit perhaps with different product defaults). Problems 2a) and 2c) are relatively unique to Wi-Fi, and we know that a visible TA is helpful for a range of things in network mgmt including 11aa. However, best practice is always to be open to users about what is happening, and to give users the ability to opt-in/opt-out for the different kinds of tracking (3a?/3b?/3c?/and certainly 3d). Legal requirements vary around the world, and pre-assoc efficiency is vital, but certainly 802.11 can permit STAs to express efficiently their default policies about how their identifiable information gets treated ("default policy" = policy for entities with whom a STA does not have an overriding relationship/agreement with). Commenter will bring a discussion document as a prelude to making any normative text changes | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:36 | MAC
1084 | Brian Hart | 193 | 1 | 10.25.3.2.10 | 1286 | 15 | T | Y | 1286.15 | 15 | 10.25.3.2.10 |  | J | Brian Hart |  |  | Fig 10-29 shows STA1 sending an ANQP query request containing a TDLS capability ANQP-element but earlier in the section the procedure for this exchange is the "Query List procedure" defined in 10.25.3.2 but this procedure only refers to a Query List ANQP-element being included: i.e. the procedure makes no allowance for the inclusion of a TDLS capability ANQP-element | Generalize ANQP procedure to allow a request to contain any kind of elements as appropriate, so as to make the existing TDLS procedure legal (and GAS/ANQP more valuable). I believe that work in a fraternal organizaiton would benefit from this refinement too | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:36 | MAC
1046 | Adrian Stephens | 193 | 1 | 8.5.8.25 | 849 | 55 | G | N | 849.55 | 55 | 8.5.8.25 |  | J | Carlos Aldana |  |  | The terminology is hopelessly confused here. How can a "receiving STA request"? Recom-mend roles in the Fine Timing Measurement exchange are not called "sending" and "receiving" STA, which are hopelessly overloaded, but something like "Fine Timing Measurement Initiator STA" | Choose terms for these roles and use them consistently here and in clause 10 description. | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:36 | MAC
1025 | Adrian Stephens | 193 | 1 | 8.2.4.1.8 | 443 | 46 | T | N | 443.46 | 46 | 8.2.4.1.8 |  | V |  |  |  | "The More Data field is set to 0 in group addressed frames transmitted by the AP when no more group addressed BUs that are part of an active GCR-SP remain to be transmitted by the AP during this GCR-SP." Does this addition by .11aa conflict with the the first sentence of the preceding para: "The More Data field is set to 1 in group addressed frames transmitted by the AP when additional group addressed bufferable units (BUs) that are not part of an active GCR-SP(11aa)remain to be transmitted by the AP during this beacon interval." | Make cited statements consistent. | REVISED (MAC: 2013-09-19 06:35:53Z): Change the cited paragraphs to: "The More Data field is set to 1 in non-GCR-SP group addressed frames transmitted by the AP when additional group addressed bufferable units (BUs) that are not part of an active GCR-SP remain to be transmitted by the AP during this beacon interval. The More Data field is set to 0 in non-GCR-SP group addressed frames transmitted by the AP when no more group addressed BUs that are not part of an active GCR-SP remain to be transmitted by the AP during this beacon interval and in all group addressed frames transmitted by non-AP STAs. The More Data field is set to 1 in GCR-SP group addressed frames transmitted by the AP when additional group addressed BUs that are part of an active GCR-SP remain to be transmitted by the AP during this GCR-SP. The More Data field is set to 0 in GCR-SP group addressed frames transmitted by the AP when no more group addressed BUs that are part of an active GCR-SP remain to be transmitted by the AP during this GCR-SP." | MAC | Motion MAC-P | Ready for motion | Mark will confirm with Alex. I believe that the GCR operation is intended to be separated from 'normal' group addressed frame transmission, so the paragraphs about the More Data bit should say "part of an active GCR-SP" or "not part of an active GCR-SP" on every mention of a group addressed frame. Thus: "The More Data field is set to 1 in non-GCR-SP group addressed frames transmitted by the AP when additional group addressed bufferable units (BUs) that are not part of an active GCR-SP remain to be transmitted by the AP during this beacon interval. The More Data field is set to 0 in non-GCR-SP group addressed frames transmitted by the AP when no more group addressed BUs that are not part of an active GCR-SP remain to be transmitted by the AP during this beacon interval and in all group addressed frames transmitted by non-AP STAs. The More Data field is set to 1 in GCR-SP group addressed frames transmitted by the AP when additional group addressed BUs that are part of an active GCR-SP remain to be transmitted by the AP during this GCR-SP. The More Data field is set to 0 in GCR-SP group addressed frames transmitted by the AP when no more group addressed BUs that are part of an active GCR-SP remain to be transmitted by the AP during this GCR-SP." As an aside, it is noted that these paragraphs are getting very wordy, and the second sentence is the inverse of the first. This could be simplified by making the second sentence, "The More Data field is set to 0 otherwise." |  |  |  | 2013-09-19 06:37 | MAC
363 | Mark Rison | 193 | 2012 |  |  |  | T | N | 402 |  | 8.2.5 |  | J | Mark Rison |  |  | What happens to the rules for setting the Duration/ID field for 11n if the beamforming report duration estimate is wrong (too low)? Can the duration be floored to 0 (so it doesn't go negative)? Can the duration of an acknowledgement be added by the TXOP holder (since it's going to be transmitted anyway so might as well be protected)? | Clarify | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | [MAH] Needs submission |  |  |  | 2013-09-19 07:36 | MAC
361 | Mark Rison | 193 | 2012 |  |  |  | T | N |  |  |  |  | J | Mark Rison |  |  | Can a STA in an MBSS or IBSS (usefully) send a Notify Channel Width MMPDU? | Clarify | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:36 | MAC
283 | Matthew Fischer | 193 | 2012 | 9.7.6.5 | 859 | 1 | T | N | 859.01 | 1 | 9.7.6.5 |  | J | Matthew Fischer |  |  | ACK (and other control response frames) are supposed to be sent at rates as specified in this subclause. Generally speaking, this subclause prescribes ACK transmission at a Basic Rate, which is, for eliciting frames that are transmitted at higher rate or MCS values, typically a rate that is lower than the rate or MCS of the eliciting frame by at least two increments. When the eliciting frame is at one of the lower rates/MCS, then the ACK will often be at the same rate/MCS. Normally, this is ok - reliability of the ACK transmission is good or better than the eliciting frame because the eliciting frame usually has significantly more bits than the ACK. But if the eliciting STA has a higher TX power, then the rate for the ACK can be too high and is very likely to fail. It would be nice if the eliciting STA can signal to the responder that a lower rate/MCS will be needed. This ensures a receiveable ACK and it allows the eliciting STA to correctly compute the ACK duration for DUR field use. | Allow a control response frame to be sent at a rate/MCS lower than otherwise allowed when there is a power difference or for other reasons. Create a mechanism that allows the eliciting STA to indicate the preferred response rate/MCS. E.g. signal in the eliciting frame, a value of step down in rate/MCS from the normally computed value for the response frame. | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | MAC: 2013-05-15 03:55:15Z: No concrete proposal yet. Discussion. Will consider a submission when one is available. |  |  |  | 2013-09-19 07:36 | MAC
222 | Mark RISON | 193 | 2012 |  |  |  | E | N | 1174 |  |  |  | J | Mark Rison |  |  | "dot11WEPDefault-KeyID" on p. 1174 "(PMKI)" on p.444 "since the key id 0 is reserved for individually" -- misleading if the key id 1 option is supported | Fix all the issues noted | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | EDITOR: 2012-10-03 11:19:08Z - This is not an editorial comment. Assigning to MAC. |  |  |  | 2013-09-19 07:36 | MAC
211 | Mark RISON | 193 | 2012 | 11.4.3.4.4 |  |  | T | N | 1211 |  | 11.4.3.4.4 |  | A |  |  |  | "g) The receiver shall discard MSDUs, A-MSDUs, and MMPDUs whose constituent MPDU PN values are not sequential." -- but A-MSDUs cannot be fragmented | Delete ", A-MSDUs," | ACCEPTED (MAC: 2013-09-19 07:30:17Z) | MAC | Motion MAC-P | Ready for motion |  |  |  |  | 2013-09-19 07:30 | MAC
1155 | Qi Wang | 193 | 1 | 10.1.3.6 | 1086 |  | T | Y | 1086 |  | 10.1.3.6 |  | J | Qi Wang |  |  | It is unclear whether the SSID of each of the BSSID Set should be the same or not. | Please clarify whether the SSID of each of the BSSID Set should be the same or not. | The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | MAC | Motion MAC-P | Ready for motion | MAC: 2013-07-24 02:35:13Z - Removed from motion MAC-L July 18, 2013. Needs further discussion. REJECTED (MAC: 2013-07-18 04:22:32Z): 1086.43 states: "The nontransmitted BSSID profile shall include the SSID element (see 8.4.2.2 (SSID element)) and Multiple BSSID-Index element (see 8.4.2.73 (Multiple BSSID-Index element)) for each of the supported BSSIDs." From this it is evident that the SSID may be different for each nontransmitted BSSID. |  |  |  | 2013-09-19 07:36 | MAC

## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-12/0361r14
Venue Date: | September 2013
First Author: | Mark Hamilton, Spectralink
Subject: | REVmc Working Group Ballot Comments for MAC ad-hoc
Full Date: | 2013-09-19
Author(s): | Name(s) | Mark Hamilton
| Company | Spectralink
Address
Phone:
Fax:
| email: | mark.hamilton@spectralink.com
Abstract:
This document contains comments in the "MAC ad hoc" group, submitted on REVmc letter ballots and by interested parties on the published IEEE Std 802.11-2012

## Revision History
Revision | Date | Description
0 | 2013-03-20 | Initial revision after first letter ballot. CIDs with resolutions ready for Motion MAC-F: 1074, 224, 1477, 1042, 1044, 1052, 1053, 118, 1065, 1628, 1194, 1429, 1456, 1555, 1556, 1585, 1622, 1060.
1 | 2013-03-21 | CIDs with resolution ready for Motion MAC-G (per TG discussion on 3-20): 1098, 1073, 1092, 1093, 1094, 1095, 1071, 1097, 1337, 1108, 1168, 1328, 1331, 1332, 1333, 1096.
2 | 2013-03-21 | Updates done during Orlando Thursday meetings. CIDs with resolution ready for Motion MAC-H: 1707, 1039, 1038, 1031, 284, 128.
3 | 2013-04-04 | Proposed resolutions to CIDs (ready for review): 89, 1008, 1134, 1135, 1424.
4 | 2013-04-23 | From teleconferences, CIDs with resolution ready for Motion MAC-H: 1006, 1008, 1026, 1027, 1049, 1051, 1055, 1056, 1057, 1058, 1062, 1102, 1134, 1136, 1151, 1172, 1222, 1229, 1263, 1269, 1392, 1410, 1430, 1469, 1480, 1549, 1638, 1694, 1703, 1704, 1705, 1706.
5 | 2013-05-06 | From Apr 26 teleconference, CIDs with resolution ready for Motion MAC-H: 1109, 1091, 1075, 1054, 1035, 1034, 1032, 1030, 1029, 1455, 1578, 1552, 1550, 1499, 1712, 1454, 1422, 1419, 1340, 1339, 1338.
6 | 2013-05-13 | Updates done during Kona Monday meetings. CIDs with resolution ready for Motion MAC-H: 1059, 1080, 1061, 1063, 1064, 1069, 1070, 30, 1005, 1043, 1037, 1104.
7 | 2013-05-14 | Updates done during Kona Tuesday meetings. CIDs with resolution ready for Motion MAC-H: 277, 1003, 287, 1251, 1257.
8 | 2013-07-02 | Updates from teleconferences, CIDs with resolution ready for Motion MAC-I: 1067, 1160, 1159, 1158, 1152, 1118, 1111, 50, 1106, 1163, 1066, 1007, 312, 309, 1460, 1448, 1107, 1398, 1534, 1474, 1473, 1472, 1406, 1402, 1161, 1399, 1162, 1397, 1315, 1169, 1166, 1165, 1164, 1661, 1401.
9 | 2013-07-15 | Updates from Geneva meeting, CID 1009 with resolution ready for Motion MAC-K (to be motioned independently). CIDs with resolution ready for Motion MAC-J: 1515, 1068, 1100, 1274, 1275, 1281, 1290, 1396, 1047, 1503, 1711, 1617, 1652, 1664, 1666, 1667, 1709, 1710, 1407. CID 309 removed from Motion MAC-I, and returned to unresolved (Comments tab).
10 | 2013-07-17 | Updates from Geneva meeting, CIDs with resolution ready for Motion MAC-L: 1511, 1155, 1167, 1170, 1292, 1295, 1400, 1439, 1150, 1482, 1679, 1516, 1566, 1615, 1616, 1656, 1658, 1678, 1481.
11 | 2013-07-23 | Updates from Geneva meeting, Motion MAC-L CIDs resolutions moved (except CID 1155). CIDs 78, 309, 310 resolutions moved. All remaining comments assigned to someone.
12 | 2013-09-17 | Updates from teleconferences, CIDs with resolution ready for Motion MAC-M: 1141, 263, 314, 317, 324, 1021, 1028, 1088, 1132, 1135, 1137, 1138, 77, 1140, 1654, 1148, 1153, 1154, 1258, 1259, 1260, 1296, 1305, 1311, 1335, 1367, 1373, 1139. Updates from Nanjing meeting, CIDs with resolution ready for Motion MAC-N: 1510, 1418, 278, 280, 285, 1216, 1411, 1458, 1671, 1525, 1548, 1602, 1635, 1660, 1668, 1424.
13 | 2013-09-18 | Updates from Nanjing meeting, CIDs with resolution ready for Motion MAC-O: 1291, 1050, 58.
14 | 2013-09-19 | Updates from Nanjing meeting, CIDs with resolution ready for Motion MAC-P: 1632, 1433, 1261, 1146, 1087, 1046, 1025, 1483, 1468, 1425, 1157, 1156, 1084, 91, 132, 131, 124, 121, 120, 11, 117, 148, 89, 88, 86, 59, 36, 31, 119, 201, 1442, 1155, 1086, 363, 361, 283, 145, 211, 147, 200, 198, 177, 157, 153, 1526, 222.
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29