## Slide 1: IEEE 802.11mc Closing Report for March 2013
Date: 2013-03-21
Authors:

## Slide 2: Abstract
This document contains the TGmc closing report for March 2013.

## Slide 3: Status: comment resolution
Continued processing comments received in the recent Initial Letter Ballot
  801 comments (713 LB, 88 remaining 2012 Call for comments)
  Approved resolutions to approximately 350 comments

## Slide 4: TGmc Plan of Record
Slide 4
20 July 2012 – 12 Sept 2012 – Call for Comment/Input
29-30 Aug 2012 – NesCom, SASB PAR Approval
Sept 2012 – Begin to process input
Sept 2012 – 11aa, 11ae integration
Jan – First WG Letter ballot - without 11ad
Dec 2012 – March/May 2013 – 11ad integration – May/July ballot on D2.0
Dec 2013 – March 2014 – 11ac integration
Feb 2014 – Mandatory Draft Review
Feb-March 2014 – Form Sponsor Pool (45 days)
April/May 2014 – Initial Sponsor Ballot
TBD – integration of additional completed amendments (e.g. 11af)
Nov 2014 – WG/EC Final Approval
March 2015 – RevCom/SASB Approval
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 4

## Slide 5: Teleconferences
Conference Calls 10am Eastern (2 hours)
  April 5, 12, 19, 26 (Friday)

## Slide 6: Next Steps
Continued Comment Resolution
Recirculation Letter ballot (expect July)