## Slide 1: May 802.19 Liaison Report
Date: 2013-05-15
Authors:

## Slide 2: Abstract
May 802.19 liaison report

## Slide 3: 802.19 May Meeting Plan
Working Group
Task Group 1 – TVWS Coexistence
  Letter ballot comment resolution

## Slide 4: Coexistence Assurance Documents
802.19 ballot on the 802.15.4p CA document closed on May 3, 2013
  Passed with vote of 28/1/1

## Slide 5: 802.19.1 LB
1st re-circulation on D3.03 closed early May
  Approval rate: 72% (Approves: 23, Disapproves: 9)
82 comments received
  General comments: 1
  Editorial comments: 22
  Technical comments: 59
Goal of meeting to resolve all comments

## Slide 6: 802.19.1 Timeline
Targeted TG1 Timeline:
  Second Working Group Letter Ballot: October 2012
  Recirculation Letter Ballot: March 2013
  Recirculation Letter Ballot: July 2013
  Form Sponsor Ballot Pool: July 2013
  Initial Sponsor Ballot: November 2013
  Recirculation Sponsor Ballot: March 2014
  Final WG/EC Approval: July 2014
  RevCom/Standards Board Approval: September 2014

## Slide 8: References
https://mentor.ieee.org/802.19/dcn/13/19-13-0058-01-0001-may-2013-tg1-agenda.xls
https://mentor.ieee.org/802.19/dcn/13/19-13-0059-00-0001-tg1-opening-report-for-may-2013.pptx
https://mentor.ieee.org/802.19/dcn/13/19-13-0056-00-0000-may-2013-wg-agenda.xls