## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-13/1160r12
Venue Date: | May 2014
First Author: | Jon Rosdahl, CSR
Subject: | REVmc Working Group Ballot Comments
Full Date: | 2014-05-14
Author(s): | Name(s) | Jon Rosdahl
| Company | CSR Technologies Inc.
| Address | 10871 N 570 W, Highland, UT 84003
| Phone: | +1-801-492-4023
Fax:
| email: | adrian.p.stephens@intel.com
Abstract:
This document contains the GenAdHoc comments received on LB199 for P802.11REVmc during working group letter ballot LB199 .
As comment resolutions are approved, comments are moved to the editor for implementation and this will will shrink.

## Revision History
Revision | Date | Description
0 | 2013-11-11 | Initial version with LB199mc comments for Gen AdHoc -
1 | 2013-11-12 | After discussion during RevMC Tuesday PM1 and PM2
2 | 2013-11-21 | GEN Comment status after the 2013 Nov Plenary in Dallas - Note Gen Motion Dallas C is ready for Motion. Submission requested are for CIDs that are assigned needing submission. Comments tab are unassigned looking for volunteers.
3 | 2014-01-20 | Comment updates from the Telecons from Dec and January
4 | 2014-01-23 | Comment updates from the discussion of the week through Thurs PM1
5 | 2014-01-24 | Resolved comments moved to Editor - updated comments through the January Interim Session. GEN Comment Status after the 2014 January Interim in LA.
6 | 2014-02-24 | Gen Comment Status after the Feb 21st Telecon -
7 | 2014-03-04 | Gen Comment Status updated after the Feb 28th Telecon
8 | 2014-03-13 | Status updated after the March 12th Telecon
9 | 2014-03-20 | Status as of Thursday PM1 (March 20) in Beijing - CIDs covered by Motion #48 have moved to Editor.
10 | 2014-05-07 | Status after the April/May Telecons - 11 CIDs left to resolve
11 | 2014-05-13 | Status of GEN adhoc comments after Tuesday PM2 - note CID resolutions that were approved in PM1 were note removed in this version.
12 | 2014-05-14 | One comment remains and is awaiting resolution -- 2 CIDs await motion
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29

## Gen Motion Hawaii 2
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
2231 | David Hunter | 199 | 2 | 3.2 | 33 | 20 | T | Y | 33.2 | 20 | 3.2 |  | J | David Hunter |  |  | Terms such as "multiple MAC sublayers link" are defined in terms of "link", but this type of "link" is not defined (assuming that downlink, uplink, ESS link, STSL and TDLS are not referring to this type of link). Need a definition of this type of "link". | Define this type of link, or replace "link" in the definitions of multiple MAC sublayers link and multiple MAC sublayers link cluster with something that is defined. | REJECTED (GEN: 2014-05-15 01:20:31Z) Commenter has provided insufficient detail to resolve the comment. | GEN | Gen Motion Hawaii 2 | Ready for motion |  |  |  |  | 2014-05-15 02:24 | GEN
2183 | Adrian Stephens | 199 | 2 | B.4.24.1 |  |  | G | Y | 2383 | 27 | B.4.24.1 |  | V | Adrian Stephens | 11-14/207r8 |  | Invalid or bogus references at: 2386.10 (8.4.2.111.2), 2386.11 (11.3), 2386.15 (8.4.2.145), 2386.23 (9.13a9.14), 2387.31 (9.4.2.138), 2387.35 (8.4.2.140), 2387.44 & 2387.57 (8.4.2.138), 2392.55 (8.4.2.138), 2392.59 (8.4.2.140), 2393.07 (8.4.2.138), 2393.11 (8.4.2.140) |  | REVISED (GEN: 2014-05-13) Make changes under CID 2183 in 11-14/207r8 | GEN | Gen Motion Hawaii 2 | Ready for motion | GEN: 2014-05-15 - updated the resolution to indicate R8, and change to Comment Group "Gen Motion Hawaii 2" GEN: 2014-02-21 16:00:18Z change assignment to Adrian |  |  |  | 2014-05-15 02:20 | GEN

## Submission requested
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
2434 | Mark Hamilton | 199 | 2 | 5.2.1 | 116 | 1 | T | Y | 116.01 | 1 | 5.2.1 |  |  | Mark Hamilton | 11-13/115r11 |  | Figure 5-1 is confusing. It looks a lot like 802.1Q's bridge diagram, but this is not at all the same thing. It also has several unlabeled blocks which are confusing. And, it implies that 802.1X port control is above LLC which is incorrect. | Replace Figure 5-1 with that contained in a submission from the ARC SC. |  | GEN | Submission requested | Needs submission | GEN: 2014-05-13 02:23:24Z - Review of the updated figure changes. fix just the missing arrow in r12, and then if r13 can be made, then great if not, we can incorporate r12 into the document for now. GEN: 2014-05-02 review during Hawaii meeting: Proposed resolution: Revised, Incorporate the changes from 11-14/115r11 |  |  |  | 2014-05-13 04:02 | GEN