## Slide 1: IEEE 802.11mc Closing Report for September 2013
Date: 2013-09-19
Authors:

## Slide 2: Abstract
This document contains the TGmc closing report for September 2013.

## Slide 3: Status
Completed processing comments received in LB 193 - Initial Letter Ballot
  801 comments (713 LB, 88 remaining 2012 Call for comments)
Approved motion for recirc LB on D2.0 (est open by Oct 4)
Completed resolution of ISO comments on IEEE Std 802.11-2012
  See https://mentor.ieee.org/802.11/dcn/13/11-13-0123-05-000m-iso-jtc1-sc6-8802-11-2012-comments.xls
Request addition of P802.11REVmcD2.0 to IEEE store (pending successful recirculation ballot)

## Slide 4: Recirculation LB Motion
Having approved comment resolutions for all of the comments received from LB193 on P802.11mc D1.0
Instruct the editor to prepare P802.11mc D2.0 incorporating these resolutions and
Approve a 20 day Working Group Recirculation Ballot asking the question “Should P802.11mc D2.0 be forwarded to Sponsor Ballot?”
Moved: Adrian Stephens
Seconded: Jon Rosdahl
Result: 11-0-1 Passes

## Slide 5: TGmc Plan of Record (to be revised)
Slide 5
20 July 2012 – 12 Sept 2012 – Call for Comment/Input
29-30 Aug 2012 – NesCom, SASB PAR Approval
Sept 2012 – Begin to process input
Sept 2012 – 11aa, 11ae integration
Jan – First WG Letter ballot - without 11ad
Dec 2012 – March/May 2013 – 11ad integration –
Sept 2013 – Letter ballot on D2.0
Dec 2013 – March 2014 – 11ac integration
  Letter Ballot on D3.0 (includes 11ac) March 2014
Feb 2014 – Mandatory Draft Review
Feb-March 2014 – Form Sponsor Pool (45 days)
April/May – Initial Sponsor Ballot
TBD – integration of additional completed amendments (e.g. 11af)
  Integrate after initial SB
Nov 2014 – WG/EC Final Approval
March 2015 – RevCom/SASB Approval
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 5

## Slide 6: Teleconferences
Conference Calls 10am Eastern (2 hours)
  October 11, November 1, 8

## Slide 7: Next Steps
Comment Resolution of comments received from recirculation LB on P802.11REVmc D2.0