## Slide 1: HEW SG September 2013 Closing Report
Date: 2013-09-19
Authors:

## Slide 2: Abstract
This document is the closing report for the HEW SG for the September 2013 session.

## Slide 3: Work Completed
Close to 50 submissions were covered during this meeting in areas related to:
  Evaluation Methodologies, Simulation Scenarios, and Channel Models
  MAC/PHY Technologies
  Discussions related to possible progress on the PAR
A number of straw polls were conducted to sense the group consensus on topics related to simulation scenarios, evaluation methodology and channel models.
The SG agenda is available at: https://mentor.ieee.org/802.11/dcn/13/11-13-0951-07-0hew-september-2013-hew-sg-meeting-agenda.ppt

## Slide 4: November 2013 Goals
Presentations addressing issues related to SS/SM/EM/FR/CM/TECH
Attempt to consolidate documents related to the above areas of discussion.
Priority will be given to presentations with consolidated views
Start discussion on PAR related issues
Motion for SG extension
WFA feedback on the usage cases

## Slide 5: Timeline
May 2013
  Initial meeting
July 2013
  Presentations
  SG Extension
Sept 2013
  Presentations
Nov 2013
  Presentations
  Initial PAR and 5C
  SG Extension
Jan 2014
  Presentations
  Final version of PAR and 5C
  WG Approval
March 2014
  Presentations
  EC Approval
May-June 2014
  Nescom approval
July 2014
  TG starts

## Slide 6: Conference Call Times
Oct 9 10:00 – 12:00 ET
Oct 17 00:01 – 02:00 ET
Oct 30 10:00 – 12:00 ET