## Sheet1
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
2416 | George Calcev | 198 | 1 | 10.44.3 | 89 | 54 | T | Y | 89.54 | 54 | 10.44.3 |  |  | Santosh Pandey |  |  | TMBB Information Field Type' subfield in the neighbor AP information field, not clear where is generated | Please provide detail descriptions to clarify it. |  | TGai General |  | Discuss | See first sentence of the previous paragraph |  |  |  | 2013-09-16 16:10 | TGai General
2705 | Jens Tingleff | 198 | 1 | 8.3.3.2 | 26 | 16 | G | N | 26.16 | 16 | 8.3.3.2 |  |  | Santosh Pandey |  |  | Table 8-20. Is the Reduced Neighbor Report, ID 204, similar to the Reduced Neighbor Report, ID 201, of 802.11af D5 ? | If they are different, make different names? |  | TGai General | Discovery | Revised | They are the same, submission 1204r0 fixes this issue |  |  |  | 2013-09-17 03:25 | TGai General
2691 | Jarkko Kneckt | 198 | 1 | 10.44.3 | 89 | 38 | T | N | 89.38 | 38 | 10.44.3 |  |  | Santosh Pandey |  |  | Why the use of the Reduced Neighbor Report is only limited to passive scanning? The TBTT information may be beneficial also for active scanning. | Change the line to read: "A STA receiving a Reduced Neighbor Report may use the report to schedule scanning." |  | TGai General |  | Accepted | This sentence maps to page 90.13 of Tgai draft 1.1 |  |  |  | 2013-09-16 16:10 | TGai General
2663 | Jarkko Kneckt | 198 | 1 | 8.4.2.176 | 39 | 58 | E | N | 39.58 | 58 | 8.4.2.176 |  |  | Santosh Pandey |  |  | The explanation of the value 1 in TBTT Information Length field is written negatively. It is better to say positively that TBTT Offset is present. Also the text confuses on the field name. The paragraph should discuss on TBTT Information Length, not on TBTT Information Field Type. | Change the second setence to: " The TBTT Information field contains TBTT Offset field when the TBTT Information Length is 1. The TBTT Information field contains the TBTT Offset and the BSSID field when the TBTT Information Length is 7. |  | TGai General |  | Revised | In TGai Draft 1.1 39.54, replace the second and third setence of the paragraph with the following: "When the value of TBTT Information Length is 1, the TBTT Information field contains the TBTT Offset subfield. When the value of TBTT Information Length is 7, the TBTT Information field contains the TBTT Offset and the BSSID subfields. Other values are reserved." |  |  |  | 2013-09-16 15:41 | TGai General
2661 | Jarkko Kneckt | 198 | 1 | 8.4.2.176 | 39 | 6 | T | N | 39.06 | 6 | 8.4.2.176 |  |  | Santosh Pandey |  |  | The operating bandwidth of the neighbor APs that are included to the Neighbor AP field may operate in multiple channels, i.e. The AP may be HT or VHT AP. Thus, the APs may not operate only on one channel. | Change :" ... Information related to neighbor APs having the same primary channel". |  | TGai General |  | Revised | In TGai Draft 1.1 39.3, replace the first setence of the paragraph with the following: "The Neighbor AP Information field specifies TBTT and other information related to a group of neighbor APs having the same primary channel" |  |  |  | 2013-09-16 15:43 | TGai General
2660 | Jarkko Kneckt | 198 | 1 | 8.4.2.176 | 39 |  | E | N | 39 |  | 8.4.2.176 |  |  | Santosh Pandey |  |  | The TBTT information is poor name, because also other information may be present. | Change the "TBTT Information Header" to "Neighbor Information Header". Change "TBTT Informaiton field" to "Neighbor Information field". Change "TBTT Information Type" to "Neighbor Information Type". Change "TBTT Information Count" to "Neighbor Information Count". Change TBTT Information Length" to "Neighbor Information Length". |  | TGai General |  | Rejected | Baseline in TGaf - please submit the comment in TGaf |  |  |  | 2013-09-16 15:42 | TGai General
2659 | Jarkko Kneckt | 198 | 1 | 8.4.2.176 | 38 | 46 | E | N | 38.46 | 46 | 8.4.2.176 |  |  | Santosh Pandey |  |  | The Reduced Neighbor Report introduction could just list that reduced neighbor report contains information related to neighbor APs. There is no need to specify that there is channel information and other information. | delete "channel and other". |  | TGai General |  | Accepted |  |  |  |  | 2013-09-16 15:42 | TGai General
2523 | GEORGE CHERIAN | 198 | 1 | 30 | 89 | 10 | T | N | 89.1 | 10 | 30 |  |  | Santosh Pandey |  |  | Contradiction regarding number of Neighbor AP Information field per channel/operating class | Lines 30-31: Need to reword this sentence to be consistent with lines 5-6 on pg 39 |  | TGai General |  | Discuss | Not sure about the contradiction - check with commentor. 89.30: "Multiple Neighbor AP Information field with the same operating class and channel number values may be present in a Reduced Neighbor Report element." 39.5: "The Neighbor AP Information field specifies TBTT and other information related to a group of neighbor APs on one channel" |  |  |  | 2013-09-16 16:10 | TGai General
2482 | GEORGE CHERIAN | 198 | 1 |  | 89 | 10 | T | N | 89.1 | 10 |  |  |  | Santosh Pandey |  |  | Verbose text without clear description of what is normative and informative. Using statements such as "may optionally" does not make any sense. To much use of "may". Contains a sentence with "shall consider", which does not mean any thing. | Entire clause: The text of this clause should be described as informative. There should not be any "shall" statements in the text. |  | TGai General |  | Discuss | Consistent with baseline IEEE 802.11-2012. Also please submit the comment in Tgaf for any major changes. |  |  |  | 2013-09-16 16:10 | TGai General
3004 | Minyoung Park | 198 | 1 | 8.3.3.2 | 26 | 5 | E | Y | 26.05 | 5 | 8.3.3.2 |  |  | Santosh Pandey |  |  | The Order column of Table 8-20 should reflect the numbering in Tgac D5.1. Tgac added Order 60 - 66. Tgai should add numbering from Order 67. | As in comment. |  | TGai General |  | Discuss | Move to editorial - discussed with Lee |  |  |  | 2013-09-16 15:36 | TGai General
2436 | GEORGE CHERIAN | 198 | 1 | 31 | 26 | 8 | T | N | 26.31 | 8 | 8 |  |  | Santosh Pandey |  |  | Remove FILS Identity from Beacon frame. The information is already available in FILS Indication |  |  | TGai General | Discovery | Accepted |  |  |  |  | 2013-09-17 03:25 | TGai General
2709 | Jing-Rong Hsieh | 198 | 1 | 8.4.2.176 | 39 | 59 | E | N | 39.59 | 59 | 8.4.2.176 |  |  | Santosh Pandey |  |  | Should it be "TBTT Information Length subfield" rather than "TBTT Information Field Type" to specifiy if BSSID is included in TBTT Information? | Change to TBTT Information Length subfield. |  | TGai General |  | Revised | See CID 2663 |  |  |  | 2013-09-16 15:41 | TGai General
2412 | George Calcev | 198 | 1 | 8.4.2.176 | 39 |  | T | Y | 39 |  | 8.4.2.176 |  |  | Santosh Pandey |  |  | If the value is 7', what is the value referring to? Is it the value of TBTT Information Field Type? However, 'TBTT information field type' subfield has only two bits, and cannot be 7. | Please clarify. |  | TGai General |  | Revised | See CID 2663 |  |  |  | 2013-09-16 15:42 | TGai General
2303 | David Hunter | 198 | 1 | 8.4.2.176 | 40 |  | T | Y | 40 |  | 8.4.2.176 |  |  | Santosh Pandey |  |  | "A STA may send the Probe Request frame including the received BSSID on channel indicated in Neighbor AP Information filed subject to regulations." not only contains a normative verb, but is generally confusing. | Replace this sentence with: "Subject to regulations, a STA can send a Probe Requst frame (including the received BSSID) on a channel listed in the Neighbor AP Information field." |  | TGai General |  | Accepted | This is in Tgai draft 1.1 40.33 |  |  |  | 2013-09-16 15:41 | TGai General
2293 | David Hunter | 198 | 1 | 8.4.2.26 | 37 |  | E | Y | 37 |  | 8.4.2.26 |  |  | Santosh Pandey |  |  | "and is 0 otherwise." might apply to the STA. | Replace "procedures and is 0 otherwise." with: "procedures. Otherwise the value of the FILS Capability field is 0." |  | TGai General | General | Revised | Accept the proposed change for line 43 on page 37. |  |  |  | 2013-09-17 03:39 | TGai General
2188 | Clint Chaplin | 198 | 1 | 8.4.2.176 | 40 | 31 | T | Y | 40.31 | 31 | 8.4.2.176 |  |  | Santosh Pandey |  |  | "subject to regulations." What regulations? Regional regulatory requirements? Wi-Fi testing regulations? 802.11 requirements? | Please be more specific about the limitations here. |  | TGai General |  | Discuss | Disscuss with PeterE and others |  |  |  | 2013-09-16 15:41 | TGai General
2087 | Adrian Stephens | 198 | 1 | 10.44.3 | 89 | 54 | T | Y | 89.54 | 54 | 10.44.3 |  |  | Santosh Pandey |  |  | "If the STA detects that the TBTT Information Field Type is 1 and BSSID field is not included in the TBTT". The act of detection is not germain. | "If the TBTT Information Field Type is 1 and BSSID field is not included in the TBTT". Or reword into canonical form "A STA that receives a Reduced Neighbor Report element in which the TBTT Information Field Type field is 1 and in which the BSSID field is not present may switch..." Similar rewording in the next sentence. |  | TGai General |  | Discuss | TBD |  |  |  | 2013-09-16 16:10 | TGai General
2086 | Adrian Stephens | 198 | 1 | 10.44.3 | 89 | 45 | G | Y | 89.45 | 45 | 10.44.3 |  |  | Santosh Pandey |  |  | "If the AP considers". APs don't consider, muse, think ... etc. Where this "consideration" forms part of a normative statement, it needs to be reworded into something less touchy-feely. | Replace "If the AP considers " with "If the AP determines" and add a sentence "How the AP makes this determination is implementation dependent" or some such. |  | TGai General |  | Discuss | TBD |  |  |  | 2013-09-16 16:10 | TGai General
2085 | Adrian Stephens | 198 | 1 | 10.44.3 | 89 | 34 | E | Y | 89.34 | 34 | 10.44.3 |  |  | Santosh Pandey |  |  | " value lessthan 255 in TBTT Offset in TUs" There are a number of issues for this. The "in TUs" is awkward. All references to fields/subfields/elements/frames should be <initial caps proper name> <lower case name of type of structure>. | This specific occurance can be replaced by "value less than 255 TUs in the TBTT Offset field" I encourage the editor or designee to review the draft and ensure that all references to the name of a frame/field/subfield/element are followed by one of those terms. There are also a number of "Report"s floating around that are, I think, references either to an element, or a frame containing an eleemnt (e.g. 89.38 and 89.16 for examples of these two different uses). |  | TGai General |  | Discuss | Move to editorial - discussed with Lee - seems to apply for the entire draft |  |  |  | 2013-09-16 16:10 | TGai General
2012 | Adrian Stephens | 198 | 1 |  | 39 | 52 | G | Y | 39.52 | 52 |  |  |  | Santosh Pandey |  |  | " is 4 bits in length and contains". Figures are normative, so is this text. It is bad to repeat the same normative specification in two places, because Le Chatallier's theory of natural cussedness indicates that eventually they will say different things. | Review the descriptions of all fields and remove any redundant definitions of field size. |  | TGai General |  | Discuss | TBD |  |  |  | 2013-09-16 15:41 | TGai General
2465 | GEORGE CHERIAN | 198 | 1 |  | 40 | 8 | T | N | 40.08 | 8 |  |  |  | Santosh Pandey |  |  | OUI response criteria has no place in a non vendor specific element | Remove referenceces to OUI (pp 40-42, several lines) |  | TGai General |  | Discuss | move to person looking into comments related to FILS Request Parameters |  |  |  | 2013-09-16 15:41 | TGai General
2895 | Lin Cai | 198 | 1 | 8.4.2.176 | 39 |  | T | Y | 39 |  | 8.4.2.176 |  |  | Santosh Pandey |  |  | If the value is 7', what is the value referring to? Is it the value of TBTT Information Field Type? However, 'TBTT information field type' subfield has only two bits, and cannot be 7. | Please clarify. |  | TGai General |  | Revised | See CID 2663 |  |  |  | 2013-09-16 15:42 | TGai General
3369 | Yongho Seok | 198 | 1 | 8.4.2.176 | 39 | 58 | T | Y | 39.58 | 58 | 8.4.2.176 |  |  | Santosh Pandey |  |  | "If the TBTT Information Field Type is 1 then the BSSID subfield is not included in the TBTT Information field. If the value is 7, then the BSSID" The sentence is not clear. Change the sentenc as the following: "If the TBTT Information Field Type is 0, the value of the TBTT Information Length subfield is set to 1. If the TBTT Information Field Type is 1, the value of the TBTT Information Length subfield is set to 7." | As per comment |  | TGai General |  | Revised | See CID 2663 |  |  |  | 2013-09-16 15:41 | TGai General
3348 | Wookbong Lee | 198 | 1 | 8.4.2.176 | 40 | 21 | T | Y | 40.21 | 21 | 8.4.2.176 |  |  | Santosh Pandey |  |  | FILS Discovery frame does not have a timestamp and BI field. How does a STA calculate the immediately prior TBTT of the AP that transmits this element? | Remove the Reduced Neighbor Report element from the FILS Discovery frame or include the Timestamp and BI to the FILS Discovery frame. |  | TGai General |  | Discuss | TBD |  |  |  | 2013-09-16 15:41 | TGai General
3347 | Wookbong Lee | 198 | 1 | 8.4.2.176 | 39 | 58 | T | Y | 39.58 | 58 | 8.4.2.176 | 2707 |  | Santosh Pandey |  |  | "If the TBTT Information Field Type is 1 then the BSSID subfield is not included in the TBTT Information field. If the value is 7, then the BSSID" The sentence is not clear. Change the sentenc as the following: "If the TBTT Information Field Type is 0, the value of the TBTT Information Length subfield is set to 1. If the TBTT Information Field Type is 1, the value of the TBTT Information Length subfield is set to 7." | As per comment |  | TGai General |  | Revised | See CID 2663 |  |  |  | 2013-09-16 15:28 | TGai General
3291 | Stephen Mccann | 198 | 1 | 8.4.2.176 | 38 | 54 | T | Y | 38.54 | 54 | 8.4.2.176 |  |  | Santosh Pandey |  |  | This is a huge frame to be transmitted in the beacon !! What is the maximum size of this element? It breaks the whole GAS/ANQP model, which was designed to provide information to the STA prior to association, so that beacon bloat could be avoided. Please use the ANQP-element Neighbor Report element instead. | Use the ANQP-element neighbor report instead. Alternative create an ANQP-element reduced neighbor report. |  | TGai General |  | Discuss | TBD |  |  |  | 2013-09-16 15:42 | TGai General
3284 | Stephen Mccann | 198 | 1 | 8.3.3.2 | 26 | 9 | T | Y | 26.09 | 9 | 8.3.3.2 |  |  | Santosh Pandey |  |  | When dot11FILSActivated is true, there appear to be quite a few new elements available to the beacon. What is the maximum size increase if all these elements are present? | Add some text stating how large the beacon would be increased by, when all these optional elements are added. |  | TGai General | Discovery | Discuss | TBD |  |  |  | 2013-09-17 03:25 | TGai General
3180 | Robert Stacey | 198 | 1 | 8.4.2.176 | 39 | 45 | T | Y | 39.45 | 45 | 8.4.2.176 |  |  | Santosh Pandey |  |  | Surely the AP should only recommend that a STA try a different channel if the AP can be sure the STA will find an AP in the same management domain and able to make use of the suggested AP. What if both APs make the recommendation not to associate? How is this feature related to BSS Load and do we really need two ways of doing the same thing? I don't believe this feature (recommending that a STA not associate with the beaconing AP) has any value. The STA will make its decision based on BSS Load and likelyhood of association success (security credentials, network features, etc.). An AP suggestion not to associate adds no value. | Remove the TBTT Information Field Type field. |  | TGai General |  | Discuss | discuss with others - seems reasonable |  |  |  | 2013-09-16 15:41 | TGai General
3179 | Robert Stacey | 198 | 1 |  | 89 | 44 | T | Y | 89.44 | 44 |  |  |  | Santosh Pandey |  |  | "If the AP considers its operating channel too congested to accommodate STAs" -- What does this mean? Presumably the congestion is a result of STAs operating on that channel. | Clarify. Perhaps "to accommodate additional STAs". |  | TGai General |  | Accepted |  |  |  |  | 2013-09-16 16:10 | TGai General
3043 | Mitsuru Iwaoka | 198 | 1 | 8.4.2.176 | 39 | 57 | T | N | 39.57 | 57 | 8.4.2.176 |  |  | Santosh Pandey |  |  | A TBTT Information Length subfield can have value of 1 or 7. Assigning 1 octet to the TBTT Information subfield is wasting. | Apply following changes. 1) Change the length of the TBTT Information subfield to 1 bit (Figure 8-401cr and 8th paragraph). 2) Change the length of a TBTT information Header subfield (Figure 8-401cr) to 1 octet. 3) Change the length of the TBTT Information field in Figure 8-401cq from 'variable' to '1 or 7'. |  | TGai General |  | Discuss | TBD This is kept because as the standards would develop, this will be an extendable field -- discuss |  |  |  | 2013-09-16 15:41 | TGai General
2707 | Jeongki Kim | 198 | 1 | 8.4.2.176 | 39 | 58 | T | Y | 39.58 | 58 | 8.4.2.176 |  |  | Santosh Pandey |  |  | "If the TBTT Information Field Type is 1 then the BSSID subfield is not included in the TBTT Information field. If the value is 7, then the BSSID" The sentence is not clear. Change the sentenc as the following: "If the TBTT Information Field Type is 0, the value of the TBTT Information Length subfield is set to 1. If the TBTT Information Field Type is 1, the value of the TBTT Information Length subfield is set to 7." | As per comment |  | TGai General |  | Revised | See CID 2663 |  |  |  | 2013-09-16 15:41 | TGai General
2932 | MARC EMMELMANN | 198 | 1 | 8.4.2.176 | 39 | 45 | T | Y | 39.45 | 45 | 8.4.2.176 |  |  | Santosh Pandey |  |  | The value of the TBTT Information Field Type does not indicate the presence of the Neibhbor AP Information (which is always there if the bit exists) but how to interpret it. | Change the 2nd and 3rd sentence of the paragraph as follows: Value 0 indicates the Neighbor AP Information as informative and to be used to help the STA in AP discovery. Value 1 indicates the Neighbor AP Information to be considered as a recommendation to the STA to switch to another channel, another band ........ |  | TGai General |  | Discuss | TBD |  |  |  | 2013-09-16 15:41 | TGai General
2708 | Jing-Rong Hsieh | 198 | 1 | 8.4.2.176 | 39 | 49 | E | N | 39.49 | 49 | 8.4.2.176 |  |  | Santosh Pandey |  |  | Should be Neighbor "AP" Information field and there is one redundant period in the end of the sentence. | As per comment |  | TGai General |  | Accepted | Move to editorial? - seems to be okay |  |  |  | 2013-09-16 15:41 | TGai General
2890 | Lin Cai | 198 | 1 | 8.3.3.2 | 26 |  | E | Y | 26 |  | 8.3.3.2 |  |  | Santosh Pandey |  |  | Delete '(see 8.4.2.175 (ANQP Configuration Sequence Number element))' for format consistency. | Delete '(see 8.4.2.175 (ANQP Configuration Sequence Number element))' for format consistency. |  | TGai General |  | Accepted | Move to editorial? - seems to be okay |  |  |  | 2013-09-16 15:36 | TGai General
2883 | Lin Cai | 198 | 1 | 10.44.3 | 89 |  | T | Y | 89 |  | 10.44.3 |  |  | Santosh Pandey |  |  | Should a STA always select an AP that its neighbor AP information fields do not have a TBTT information field type with a value of 1? Why a STA 'shall' consider the first neighbor AP information field for redirection purpose when multiple Neighbor AP information fields have a TBTT information field type value of 1? | Please specify that a STA shall select a neighbor AP with its corresponding TBTT information field type of 0. If all Neighbor AP Information fields have a TBTT information field type of 1, the STA may consider the information in the first neighbor AP Information field for re-direction purposes. Please change 'shall' to 'may' in the second case. |  | TGai General |  | Discuss | TBD |  |  |  | 2013-09-16 16:10 | TGai General
2882 | Lin Cai | 198 | 1 | 10.44.3 | 89 | 54 | T | Y | 89.54 | 54 | 10.44.3 |  |  | Santosh Pandey |  |  | Who decides the value of the 'TMBB Information Field Type' subfield in the neighbor AP information field, the transmitting AP or the neighbor AP itself? If neighbor AP, how the transmitting AP get the information? More detail description should be provided. | Please provide detail descriptions to clarify it. |  | TGai General |  | Discuss | TBD |  |  |  | 2013-09-16 16:10 | TGai General
2862 | Lei Wang | 198 | 1 | 10.44.3 | 89 | 54 | T | Y | 89.54 | 54 | 10.44.3 |  |  | Santosh Pandey |  |  | don't see any reasons why a STA can switch to a band/channel without knowing the BSSID, for the redirection purpose in the Reduced Neighbor Report. If the BSSID is unknown, then a STA can use the given class/channel info to identify the channel and use the next TBTT info to know the good time for channel switching. | Change the sentence in line 54 page 89 to the following: If the STA detects that the TBTT Information Field Type is 1 and BSSID field is not included in the TBTT Information, the STA may switch to the channel as specified by the received Operating Class field and Channel Number field. |  | TGai General |  | Discuss | TBD |  |  |  | 2013-09-16 16:10 | TGai General
2861 | Lei Wang | 198 | 1 | 10.44.3 | 89 | 49 | T | Y | 89.49 | 49 | 10.44.3 |  |  | Santosh Pandey |  |  | The "shall" in line 49 page 89 is inappropriate, as it defeats the purpose of having multiple neighbor AP info in the Reduced Neighbor report, if only the first one shall be considered, for the redirection purpose. In addition, how a STA use the info provided in the Redueced Neighbor report has no impact on IoT (Interoperability) | in line 49 page 89, change "shall" to "should". |  | TGai General |  | Discuss | TBD |  |  |  | 2013-09-16 16:10 | TGai General
2859 | Lei Wang | 198 | 1 | 10.44.3 | 89 | 38 | T | Y | 89.38 | 38 | 10.44.3 |  |  | Santosh Pandey |  |  | The sentence in line 38 page 89 is technically incorrect, as the Reduced Neighbor Report element does not contain any subelement, based its format defintion in Section 8.4.2.176. | Delete the sentence in line 38 page 89, i.e., delete the following sentence: A STA receiving a Reduced Neighbor Report element with an unknown subelement identifier shall ignore the unknown subelement and continue to process the remaining subelements. |  | TGai General |  | Accepted |  |  |  |  | 2013-09-16 16:10 | TGai General
2858 | Lei Wang | 198 | 1 | 10.44.3 | 89 | 30 | T | Y | 89.3 | 30 | 10.44.3 |  |  | Santosh Pandey |  |  | The sentence in line 30 page 89 is incomplete, as it only covers one aspects of multiple neighbors in a reduced neighbor report, i.e., on the same class / channel; while another aspect is missing, i.e., multiple class/channel can be included too. | Change the sentence in line 30 page 89 to the following: A Reduced Neighbor Report element may contain neighbor AP information for mulitple channels, each specified by operation class and channel number, and each with one or multiple neighbor AP. |  | TGai General |  | Revised | TBD - agree but need to capitalize field names etc |  |  |  | 2013-09-16 16:10 | TGai General
2819 | Lei Wang | 198 | 1 | 8.4.2.176 | 39 | 58 | T | Y | 39.58 | 58 | 8.4.2.176 |  |  | Santosh Pandey |  |  | Multiple questions about the sentence in line 58 page 39: 1. why cannot the BSSID be provided for the case that TBTT Information Field Type is 1? 2. if only have values 1 or 7, then why do we need to use 8 bits to represent the length? | Make the following changes: 1. change the paragraph in line 58 page 39 to the following: The TBTT Information Length subfield is 4 bits in length and contains the length in octets of each TBTT Information field included in the Neighbor AP Information field. It can be set to value 1 or 7, and other values are reserved. 2. in line 32 page 39, in Figure 8-401cr--TBTT Information Header subfield, change the size the box of TBTT Information Length to 4 bits; and add another box and mark it as Reserved with size 4 bits. |  | TGai General |  | Discuss | TBD - mostly accepted and revised - consider legacy Tgaf |  |  |  | 2013-09-16 15:41 | TGai General
3370 | Yongho Seok | 198 | 1 | 8.4.2.176 | 40 | 21 | T | Y | 40.21 | 21 | 8.4.2.176 |  |  | Santosh Pandey |  |  | FILS Discovery frame does not have a timestamp and BI field. How does a STA calculate the immediately prior TBTT of the AP that transmits this element? | Remove the Reduced Neighbor Report element from the FILS Discovery frame or include the Timestamp and BI to the FILS Discovery frame. |  | TGai General |  | Discuss | TBD |  |  |  | 2013-09-16 15:41 | TGai General
3042 | Mitsuru Iwaoka | 198 | 1 | 8.4.2.176 | 39 | 58 | E | Y | 39.58 | 58 | 8.4.2.176 |  |  | Santosh Pandey |  |  | In the 2nd sentence of the 8th paragraph of 8.4.2.176, 'TBTT Information Field Type' may be wrong. The 'TBTT Information Length subfield' shall be used. | In the 2nd sentence of the 8th paragraph of 8.4.2.176, replace 'TBTT Information Field Type' by 'TBTT Information Length subfield'. |  | TGai General |  | Revised | See CID 2663 |  |  |  | 2013-09-16 15:41 | TGai General