## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-14/0148
Venue Date: | January 2014
First Author: | Sun Bo, ZTE
Subject: | LB200 November 2013 PHY motion1
Full Date: | 2014-01-21
Author(s): | Sun Bo
ZTE Corporation
Address
Phone:
Fax:
| email: | sun.bo1@zte.com.cn
Abstract:
This document contains comment resolutions for PHY comments of TGah D01.0 LB200.
TGah Jan 2014 F2F meeting

## Jan 2014 PHY motion 1
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1571 | Bo Sun | 200 | 1 | 24.3.18.5.2 | 341 | 50 | T | Y | 341.5 | 50 | 24.3.18.5.2 |  | A | Eugene Baik |  |  | what is the conditions for CCA BUSY on the Primary 1 MHz? | Clarify the primitive used for 1MHz channel conditions | ACCEPTED (PHY: 2014-01-22 04:22:37Z) Please see the rewrite of Section 24.3.18.5.4 for the conditions in which Primary 1MHz channel is busy (i.e. PHY-CCA.indication(BUSY, {primary1}) in 11-14/0109r2 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1766 | Eugene Baik | 200 | 1 | 24.3.8.3.3 | 308 | 20 | T | N | 308.2 | 20 | 24.3.8.3.3 |  | A | Eugene Baik |  |  | Equation 24-38 for LTF1 is incorrect. The P-matrix factor [A^{k}_{LTF}]_{m,n} should be [A^{k}_{LTF}]_{m,1} as all symbols for LTF1 receive same mapping (n=1, first column) | In equation 24-38, change [A^{k}_{LTF}]_{m,n} to [A^{k}_{LTF}]_{m,1} | ACCEPTED (PHY: 2014-01-22 00:24:17Z) See reproduced text in 11-14/0108r2 for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1765 | Eugene Baik | 200 | 1 | 24.3.8.3.3 | 308 | 13 | T | N | 308.13 | 13 | 24.3.8.3.3 |  | A | Eugene Baik |  |  | Equation 24-37 for LTF1 is incorrect. The P-matrix factor [A^{k}_{LTF}]_{m,n} should be [A^{k}_{LTF}]_{m,1} as all symbols for LTF1 receive same mapping (n=1, first column) | In equation 24-37, change [A^{k}_{LTF}]_{m,n} to [A^{k}_{LTF}]_{m,1} | ACCEPTED (PHY: 2014-01-22 00:23:53Z) See reproduced text in 11-14/0108r2 for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1762 | Edward Reuss | 200 | 1 | 24.3.8.2.2.1.3 | 300 | 58 | E | N | 300.58 | 58 | 24.3.8.2.2.1.3 |  | A | Eugene Baik |  |  | Figure 24-34 indicates that the constellation for SIG-A-1 can be either +1j or something less than -1j. I assume that this is a diagram error. Also, are they "SIG-A-1" and "SIG-A-2", or should they be labeled "SIG-A1" and SIG-A2"? | Fix Figure 24-34. | ACCEPTED (PHY: 2014-01-22 00:22:18Z) See reproduced text in 11-14/0108r2 for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1761 | Edward Reuss | 200 | 1 | 24.3.8.2.1.4 | 291 | 20 | E | N | 291.2 | 20 | 24.3.8.2.1.4 |  | A | Eugene Baik |  |  | Figure 24-28 indicates that the QBPSK constellation is either +1j or something less than -1j. Shouldn't this be +1j and -1j? | Modify Figure 24-28 to indicate the constellation contains +1j and -1j. | ACCEPTED (PHY: 2014-01-22 00:18:05Z) See reproduced text in 11-14/0108r2 for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1623 | Brian Hart | 200 | 1 | 24.3.18.5 | 339 | 54 | T | Y | 339.54 | 54 | 24.3.18.5 |  | A | Eugene Baik |  |  | I don't see a mandatory energy detection CCA for the primary channels. I only see a mandatory energy detection CCA for the secondary channels. (24.3.18.5.3 is for specific (theoretical) bands only) | Add a mandatory energy detection CCA for the primary channels, as expected by the NOTE at P340L52. | ACCEPTED (PHY: 2014-01-22 04:18:48Z) Although Section 24.3.18.5.3 mentions ED requirements for Primary 1, Primary 2MHz channels, they are now explicitly stated again in 24.3.18.5.4 as described in 11-14/0109r2 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1614 | Brian Hart | 200 | 1 | 24.3.8.2.1.4 | 288 | 33 | T | Y | 288.33 | 33 | 24.3.8.2.1.4 |  | J | Eugene Baik |  |  | "B10-B15 are set to the value of the TXVECTOR parameter PARTIAL_AID" but the TXVECTOR table indicates PARTIAL_AID ranges from 0-511 | Need to define a restriction on PARTIAL_AID in the TXVECTOR table OR how to crop 9 bits down to 6 bits (or a ref) | REJECTED (PHY: 2014-01-22 00:16:09Z) The Partial AID field in TXVECTOR can either be 9-bits or 6 bits. The definitions are in Section 9.17b Group ID, partial AID, UPLINK, and Color in S1G PPDUs. When a >=2MHz PPDU is sent by an AP and is addressed to a STA associated with that AP, the formula is: (dec(AID[0:8])+ dec(BSSID[44:47] xor BSSID[40:43])×2^5 ) mod 2^6 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1613 | Brian Hart | 200 | 1 | 24.3.8.2.1.4 | 288 | 31 | T | Y | 288.31 | 31 | 24.3.8.2.1.4 |  | J | Eugene Baik |  |  | "If UPLINK is set to 0, B7-B9 are set to the value of the TXVECTOR parameter COLOR and B10-B15 are set to the value of the TXVECTOR parameter PARTIAL_AID." is SIG structure not reflected in the SIG diagram | Need to reflect this explosion in Fig 24-26/27 | REJECTED (PHY: 2014-01-22 00:15:45Z) The field ID is properly described in Table 24-11. Description clearly indicates how the bits of the “ID” field in the SIG should be populated. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1612 | Brian Hart | 200 | 1 | 24.3.8.2.1.4 | 288 | 26 | T | Y | 288.26 | 26 | 24.3.8.2.1.4 |  | V | Eugene Baik |  |  | UPLINK - is the is the TXVECTOR parameter or the SIG field? | Be specific. Better still, lowercase the field name | REVISED (PHY: 2014-01-22 00:14:55Z) Rename SIG field entry as Uplink Indication, which will have same value as UPLINK of TXVECTOR. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1611 | Brian Hart | 200 | 1 | 24.3.8.2.1.4 | 287 | 31 | E | Y | 287.31 | 31 | 24.3.8.2.1.4 |  | A | Eugene Baik |  |  | "reserved" is lowercase | Reserved | ACCEPTED (PHY: 2014-01-22 00:12:41Z) See reproduced text in 11-14/0108r2 for applied changes | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1610 | Brian Hart | 200 | 1 | 24.3.8.2.1.4 | 287 | 56 | T | Y | 287.56 | 56 | 24.3.8.2.1.4 |  | A | Eugene Baik |  |  | "The SIG field is composed of two OFDM symbols, SIG-1 and SIG-2, each containing 24 data bits, as shown in Table 24-11" | Due to BCC encoding the end data bits in SIG1 are spread into SIG2, so not correct to say "each containing 24 data bits" Instead talk about first part and second part containing 48 bits total ... (see 11ac for the template) | ACCEPTED (PHY: 2014-01-22 00:13:59Z) See reproduced text in 11-14/0108r2 for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1583 | Bo Sun | 200 | 1 | 24.3.18.5.5 | 343 | 7 | T | Y | 343.07 | 7 | 24.3.18.5.5 |  | A | Eugene Baik |  |  | Table 7-5 has defined primary, secondary, secondary1, secondary40/80. There's no definition for secondary2, secondary4 and secondary8. | Unify the terms to keep spec consistance. | ACCEPTED (PHY: 2014-01-22 04:26:35Z) Table 7-5 has been re-written (separate CID resolution document, 13/1522r0 by Yongho Seok) to use terminology consistent with 24.3.18.5 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1579 | Bo Sun | 200 | 1 | 7.3.5.11.2 | 28 | 10 | E | Y | 28.1 | 10 | 7.3.5.11.2 |  | V | Yongho |  |  | the reference is wrong in this table | Modify the reference to "24.3.18.5.5" to all added text. | REVISED (PHY: 2014-01-22 05:17:38Z) TGah editor to make changes shown in 11-13-1522r0 under the heading for CID 1033, 1412, 1577, 1578, 1579, 1773, 1787, 1788, 1789, 1790, 1791 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1578 | Bo Sun | 200 | 1 | 7.3.5.11.2 | 27 | 53 | E | Y | 27.53 | 53 | 7.3.5.11.2 |  | V | Yongho |  |  | the reference is wrong in this table | change "...according to the rules specified in 24.3.18.5.3 (CCA sensitivity for signals occupying the primary 2MHz channel)." to"according to the rules specified in 24.3.18.5.5 (CCA sensitivity for signals not occupying the primary 2MHz channel)." in row "secondary"; change" 24.3.18.5.4" to "24.3.18.5.5" in this table. | REVISED (PHY: 2014-01-22 05:16:30Z) TGah editor to make changes shown in 11-13-1522r0 under the heading for CID 1033, 1412, 1577, 1578, 1579, 1773, 1787, 1788, 1789, 1790, 1791 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1032 | Adrian Stephens | 200 | 1 | 7.3.5.11.2 | 27 | 19 | T | Y | 27.19 | 19 | 7.3.5.11.2 |  | A | Yongho |  |  | ", a TVHT STA" -- why is this insertion here? .11af has no business (i.e. it is outside the scope of the .11ah PAR) to modify the TVWS operation. | Remove cited text. | ACCEPTED (PHY: 2014-01-22 05:14:37Z) Agree with the comment. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1324 | Adrian Stephens | 200 | 1 | 24.3.8.3.3 | 309 | 1 | E | Y | 309.01 | 1 | 24.3.8.3.3 |  | A | Eugene Baik |  |  | Notes within a subclause are numbered consecutively. | Change previous note to "NOTE 1<em-dash>", and this one to "NOTE 2<em-dash>". Review all NOTEs in the draft and ensure any multiples within the same subclause are numbered. | ACCEPTED (PHY: 2014-01-22 00:24:42Z) See reproduced text in 11-14/0108r2 for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1033 | Adrian Stephens | 200 | 1 | 7.3.5.11.2 | 28 | 10 | T | Y | 28.1 | 10 | 7.3.5.11.2 |  | V | Yongho |  |  | I don't understand why secondary40 is at all relevant to a "secondary 4 MHz channel". | Give S1G its own secondary 4 and secondary 8 entries. | REVISED (PHY: 2014-01-22 05:17:20Z) TGah editor to make changes shown in 11-13-1522r0 under the heading for CID 1033, 1412, 1577, 1578, 1579, 1773, 1787, 1788, 1789, 1790, 1791 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1318 | Adrian Stephens | 200 | 1 | 24.3.8.2 | 283 | 28 | G | Y | 283.28 | 28 | 24.3.8.2 |  | A | Eugene Baik |  |  | "Greater than or equal to 2MHz PHY" I don't think Clause 24 defines multiple PHYs. It defines a single PHY with multiple formats. | Change title to relate to PPDU format. | ACCEPTED (PHY: 2014-01-22 00:05:18Z) See reproduced text in 11-14/0108r2 for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1319 | Adrian Stephens | 200 | 1 | 24.3.8.2.1.4 | 287 | 53 | G | Y | 287.53 | 53 | 24.3.8.2.1.4 |  | A | Eugene Baik |  |  | "NOTE--Integer fields are represented in unsigned binary format with the least significant bit in the lowest numbered bit position." This should not be a note, because this information is necessary for interoperability. | Promote to body text. | ACCEPTED (PHY: 2014-01-22 00:13:21Z) See reproduced text in 11-14/0108r2 for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1320 | Adrian Stephens | 200 | 1 | 24.3.8.2.1.4 | 289 | 5 | E | Y | 289.05 | 5 | 24.3.8.2.1.4 |  | A | Eugene Baik |  |  | "(AMPDU)" - terminology | Replace all "AMPDU" with "A-MPDU" | ACCEPTED (PHY: 2014-01-22 00:17:01Z) See reproduced text in 11-14/0108r2 for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1321 | Adrian Stephens | 200 | 1 | 24.3.8.2.1.4 | 291 | 19 | E | N | 291.19 | 19 | 24.3.8.2.1.4 |  | A | Eugene Baik |  |  | The "0" dots in figure 24-28 have drooped. | Raise them up. Ditto at 300.57 on the left. | ACCEPTED (PHY: 2014-01-22 00:17:35Z) See reproduced text in 11-14/0108r2 for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1577 | Bo Sun | 200 | 1 | 7.3.5.11.2 | 27 | 40 | E | Y | 27.4 | 40 | 7.3.5.11.2 |  | V | Yongho |  |  | the reference is wrong in this table | change the reference to "24.3.18.5.4 (CCA sensitivity for signals occupying the primary 2MHz channel and/or primary 1MHz channel" | REVISED (PHY: 2014-01-22 05:15:39Z) TGah editor to make changes shown in 11-13-1522r0 under the heading for CID 1033, 1412, 1577, 1578, 1579, 1773, 1787, 1788, 1789, 1790, 1791 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1323 | Adrian Stephens | 200 | 1 | 24.3.8.2.2.1.4 | 295 | 65 | E | N | 295.65 | 65 | 24.3.8.2.2.1.4 |  | A | Eugene Baik |  |  | More red text | make it black | ACCEPTED (PHY: 2014-01-22 00:20:41Z) See reproduced text below for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1572 | Bo Sun | 200 | 1 | 24.3.8.3.4 | 311 | 35 | T | Y | 311.35 | 35 | 24.3.8.3.4 |  | A | Eugene Baik |  |  | For 1MHz PPDU, the roatation of SIG field symbols makes no sense. For example, in 11ac, the rotation is used to distinguish VHT format from HT format. In S1G 2MHz PPDU, the rotation is used to distinguish short preamble from long preamble. | Delete the term "rotated" in this section | ACCEPTED (PHY: 2014-01-22 00:25:38Z) See reproduced text in 11-14/0108r2 for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1412 | amin jafarian | 200 | 1 | 7.3.5.11.2 | 28 | 30 | T | Y | 28.3 | 30 | 7.3.5.11.2 |  | V | Yongho |  |  | The relationship of the channel-list parameter elements to the 1MHz, 4MHz, ..." Shouldn't 2MHz be included as well? | As in comment. | REVISED (PHY: 2014-01-22 05:18:49Z) TGah editor to make changes shown in 11-13-1522r0 under the heading for CID 1033, 1412, 1577, 1578, 1579, 1773, 1787, 1788, 1789, 1790, 1791 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1567 | Bo Sun | 200 | 1 | 24.3.8.2.1.2 | 284 | 32 | E | Y | 284.32 | 32 | 24.3.8.2.1.2 |  | A | Eugene Baik |  |  | the expain of NSR is missing | chang to NSR is defined Table 24-4 (Timing-related constants) | ACCEPTED (PHY: 2014-01-22 00:09:36Z) See reproduced text in 11-14/0108r2 for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1568 | Bo Sun | 200 | 1 | 24.3.8.2.1.2 | 284 | 32 | T | Y | 284.32 | 32 | 24.3.8.2.1.2 |  | A | Eugene Baik |  |  | the parameter of Qk is not defined in equation (24-13), also missing in the time domain representation of other signal of preamble. | add the definition of Qk under formula that uses Qk throughout the spec | ACCEPTED (PHY: 2014-01-22 00:10:40Z) See reproduced text in 11-14/0108r2 for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1569 | Bo Sun | 200 | 1 | 24.3.18.5.2 | 340 | 22 | T | Y | 340.22 | 22 | 24.3.18.5.2 |  | A | Eugene Baik |  |  | Type 2 channel CCA levels (i.e. thresholds) are never set to be equal to Type 1channel CCA levels | remove "equal to or" | ACCEPTED (PHY: 2014-01-22 04:21:14Z) See reproduced text for changes in 11-14/0109r2. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1570 | Bo Sun | 200 | 1 | 24.3.18.5.2 | 342 | 20 | E | Y | 342.2 | 20 | 24.3.18.5.2 |  | A | Eugene Baik |  |  | there is no 9.19.2.8a | change 9.19.2.8a into 9.20.2.9 | ACCEPTED (PHY: 2014-01-22 04:23:18Z) See reproduced text for change in 11-14/0109r2. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1769 | Eugene Baik | 200 | 1 | 24.3.8.2.2.1.4 | 299 | 4 | T | N | 299.04 | 4 | 24.3.8.2.2.1.4 |  | J | Eugene Baik |  |  | Coding bits in Table 24-15 define how LDPC codeword lengths are calculated, and reference Section 22.3.10.5.4 of the 11ac spec and Section 20.3.11.6.5 of the 11n spec. These specs assume the Service field length is 16 bits when it is now 8 bits for 11ah. Need to define 11ah-specific LDPC length calculations for 11ah | Need to create new section in 11ah spec to specify LDPC length calculations. Coding bit definition should reference this section | REJECTED (PHY: 2014-01-22 00:22:02Z) Length, Number of symbol (N_sym), and available bits (N_pld) equations in Section 22.3.10.5.5 LDPC coding of 11ac spec are still applicable because number of service bits (N_service) are treated as variable. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1322 | Adrian Stephens | 200 | 1 | 24.3.8.2.2.1 | 292 | 38 | E | Y | 292.38 | 38 | 24.3.8.2.2.1 |  | A | Eugene Baik |  |  | " long preamble is always single user modulated" -- the 'reassurance' given by "always" is unnecessary. | " long preamble is single user modulated. | ACCEPTED (PHY: 2014-01-22 00:19:06Z) See reproduced text in 11-14/0108r2 for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
2460 | Mark RISON | 200 | 1 | 24.3.18.5.5 | 343 |  | T | Y | 343 |  | 24.3.18.5.5 |  | V | Eugene Baik |  |  | secondary2 only appears in this subclause (thrice) | Was plain secondary intended? | REVISED (PHY: 2014-01-22 04:24:31Z) Agree that there was inconsistency with Table 7-5 in Section 7.3.5.11. That text has been modified to make terminology consistent (see separate CID resolution doc 13/1522r0 by Yongho Seok) | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1767 | Eugene Baik | 200 | 1 | 24.3.8.2.1.4 | 288 | 40 | T | N | 288.4 | 40 | 24.3.8.2.1.4 |  | J | Eugene Baik |  |  | Coding bits in Table 24-11 defines how LDPC codeword lengths are calculated, and reference Section 22.3.10.5.4 of the 11ac spec and Section 20.3.11.6.5 of the 11n spec. These specs assume the Service field length is 16 bits when it is now 8 bits for 11ah. Need to define 11ah-specific LDPC length calculations for 11ah | Need to create new section in 11ah spec to specify LDPC length calculations. Coding bit definition should reference this section | REJECTED (PHY: 2014-01-22 00:16:37Z) Length, Number of symbol (N_sym), and available bits (N_pld) equations in Section 22.3.10.5.5 LDPC coding of 11ac spec are still applicable because number of service bits (N_service) are treated as variable. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
2073 | Jens Tingleff | 200 | 1 | 24.3.8.2.1.3 | 285 | 31 | T | Y | 285.31 | 31 | 24.3.8.2.1.3 |  | A | Eugene Baik |  |  | LTF fields in clause 22 are not defined in equations 22-32 and friends. (Those equations are still in the STF part of clause 22.) | Figure out correct reference | ACCEPTED (PHY: 2014-01-22 00:11:14Z) See reproduced text in 11-14/0108r2 for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
2074 | Jens Tingleff | 200 | 1 | 243.8.2.1.3 | 285 | 42 | E | N | 285.42 | 42 | 24.3.8.2.1.3 |  | A | Eugene Baik |  |  | (Equation 24-14) The dot before the second open square bracket looks like it should be an implied multiplication. Where the baseline (well, clause 22 and 23, specifically - although clause 23 has 'x' a few times) uses dot (not consistent, BTW), it is centered vertically. In clause 24 the dots that there are appear vertically aligned with the base. (also in 24-15, 24-16, 24-17 and others). Suggest you align with clause 22 and 23 (or eliminate explicit multiplication dots and xs). | Decide how to write mutiplication in equations | ACCEPTED (PHY: 2014-01-22 00:35:43Z) See reproduced text in 11-14/0108r2 for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
2092 | John Coffey | 200 | 1 | 24.3.8.2.1.5 | 291 | 28 | T | Y | 291.28 | 28 | 24.3.8.2.1.5 |  | J | Eugene Baik |  |  | It makes little sense to have a 4-bit CRC. The overall packet is already protected by a true CRC, so the S1G SIGA CRC amounts to a waste of 4 bits that could be put to some other purpose. If there's nothing useful at present, the bits should be reserved for future use. | Delete Subcluase 24.3.8.2.1.5 in its entirety, along with all references thereto. Make appropriate other changes,e.g., in Table 24-11 (P289 LL30-32), change the entry for B14-B17 to "Reserved / 4 / Set to 0" | REJECTED (PHY: 2014-01-22 00:18:26Z) SIG CRC essential for ensuring integrity of decoded SIG bits, and preventing false alarms and incorrect deferral behaviour for unintended recipients of any S1G PPDU. 4-bit CRC calculation has Hamming distance of 2, as described in document 11-12/1092r0. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
2171 | Kenichi Mori | 200 | 1 | 24.3.8.2.2.1.3 | 297 | 24 | T | N | 297.24 | 24 | 24.3.8.2.2.1.3 |  | J | Eugene Baik |  |  | Bit location of "Doppler" and "Reserved" should be swapped to align with 2MHz and above short preamble format. By doing this, it should be easier to implement because decoded data can be stored without considering short and long format. | Bit location of "Doppler" and "Reserved" should be swapped to align with 2MHz and above short preamble format. | REJECTED (PHY: 2014-01-22 00:21:37Z) Separate Bitmaps for SIG fields have to be used anyways. Not useful to optimize individual bit locations, since Rx will know SIG type by this point and parse each time separately. No hardware shared during parsing, most likely. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1794 | G Rajendra Kumar | 200 | 1 | 24.3.18.5.5 | 343 |  | T | N | 343 |  | 24.3.18.5.5 |  | V | Eugene Baik |  |  | "secondary8" is used instead of "secondary80" as per Table 7-5 | Change "secondary8" to "secondary80" in subclause 24.3.18.5.5 to maintain consistency | REVISED (PHY: 2014-01-22 04:24:59Z) Agree in principle. Instead, Table 7-5 in Section 7.3.5.11 has been re-written (separate CID resolution document 13/1522r0 by Yongho Seok) to use terminology consistent with 24.3.18.5 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
2281 | Li Chia Choo | 200 | 1 | 24.3.8.2.2.2.4 | 302 |  | E | Y | 302 |  | 24.3.8.2.2.2.4 |  | V | Eugene Baik |  |  | It is not clear how the SIG-B bits are repeated as a function of CH_BANDWIDTH as defined in 24.3.8.2.2.2.4 (SIG-B definition). | Please clarify how SIG-B bits are repeated as a function of CH_BANDWIDTH. | REVISED (PHY: 2014-01-22 00:23:09Z) The SIG-B bits are repeated for 4, 8, and 16MHz in a way similar to 40, 80, and 160MHz for VHT SIG-B. See reproduced text below for applied changes. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1793 | G Rajendra Kumar | 200 | 1 | 24.3.18.5.5 | 343 |  | T | N | 343 |  | 24.3.18.5.5 |  | V | Eugene Baik |  |  | "secondary4" is used instead of "secondary40" as per Table 7-5 | Change "secondary4" to "secondary40" in subclause 24.3.18.5.5 to maintain consistency | REVISED (PHY: 2014-01-22 04:25:27Z) Agree in principle. Instead, Table 7-5 in Section 7.3.5.11 has been re-written (separate CID resolution document 13/1522r0 by Yongho Seok) to use terminology consistent with 24.3.18.5 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
2461 | Mark RISON | 200 | 1 | 24.3.18.5 |  |  | T | Y | 340 | 32 | 24.3.18.5 |  | V | Eugene Baik |  |  | What is primary2 (7 times)? | Was plain primary intended? | REVISED (PHY: 2014-01-22 04:20:36Z) Agree that there was inconsistency with Table 7-5 in Section 7.3.5.11. That text has been modified to make terminology consistent (see separate CID resolution doc 13/1522r0 by Yongho Seok) | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
2692 | ron porat | 200 | 1 | 24.3.18.5.4.1 | 342 | 54 | T | Y | 342.54 | 54 | 24.3.18.5.4.1 |  | J | Eugene Baik |  |  | there are many CCA levels (three), complicating implementation. Propose to harmonize some of the levels | propose to change the levels of 8/16MHz in this section to the same levels as for type 2 because this section should not allow even higher levels for 8/16MHz but rather only to the lower BW | REJECTED (PHY: 2014-01-22 04:24:07Z) Different sets of CCA levels do not necessarily complicate implementation, since PHY can load in different sets of CCA levels depending on scenario. Separate set of CCA levels for 8/16MHz BW are strictly optional for devices that choose to implement that special EDCA procedure. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
2693 | ron porat | 200 | 1 | 24.3.18.5.5 | 343 | 41 | T | Y | 343.41 | 41 | 24.3.18.5.5 |  | J | Eugene Baik |  |  | not clear why secondary levels do not scale with BW |  | REJECTED (PHY: 2014-01-22 04:27:21Z) Spacing between bandwidths (for either Type 1 or Type 2) are the same as spacing in 11ac. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
2694 | Ronald Murias | 200 | 1 | 24.3.8.2.2.1.4 | 295 | 1 | T | Y | 295.01 | 1 | 24.3.8.2.2.1.4 |  | J | Eugene Baik |  |  | Because the SGI is signalled in the SIG-A field, the short GI may not be applied until the data field. If the channel supports a short GI, it is more efficient to apply to all symbols. Known methods exist to signal this bit before the SIG field. | Indicate short GI before the SIG field. | REJECTED (PHY: 2014-01-22 00:20:12Z) Overhead savings from Short GI shows up for longer Data packets. Delta from rate benefit of SGI on SIG would be minimal with high overhead. Would not want to use SGI on SIG, since all devices in network would then need to support SGI to decode SIG (for deferral purposes, e.g.). Additionally not all devices in BSS or network may see the same short-delay spread channel. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
2695 | Ronald Murias | 200 | 1 | 24.3.8.3.2 | 307 | 17 | T | Y | 307.17 | 17 | 24.3.8.3.2 |  | J | Eugene Baik |  |  | The new STF sequence for 1 MHz is sub-optimal, resulting in poor (by comparison to the 2+MHz) autocorrelation for timing sync. | Generate a 1 MHz STF with autocorrelation performance that rivals the 2 MHz mode. | REJECTED (PHY: 2014-01-22 00:23:27Z) See contribution 11-12/0115r0 for selection criteria and process for 1MHz STF and LTF sequences. Autocorrelation drop between 1MHz STF and LTF sequence shown in Slide 12. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
2817 | Vinko Erceg | 200 | 1 | 24.3.18.5 | 339 |  | T | Y | 339 |  | 24.3.18.5 |  | J | Eugene Baik |  |  | There are too many CCA levels including different types of channelization for the CCA levels. | Deterrnine only 1 CCA level without different channelization types. No simulations were presented that show benefits of the current CCA spec. | REJECTED (PHY: 2014-01-22 04:07:23Z) Need for Type 1 and Type 2 levels in US/China agreed upon within TGah, based on the different needs of expected sensor and extended range WiFi use cases. Tradeoff of Tx Protection/Range for sensor devices vs. Ease of Medium acces for wider BW devices | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
2172 | Kenichi Mori | 200 | 1 | 24.3.18.5.3 | 340 | 56 | E | N | 340.56 | 56 | 24.3.18.5.3 |  | V | Eugene Baik |  |  | The line 56 says details of CCA-ED threshold is explained in D.2.5 but there is no section such that. Add D.2.5 in Annex D. | Add D.2.5 that explains CCA-ED threshold in detail in Annex D based on the discussion result on CCA-ED. | REVISED (PHY: 2014-01-22 04:22:03Z) Reference to Annex D2.5 not needed, as current Section 24.3.18.5.3 contains all thresholds relevant for Energy Detection. Removed referencing text. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1783 | Eugene Baik | 200 | 1 | 24.3.8.2.2.1.4 | 295 | 1 | T | N | 295.01 | 1 | 24.3.8.2.2.1.4 |  | V | Eugene Baik |  |  | The 2MHz long frame SU SIG definition needs an Uplink indication bit | Add a field in the SU SIG bit map and definitions table for Uplink indication | REVISED (PHY: 2014-01-22 00:19:48Z) Previous CID resolution 12/1207r1 addresses this, the Uplink indication definition has been added. For editor: no change necessary to current Draft 1.0. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
2849 | Yongho Seok | 200 | 1 | 7.3.4.4 | 27 | 6 | T | N | 27.06 | 6 | 7.3.4.4 |  | V | Yongho |  |  | In 24.3.18.5.4.1, "For devices operating in Type 2 channels, if the device intends to transmit an 8 or 16 MHz channel width PPDU and the device implements the procedure and rules for high intended BW transmission channel access, the PHY shall issue a PHY-CCA.indication(BUSY, {primary2}) if one of the conditions listed in Table 24-35 is met in an otherwise idle 1 MHz, 2 MHz, 4 MHz, 8 MHz, 16 MHz operating channel width." After receiving a PHY-CCA.indication primitives, how can a local MAC entity know the type of CCA between Table 24-35 and Table 24-34? The local MAC entity shall support a primitive to change the CCA Type between Table 24-35 and Table 24-34 through PHYCONFIG_VECTOR. Otherwise, the PHY-CCA.indication primitives shall has an additional field for indicating which CCA Type is met. | The local MAC entity shall support a primitive to change the CCA Type between Table 24-35 and Table 24-34 through PHYCONFIG_VECTOR. Otherwise, the PHY-CCA.indication primitives shall has an additional field for indicating which CCA Type is met. Commenter will submit a resolution. | REVISED (PHY: 2014-01-22 03:58:26Z) TGah editor to make changes shown in 11-13-1521r1 under the heading for CID 2849. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1770 | Eugene Baik | 200 | 1 | 24.3.8.3.4 | 310 | 18 | T | N | 310.18 | 18 | 24.3.8.3.4 |  | J | Eugene Baik |  |  | Coding bits in Table 24-18 define how LDPC codeword lengths are calculated, and reference Section 22.3.10.5.4 of the 11ac spec and Section 20.3.11.6.5 of the 11n spec. These specs assume the Service field length is 16 bits when it is now 8 bits for 11ah. Need to define 11ah-specific LDPC length calculations for 11ah | Need to create new section in 11ah spec to specify LDPC length calculations. Coding bit definition should reference this section | REJECTED (PHY: 2014-01-22 00:25:19Z) Length, Number of symbol (N_sym), and available bits (N_pld) equations in Section 22.3.10.5.5 LDPC coding of 11ac spec are still applicable because number of service bits (N_service) are treated as variable | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1773 | Eugene Baik | 200 | 1 | 7.3.5.11.2 | 27 | 24 | T | N | 27.24 | 24 | 7.3.5.11.2 |  | V | Yongho |  |  | No technical reason why names of channel list elements must be shared with those of 11n/11ac. For example, it makes it more confusing when secondary20 actually corresponds to secondary 2MHz channel. Additionally, "primary" element needs to be split to distinguish Primary 1MHz and Primary 2MHz. Current naming and definitions of channel list parameters don't match those defined in CCA section, 24.3.18.5 | Create separate table to define elements specific for 11ah, rather than share terminology with 11n/11ac. Separate definitions for Primary2 and Primary1, since EDCA for 1 and >=2MHz transmissions are separate procedures. | REVISED (PHY: 2014-01-22 05:15:08Z) TGah editor to make changes shown in 11-13-1522r0 under the heading for CID 1033, 1412, 1577, 1578, 1579, 1773, 1787, 1788, 1789, 1790, 1791 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1775 | Eugene Baik | 200 | 1 | 24.3.18.5 | 339 | 54 | T | N | 339.54 | 54 | 24.3.18.5 |  | A | Eugene Baik |  |  | Primary channel CCA in 11ah should include a Midpacket detection requirement (within PIFS duration) to protect against collisions in cases where the preamble is missed or not detected. This includes cases where devices are waking up out of sleep mode, and cases where transmission failure and retry lead to the preamble detection not triggering the CCA indication. Additionally, transmissions in secondary 1MHz are given implicit protection from a 2MHz Midpacket detection requirement | Add Midpacket detection criteria to Primary channel CCA. Add Midpacket detection levels for Type 1, Type 2 channels. | ACCEPTED (PHY: 2014-01-22 04:09:10Z) Please see the rewrite of Section 24.3.18.5.4 for the conditions in which Primary 1MHz channel is busy (i.e. PHY-CCA.indication(BUSY, {primary1}) and PHY-CCA.indication(BUSY, {primary2})) in 11-14/0109r2 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1776 | Eugene Baik | 200 | 1 | 24.3.18.5 | 339 | 54 | T | N | 339.54 | 54 | 24.3.18.5 |  | V | Eugene Baik |  |  | Terminology for "primary2, secondary2, secondary4, secondary8, etc" do not match up with the current channel-list parameter definitions in 7.3.5.11 | Fix definitions in section 7.3.5.11 and coordinate CCA section text to align and be consistent | REVISED (PHY: 2014-01-22 04:08:34Z) Table 7-5 in Section 7.3.5.11 has been re-written (separate CID resolution document 13/1522r0 by Yongho Seok) to use terminology consistent with 24.3.18.5 in 11-14/0109r2 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1824 | Graham Smith | 200 | 1 | 7.3.5.11.2 | 50 | 31 | T | Y | 50.31 | 31 | 7.3.5.11.2 |  | J | Yongho |  |  | Not sure why "by example" is included here. Suggest delete | Delete "by example" | REJECTED (PHY: 2014-01-22 05:19:21Z) Figure 7-1a just shows one example of channel-list parameter element. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1782 | Eugene Baik | 200 | 1 | 24.3.8.2.1.4 | 287 | 17 | T | N | 287.17 | 17 | 24.3.8.2.1.4 |  | V | Eugene Baik |  |  | The 2MHz short frame SIG definition needs an Uplink indication bit | Add a field in the SIG bit map and definitions table for Uplink indication | REVISED (PHY: 2014-01-22 00:11:34Z) Previous CID resolution 12/1207r1 addresses this, the Uplink indication definition has been added. For editor: no change necessary to current Draft 1.1. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1768 | Eugene Baik | 200 | 1 | 24.3.8.2.2.1.4 | 296 | 37 | T | N | 296.37 | 37 | 24.3.8.2.2.1.4 |  | J | Eugene Baik |  |  | Coding bits in Table 24-14 define how LDPC codeword lengths are calculated, and reference Section 22.3.10.5.4 of the 11ac spec and Section 20.3.11.6.5 of the 11n spec. These specs assume the Service field length is 16 bits when it is now 8 bits for 11ah. Need to define 11ah-specific LDPC length calculations for 11ah | Need to create new section in 11ah spec to specify LDPC length calculations. Coding bit definition should reference this section | REJECTED (PHY: 2014-01-22 00:21:11Z) Length, Number of symbol (N_sym), and available bits (N_pld) equations in Section 22.3.10.5.5 LDPC coding of 11ac spec are still applicable because number of service bits (N_service) are treated as variable. | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1787 | G Rajendra Kumar | 200 | 1 | 7.3.5.11.2 | 27 | 54 | T | N | 27.54 | 54 | 7.3.5.11.2 |  | V | Yongho |  |  | The meaning for the "secondary" channel list element in Table 7-5 is wrong. "For an S1G STA, indicates that the secondary 2MHz channel is busy according to the rules specified in 24.3.18.5.3 (CCA sensitivity for signals occupying the primary 2MHz channel)." | The statement should instead read as "For an S1G STA, indicates that the secondary 2MHz channel is busy according to the rules specified in 24.3.18.5.3 5 (CCA sensitivity for signals not occupying the primary 2MHz channel). | REVISED (PHY: 2014-01-22 05:16:59Z) TGah editor to make changes shown in 11-13-1522r0 under the heading for CID 1033, 1412, 1577, 1578, 1579, 1773, 1787, 1788, 1789, 1790, 1791 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1788 | G Rajendra Kumar | 200 | 1 | 7.3.5.11.2 | 28 | 23 | T | N | 28.23 | 23 | 7.3.5.11.2 |  | V | Yongho |  |  | The meaning for the "secondary1" channel list element in Table 7-5 is wrong. It should have a separate rule for CCA sensitivity for signals not occuping the primary 1 MHz signal, | The meaning should instead read as "For an S1G STA, indicates that the secondary 1MHz channel is busy according to the rules specified in 24.3.18.5.4x (CCA sensitivity for signals not occupying the primary 21MHz channel)." Also an appropriate clause for this needs to be added in 24.3.18.5.x. | REVISED (PHY: 2014-01-22 05:18:31Z) TGah editor to make changes shown in 11-13-1522r0 under the heading for CID 1033, 1412, 1577, 1578, 1579, 1773, 1787, 1788, 1789, 1790, 1791 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1789 | G Rajendra Kumar | 200 | 1 | 7.3.5.11.2 | 27 | 41 | T | N | 27.41 | 41 | 7.3.5.11.2 |  | V | Yongho |  |  | Incorrect mention of clause number in meaning of primary CCA in Table 7-5 | Clause number should be 24.3.18.5.4 instead of 24.3.18.5.3 | REVISED (PHY: 2014-01-22 05:16:13Z) TGah editor to make changes shown in 11-13-1522r0 under the heading for CID 1033, 1412, 1577, 1578, 1579, 1773, 1787, 1788, 1789, 1790, 1791 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1790 | G Rajendra Kumar | 200 | 1 | 7.3.5.11.2 | 28 | 11 | T | N | 28.11 | 11 | 7.3.5.11.2 |  | V | Yongho |  |  | Incorrect mention of clause number in meaning of secondary40 CCA in Table 7-5 | Clause number should be 24.3.18.5.5 instead of 24.3.18.5.4 | REVISED (PHY: 2014-01-22 05:17:57Z) TGah editor to make changes shown in 11-13-1522r0 under the heading for CID 1033, 1412, 1577, 1578, 1579, 1773, 1787, 1788, 1789, 1790, 1791 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1791 | G Rajendra Kumar | 200 | 1 | 7.3.5.11.2 | 28 | 19 | T | N | 28.19 | 19 | 7.3.5.11.2 |  | V | Yongho |  |  | Incorrect mention of clause number in meaning of secondary80 CCA in Table 7-5 | Clause number should be 24.3.18.5.5 instead of 24.3.18.5.4 | REVISED (PHY: 2014-01-22 05:18:14Z) TGah editor to make changes shown in 11-13-1522r0 under the heading for CID 1033, 1412, 1577, 1578, 1579, 1773, 1787, 1788, 1789, 1790, 1791 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1792 | G Rajendra Kumar | 200 | 1 | 24.3.18.5.5 | 343 |  | T | N | 343 |  | 24.3.18.5.5 |  | V | Eugene Baik |  |  | "secondary2" is used instead of "secondary" as per Table 7-5 | Change "secondary2" to "secondary" in subclause 24.3.18.5.5 to maintain consistency | REVISED (PHY: 2014-01-22 04:25:47Z) Agree in principle. Instead, Table 7-5 in Section 7.3.5.11 has been re-written (separate CID resolution document 13/1522r0 by Yongho Seok) to use terminology consistent with 24.3.18.5 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY
1777 | Eugene Baik | 200 | 1 | 24.3.18.5 | 339 | 54 | T | N | 339.54 | 54 | 24.3.18.5 |  | A | Eugene Baik |  |  | CCA for the Primary 1MHz channel needs to be clarified from the current definition and criteria, which ostensibly describes that for the Primary 2MHz channel. This is needed because EDCA for 1MHz and >=2MHz PPDUs are performed with separate processes. For transmission of 1MHz PPDUs, backoff is performed on the Primary 1MHz channel, while for transmission of >=2MHz PPDUs backoff is performed on the Primary 2MHz channel | Add definitions and criteria for Primary 1MHz channel criteria to work alongside current Primary 2MHz definitions in text. | ACCEPTED (PHY: 2014-01-22 04:08:05Z) Please see the rewrite of Section 24.3.18.5.4 in 11-14/0109r2 | PHY | Jan 2014 PHY motion 1 | [5 empty] | 2014-01-22 05:21 | PHY