## Slide 1: IEEE 802.11mc Closing Report for March 2014
Date: 2014-03-20
Authors:

## Slide 2: Abstract
This document contains the TGmc closing report for March 2014.

## Slide 3: Status
Continued processing comments received in LB 199 – First recirculation LB
  497 comments
  Have approved resolutions to approximately 440 comments (50 this week)
Discussed “deprecation” comments
  May 2014 meeting: Weds PM2

## Slide 4: TGmc Plan of Record
Slide 4
20 July 2012 – 12 Sept 2012 – Call for Comment/Input
29-30 Aug 2012 – NesCom, SASB PAR Approval
Sept 2012 – Begin to process input
Sept 2012 – 11aa, 11ae integration
Jan – First WG Letter ballot - without 11ad
Dec 2012 – March/May 2013 – 11ad integration
Sept 2013 – Letter ballot on D2.0
Dec 2013 – May 2014 – 11ac, 11af integration – D3.0 in May 2014
July 2014 – Mandatory Draft Review
Jul - Aug 2014 – Form Sponsor Pool (45 days)
Nov 14 – Initial Sponsor Ballot
July 2015– WG/EC Final Approval
Dec 2015 – RevCom/SASB Approval – Was Sept 2015
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 4

## Slide 5: Teleconferences
Conference Calls 10am Eastern (2 hours)
  April 4, 11, May 2

## Slide 6: Next Steps
Complete comment resolution of comments received from LB 199 on P802.11REVmc D2.0