## Slide 1: 802.11ax Timeline Scenarios
Date: 2014-05-12
Authors:

## Slide 2: Contents
Timeline benchmarks from 802.11ac
Discussion of .11ax timeline relative to .11ac timeline
Two scenarios for preliminary projection of .11ax timeline

## Slide 3: Timeline Benchmarks from .11ac
 | Start | Finish | Duration
PAR approval -> Approved Standard | Sept 2008 | Dec 2013 | 5 yr, 4 mos (64 mos)
PAR approval -> Draft 1.0 | Sept 2008 | June 2011 | 2 yr, 10 mos (34 mos)
PAR approval -> SFD R0 | Sept 2008 | Sept 2009 | 1 yr (12 mos)
FR/EM R0 -> FR/EM R15 (compl) | Mar 2009 | July 2010 | 1 yr 4 mos (16 mos)
SFD R0 – final Rev (R21, D0.1) | Sept 2009 | Jan 2011 | 1 yr, 5 mos (17 mos)
SFD final (D0.1) – Draft 1.0 | Jan 2011 | June 2011 | 6 mos
Draft 1.0 – Draft 2.0 | June 2011 | Feb 2012 | 8 mos
Draft 2.0 - Final | Feb 2012 | Dec 2013 | 1 yr, 10 mos (22 mos)

## Slide 4: Timeline discussion
Factors pointing to a faster timeline than .11ac:
Potentially shorter FR/EM phase due to reuse from .11ac and early start in SG phase
  However the .11ax EM is more elaborate (more complex simulation scenarios, MAC/PHY simulator models/calibration)
Factors pointing to a potentially longer duration than .11ac:
Larger and more diverse audience, with mixed experience / background
More diverging expectations / requirements
Unclear and broader set of features to evaluate
Feature selection, gain evaluation and specification details, require more complex network level simulations

## Slide 5: Preliminary Timeline Projection, Scenario A, with ‘normalized’* .11ac timeline for reference
2018
2017
2015
2014
2013
2016
2019
Sept ‘08
11ac PAR Approved
11ac SFD R0 (Mar)
Sept ‘09
11ac SFD
SFD R21, D 0.1 (July )
Jan ‘11
.11ac Draft 1.0
Jan
July ‘11
.11ac Draft 2.0
Sept
Feb ‘12
.11ac Final
July
Dec ‘13
* .11ac timeline shown based on the .11ax PAR approval date
.11ax Draft 2.0
(Nov 2016)
.11ax Final
PAR Approved
(Mar 2014)
.11ax Draft 1.0
(January 2016)
Study Group
Launch
(March 2013)
Spec Framework
Document
(Sept 14 - July 2015)
11ax SFD
TG Kick Off
(May 2014)

## Slide 6: Preliminary Timeline Projection, Scenario B, with ‘normalized* .11ac timeline for reference
2018
2017
2015
2014
2013
2016
2019
Sept ‘08
11ac PAR Approved
11ac SFD R0 (Mar)
Sept ‘09
11ac SFD
SFD R21, D 0.1 (July )
Jan ‘11
.11ac Draft 1.0
Jan
July ‘11
.11ac Draft 2.0
Sept
Feb ‘12
.11ac Final
July
Dec ‘13
* .11ac timeline shown based on the .11ax PAR approval date
.11ax Draft 2.0 (Mar 2017)
.11ax Final
PAR Approved
(Mar 2014)
.11ax Draft 1.0 (July 2016)
Study Group
Launch
(March 2013)
Spec Framework
Document
(Nov 14 - Jan 2016)
11ax SFD
TG Kick Off
(May 2014)

## Slide 7: Preliminary Timeline Projection, Scenario C, with ‘normalized* .11ac timeline for reference
2018
2017
2015
2014
2013
2016
.11ax Draft 2.0 (Nov 2017)
.11ax Final
PAR Approved
(Mar 2014)
.11ax Draft 1.0 (Jan 2017)
Study Group
Launch
(March 2013)
Spec Framework
Document
(Jan 15 - July 2016)
2019
11ax SFD
TG Kick Off
(May 2014)
Sept ‘08
11ac PAR Approved
11ac SFD R0 (Mar)
Sept ‘09
11ac SFD
SFD R21, D 0.1 (July )
Jan ‘11
.11ac Draft 1.0
Jan
July ‘11
.11ac Draft 2.0
Sept
Feb ‘12
.11ac Final
July
Dec ‘13
* .11ac timeline shown based on the .11ax PAR approval date

## Slide 8: Strawpoll
What scenario should be reflected in the 802.11ax timeline estimate:
A: Scenario A (D1.0 in Jan 2016)
B: Scenario B (D1.0 in July 2016)
C: Scenario C (D1.0 in Jan 2017)
C: Other timeline
D: Don’t know / Abstain