## Lin Cai
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
4844 | Mark RISON | 201 | 2 | 10.44.5.2 | 98 | 36 | T | Y | 98 | 36 | 10.44.5.2 |  |  | Lin Cai |  |  | What's a category of STA? | Clarify | Revised. We have deleted 'categories of' in 814r0. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4679 | Lin Cai | 201 | 2 | 10.44.5.1 | 97 |  | T | Y | 97 |  | 10.44.5.1 |  |  | Lin Cai |  |  | User priority B0, B1, and B2 are used for indicating STAs that have frames with user priority 4-7, user priority 0-3, and no frame, respectively. Basically, the B1 is not well defined in the text and description of user priority 0-3 is missing. | Replace the first sentence in the third paragraph of 10.44.5.1 to ' An AP may set the FILS user priority B0, B1 and B2 to 1 to indicate high priority link setup without additional delays for the STAs that have frames with user priority 4-7 in their transmission queue(s), STAs that have frames with user priority 0-3 in their transmission queue(s), and STAs that have no frame in their transmission queue(s) respectively and to 0 otherwise.' | Accepted. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4677 | Lin Cai | 201 | 2 | 10.44.5.1 | 97 | 55 | T | Y | 97 | 55 | 10.44.5.1 |  |  | Lin Cai |  |  | There is no 'Vendor Specific Category' subfield but 'Vendor Specific' field. | Delete 'Category'. | Accepted. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4676 | Lin Cai | 201 | 2 | 10.44.5.1 | 97 | 48 | T | Y | 97 | 48 | 10.44.5.1 |  |  | Lin Cai |  |  | Differentiated initial link setup is not used for IP address request. | Delete 'Fused to explicitly request for an IP address'. | Accepted. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4675 | Lin Cai | 201 | 2 | 10.44.5.1 | 97 |  | T | Y | 97 |  | 10.44.5.1 |  |  | Lin Cai |  |  | It is not clear how Vendor Specific subelement is used in the Differentiated Initial Link Setup procedure in the first paragraph of 10.44.5.1. | Delete the last sentence of the Vendor Specific subelement in the first paragraph of 10.44.5. | Accepted. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4674 | Lin Cai | 201 | 2 | 10.44.5 | 97 |  | T | Y | 97 |  | 10.44.5 |  |  | Lin Cai |  |  | It is not clear how Vendor Specific subelement is used in the Differentiated Initial Link Setup procedure in the first paragraph of 10.44.5. | Delete the last sentence of the Vendor Specific subelement in the first paragraph of 10.44.5. | Accepted. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4606 | Jarkko Kneckt | 201 | 2 | 10.44.5.2 | 98 | 36 | T | N | 98 | 36 | 10.44.5.2 |  |  | Lin Cai |  |  | The werb "can" relates to possibilty to perform an operation. May is more correct here, because here the condition is more present | Change can to may. | Revised. We have changed 'can' to 'should' in 814r0. We recommend STAs to initiate the initial link setup after the specified time expires, although STA's behavior is an implementation issue. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4605 | Jarkko Kneckt | 201 | 2 | 10.44.5.2 | 98 | 29 | T | N | 98 | 29 | 10.44.5.2 |  |  | Lin Cai |  |  | The STA shall not be forced to initiate link. The STA shall have possibiility to select does it desire to establish a link. The current text forces every STA to create a link to the AP to which it has FILSC value 1. The STA should be able to select the best AP for link setup. | change shall to may. Write the sentence:"... FILSC value of 1 and it may proceed..." | Revised. We have changed 'shall to 'should' in 814r0. We recommend high priority STAs to initiate the initial link setup without additional delay, although STA's behavior is an implementation issue. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4601 | Jarkko Kneckt | 201 | 2 | 10.44.5.1 | 97 | 48 | T | N | 97 | 48 | 10.44.5.1 |  |  | Lin Cai |  |  | FUsed? I am confused. FUsed is not specified in 802.11ai. | Clarify what is Fused? | Revised. We have deleted 'Fused to explicitly request for an IP address' in 814r0. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4291 | GEORGE CHERIAN | 201 | 2 | 10.44.5.1 | 97 |  | T | N | 97 |  | 10.44.5.1 |  |  | Lin Cai |  |  | Vendor Specific field need not be included for Differential Initial Link Setup | Delete Vendor specific filtering | Reject. Vendor Specific field in DILS element is used for an AP to set up a filter or criteria to allow a subset of STAs to transmit initial link setup request frames to the AP without additional delays. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4845 | Mark RISON | 201 | 2 | 10.44.5.2 | 98 | 52 | T | Y | 98 | 52 | 10.44.5.2 |  |  | Lin Cai |  |  | What constitutes "understanding" an OI subfield? | Clarify | Revised. We have changed 'understand' to 'identify' in 814r0. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4880 | Mark RISON | 201 | 2 | 8.4.2.183 | 57 | 45 | T | Y | 57 | 45 | 8.4.2.183 |  |  | Lin Cai |  |  | Those "must be 0" bits are not very forward-compatible | Make them reserved instead | Revised. The comment resolution is accepted in general. The "0" bits are set to "Reserved". | TGai General | [6 empty] | 2014-05-13 02:04 | TGai General
4843 | Mark RISON | 201 | 2 | 10.44.5.2 | 98 | 31 | T | Y | 98 | 31 | 10.44.5.2 |  |  | Lin Cai |  |  | "Each time a STA with dot11FILSActivated and dot11DILSActivated equal to true receives" -- no, only a non-AP STA | "Each time the STA receives" | Accepted. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4842 | Mark RISON | 201 | 2 | 10.44.5.2 | 98 | 28 | T | Y | 98 | 28 | 10.44.5.2 |  |  | Lin Cai |  |  | "including the FILS user priority, MAC address filter, and Vendor Specific" -- it's already been stated that all conditions have to be satisfied | Delete | Accepted. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4841 | Mark RISON | 201 | 2 | 10.44.5.2 |  |  | T | Y |  |  | 10.44.5.2 |  |  | Lin Cai |  |  | What is the incentive for a non-AP STA to use DILS? | Delete this feature | Reject. DILS is used to improve the link setup performance in pre-association stage by differentiating STAs with different priorities . The incentive for non-AP STA is similar to that of EDCA which is used for associated STAs. | TGai General |  |  | TGai General: 2014-05-09 18:05:02Z - Assigned to 2nd Editor to provide page and line numbers as well as a suggested assignee for further handling the comment. |  |  |  | 2014-05-12 18:30 | TGai General
4836 | Mark RISON | 201 | 2 | 10.44.5 | 97 | 50 | T | Y | 97 | 50 | 10.44.5 |  |  | Lin Cai |  |  | "The Vendor Specific subelement has the same format as the Vendor Specific element" -- that's still nice to know, but where is this subelement used for DILS at the AP? | Clarify | Revised. We Have deleted the sentence in line 50, page 97, clause 10.44.5, in 814r0. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4834 | Mark RISON | 201 | 2 | 10.44.5 | 97 | 34 | T | Y | 97 | 34 | 10.44.5 |  |  | Lin Cai |  |  | "The Vendor Specific subelement has the same format as the Vendor Specific element" -- that's nice to know, but where is this subelement used for DILS? | Clarify | Revised. We Have deleted the sentence in line 34, page 97, clause 10.44.5, in 814r0. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4833 | Mark RISON | 201 | 2 | 10.44.5 | 97 | 33 | T | Y | 97 | 33 | 10.44.5 |  |  | Lin Cai |  |  | "authentication request" | "Authentication" [no "request"] | Accepted. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4832 | Mark RISON | 201 | 2 | 10.44.5 | 97 | 32 | T | Y | 97 | 32 | 10.44.5 |  |  | Lin Cai |  |  | "association request" | "(Re)Association Request" | Revised. Please read comment resolution for CIDs 4831 and 4600. We have deleted 'association request' as the FILS is initiated with an Authentication frame. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4831 | Mark RISON | 201 | 2 | 10.44.5 | 97 | 32 | T | Y | 97 | 32 | 10.44.5 |  |  | Lin Cai |  |  | I don't understand "first frame initializing the link setup procedure" -- isn't this always an Authentication frame? | Clarify | Revised. We have revised the text in 814r0 as the FILS is initiated with an Authentication frame. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4600 | Jarkko Kneckt | 201 | 2 | 10.44.5 | 97 | 30 | T | N | 97 | 30 | 10.44.5 |  |  | Lin Cai |  |  | To my understanding the initial link setup is always initiated with (FILS) Auhtentication Request frame transmission. The FILS Association frames cannot be used without FILS authentication frames, i.e. FILS association request frame cannot be transmitted separately to new AP. | Clarify the text by deleting the option where FILS signaling would only contain the FILS association signaling. | Revised. Please read resolution for CID 4831. We have revised the text in 814r0 as the FILS is initiated with an Authentication frame. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
5018 | Qi Wang | 201 | 2 | 10.44.5.1 | 98 | 8 | T | Y | 98 | 8 | 10.44.5.1 |  |  | Lin Cai |  |  | If the Differentiated Initial Link Setup element includes both the "FILS User Priority" and "MAC Address filter" subfields in the "FILSC information" fields, what is the expected AP behavior? Does one or both subfields apply? | Please specify the expected AP behavior when the Differentiated Initial Link Setup element includes both the "FILS User Priority" and "MAC Address filter" subfields in the "FILSC information" fields. | Revised. We have specified in 10.44.5.1 that AP may include different fields in the Differentiated Initial Link Setup element. How AP set the fields is implementation specific. In 10.44.5.2, we specify the STA's behavior when multiple fields are included, i.e., STAs satisfying all criteria should proceed FILS immediately without additional delay. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
5129 | Vinko Erceg | 201 | 2 | 10.44.5.1 | 98 | 8 | T | Y | 98 | 8 | 10.44.5.1 | 5018 |  | Lin Cai |  |  | If the Differentiated Initial Link Setup element includes both the "FILS User Priority" and "MAC Address filter" subfields in the "FILSC information" fields, what is the expected AP behavior? Does one or both subfields apply? | Please specify the expected AP behavior when the Differentiated Initial Link Setup element includes both the "FILS User Priority" and "MAC Address filter" subfields in the "FILSC information" fields. | Revised. We have specified in 10.44.5.1 that AP may include different fields in the Differentiated Initial Link Setup element. How AP set the fields is implementation specific. In 10.44.5.2, we specify the STA's behavior when multiple fields are included, i.e., STAs satisfying all criteria should proceed FILS immediately without additional delay. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
5128 | Vinko Erceg | 201 | 2 | 10.44.5 | 98 | 26 | T | Y | 98 | 26 | 10.44.5 |  |  | Lin Cai |  |  | An AP has no knowledge of (1) the user priority level of the traffic and (2) the MAC address of the STA that intends to associate, therefore the AP cannot fill in the content of the Differentiated Initial Link Setup element intelligently. When the AP includes such an element, there might be no or only a very few STAs that meet the criteria established, so that the AP unnecessarily prevents other STAs from attempting the link setup for the "FILS Time". | Please explain how an AP can establish the parameters in the Differentiated Initial Link Setup element; otherwise please remove section 10.44.5. | Revised. We have specified in 10.44.5 that AP may set different fields in DILS element to moderate the rate non-AP STAs transmit Authentication frames to the AP. Basically, when AP detected a channel access congetion or bursty association, AP can decide to setup DILS element for differentiated association, to ensure fast link setup for high priority STAs, and in the mean time to reduce the impacts of bursty association on the associated STAs. In CSMA/CA based WiFi, optimizing the parameter setting is always a very challenging task, however, the optional feature of differentiated association can ensure fast link setup for high priority STAs, especially when the network is heavily loaded or approaches its capacity. How AP detects the congestion and/or sets the parameters are implementation specific. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
5109 | Vinko Erceg | 201 | 2 | 8.4.2.183 | 55 | 61 | T | Y | 55 | 61 | 8.4.2.183 |  |  | Lin Cai |  |  | An AP has no knowledge of (1) the user priority level of the traffic and (2) the MAC address of the STA that intends to associate, therefore the AP cannot fill in the content of the Differentiated Initial Link Setup element intelligently. When the AP includes such an element, there might be no or only a very few STAs that meet the criteria established, so that the AP unnecessarily prevents other STAs from attempting the link setup for the "FILS Time". | Please explain how an AP can fill in the content of the Differentiated Initial Link Setup; otherwise remove the feature. | Revised. We have specified in 10.44.5 that AP may set different fields in DILS element to moderate the rate non-AP STAs transmit Authentication frames to the AP. Basically, when AP detected a channel access congetion or bursty association, AP can decide to setup DILS element for differentiated association, to ensure fast link setup for high priority STAs, and in the mean time to reduce the impacts of bursty association on the associated STAs. In CSMA/CA based WiFi, optimizing the parameter setting is always a very challenging task, however, the optional feature of differentiated association can ensure fast link setup for high priority STAs, especially when the network is heavily loaded or approaches its capacity. How AP detects the congestion and/or sets the parameters are implementation specific. | TGai General | [6 empty] | 2014-05-13 02:04 | TGai General
5108 | Vinko Erceg | 201 | 2 | 8.4.2..183 | 57 | 32 | T | Y | 57 | 32 | 8.4.2..183 |  |  | Lin Cai |  |  | "The usage of the Bit Pattern Length subfield and Bit Pattern subfield is defined in Table 8-221k (MAC Address Filter subfield). The Bit Pattern Length subfield specifies the number of bits and the position of the bits in the Bit Pattern subfield that are used for MAC address filtering. The values of the bits specify the MAC addresses of the STAs that are allowed to attempt initial link setup" The text is unclear about how the content of the MAC Address Filter subfield is used to perform MAC address filtering. | Please improve the text and explain how the content of the MAC Address Filter subfield is used to perform MAC address filtering. | Revised The details of MAC address filtering is described in 10.44.5.2. Sentence "The details of MAC address filtering is described in 10.44.5.2." is added to the end of the paragraph in the comment in 814r0. | TGai General | [6 empty] | 2014-05-13 02:04 | TGai General
5107 | Vinko Erceg | 201 | 2 | 8.4.2.183 | 57 | 2 | T | Y | 57 | 2 | 8.4.2.183 |  |  | Lin Cai |  |  | Please explain the meaning of the B0, B1 and B2 of "FILS User Priority subfield" as illustrated in Figure 8-401di and how each of the bits should be set. | As in comment. | Revised. We defined B0, B1, and B2 in 8.4.2.183, and detail explaination of the frame usage is provided in 10.44.5, based on the previous comments. We have also revised the text on B0, B1, and B2 in 10.44.5.1 in 814r0. | TGai General | [6 empty] | 2014-05-13 02:04 | TGai General
5106 | Vinko Erceg | 201 | 2 | 8.4.2.183 | 56 | 30 | T | Y | 56 | 30 | 8.4.2.183 |  |  | Lin Cai |  |  | Should "octets" in Figure 8-401 be replaced with "Bits"? The text "The FILSC Type subfield is 1 octet in length..." in line 42 suggests so, but Figure 8-401di indicates otherwise. | Please fix the inconsistence. | Accepted. We have changed 'octets' to 'Bits' in 814r0. | TGai General | [6 empty] | 2014-05-13 02:04 | TGai General
5105 | Vinko Erceg | 201 | 2 | 8.4.2.183 | 56 | 7 | T | Y | 56 | 7 | 8.4.2.183 | 4994 |  | Lin Cai |  |  | "FILS Time" is a non-descriptive name for the corresponding field in the Differentiated Initial Link Setup element. | Change the field name from "FILS Time" to "Differented FILS Time" or something along the line. | Accepted. | TGai General | [6 empty] | 2014-05-13 02:04 | TGai General
5068 | Santosh Ghanshyam Pandey | 201 | 2 | 8.4.2.183 | 56 | 52 | T | Y | 56 | 52 | 8.4.2.183 |  |  | Lin Cai |  |  | The figure 8-401dh shows the size in Octets it should however be Bits | Change Octets to Bits | Accepted. | TGai General | [6 empty] | 2014-05-13 02:04 | TGai General
4684 | Mark Hamilton | 201 | 2 | 3.2 | 3 | 43 | T | N | 3 | 43 | 3.2 |  |  | Lin Cai |  |  | That a FILSC can be encoded in binary is not part of the definition of the term | Delete "binary" | Accepted. | TGai General | [6 empty] | 2014-05-13 07:49 | TGai General
5019 | Qi Wang | 201 | 2 | 10.44.5.2 | 98 | 52 | T | Y | 98 | 52 | 10.44.5.2 | 5018 |  | Lin Cai |  |  | If the Differentiated Initial Link Setup element includes both the "FILS User Priority" and "MAC Address filter" subfields in the "FILSC information" fields, what is the expected AP behavior? Does one or both subfields apply? | Please specify the expected STA behavior when the Differentiated Initial Link Setup element includes both the "FILS User Priority" and "MAC Address filter" subfields in the "FILSC information" fields. | Revised. We have specified in 10.44.5.1 that AP may include multiple fields in the Differentiated Initial Link Setup element. How AP set the fields is implementation specific. In 10.44.5.2, we specify the STA's behavior when multiple fields are included, i.e., STAs satisfying all criteria should proceed FILS immediately without additional delay. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4685 | Mark Hamilton | 201 | 2 | 8.4.2.183 | 56 | 46 | T | N | 56 | 46 | 8.4.2.183 |  |  | Lin Cai |  |  | "when Differentiated Initial Link Setup element is present." is redundant for a subelement of the DILS element. | Delete "when Differentiated Initial Link Setup element is present." | Accepted. | TGai General | [6 empty] | 2014-05-13 02:04 | TGai General
5017 | Qi Wang | 201 | 2 | 10.44.5 | 98 | 26 | T | Y | 98 | 26 | 10.44.5 |  |  | Lin Cai |  |  | An AP has no knowledge of (1) the user priority level of the traffic and (2) the MAC address of the STA that intends to associate, therefore the AP cannot fill in the content of the Differentiated Initial Link Setup element intelligently. When the AP includes such an element, there might be no or only a very few STAs that meet the criteria established, so that the AP unnecessarily prevents other STAs from attempting the link setup for the "FILS Time". | Please explain how an AP can establish the parameters in the Differentiated Initial Link Setup element; otherwise please remove section 10.44.5. | Rejected. We have specified in 10.44.5 that AP may set different fields in DILS element to moderate the rate non-AP STAs transmit Authentication frames to the AP. Basically, when AP detected a channel access congetion or bursty association, AP can decide to setup DILS element for differentiated association, to ensure fast link setup for high priority STAs, and in the mean time to reduce the impacts of bursty association on the associated STAs. In CSMA/CA based WiFi, optimizing the parameter setting is always a very challenging task, however, the optional feature of differentiated association can ensure fast link setup for high priority STAs, especially when the network is heavily loaded or approaches its capacity. How AP detects the congestion and/or sets the parameters are implementation specific. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4998 | Qi Wang | 201 | 2 | 8.4.2.183 | 55 | 61 | T | Y | 55 | 61 | 8.4.2.183 |  |  | Lin Cai |  |  | An AP has no knowledge of (1) the user priority level of the traffic and (2) the MAC address of the STA that intends to associate, therefore the AP cannot fill in the content of the Differentiated Initial Link Setup element intelligently. When the AP includes such an element, there might be no or only a very few STAs that meet the criteria established, so that the AP unnecessarily prevents other STAs from attempting the link setup for the "FILS Time". | Please explain how an AP can fill in the content of the Differentiated Initial Link Setup; otherwise remove the feature. | Revised. We have specified in 10.44.5 that AP may set different fields in DILS element to moderate the rate non-AP STAs transmit Authentication frames to the AP. Basically, when AP detected a channel access congetion or bursty association, AP can decide to setup DILS element for differentiated association, to ensure fast link setup for high priority STAs, and in the mean time to reduce the impacts of bursty association on the associated STAs. In CSMA/CA based WiFi, optimizing the parameter setting is always a very challenging task, however, the optional feature of differentiated association can ensure fast link setup for high priority STAs, especially when the network is heavily loaded or approaches its capacity. How AP detects the congestion and/or sets the parameters are implementation specific. | TGai General | [6 empty] | 2014-05-13 02:04 | TGai General
4997 | Qi Wang | 201 | 2 | 8.4.2..183 | 57 | 32 | T | Y | 57 | 32 | 8.4.2..183 |  |  | Lin Cai |  |  | "The usage of the Bit Pattern Length subfield and Bit Pattern subfield is defined in Table 8-221k (MAC Address Filter subfield). The Bit Pattern Length subfield specifies the number of bits and the position of the bits in the Bit Pattern subfield that are used for MAC address filtering. The values of the bits specify the MAC addresses of the STAs that are allowed to attempt initial link setup" The text is unclear about how the content of the MAC Address Filter subfield is used to perform MAC address filtering. | Please improve the text and explain how the content of the MAC Address Filter subfield is used to perform MAC address filtering. | Revised. The details of MAC address filtering is described in 10.44.5.2. Sentence "The details of MAC address filtering is described in 10.44.5.2." is added to the end of the paragraph in the comment in 814r0. | TGai General | [6 empty] | 2014-05-13 02:04 | TGai General
4996 | Qi Wang | 201 | 2 | 8.4.2.183 | 57 | 2 | T | Y | 57 | 2 | 8.4.2.183 |  |  | Lin Cai |  |  | Please explain the meaning of the B0, B1 and B2 of "FILS User Priority subfield" as illustrated in Figure 8-401di and how each of the bits should be set. | As in comment. | Revised. We defined B0, B1, and B2 in 8.4.2.183, and detail explaination of the frame usage is provided in 10.44.5, based on the previous comments. We have also revised the text on B0, B1, and B2 in 10.44.5.1 in 814r0. | TGai General | [6 empty] | 2014-05-13 02:04 | TGai General
4995 | Qi Wang | 201 | 2 | 8.4.2.183 | 56 | 30 | T | Y | 56 | 30 | 8.4.2.183 |  |  | Lin Cai |  |  | Should "octets" in Figure 8-401 be replaced with "Bits"? The text "The FILSC Type subfield is 1 octet in length..." in line 42 suggests so, but Figure 8-401di indicates otherwise. | Please fix the inconsistence. | Accepted. We have changed 'octets' to 'Bits' in 814r0. | TGai General | [6 empty] | 2014-05-13 02:04 | TGai General
4994 | Qi Wang | 201 | 2 | 8.4.2.183 | 56 | 7 | T | Y | 56 | 7 | 8.4.2.183 |  |  | Lin Cai |  |  | "FILS Time" is a non-descriptive name for the corresponding field in the Differentiated Initial Link Setup element. | Change the field name from "FILS Time" to "Differented FILS Time" or something along the line. | Accepted. | TGai General | [6 empty] | 2014-05-13 02:04 | TGai General
4977 | Ping Fang | 201 | 2 | 10.44.5.1 | 97 | 44 | T | Y | 97 | 44 | 10.44.5.1 |  |  | Lin Cai |  |  | This sentence is not complete for "and Fused", and the FILS Time is a field in DILS element. | change the sentence to "An AP with dot11FILSActivated true may include the Differentiated Initial Link Setup element in Beacon and Probe Response frames to limit the number of STAs that are allowed to attempt link setup during the FILS Time." | Revised. We have deleted 'Fused to explicitly request for an IP address' in 814r0. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
4972 | Ping Fang | 201 | 2 | 8.4.2.183 | 55 | 64 | T | Y | 55 | 64 | 8.4.2.183 |  |  | Lin Cai |  |  | The description for DILS element "includes the conditions for a STA to determine the FILSC value for the duration specified in the element" is almost same as FILSC Information field "indicates the conditions to determine FILSC value for the time as indicated in the FILS Time field". change the element description to describe the function of the element. | change "The Differentiated Initial Link Setup element includes the conditions for a STA to determine the FILSC value for the duration specified in the element." to "The Differentiated Initial Link Setup element includes the conditions for a STA to determine whether it is allowed to attempt initial link setup for the duration specified in the element." | Accepted. | TGai General | [6 empty] | 2014-05-13 02:04 | TGai General
5130 | Vinko Erceg | 201 | 2 | 10.44.5.2 | 98 | 52 | T | Y | 98 | 52 | 10.44.5.2 | 5018 |  | Lin Cai |  |  | If the Differentiated Initial Link Setup element includes both the "FILS User Priority" and "MAC Address filter" subfields in the "FILSC information" fields, what is the expected AP behavior? Does one or both subfields apply? | Please specify the expected STA behavior when the Differentiated Initial Link Setup element includes both the "FILS User Priority" and "MAC Address filter" subfields in the "FILSC information" fields. | Revised. We have specified in 10.44.5.1 that AP may include multiple fields in the Differentiated Initial Link Setup element. How AP set the fields is implementation specific. In 10.44.5.2, we specify the STA's behavior when multiple fields are included, i.e., STAs satisfying all criteria should proceed FILS immediately without additional delay. | TGai General | [6 empty] | 2014-05-09 18:54 | TGai General
5067 | Santosh Ghanshyam Pandey | 201 | 2 | 8.4.2.183 | 56 | 45 | T | N | 56 | 45 | 8.4.2.183 |  |  | Lin Cai |  |  | Ambiguous field name, is the field "FILS User Priority" as speficied in figure 8-401dh or "User Priority" as speficied in text in line 45 | Clarify field name and keep it consistent | Revised. We have changed the text in 814r0 and used 'FILS User Priority' consistently. | TGai General | [6 empty] | 2014-05-13 02:04 | TGai General