## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-15/0299r1
Venue Date: | March 2015
First Author: | Marc Emmelmann
Subject: | LB209 Suggested Comment Resolutions
Full Date: | 2015-03-03
Author(s): | Marc Emmelmann
| Company: | self
Address
Phone:
Fax:
| email: | emmelmann@ieee.org
Abstract:
Suggested comment resolutions for CIDs assigned to Marc E.

## Revision History
Revision | Date | Description
0 | 2015-03-03 | Initial version
1 | 2015-03-03 | Reflects changes agreed to in Telco

## Marc Emmelmann
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
7017 | MARC EMMELMANN | 209 | 4 | 8.3.3.5 | 32 | 38 | T | N | 32.38 | 38 | 8.3.3.5 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7025 | MARC EMMELMANN | 209 | 4 | 8.3.3.6 | 33 | 25 | T | N | 33.25 | 25 | 8.3.3.6 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7024 | MARC EMMELMANN | 209 | 4 | 8.3.3.6 | 33 | 18 | T | N | 33.18 | 18 | 8.3.3.6 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7023 | MARC EMMELMANN | 209 | 4 | 8.3.3.6 | 33 | 13 | T | N | 33.13 | 13 | 8.3.3.6 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7022 | MARC EMMELMANN | 209 | 4 | 8.3.3.6 | 33 | 9 | T | N | 33.09 | 9 | 8.3.3.6 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7021 | MARC EMMELMANN | 209 | 4 | 8.3.3.5 | 32 | 52 | T | N | 32.52 | 52 | 8.3.3.5 |  |  | Marc Emmelmann |  |  | Sentence in notes column is not complete (ending in ....if.) | Add the missing condition. Assure that the sentence follows the style suggested by the 802.11 editor, i.e. "[optionally] present if <condition> [; otherwise not present]" | Revised: add at the end of the sentence "dot11FILSActivated is true; otherwise not present" Note to editor: correct line number is 52. | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7020 | MARC EMMELMANN | 209 | 4 | 8.3.3.5 | 32 | 52 | T | N | 32.52 | 52 | 8.3.3.5 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7054 | MARC EMMELMANN | 209 | 4 | 10.1.4.3.5 | 89 | 54 | T | N | 89.54 | 54 | 10.1.4.3.5 |  |  | Marc Emmelmann |  |  | Multiple issues here: 1) text does not show exactly the baseline to be changed (REVmc D4.0). 2) comparing to REVmc D4.0 shows that this is not purely editoral but additional changes have to be made. E.g. REVmc D4.0 talks in the first paragraph about responses individually addressed to the STA sending the probe request which we do not want to do. | Closely compare the text against REVmc D4.0, make sure that the baseline text is shown correctly and _afterwards_ highlight additonal changes that are required. |  | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7018 | MARC EMMELMANN | 209 | 4 | 8.3.3.5 | 32 | 41 | T | N | 32.41 | 41 | 8.3.3.5 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7028 | MARC EMMELMANN | 209 | 4 | 8.3.3.7 | 34 | 16 | T | N | 34.16 | 16 | 8.3.3.7 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7016 | MARC EMMELMANN | 209 | 4 | 8.3.3.2 | 32 | 18 | T | N | 32.18 | 18 | 8.3.3.2 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7015 | MARC EMMELMANN | 209 | 4 | 8.3.3.2 | 32 | 15 | T | N | 32.15 | 15 | 8.3.3.2 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7014 | MARC EMMELMANN | 209 | 4 | 8.3.3.2 | 32 | 12 | T | N | 32.12 | 12 | 8.3.3.2 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7008 | MARC EMMELMANN | 209 | 4 | 6.3.5.5.2 | 18 | 18 | T | N | 18.18 | 18 | 6.3.5.5.2 |  |  | Marc Emmelmann |  |  | "Minimum Association Response timeout (in TU) that the non-AP STA to be set to dot11Association- ResponseTimeOut." Sentence is hard to understand (... Non-AP STA to be set to ... Part of the sentence. | "Minimum Association Response timeout (in TU) that the non-AP STA to be set to dot11Association- ResponseTimeOut." Sentence is hard to understand (... Non-AP STA to be set to ... Part of the sentence. | Revised: Change sentence to Minimum Association Response timeout (in TU) that the non-AP STA sets to the value given by dot11AssociationResponseTimeOut. | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7007 | MARC EMMELMANN | 209 | 4 | 6.3.5.3.2 | 17 | 20 | T | N | 17.2 | 20 | 6.3.5.3.2 |  |  | Marc Emmelmann |  |  | "Minimum Association Response timeout (in TU) that the non-AP STA to be set to dot11Association- ResponseTimeOut." Sentence is hard to understand (... Non-AP STA to be set to ... Part of the sentence. | Change sentence to: Minimum Association Response timeout (in TU) that the non-AP STA sets to the value given by dot11AssociationResponseTimeOut. | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7003 | MARC EMMELMANN | 209 | 4 | 4.10.3.6.2 | 9 | 13 | T | N | 9.13 | 13 | 4.10.3.6.2 |  |  | Marc Emmelmann |  |  | 2) an a priori knowledge of and trust in , a .... Is it "knowledge and trust" or is it "knowledge of trust"? | replace "of and" with "and" | Revised: change to: "...knowledge of, and trust in, an uncertified ...." Note to editor: insert comma after of & a --> an Additionally: delte the "that they" in the second line of the paragraph. | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7019 | MARC EMMELMANN | 209 | 4 | 8.3.3.5 | 32 | 45 | T | N | 32.45 | 45 | 8.3.3.5 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7035 | MARC EMMELMANN | 209 | 4 | 8.3.3.10 | 36 | 58 | T | N | 36.58 | 58 | 8.3.3.10 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7393 | Mark RISON | 209 | 4 |  |  |  | T | Y | [5 empty] | Marc Emmelmann |  |  | Various definitions in the baseline probably need to be updated for FILS, since it does not use a 4WH. Examples: GTKSA, PTKSA, RSNA key management |  | NEEDS DISCUSSION in telco --> then reassign or agree that the comment is not specific for which the resolution could be: REJECT -- The comment speculates about a potential technical remedy but does not identify a specific technical remedy nor does it provide a proposed change that can be immediately adopted to satisfy the comment. | TGai General | [6 empty] | 2015-02-26 16:12 | TGai General
7345 | Mark RISON | 209 | 4 | 8.3.3.2 | 32 | 50 | T | Y | 32.5 | 50 | 8.3.3.2 |  |  | Marc Emmelmann |  |  | If what? Also at 35.24 | Add "dot11FILSActivated is true; otherwise not present" at the end of the sentence in all indicated locations | Accept. -- Attention: they might have been similar comments addressing this issue --> reassign to Marc if group agrees to accept | TGai General | [6 empty] | 2015-02-27 08:27 | TGai General
7342 | Mark RISON | 209 | 4 | 8.3.3.2 | 32 | 12 | T | Y | 32.12 | 12 | 8.3.3.2 |  |  | Marc Emmelmann |  |  | Does not specify what happens if dot11FILSActivated is not true. One of many instances referred to; others at 32.15, 32.18, 32.39, 32.43, 32.47, 32.53, 33.10, 33.15, 33.20, 33.23, 33.27, 33.30, 34.12, 34.18, 34.22, 34.35, 34.29, 35.12, 35.17, 35.21, 35.28, 35.31, 36.13, 36.16, 36.50, 36.53, 36.58, 36.62 | Add "; otherwise not present" at the end of the sentence in all indicated locations; also make the font size consistent in the tables in question | Accept | TGai General | [6 empty] | 2015-02-27 08:27 | TGai General
7295 | Hiroki Nakano | 209 | 4 | 8.3.3.8 | 35 | 24 | T | Y | 35.24 | 24 | 8.3.3.8 |  |  | Marc Emmelmann |  |  | One or more FILS HLP Container elements are optionally present if "what"?? | Remove "if" | Revised: add at the end of the sentence: "dot11FILSActivated is true; otherwise not present" | TGai General | [6 empty] | 2015-02-27 08:27 | TGai General
7294 | Hiroki Nakano | 209 | 4 | 8.3.3.5 | 32 | 50 | T | Y | 32.5 | 50 | 8.3.3.5 |  |  | Marc Emmelmann |  |  | One or more FILS HLP Container elements are optionally present if "what"?? | Remove "if" | Revised: add at the end of the sentence: "dot11FILSActivated is true; otherwise not present" | TGai General | [6 empty] | 2015-02-27 08:27 | TGai General
7254 | Dan Harkins | 209 | 4 | 8.4.2.183 | 67 |  | T | Y | 67 |  | 8.4.2.183 |  |  | Marc Emmelmann |  |  | differentiated link setup is more trouble than it's worth. | get rid of this capability | Needs discussion in face-to-face or telco. Based on previous discussions in the group, suggested remedy is: REJECT: When approving features for Tgai, the task group discussed the benefits and disadvantages of technical features. The majority of the group was in favor of including differential link set up in the amendment. | TGai General | [6 empty] | 2015-02-27 08:40 | TGai General
7026 | MARC EMMELMANN | 209 | 4 | 8.3.3.6 | 33 | 29 | T | N | 33.29 | 29 | 8.3.3.6 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7036 | MARC EMMELMANN | 209 | 4 | 8.3.3.10 | 36 | 63 | T | N | 36.63 | 63 | 8.3.3.10 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7027 | MARC EMMELMANN | 209 | 4 | 8.3.3.7 | 34 | 11 | T | N | 34.11 | 11 | 8.3.3.7 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7034 | MARC EMMELMANN | 209 | 4 | 8.3.3.10 | 36 | 54 | T | N | 36.54 | 54 | 8.3.3.10 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7033 | MARC EMMELMANN | 209 | 4 | 8.3.3.10 | 36 | 50 | T | N | 36.5 | 50 | 8.3.3.10 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7032 | MARC EMMELMANN | 209 | 4 | 8.3.3.9 | 36 | 16 | T | N | 36.16 | 16 | 8.3.3.9 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7031 | MARC EMMELMANN | 209 | 4 | 8.3.3.9 | 36 | 12 | T | N | 36.12 | 12 | 8.3.3.9 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7030 | MARC EMMELMANN | 209 | 4 | 8.3.3.7 | 34 | 27 | T | N | 34.27 | 27 | 8.3.3.7 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7029 | MARC EMMELMANN | 209 | 4 | 8.3.3.7 | 34 | 20 | T | N | 34.2 | 20 | 8.3.3.7 |  |  | Marc Emmelmann |  |  | Condition when the element is present is not complete / does not follow the conventions suggested by the 802.11 Editor which is "[optionally] present if <condition> [; otherwise not present]" | Add "; otherwise not present" at the end of the sentence in the Notes column | Accept | TGai General | [6 empty] | 2015-02-26 16:00 | TGai General
7440 | Mark RISON | 209 | 4 |  |  |  | G | Y | [5 empty] | Marc Emmelmann |  |  | There is no reason DMG STAs shouldn't be able to use FILS, except maybe for some of the scanning optimisations, which are not appropriate to a directional context | Allow most of FILS to be used with DMG | Needs discussion during telco or face to face. Suggested resolution: Reject The suggested change has been raised in previous ballots and has been discussed and rejected by the task group as the task group does not support the proposed change. Support of FILS for DMG STAs may require the separation of FILS discovery and authentication functionality. The risk of introducing errors and the lack of support for validating the proposal are contributing factors to the decision. | TGai General | [6 empty] | 2015-02-26 16:12 | TGai General
7212 | Yongho Seok | 209 | 4 | 8.3.3.5 | 32 | 50 | T | Y | 32.5 | 50 | 8.3.3.5 |  |  | Marc Emmelmann |  |  | if what? | Specify the condition of "if". | Needs discussion in telco or face-to-face | TGai General | [6 empty] | 2015-02-27 08:27 | TGai General