## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-15/0450r0
Venue Date: | March 2015
First Author: | Yunsong Yang, Huawei Technologies
Subject: | LB208 Comment Resolutions
Full Date: | 2015-03-11
Author(s): | Name(s) | Yunsong Yang
| Company | Huawei Technologies
Address
Phone:
Fax:
| email: | yangyunsong@huawei.com
Abstract:
This document contains the comment resolutions to LB208 comments that have been proposed by various assignees in March meeting. The proposal is to approve these comment resolutions.

## Clause 1
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1618 | Robert Slater | 208 | 1 | 1.2 | 5 | 9 | E | N | 5.09 | 9 | 1.2 |  |  | Emily Qi, Dan Gal |  |  | Remove section 1.2, as this is not updated from the base specification. | Remove section | REVISED. Incorporate the changes in Doc. 11-15/418r0. | EDITOR | Clause 1 | [5 empty] | 2015-03-11 17:47 | EDITOR
1617 | Robert Slater | 208 | 1 | 1 | 5 | 2 | E | Y | 5.02 | 2 | 1 |  |  | Emily Qi, Dan Gal |  |  | Remove first sentence of Overview. This boilerplate is not appropriate to this amendment | Remove "This amendment of IEEE 802 Std 802.11 defines one medium access control (MAC) and several physical layer (PHY) specifications for wireless connectivity for fixed, portable, and moving stations (STAs) within a local area." | REVISED. Incorporate the changes in Doc. 11-15/418r0. | EDITOR | Clause 1 | [5 empty] | 2015-03-11 17:46 | EDITOR
1495 | Richard Roy | 208 | 1 | 1.2 | 5 | 10 | E | Y | 5.1 | 10 | 1.2 |  |  | Emily Qi, Dan Gal |  |  | The Purpose clause seems totally out of context. | Either rewrite it so it makes sense or remove it. | REVISED. Incorporate the changes in Doc. 11-15/418r0. | EDITOR | Clause 1 | [5 empty] | 2015-03-11 17:47 | EDITOR
1494 | Richard Roy | 208 | 1 | 1.1 | 5 | 7 | E | Y | 5.07 | 7 | 1.1 |  |  | Emily Qi, Dan Gal |  |  | Change "This amendment defines modifications to the IEEE 802.11 standard, above the physical layer (PHY), to enable delivery of pre-association Service Discovery information by IEEE 802.11 stations (STAs)." | to "This amendment defines modifications to the IEEE 802.11 standard, above the physical layer (PHY), to enable delivery of pre-association Service Discovery information to IEEE 802.11 stations (STAs)." | REVISED. Incorporate the changes in Doc. 11-15/418r0. | EDITOR | Clause 1 | [5 empty] | 2015-03-10 09:39 | EDITOR
1493 | Richard Roy | 208 | 1 | 1 | 5 | 2 | T | Y | 5.02 | 2 | 1 |  |  | Emily Qi, Dan Gal |  |  | Text reads: "This amendment of IEEE 802 Std 802.11 defines one medium access control (MAC) and several physical layer (PHY) specifications for wireless connectivity for fixed, portable, and moving stations (STAs) within a local area. It defines modifications to the IEEE 802.11 standard, above the physical layer (PHY), to enable delivery of pre-association service discovery information by IEEE 802.11 stations (STAs)" | Change to: "This amendment of IEEE 802 Std 802.11 defines modifications to the IEEE 802.11 standard, above the physical layer (PHY), to enable delivery of pre-association service discovery information to IEEE 802.11 stations (STAs)." | REVISED. Incorporate the changes in Doc. 11-15/418r0. | EDITOR | Clause 1 | [5 empty] | 2015-03-09 18:14 | EDITOR
1492 | Richard Roy | 208 | 1 |  | 2 | 6 | T | Y | 2.06 | 6 |  |  |  | Emily Qi, Dan Gal |  |  | Text reads: "This standard defines one medium access control (MAC) and several physical layer (PHY) specifications for wireless connectivity for fixed, portable, and moving stations (STAs) within a local area. It defines modifications to the IEEE 802.11 standard, above the physical layer (PHY), to enable delivery of pre-association Service Discovery information by IEEE 802.11 stations (STAs)." but the standard does not define a MAC or a PHY. | Change to: "This standard defines modifications to the IEEE 802.11 standard, above the physical layer (PHY), to inform IEEE 802.11 stations (STAs), prior to association, of the availability of one or more user services." | REVISED. Incorporate the changes in Doc. 11-15/418r0. | EDITOR | Clause 1 | [5 empty] | 2015-03-09 19:33 | EDITOR
1466 | Jon Rosdahl | 208 | 1 | 1 | 5 | 2 | G | Y | 5.02 | 2 | 1 |  |  | Emily Qi, Dan Gal |  |  | Overview and Scope have been swapped. | Swap the Overview and Scope Paragraphs to proper locations. | REVISED. Incorporate the changes in Doc. 11-15/418r0. | EDITOR | Clause 1 | [5 empty] | 2015-03-09 18:14 | EDITOR
1392 | Santosh Abraham | 208 | 1 | 1.1,1.2 | 5 |  | E | Y | 5 |  | 1.1,1.2 |  |  | Emily Qi, Dan Gal |  |  | The text is not written as an amendment to current 802.11 spec | Rewrite text as amendments to current 802.11 spec text | REVISED. Incorporate the changes in Doc. 11-15/418r0. | EDITOR | Clause 1 | [5 empty] | 2015-03-11 17:47 | EDITOR
1370 | Mark Hamilton | 208 | 1 | 1 | 5 | 2 | T | Y | 5.02 | 2 | 1 |  |  | Emily Qi, Dan Gal |  |  | This amendment does NOT define a MAC and several PHYs. This amendment really does not need to amend clause 1 of 802.11 at all. | Delete all this material that looks like amendment to 802.11 clause 1, but really isn't. Or, move it to the amendment specific introductory material section on page 2. | REVISED. Incorporate the changes in Doc. 11-15/418r0. | EDITOR | Clause 1 | [5 empty] | 2015-03-09 18:14 | EDITOR
1338 | Lei Wang | 208 | 1 | 1 | 5 | 2 | T | Y | 5.02 | 2 | 1 |  |  | Emily Qi, Dan Gal |  |  | The sentence in line 2 page 5 is not correct. 11aq amendment does not define one MAC and multiple PHYs. Checked with 11ah and 11ai draft spec, no such statement. | Delete the entire paragraph in line 2 page 5, as the 2nd sentence is alreay in section 1.1. | REVISED. Incorporate the changes in Doc. 11-15/418r0. | EDITOR | Clause 1 | [5 empty] | 2015-03-09 18:14 | EDITOR
1549 | Emily Qi | 208 | 1 | 1 | 5 | 1 | E | Y | 5.01 | 1 | 1 |  |  | Emily Qi, Dan Gal |  |  | It appears that Clause 1 Overview is copied from 802.11mc D4.0 and there is no change. Therefore, it shall be removed. | Remove clause 1. | REVISED. Incorporate the changes in Doc. 11-15/418r0. | EDITOR | Clause 1 | [5 empty] | 2015-03-11 17:46 | EDITOR
1299 | Tomoko Adachi | 208 | 1 | 1 | 5 | 4 | T | Y | 5.04 | 4 | 1 |  |  | Emily Qi, Dan Gal |  |  | Section 1 should be an overview of the overall 802.11 standard, not this amendment. | Delete section 1. | REVISED. Incorporate the changes in Doc. 11-15/418r0. | EDITOR | Clause 1 | [5 empty] | 2015-03-09 18:14 | EDITOR
1041 | Adrian Stephens | 208 | 1 | 1 | 5 | 2 | E | Y | 5.02 | 2 | 1 |  |  | Emily Qi, Dan Gal |  |  | "This amendment of IEEE 802 Std 802.11 defines one medium access control (MAC) and several physical 2 layer (PHY) specifications". No, it doesn't. And it never will. You do not get to modify the 802.11 scope and purpose statements without modifying the 802.11 PAR. Everything after the Title Page is an instruction to modify the baseline. The word "amendment" should not occur. | Remove any occurences of "amendment" from page 5 onward. Remove 1.1 and 1.2. Consider adding to 1.3. Optionally reproduce scope and purpose from the PAR in the frontmatter. | REVISED. Incorporate the changes in Doc. 11-15/418r0. | EDITOR | Clause 1 | [5 empty] | 2015-03-11 17:46 | EDITOR

## Clause 6
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1624 | Robert Slater | 208 | 1 | 6.3.11.2 | 7 | 20 | T | Y | 7.2 | 20 | 6.3.11.2 |  |  | Emily Qi, Robert Slater |  |  | MLME-Start.request primitive requires entries for Service Hint, Service Advertisement, Service Hash, and Supported ULP elements | Add Section 6.3.11.2 and add new parameter and table entry to the end of the existing parameters as specified | REVISED. Incorporate the changes in Doc. 11-15/412r2. | EDITOR | Clause 6 | [5 empty] | 2015-03-09 19:26 | EDITOR
1623 | Robert Slater | 208 | 1 | 6.3.3.3 | 7 | 20 | T | Y | 7.2 | 20 | 6.3.3.3 |  |  | Emily Qi, Robert Slater |  |  | MLME-Scan.confirm primitive requires entries for the Service Hint, Service Advertisement, Service Hash, and Supported ULP elements | Add Section 6.3.3.3 and add new parameter and table entry to the end of the existing parameters as specified | REVISED. Incorporate the changes in Doc. 11-15/412r2. | EDITOR | Clause 6 | [5 empty] | 2015-03-09 18:32 | EDITOR
1622 | Robert Slater | 208 | 1 | 6.3.3.2 | 7 | 20 | T | Y | 7.2 | 20 | 6.3.3.2 |  |  | Emily Qi, Robert Slater |  |  | MLME-Scan.request primitive requires an entry for the Service Hash element | Add Section 6.3.3.2 and add new parameter and table entry to the end of the existing parameters as specified | REVISED. Incorporate the changes in Doc. 11-15/412r2. | EDITOR | Clause 6 | [5 empty] | 2015-03-09 18:31 | EDITOR
1556 | Emily Qi | 208 | 1 | 6 |  |  | T | Y |  |  | 6 |  |  | Emily Qi, Robert Slater |  |  | Clause 6 is missing. MLME primitives for PAD should be defined in clause 6. | Add MLME primitives for PAD in Clause 6. | REVISED. Incorporate the changes in Doc. 11-15/412r2. | EDITOR | Clause 6 | [5 empty] | 2015-03-09 18:30 | EDITOR
1240 | Michael Montemurro | 208 | 1 | 6 | 8 | 1 | T | Y | 8.01 | 1 | 6 |  |  | Emily Qi, Robert Slater |  |  | The MLME primitives are missing. All Clause 6 modifications are missing. | Add the appropriate sub-clauses to Clause 6 to cover the PAD protocol. | REVISED. Incorporate the changes in Doc. 11-15/412r2. | EDITOR | Clause 6 | [5 empty] | 2015-03-09 18:30 | EDITOR
1168 | Jarkko Kneckt | 208 | 1 | 6.3.3.3.2 |  |  | T | Y |  |  | 6.3.3.3.2 |  |  | Emily Qi, Robert Slater |  |  | How the new elements are listed in BSSDescriptionSet? | Add information how the new element values are provided through BSSDescriptionSet. | REVISED. Incorporate the changes in Doc. 11-15/412r2. | EDITOR | Clause 6 | [5 empty] | 2015-03-09 19:22 | EDITOR
1167 | Jarkko Kneckt | 208 | 1 | 6.3.3. |  |  | T | Y |  |  | 6.3.3. |  |  | Emily Qi, Robert Slater |  |  | The use of the new information elements should be described in MLME-scanning operations. How they are used? | Add information how the new elements and PAD is used through MLME queries. | REVISED. Incorporate the changes in Doc. 11-15/412r2. | EDITOR | Clause 6 | [5 empty] | 2015-03-09 19:22 | EDITOR
1060 | Adrian Stephens | 208 | 1 | Clause 6 |  |  | T | Y |  |  | Clause 6 |  |  | Emily Qi, Robert Slater |  |  | There are no changes shown to the MLME-SAP interface. There certainly should be changes shown where the Beacon and Probe Response contains PAD data. There might also be specific interfaces to support other exchanges, or the ANQP interfaces defined in TGu might suffice. This is a glaring omission, and fails to meet the criteria for "ready for ballot" that the 802.11 OM describes. | Add changes for Clause 6. | REVISED. Incorporate the changes in Doc. 11-15/412r2. | EDITOR | Clause 6 | [5 empty] | 2015-03-09 19:20 | EDITOR

## Clause 8.3
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1333 | Yongho Seok | 208 | 1 | 8.4.2.173 | 10 | 31 | T | Y | 10.31 | 31 | 8.4.2.173 |  |  | Robert Slater |  |  | "The Service Hash element consists of Service Hash Values. The Service Hash element may be included in the Beacon and the Probe Request frames." | Please add the row for the Service Hash element in Table 8-27--Beacon frame body and Table 8-33--Probe Request frame body. | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-11 17:56 | EDITOR
1304 | Tomoko Adachi | 208 | 1 | 8.4.2.171 | 9 | 12 | T | Y | 9.12 | 12 | 8.4.2.171 |  |  | Robert Slater |  |  | Why can't the Service Hint element be in probe responses? | Change the sentence in l.12 to read "... Beacon frames and Probe Response frames." | ACCEPTED. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-11 17:52 | EDITOR
1306 | Tomoko Adachi | 208 | 1 | 8.4.2.173 | 10 | 32 | T | Y | 10.32 | 32 | 8.4.2.173 |  |  | Robert Slater |  |  | Why can't the Service Hash element be in probe responses? | Add Probe Response frames to the first sentence in 8.4.2.173. | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-11 17:56 | EDITOR
1158 | Jarkko Kneckt | 208 | 1 | 8.4.2.171 | 9 | 12 | T | Y | 9.12 | 12 | 8.4.2.171 |  |  | Robert Slater |  |  | The Service Hints element should be possible to use in Probe Response frames too. The probe response can contain at least the same information as the beacon frame. Also the group addressed probe response frame will be received similarly as the Beacon frame. | Allow the Service Hint element usage also in Probe Response frames. | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-11 17:52 | EDITOR
1165 | Jarkko Kneckt | 208 | 1 | 8.4.2.172 | 10 | 32 | T | Y | 10.32 | 32 | 8.4.2.172 |  |  | Robert Slater |  |  | The Service Hash element should be possible to use in Probe Response frames too. The probe response can contain at least the same information as the beacon frame. Also the group addressed probe response frame will be received similarly as the Beacon frame. | Allow the Service Hash element usage also in Probe Response frames. | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-11 17:55 | EDITOR
1166 | Jarkko Kneckt | 208 | 1 | 8.3.3.4 |  |  | T | Y |  |  | 8.3.3.4 |  |  | Robert Slater |  |  | The content of the Beacon and Probe Response frames are not shown. The structure of the frames with new elements should be shown. | Add the new elements to the Beacon and Probe Response frames. Show their order and information in the frames. | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-09 19:31 | EDITOR
1232 | Michael Montemurro | 208 | 1 | 8.4.2.171 | 9 | 12 | T | Y | 9.12 | 12 | 8.4.2.171 |  |  | Robert Slater |  |  | The cited sentence indicates that the Service Hint element is included in Beacon frames. However the presense of the element is not included in clause 8.3.3.2. | Add this element to the table in clause 8.3.3.2 | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-11 17:52 | EDITOR
1233 | Michael Montemurro | 208 | 1 | 8.4.2.171 | 9 | 12 | T | Y | 9.12 | 12 | 8.4.2.171 |  |  | Robert Slater |  |  | The cited sentence does not include the element in probe responses. Depending on the implementation, a STA may miss this information in the pre-associated state. | If this element is in the beacon, it should be at least included (optionally) in the Probe Response. Update the text at the cited location and update the table in 8.3.3.10. | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-11 17:52 | EDITOR
1123 | Filip Mestanov | 208 | 1 | 8.4.2.173 | 10 | 31 | E | N | 10.31 | 31 | 8.4.2.173 |  |  | Robert Slater |  |  | "The Service Hash element consists of Service Hash Values. The Service Hash element may be included in the Beacon and the Probe Request frames." | Change to "The Service Hash element consists of Service Hash Values. The Service Hash element may be included in Beacon and Probe Request frames." | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 |  | Clause 8 should not include normative text ("shall", "should", "may"). Recommand to change "may be" to "is". |  |  |  | 2015-03-11 17:56 | EDITOR
1332 | Yongho Seok | 208 | 1 | 8.4.2.172 | 10 | 9 | T | Y | 10.09 | 9 | 8.4.2.172 |  |  | Robert Slater |  |  | "The Service Advertisement element is included in the Probe Response returned by the AP in response to a Probe Request from a non-AP STA that has one or more matching Service Hashes." | Please add the row for the Service Advertisement element in Table 8-34--Probe Response frame body. | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-11 17:55 | EDITOR
1627 | Robert Slater | 208 | 1 | 8.3.3.10 | 8 | 2 | T | Y | 8.02 | 2 | 8.3.3.10 |  |  | Robert Slater |  |  | Probe Response frame format description requires entries for Service Advertisement and Supported ULP | Add Section 8.3.3.10 and add new entries to the end of table 8-34 as specified | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-09 19:31 | EDITOR
1334 | Yongho Seok | 208 | 1 | 8.4.2.174 | 11 | 7 | T | Y | 11.07 | 7 | 8.4.2.174 |  |  | Robert Slater |  |  | "The Supported Upper Layer Protocol (ULP) element is used to indicate the ULP supported by the AP. The Supported ULP element may be included in the Beacon frame and the Probe Response frame." | Please add the row for the Supported ULP element in Table 8-27--Beacon frame body and Table 8-34--Probe Response frame body. | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-11 17:57 | EDITOR
1366 | Jouni Malinen | 208 | 1 | 8.4.2.173 | 10 | 32 | T | N | 10.32 | 32 | 8.4.2.173 |  |  | Robert Slater |  |  | Normally Beacon and Probe Response frames are allowed to include same set of elements. However, Service Hash element is described as being included only in Beacon and Probe Request frames which seems to imply that it would not be included in Probe Response frames. That looks undesirable for active scanning. | Replace "included in the Beacon and the Probe Request frames" with "included in Beacon, Probe Request, and Probe Response frames". | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-11 17:56 | EDITOR
1377 | Mark Hamilton | 208 | 1 | 8.4.2.171 | 9 | 12 | T | Y | 9.12 | 12 | 8.4.2.171 |  |  | Robert Slater |  |  | If the Service Hint element is in Beacons, there needs to be a row added to Table 8-27 in subclause 8.3.3.2 for it. | Add text that amends 8.3.3.2 to add this elemnet to the Beacon Format table. Same thing for Service Hash and Supported ULP element. | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-11 17:52 | EDITOR
1378 | Mark Hamilton | 208 | 1 | 8.4.2.172 | 10 | 10 | T | Y | 10.1 | 10 | 8.4.2.172 |  |  | Robert Slater |  |  | If the Service Advertisement element is in Probe Response, there needs to be a row added to Table 8-34 in subclause 8.3.3.10 for it. | Add text that amends 8.3.3.10 to add this element to the Probe Response format Table. Same thing for ULP Supported element. | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-11 17:55 | EDITOR
1379 | Mark Hamilton | 208 | 1 | 8.4.2.173 | 10 | 32 | T | Y | 10.32 | 32 | 8.4.2.173 |  |  | Robert Slater |  |  | If the Servic eHash element is in Probe Requests, there needs to be a row added to Table 8-33 in subclause 8.3.3.9 for it. | Add text that amends 8.3.3.9 to add this element to the Probe Request format Table. | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-11 17:56 | EDITOR
1431 | Matthew Fischer | 208 | 1 | 8.3.3.2 | 8 | 2 | T | Y | 8.02 | 2 | 8.3.3.2 |  |  | Robert Slater |  |  | in all previous amendments, whenever an IE is created and allowed to be included within a frame, that IE is listed in the frame body contents in the frame fomat subclause - Tgaq has not followed this convention | add subclauses for beacon, probe request and probe response formats that show additional frame body contents for the new Tgaq elements | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-09 19:31 | EDITOR
1625 | Robert Slater | 208 | 1 | 8.3.3.2 | 8 | 2 | T | Y | 8.02 | 2 | 8.3.3.2 |  |  | Robert Slater |  |  | Beacon frame format description requires entries for Service Hint, Service Hash, and Supported ULP information | Add Section 8.3.3.2 and add new entries to the end of Table 8-27 as specified | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-09 19:31 | EDITOR
1626 | Robert Slater | 208 | 1 | 8.3.3.9 | 8 | 2 | T | Y | 8.02 | 2 | 8.3.3.9 |  |  | Robert Slater |  |  | Probe request frame format description requires entry for Service Hash | Add Section 8.3.3.9 and add new entry to the end of table 8-33 as specified | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-09 19:31 | EDITOR
1329 | Yongho Seok | 208 | 1 | 8.4.2.171 | 9 | 11 | T | Y | 9.11 | 11 | 8.4.2.171 |  |  | Robert Slater |  |  | "The Service Hint element is transmitted in beacons." | Please add the row for the Service Bint element in Table 8-27--Beacon frame body. | REVISED. Incorporate the changes in Doc. 11-15/419r3. | EDITOR | Clause 8.3 | [5 empty] | 2015-03-11 17:52 | EDITOR

## Clause 10.25.3.4.4
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1400 | Koichi Ishihara | 208 | 1 | 10.25.3.4.4 | 20 | 14 | G | N | 20.14 | 14 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | No text for this subclause. | Please add text for this subclause. | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also potentially duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1020 | Katsuo Yunoki | 208 | 1 | 10.25.3.4.4 | 20 | 14 | G | Y | 20.14 | 14 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | Clause is empty |  | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | No proposed changes. |  |  |  | 2015-03-09 19:07 | EDITOR
1024 | Zhongding Lei | 208 | 1 | 10.25.3.4.4 | 20 | 13 | T | N | 20.13 | 13 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | content is missing | Add in details | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also potentially duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1033 | Yongho Seok | 208 | 1 | 10.25.3.4.4 | 20 | 13 | T | Y | 20.13 | 13 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | PAD encapsulation protocol procedures is empty. Please complete the protocol description or delete this sub-clause. | As suggested by comment. | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1064 | Adrian Stephens | 208 | 1 | 10.25.3.4.4 | 20 | 13 | G | Y | 20.13 | 13 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | This subclause is just a little uninformative. | Remove it | ACCEPTED. | EDITOR | Clause 10.25.3.4.4 |  | Recommand to accept the proposed changes but for slightly different reasons. |  |  |  | 2015-03-09 19:07 | EDITOR
1292 | Stephen McCann | 208 | 1 | 10.25.3.4.4 | 20 | 13 | T | Y | 20.13 | 13 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | This clause needs to be completed or deleted. It's possibly a duplicate of 10.25.3.2.11.3 above, the ULP encapsulation ANQP-element. | Either remove or complete this sub-clause | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | The commenter is correct. |  |  |  | 2015-03-09 19:07 | EDITOR
1320 | Tomoko Adachi | 208 | 1 | 10.25.3.4.4 | 20 | 14 | T | Y | 20.14 | 14 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | Nothing written in 10.25.3.4.4. | Describe the PAD encapsulation protocol procedures in 10.25.3.4.4. | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1223 | Ganesh Venkatesan | 208 | 1 | 10.25.3.4.4 | 20 | 13 | E | N | 20.13 | 13 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | Empty Sub-Clause | Either delete this sub clause or add details on ULP Encapsulation procedure here. | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-10 09:50 | EDITOR
1238 | Michael Montemurro | 208 | 1 | 10.25.3.4.4 | 20 | 20 | T | Y | 20.2 | 20 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | PAD encapsulation protocol procedures sub-clause is empty. | Either specify a procedure or remove the sub-clause | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1536 | Richard Roy | 208 | 1 | 10.25.3.4.4 | 20 | 13 | T | Y | 20.13 | 13 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | Clause 10.25.3.4.4 is empty. | Add appropriate text. | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1351 | Lei Wang | 208 | 1 | 10.25.3.4.4 | 20 | 13 | T | Y | 20.13 | 13 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | empty section | either fill in the text or delete the section. | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1009 | Graham Smith | 208 | 1 | 10.25.3.4.4 | 27 | 13 | T | Y | 27.13 | 13 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | 10.25.3.4.4 PAD encapsulation protocol procedures - there ain't any? | Are there any procedures? If not delete clause, if there are, add them/. | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1383 | Mark Hamilton | 208 | 1 | 10.25.3.4.4 | 20 | 14 | T | Y | 20.14 | 14 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | Is this section supposed to have content? | Add the content of this subclause. It seems that much or all of the material in the Annez Za should actually be here. | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | First, Annex Za provides some graphic examples of mixed Unsolicited PAD and Solicited PAD, but none are related to ULP Encapsulation procedure. Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure).. Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1695 | David Hunter | 208 | 1 | 10.25.3.4.4 | 20 | 14 | T | Y | 20.14 | 14 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | Either this empty normative subclause is a mistake or this draft is incomplete (and therefore it is incorrect to call it "Draft D1.0"). | Delete heading 10.25.3.4.4 | ACCEPTED. | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1409 | Jouni Malinen | 208 | 1 | 10.25.3.4.4 | 20 | 14 | T | Y | 20.14 | 14 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | No contents in 10.25.3.4.4 PAD encapsulation protocol procedures. | Either remove the empty clause or fill in the description of PAD encapsulation protocol procedures. | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1430 | Matthew Fischer | 208 | 1 | 10.25.3.4.4 | 20 | 13 | T | Y | 20.13 | 13 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | empty subclause is not allowed | delete the empty subclause or fill it with meanginful normative text | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1444 | Yunsong Yang | 208 | 1 | 10.25.3.4.4 | 20 | 13 | T | N | 20.13 | 13 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | Is this subclause duplicated with 10.25.3.2.11.3? If there is no unique content in the subclause, it should be deleted. | Delete 10.25.3.4.4. | ACCEPTED. | EDITOR | Clause 10.25.3.4.4 |  | The commenter is correct. |  |  |  | 2015-03-09 19:07 | EDITOR
1483 | Guido Hiertz | 208 | 1 | 10.25.3.4.4 | 20 | 13 | T | Y | 20.13 | 13 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | Is 10.25.3.4.4 completely empty? Then delete the subclause | Delete 10.25.3.4.4 | ACCEPTED. | EDITOR | Clause 10.25.3.4.4 |  | The commenter is correct. |  |  |  | 2015-03-09 19:07 | EDITOR
1572 | Xiaofei Wang | 208 | 1 | 10.25.3.4.4 | 20 | 14 | T | Y | 20.14 | 14 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | The PAD encapsulation procedure is missing | add the procedure | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1599 | Joseph Levy | 208 | 1 | 10.25.3.4.4 | 20 | 13 | T | Y | 20.13 | 13 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | There are no procedures association with PAD encapsulation protocol procedures | provide a procedure | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1602 | Tom Kolze | 208 | 1 | 10.25.3.4.4 | 20 | 13 | T | Y | 20.13 | 13 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | empty subclause is not allowed | delete the empty subclause or fill it with drivel or normative text | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1605 | Cheol Ryu | 208 | 1 | 10.25.3.4.4 | 20 | 13 | T | Y | 20.13 | 13 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | The procedure of PAD encapsulation protocol has no description. | Provide PAD encapsulation protocol procedures. | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1607 | Yuro Lee | 208 | 1 | 10.25.3.4.4 | 20 | 13 | T | Y | 20.13 | 13 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | Pad encapsulation protocol procedures has not description. | Add PAD encapsulation protocol procedures. | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1637 | Robert Slater | 208 | 1 | 10.25.3.4.4 | 20 | 14 | T | Y | 20.14 | 14 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | Section 10.25.3.4.4 is empty | Chair and/or editor should solicit contributions for text for this section | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR
1360 | Yasuhiko Inoue | 208 | 1 | 10.25.3.4.4 | 20 | 14 | G | Y | 20.14 | 14 | 10.25.3.4.4 |  |  | Yunsong Yang |  |  | No text for this subclause. | Add text for this subclause. | REVISED. Remove clause 10.25.3.4.4 due to duplication with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). | EDITOR | Clause 10.25.3.4.4 |  | Clause 10.25.3.4.4 is empty and also duplicated with clause 10.25.3.2.11.3 (ULP Encapsulation procedure). Recommand to remove the clause. |  |  |  | 2015-03-09 19:07 | EDITOR

## Miscellaneous1
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1324 | Tomoko Adachi | 208 | 1 | General |  |  | E | N |  |  | General |  |  | Stephen McCann |  |  | The numbers of the tables that already exist seem not matching... | Check the numbers of the tables that already exist with the baselines throughout the draft. | ACCEPTED. Editor will exercise accordingly. | EDITOR | Miscellaneous | [5 empty] | 2015-03-10 09:55 | EDITOR
1145 | Jarkko Kneckt | 208 | 1 | 3-Jan | 6 | 5 | T | Y | 6.05 | 5 | 3-Jan |  |  | Stephen McCann |  |  | Definition of the application is unclear. To me an application is a active operator that causes the device to operate in programmed or commanded way. The current definition suggests that application is just the software (code?) that is stored to mass memory. | Clarify the definition of the application. | REVISED. Remove the definition of "application" on P6L5. | EDITOR | Miscellaneous | [5 empty] | 2015-03-09 19:41 | EDITOR
1148 | Jarkko Kneckt | 208 | 1 | 3-Jan | 6 | 5 | T | N | 6.05 | 5 | 3-Jan | 1145 |  | Stephen McCann |  |  | Why the task that an application perform needs to be useful? | Please clarify. | REVISED. Remove the defintion of "application" on P6L5. | EDITOR | Miscellaneous | [5 empty] | 2015-03-09 19:41 | EDITOR
1149 | Jarkko Kneckt | 208 | 1 | 3-Jan | 6 | 10 | T | Y | 6.1 | 10 | 3-Jan |  |  | Stephen McCann |  |  | The definition of the service is not easy-to-understand. Why processes need to be part of the service definition? Many examples highlight very different types of services, could these types be part of the definition? | Please clarify the service in a simple easy to understand definition. | REVISED. Remove the definition of "service" on P6L10. It is already defined in IEEE 100. | EDITOR | Miscellaneous | [5 empty] | 2015-03-09 19:41 | EDITOR
1426 | Matthew Fischer | 208 | 1 |  |  |  | T | Y | [5 empty] | Stephen McCann |  |  | lots of extra commas throughout the document | there are extraneous commas everywhere | ACCEPTED. Editor will exercise accordingly. | EDITOR | Miscellaneous | [5 empty] | 2015-03-09 19:41 | EDITOR
1491 | Richard Roy | 208 | 1 |  |  |  | E | Y | [5 empty] | Stephen McCann |  |  | Information is "delivered to STAs" rather than "delivered by STAs". | Throughout the doc, change "delivered ... by" to "delivered ... to" where appropriate. | ACCEPTED. Editor will exercise accordingly. | EDITOR | Miscellaneous |  | Propose accept: editorial |  |  |  | 2015-03-10 09:55 | EDITOR
1150 | Jarkko Kneckt | 208 | 1 | 3-Jan | 6 | 14 | T | Y | 6.14 | 14 | 3-Jan |  |  | Stephen McCann |  |  | The service discovery should be able to find any available service without any requirements. The unsolicited service discovery is not part of the service discovery definition. | Please add more descriptions for unsolicited service discovery and possibility to find available services without specific requirements for the service. | REVISED. Change "service discovery: The process of finding services that match the requirements of the service requestor. It includes procedures for querying and browsing for services offered by, or through, another STA." to "service discovery: The process of finding services, including procedures for querying and browsing for services offered by, or through, another STA." | EDITOR | Miscellaneous |  | Discuss |  |  |  | 2015-03-09 19:41 | EDITOR