## Slide 1: IEEE 802.11ah Closing Report for March 2015
Date: 2015-03-12
Authors:

## Slide 2: Abstract
This presentation is the closing report for the Berlin meeting of the IEEE 802.11 TGah.

## Slide 3: Activity in TGah
Letter Ballot 207 for Draft 4.0 closed February 14th
  214 comments received
TGah has completed all comment resolution of the Letter Ballot 207 for Draft 4.0
  15/261 LB207 Comment Spreadsheet
TGah has approved the TGah MDR Report (11-15/247r3)
Instructed the editor to generate Draft 5.0

## Slide 4: Going forward
Start third Recirculation WG Letter Ballot and address comments in May

## Slide 5: Teleconference
April 14, 8PM ET for 2 hour
April 21, 8PM ET for 2 hour
April 28, 8PM ET for 2 hour
May 5, 8PM ET for 2 hour

## Slide 6: TGah Timeline – No Change
Internal Task Group Ballot : May 2013
Initial Letter Ballot : September 2013
Initial Recirculation Letter Ballot : September 2014
Initial Sponsor Ballot : July 2015
Initial Recirculation Sponsor Ballot : November 2015
EC Approval : January 2016
Revcom Approval : March 2016

## Slide 7: Motion 5
Having approved comment resolutions for all of the comments received from LB207 on P802.11ah D4.0
Instruct the TGah editor to prepare P802.11ah D5.0 from incorporating these resolutions and changes approved by TGah at this session and
Approve a 15 day Working Group Recirculation Ballot asking the question “Should P802.11ah D5.0 be forwarded to Sponsor Ballot?”
Moved: Menzo Wentink
Seconded: Chittabrata Ghosh
Result: Motion Passed (Yes 10 No 0 Abstain 1)