## Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
7026 | David Hunter | 211 | 5 | 3.2 | 4 | 50 | E | Y | 4.5 | 50 | 3.2 |  |  | Zander |  |  | "A non-sensor STA may not": normative term used in a definition. | Replace "may" with "might". Also delete the extraneous "as" on line 51. | Rejected- The standards will be professionally edited prior to publication, and it may be rephrased if needed in the next draft of this amendment. | [7 empty] | 2015-04-17 10:25
7027 | David Hunter | 211 | 5 | 3.2 | 5 | 37 | E | Y | 5.37 | 37 | 3.2 |  |  | Yongho |  |  | "or an RPS element.": each acronym needs to be defined in each definition. | Replace "an RPS element" with "a restricted access window (RAW) parameter set (RPS) element". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7028 | David Hunter | 211 | 5 | 3.2 | 6 | 29 | E | Y | 6.29 | 29 | 3.2 |  |  | Yongho |  |  | "to wake to exchange frames": it would be clearer to say "wake in order to". | Replace "to wake to exchange" with "to wake in order to exchange frames with other STAs". Or perhaps "to wake for frame exchange with other STAs." | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7029 | David Hunter | 211 | 5 | 4.3.13a.1 | 10 | 26 | E | Y | 10.26 | 26 | 4.3.13a.1 |  |  | Zander |  |  | "enable either reducing the energy consumption of an STA or increasing the achievable range between an S1G AP and an S1G non-AP STA.": reducing and increasing are not the sorts of things that can be enabled -- though reduction and increase can. Wouldn't it be more accurate to say "usable" rather than "achievable"? And, since the first half is just about a STA, why not make the rest about an AP and a non-AP STA (note that no claims are being made about every AP and STA, just some of them)? | "enable either reducing the energy consumption of a STA"or increasing the achievable range between an S1G AP and an S1G non-AP STA." with " work to either reduce a STA's energy consumption or increase the usable range between an AP and a non-AP STA. " | Rejected- The standards will be professionally edited prior to publication, and it may be rephrased if necessary in the next draft of this amendment. | [7 empty] | 2015-04-17 10:25
7030 | David Hunter | 211 | 5 | 4.3.13a.1 | 10 | 28 | E | Y | 10.28 | 28 | 4.3.13a.1 |  |  | Yongho |  |  | "The S1G AP can provide either or both of sensor services and offloading services.": don't need "either or both of" -- no one would assume that these two would be required to be linked. | Delete "either or both of". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7031 | David Hunter | 211 | 5 | 4.3.13a.1 | 10 | 31 | E | Y | 10.31 | 31 | 4.3.13a.1 |  |  | Zander |  |  | "An S1G STA is also a QoS STA, but does not support HCCA. An S1G STA is a non-mesh STA.": clearer to put into one sentence. | Replace "An S1G STA is also a QoS STA, but does not support HCCA. An S1G STA is a non-mesh STA." with "An S1G STA is not a mesh STA, but is a QoS STA (though it does not support HCCA)." | Rejected- The standards will be professionally edited prior to publication, and it may be rephrased if necessary in the next draft of this amendment. | [7 empty] | 2015-04-17 10:25
7032 | David Hunter | 211 | 5 | 4.3.13a.2 | 10 | 36 | E | Y | 10.36 | 36 | 4.3.13a.2 |  |  | Yongho |  |  | "S1G Relay is a mechanism that allows to increase the coverage area of an AP,": the name of a mechanism does not take initial caps, and "that allows to increase" is broken English. Replace this text. | Replace "S1G Relay is a mechanism that allows to increase the coverage area of an AP," with "S1G relay is a mechanism for expanding the coverage area of an AP." | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7033 | David Hunter | 211 | 5 | 4.3.13a.2 | 10 | 36 | E | Y | 10.36 | 36 | 4.3.13a.2 |  |  | Yongho |  |  | "the coverage area of an AP, which is referred to as the root AP." So the coverage area of an AP is called "the root AP"? If it is not the coverage area, then exactly when is an AP called a "root AP"? Is every relay AP a root AP? | Need a clear description (in separate sentences from the "S1G Relay" statement) of the conditions for an AP to be a root AP. | Rejected- The comment fails to identify a specific issue to be addressed. It fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | [7 empty] | 2015-04-17 10:25
7034 | David Hunter | 211 | 5 | 4.3.13a.2 | 10 | 42 | E | Y | 10.42 | 42 | 4.3.13a.2 |  |  | Alfred |  |  | "using a 4-address frame or using an A-MSDU.": the second "using" is unnecessary. | On lines 42 and 49 replace "or using an A-MSDU." with "or an A-MSDU." | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7035 | David Hunter | 211 | 5 | 4.3.13a.2 | 10 | 52 | E | Y | 10.52 | 52 | 4.3.13a.2 |  |  | Alfred |  |  | "MAC header (PV0 or PV1)": this is the first use of "PV0" and "PV1" in the text, so both need definitions ( "protocol version 0 (PV0)" ). However, that is not sufficient for this introductory clause. The meanings of "protocol version 0" and "protocol version 1" need to be stated first. | Either provide a brief introduction to "protocol version" or delete "(PV0 or PV1)". | Rejected -- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. In addition, please note that the draft already contains, both the definitions (in subclause 3.2) and acronyms (in subclause 3.4) for these two terms. | [7 empty] | 2015-04-17 10:25
7036 | David Hunter | 211 | 5 | 5.1.5.6 | 10 | 26 | E | Y | 10.26 | 26 | 5.1.5.6 |  |  | Alfred |  |  | "A relay AP is an AP which offers": which/that problem. | Replace "which" with "that". | Rejected -- According to the IEEE SA Style guide: "That is best reserved in essential (or restrictive) clauses; which is appropriate in nonessential (or nonrestrictive) parenthetical clauses. Simply stated, if a comma can be inserted before the word that or which, the word should be which. If a comma would not be used, the word to use is that." As suggested by the style guide, in the sentence pointed out by the commenter a comma can be inserted before the "which" as follows: "A relay AP is an AP, which offers the relay function to its associated non-AP STAs, and provides access to the DS indirectly through the relay STA's path to the root AP." However, the comma is not required. | [7 empty] | 2015-04-17 10:25
7037 | David Hunter | 211 | 5 | 5.1.5.6 | 10 | 28 | E | Y | 10.28 | 28 | 5.1.5.6 |  |  | Alfred |  |  | "based on destination address as described": missing an article and a comma. | Replace "based on destination address as described" with "based on the destination address, as described". | Rejected- The current terminology is correct as it specifies that a certain function is performed based on destination address with the respective subclause describing the normative behavior being provided in the referenced subclause. | [7 empty] | 2015-04-17 10:25
7038 | David Hunter | 211 | 5 | 5.1.2 | 11 | 11 | T | Y | 11.11 | 11 | 5.1.2 |  |  | Alfred |  |  | "An S1G STA shall not": normative requirement in a definitons clause (and is not part of the meaning of a definition). | Replace "shall" with "does". If this requirement is needed in the standard, move it to a normative clause (such as clause 11). | Rejected -- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. Also please note that the same terminology can be found in multiple instances ofthe same subclause of REVmc D4.0, e.g., in P130L4: "A STA that has associated with management frame protection enabled shall not use pairwise cipher suite selectors WEP-40, WEP-104, TKIP, or “Use Group cipher suite.”" | [7 empty] | 2015-04-17 10:25
7039 | David Hunter | 211 | 5 | 6.3.2.2.2 | 13 | 38 | E | Y | 13.38 | 38 | 6.3.2.2.2 |  |  | Alfred |  |  | "For an S1G STA, this parameter is set to": sounds like this process is something done by some other entity to accommodate an S1G STA. Presumably this action is done by the S1G STA itself. | Replace "For an S1G STA, this parameter" with "In an S1G STA this parameter" | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7040 | David Hunter | 211 | 5 | 6.3.2.2.2 | 13 | 40 | E | Y | 13.4 | 40 | 6.3.2.2.2 |  |  | Yongho |  |  | "to awaken to receive Beacon frame as determined by": missing an article and a comma. | Replace "receive Beacon frame as determined bby" with "receive a Beacon frame, as determined by". On line 46 replace "frame as" with "frame, as". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7041 | David Hunter | 211 | 5 | 6.3.4.2.4 | 20 | 16 | T | Y | 20.16 | 16 | 6.3.4.2.4 |  |  | Yongho |  |  | "primitive shall contain a ResultCode": normative requirement in a definition (and is not part of the meaning of the defined term). | Replace "shall contain" with "contains". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7042 | David Hunter | 211 | 5 | 6.3.5.2.3 | 20 | 37 | T | Y | 20.37 | 37 | 6.3.5.2.3 |  |  | Yongho |  |  | "shall not generate this primitive.": normative requirement in a definition (and is not part of the meaning of the defined term). | Replace "shall" with "does". If this requirement is needed in the standard, move it to a normative clause. | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7043 | David Hunter | 211 | 5 | 6.3.11.2.4 | 41 | 45 | T | Y | 41.45 | 45 | 6.3.11.2.4 |  |  | Yongho |  |  | "primitive shall contain a ResultCode": normative requirement in a definition (and is not part of the meaning of the defined term). | Replace "shall contain" with "contains". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7044 | David Hunter | 211 | 5 | 6.3.104.3.2 | 44 | 30 | T | Y | 44.3 | 30 | 6.3.104.3.2 |  |  | Yongho |  |  | "On receipt of this primitive, the SME should operate according to": this is a normative statement that applies to operations but is being stated in a definition (and is not just part of the meaning of a defined term). | On line 30, page 45 line 28, page 47 line 61, page 49 line 23, page 50 line 49, page 52 line 23, page 54 lines 11 and 55, page 56 line 63, page 58 line 22, page 60 line 31, page 61 line 27, page 63 line 38, page 65 lines 3 and 47, page 67 line 50, and page 68 line 24 replace "SME should operate" with "SME operates". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7045 | David Hunter | 211 | 5 | 8.4.2.209 | 183 | 39 | E | Y | 183.39 | 39 | 8.4.2.209 |  |  | Yongho |  |  | "the field defined in S1G Capabilities element": doesn't say which field and is missing an article. | Replace "the field defined in S1G" with "the field with the same name that is defined in the S1G". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7046 | David Hunter | 211 | 5 | 8.4.2.210 | 184 | 39 | E | Y | 184.39 | 39 | 8.4.2.210 |  |  | Yongho |  |  | "is set to 1 i... to confirm storing of the": what is confirmed is storage, not the process of storing. | Replace "storing" with "storage". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7047 | David Hunter | 211 | 5 | 8.4.2.210 | 184 | 48 | E | Y | 184.48 | 48 | 8.4.2.210 |  |  | Yongho |  |  | "set to 0 header compression request": typo -- missing words. | Replace "0 header" with "0 in the header" | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7048 | David Hunter | 211 | 5 | 9.2.1 | 233 | 53 | E | Y | 233.53 | 53 | 9.2.1 |  |  | Zander |  |  | Per the IEEE Style Manual, items in a list that are sentences are followed with periods. | Insert periods at the ends of lines 53 and 54. | Rejected- The standards will be professionally edited prior to publication, and "periods" will most likely to be added in the next draft of this amendment. | [7 empty] | 2015-04-17 10:25
7049 | David Hunter | 211 | 5 | 9.2.4.2 | 234 | 61 | E | Y | 234.61 | 61 | 9.2.4.2 |  |  | Yongho |  |  | The 11ah change to 11mc to add "frames" after "Probe Response": this is a mistake. The 11mc version is both clear and better written. | Remove the 11ah addition of "frames". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7050 | David Hunter | 211 | 5 | 9.2.4.2 | 235 | 61 | E | Y | 235.61 | 61 | 9.2.4.2 |  |  | Zander |  |  | "using access category AC_BE by default.": the "by default is almost lost way at the end of this sentence. Insert it at the front to make it clear that this is the default setting. Also, "that is sensor" is missing an article. | Replace "An S1G STA that is sensor STA shall" with "By default an S1G STA that is a sensor STA shall" and repalce "category AC_BE by default." with "category AC_BE." | Rejected- The standards will be professionally edited prior to publication, and it may be rephrased if necessary in the next draft of this amendment. | [7 empty] | 2015-04-17 10:25
7051 | David Hunter | 211 | 5 | 9.2.4.2 | 236 | 1 | E | Y | 236.01 | 1 | 9.2.4.2 |  |  | Zander |  |  | "AC1 subfield if the value of": a longer subordinate clause needs to be separated by a comma. | Replace "subfield if the" with "subfield, if the". | Rejected- The standards will be professionally edited prior to publication, and it is entirely likely rephrased in the next draft of this amendment. | [7 empty] | 2015-04-17 10:25
7052 | David Hunter | 211 | 5 | 9.3.2.1 | 236 | 23 | E | Y | 236.23 | 23 | 9.3.2.1 |  |  | Zander |  |  | "A first virtual CS mechanism": confusing and bad English. | Replace "A first virtual CS mechanism shall be provided" with "There are two virtual CS mechansims. The first shall be provided". | Rejected- The standards will be professionally edited prior to publication, and it may be rephrased in the next draft of this amendment. | [7 empty] | 2015-04-17 10:25
7053 | David Hunter | 211 | 5 | 9.3.2.1 | 236 | 23 | E | Y | 236.23 | 23 | 9.3.2.1 |  |  | Zander |  |  | Even though 11mc has "MAC entity" in some locations, the "entity" part is superfluous. The compound sentence needs to be split up for clarity. | Replace "by all MAC entities, and an additonal second virtual CS mechanism shall be provided by an S1G MAC entity. The first" with "by all MACs. The second virtual CS mechanism is an additional capability that shall be provided by all S1G MACs. {New Paragraph} The first". | Rejected- The standards will be professionally edited prior to publication, and it may be rephrased if necessary in the next draft of this amendment. | [7 empty] | 2015-04-17 10:25
7054 | David Hunter | 211 | 5 | 9.3.2.1 | 236 | 33 | E | Y | 236.33 | 33 | 9.3.2.1 |  |  | Zander |  |  | "For S1G STAs, " and, below, "For non-S1G STAs, ": this writing style is confusing because it emphasizes separate types of STAs when these DCF descriptions should be about the CS mechanisms. Emphasizing the mechanisms simplifies the sentences. | Replace "For S1G STAs, the duration information is" with "Duration information in S1G STAs is". On line 54 replace the first two sentences with: "The CS mechanism combines the NAV state and the STA's transmitter status (and in S1G STAs also the RID state) with physical CS to determine the busy/idle state of the medium.". On lne 60 replace "For S1G STAs, when both NAV and RID counters are 0, the virtual CS indication is that the medium is idle; when either the NAV counter or the RID counter is nonzero the indication is that the medium is busy." with "In S1G STAs, if both NAV and RID counters are 0, the virtual CS indication is that the medium is idle, but if either is nonzero, the indication is that the medium is busy.". | Rejected- The standards will be professionally edited prior to publication, and it may be rephrased in the next draft of this amendment. | [7 empty] | 2015-04-17 10:25
7055 | David Hunter | 211 | 5 | 9.3.2.1 | 236 | 33 | T | Y | 236.33 | 33 | 9.3.2.1 |  |  | Zander |  |  | "in NDP Ack frames with Idle Indication field equal to 0, and in NDP_2M PS-Poll Ack frames with Idle Indication field equal to 0.": fields are never equal to 0 -- though they might have values that are 0. | Replace "in NDP Ack frames with Idle Indication field equal to 0, and in NDP_2M PS-Poll Ack frames with Idle Indication field equal to 0." with "in NDP Ack frames whose Idle Indication field value is 0, and in NDP_2M PS-Poll Ack frames whose Idle Indication field value is 0." | Rejected- The standards will be professionally edited prior to publication, and it is entirely likely to be rephrased in the next draft of this amendment. | [7 empty] | 2015-04-17 10:25
7056 | David Hunter | 211 | 5 | 9.3.2.1 | 236 | 60 | T | Y | 236.6 | 60 | 9.3.2.1 |  |  | Zander |  |  | The beginning of the paragraph about the CS mechanism (starting on line 54) mentions the combination of the NAV, transmitter status and RID. However, the sentence that begins on line 60, "For S1G STAs, when both NAV and RID counters are 0,..." loses the transmitter status. Is transmitter status omitted from the S1G combined mechanism? If so, then state directly that it is. If not, then include it in this sentence. | Include transmitter status in the sentence that begins on line 60. Or combine the S1G STA statement with the DMG-with-multiple-NAV-timers statement. | Rejected- The sentences for S1G STAs are written with styles inline with that of for non-S1G STAs in the baseline draft (11mc) where "transmitter status" is not mentioned either. | [7 empty] | 2015-04-17 10:25
7057 | David Hunter | 211 | 5 | 9.3.2.3.3 | 237 | 20 | T | Y | 237.2 | 20 | 9.3.2.3.3 |  |  | Zander |  |  | SIFS application list: adding all of the different frame names to the number already there creates confusing and perhaps incorrect statements. For instance does "that is an immediate response to an NDP Paging frame" apply to PPDU, BlockAck frame, NDP BlockAck frame and BAT frame? And does "that is a response to an NDP Paging frame" apply to A-MPDU, (NDP) PS-Poll frame, and uplink trigger frame? | Replace the first sentence with a list whose lead-in clause is: "The SIFS shall be used prior to transmission of each of the following frames:" and follow this with a bulleted list of the frame names, each including the appropriate qualifier for that name ("that is an ..."). | Rejected- This is an invalid comment, it lacks of sufficient details for the assignee to provide resolutions. | [7 empty] | 2015-04-17 10:25
7058 | David Hunter | 211 | 5 | 9.3.2.3.3 | 237 | 26 | T | Y | 237.26 | 26 | 9.3.2.3.3 |  |  | Zander |  |  | "The SIFS shall be used by an S1G AP to separate": the passive voice is vague. For instance, it hints this functionality is something that may be used by non-S1G APs. | Replace "The SIFS shall be used by an S1G AP to separate" with "An S1G AP shall use SIFS to separate". | Rejected- The standards will be professionally edited prior to publication, and it may be rephrased if necessary in the next draft of this amendment. | [7 empty] | 2015-04-17 10:25
7059 | David Hunter | 211 | 5 | 9.3.2.4 | 239 | 29 | E | Y | 239.29 | 29 | 9.3.2.4 |  |  | Zander |  |  | There are qualifiers on top of qualifiers in the paragraph that includes: "In addition to the NAV update rules", "if it is greater than", "information received from", and "except when". These overlapping rules need at least some simplification. | Replace "new NAV value if it is greater than the current NAV value, with the informaton received in the Duration field of frames of type: NDP CTS," with "new NAV value, if it receives information that the NAV is greater than the STA's current NAV value. This information shall be received in the Duration field of the following frames: NDP CTS," | Rejected- The standards will be professionally edited prior to publication, and it may be rephrased if necessary in the next draft of this amendment. | [7 empty] | 2015-04-17 10:25
7060 | David Hunter | 211 | 5 | 9.3.2.4 | 239 | 61 | E | Y | 239.61 | 61 | 9.3.2.4 |  |  | Zander |  |  | "For a non-S1G STA, the 'CTS_Time' " and "For an S1G STA, the 'CTS_Time' ": both sound as if CTS_Time is used somehow to identify the STA. Instead these are calculated in the STA, not for it. | Replace "For a non-S1G STA, the" with "In a non-S1G STA the" and replace "For an S1G STA, the" with "In an S1G STA the". | Rejected- The standards will be professionally edited prior to publication, and it may be rephrased if necessary in the next draft of this amendment." | [7 empty] | 2015-04-17 10:25
7061 | David Hunter | 211 | 5 | 9.3.2.4 | 239 | 62 | E | Y | 239.62 | 62 | 9.3.2.4 |  |  | Zander |  |  | "NDPTxTime as calculated in 9.3.2.4a.2": actually, 9.3.2.4a.2 doesn't do any calculating, though it does some specifying. | Replace "NDPTxTime as calculated in" with "NDPTxTime, as specified in". | Rejected- The standards will be professionally edited prior to publication, and it may be rephrased if necessary in the next draft of this amendment." | [7 empty] | 2015-04-17 10:25
7062 | David Hunter | 211 | 5 | 9.3.2.4a.1 | 240 | 12 | E | Y | 240.12 | 12 | 9.3.2.4a.1 |  |  | Zander |  |  | "based on the values of the RXVECTOR parameters ... and CH_BANDWIDTH of the received frame as described": the "of the received frame" is lost in the middle of a long sentence. Also, the "as described" starts a subordinate thought, so needs to be separated by a comma. | Replace "of the RXVECTOR parameters" with "of the received frame's RXVECTOR parameters", and replace "CH_BANDWIDTH of the received frame as described" with "CH_BANDWIDTH, as described". Likewise, in the sentence below (on line 17), insert a comma after "value" and before "which is defined". And on lines 50 and 51 replace "counter as defined" with "counter, as defined" and replace "update) when the" with "update), when the". | Rejected- The standards will be professionally edited prior to publication, and it may be rephrased if necessary in the next draft of this amendment." | [7 empty] | 2015-04-17 10:25
7063 | David Hunter | 211 | 5 | 9.3.2.4a.1 | 240 | 57 | E | Y | 240.57 | 57 | 9.3.2.4a.1 |  |  | Zander |  |  | "A member PPDU is a": this definition comes a bit late, as both "member PPDU" and "nonmember PPDU" are used in the paragraph above this one. | Move the sentence "A member PPDU is a ... the receiving STA." to its own paragraph on line 48. Also move the sentence on page 241 line 5 ("A PPDU that .. Is a nonmember PPDU.") into this new paragraph. | Rejected- The standards will be professionally edited prior to publication, and it will most likely be rephrased in the next draft of this amendment." | [7 empty] | 2015-04-17 10:25
7064 | David Hunter | 211 | 5 | 9.3.2.4a.1 | 240 | 57 | E | Y | 240.57 | 57 | 9.3.2.4a.1 |  |  | Zander |  |  | "is a PPDU received by a STA and which was transmitted by a STA": the "which was" is unnecessary and confusing. | Replace "PPDU received by a STA and which was transmitted by" with "PPDU received by a STA and transmitted by". | Rejected- The standards will be professionally edited prior to publication, and it will most likely be rephrased in the next draft of this amendment." | [7 empty] | 2015-04-17 10:25
7065 | David Hunter | 211 | 5 | 9.3.2.4a.1 | 240 | 65 | E | Y | 240.65 | 65 | 9.3.2.4a.1 |  |  | Zander |  |  | Per the IEEE Style Manual, items in a list that are sentences are followed with periods. | Insert periods at the ends of line 64 and page 241 line 2. | Rejected- The standards will be professionally edited prior to publication, and it will most likely be rephrased in the next draft of this amendment." | [7 empty] | 2015-04-17 10:25
7066 | David Hunter | 211 | 5 | 9.3.2.4a.1 | 241 | 21 | E | Y | 241.21 | 21 | 9.3.2.4a.1 |  |  | Zander |  |  | "except when the PPDU either contains a valid nonzero Duration field that uddates the NAV ... or it is intended to the S1G STA in which case": confusing. And what does "intended to the S1G STA" mean? | Replace "updates the NAV as described ... the NAV) or it is intended to the S1G STA in which case the RID" with "updates the NAV, as described ... the NAV), or it is intended to be received by the S1G STA, In both of these cases the RID". | Rejected- The standards will be professionally edited prior to publication, and it will most likely be rephrased in the next draft of this amendment." | [7 empty] | 2015-04-17 10:25
7067 | David Hunter | 211 | 5 | 9.3.2.4a.1 | 241 | 27 | E | Y | 241.27 | 27 | 9.3.2.4a.1 |  |  | Zander |  |  | "If the PPDU is ... frame the" and "If the PPDU is not ... frame the": subordinate clauses need to be separated by commas. | On both lines 26 and 27 replace "frame the" with "frame, the". | Rejected- The standards will be professionally edited prior to publication, and it will most likely be rephrased in the next draft of this amendment." | [7 empty] | 2015-04-17 10:25
7068 | David Hunter | 211 | 5 | 9.3.2.4a.1 | 241 | 30 | E | Y | 241.3 | 30 | 9.3.2.4a.1 |  |  | Zander |  |  | Per the IEEE Style Manual, items in a list that are not sentences are not followed with punctuation. | Delete the periods a the ends of lines 30, 32 and 35. | Rejected- The standards will be professionally edited prior to publication, and it will most likely be rephrased in the next draft of this amendment." | [7 empty] | 2015-04-17 10:25
7069 | David Hunter | 211 | 5 | 9.3.2.4a.1 | 241 | 41 | E | Y | 241.41 | 41 | 9.3.2.4a.1 |  |  | Zander |  |  | "The RID ... is omitted in the figure because it is 0 ... while the RID is reset for the STA to which the Data was addressed.: huh? One "RID" is the sort of thing that is in a figure; the other "RID" is reset for a STA. This is using one word to mean very different things -- and in the same sentence. | Replace "The RID for STAs that receive but not that of the Data frame is omitted ... in this example) while the RID is reset for the STA to which the Data was addressed." with "For STAs that receive ... but not that of the Data frame, the RID counter is omitted in the figure because it is 0 (i.e, ... in this example). But for the STA to which the Data was addressed, the RID is reset." [Somewhat better, but needs a better description than "is 0" as a contrast to "is reset". Or just show the RID counter in the figure...] | Rejected- The standards will be professionally edited prior to publication, and it will most likely be rephrased in the next draft of this amendment." | [7 empty] | 2015-04-17 10:25
7070 | David Hunter | 211 | 5 | 9.3.2.4a.2 | 242 | 3 | E | Y | 242.03 | 3 | 9.3.2.4a.2 |  |  | Zander |  |  | "as described below:" needs to be followed by text that completes this sentence. But what follows is a separate sentence. | Replace the colon with a period. | Rejected- The standards will be professionally edited prior to publication, and it will most likely be rephrased in the next draft of this amendment." | [7 empty] | 2015-04-17 10:25
7071 | David Hunter | 211 | 5 | 9.3.2.4a.2 | 242 | 28 | E | Y | 242.28 | 28 | 9.3.2.4a.2 |  |  | Zander |  |  | Need to keep headings on their tables. | Lock the table caption and the table heading to the table's cells (found on the next page). | Rejected- The standards will be professionally edited prior to publication, and it will most likely be rephrased in the next draft of this amendment." | [7 empty] | 2015-04-17 10:25
7072 | David Hunter | 211 | 5 | 9.3.2.4a.2 | 243 | 39 | E | Y | 243.39 | 39 | 9.3.2.4a.2 |  |  | Zander |  |  | "is equal to the time in microseconds, required": a single comma separates the subject from is verb. | Replace "time in microseconds, required" with "time, in microseconds, required". | Rejected- The standards will be professionally edited prior to publication, and it will most likely be rephrased in the next draft of this amendment." | [7 empty] | 2015-04-17 10:25
7073 | David Hunter | 211 | 5 | 9.3.2.7 | 244 | 52 | E | Y | 244.52 | 52 | 9.3.2.7 |  |  | Alfred |  |  | "NOTE--NDP_1M CTS frame is": missing an article. | Replace "NDP_1M" with "The NDP_1M". Likewise, on page 245 line 5 replace "if link adaptation procedure" with "if the link adaptation procedure". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7074 | David Hunter | 211 | 5 | 9.3.2.7 | 245 | 10 | E | Y | 245.1 | 10 | 9.3.2.7 |  |  | Alfred |  |  | "adjusted by subtraction of aSIFSTime": the adjustment is made via the process of subtracting. | Replace "by subtraction of" with "by subtracting the value of". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. Also, please note that the same terminology is used in REVmc D4.0 in the same subclause in P1256L50: "...received RTS frame, adjusted by subtraction of aSIFSTime and the number of microseconds required to transmit the CTS frame..." | [7 empty] | 2015-04-17 10:25
7075 | David Hunter | 211 | 5 | 9.3.2.7 | 245 | 18 | E | Y | 245.18 | 18 | 9.3.2.7 |  |  | Alfred |  |  | "with which the non-AP STA is associated to.": extraneous "to". | Delete "to" from "is associated to." | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7076 | David Hunter | 211 | 5 | 9.3.2.8.1 | 245 | 32 | E | Y | 245.32 | 32 | 9.3.2.8.1 |  |  | Alfred |  |  | "shall not support the Dual CTS Protection procedure as defined in": indicates the process of _not_ supporting the procedure is defined in the subclause. Doubt that implication was intended. | Replace "procedure as define in" with "procedure defined in". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7077 | David Hunter | 211 | 5 | 9.3.2.9 | 246 | 20 | E | Y | 246.2 | 20 | 9.3.2.9 |  |  | Alfred |  |  | Per the IEEE Style Manual, items in a list that are sentences are followed with periods. | Insert periods at the ends of lines 18, 24, 32, 37, 55, 58 and 59. | Rejected-- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. It is expected that the IEEE publishing editor will take care of this minor editorial inconsistencies. | [7 empty] | 2015-04-17 10:25
7078 | David Hunter | 211 | 5 | 9.3.2.13 | 250 | 34 | E | Y | 250.34 | 34 | 9.3.2.13 |  |  | Alfred |  |  | "the value in the Duration field of the NDP CTS frame shall protect the pending transmission plus possibly an (NDP) Ack frame." what does "possibly" mean inside a shall statement? | Replace "protect the pending transmisssion plus possibly and (NDP) Ack frame." with "protect the pending transmission and may protect a resulting (NDP) Ack frame." | Rejected-- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7079 | David Hunter | 211 | 5 | 9.3.2.15 | 251 | 54 | E | Y | 251.54 | 54 | 9.3.2.15 |  |  | Alfred |  |  | Need to keep headings on their tables. | Lock the table caption and the table heading to the table's cells (found on the next page). | Rejected-- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. It is expected that the IEEE publishing editor will take care of this minor editorial inconsistencies. | [7 empty] | 2015-04-17 10:25
7080 | David Hunter | 211 | 5 | 9.3.2.15 | 253 | 19 | E | Y | 253.19 | 19 | 9.3.2.15 |  |  | Alfred |  |  | "element to 1 in which case the S1G STA may carry the eliciting frame in a VHT Single MPDU.": not sure how a STA _carries_ a frame. Also, "in which case" begins a subordinate clause. | Replace "may carry" with "may transmit" and insert a comma between "1" and "in which case". | Rejected-- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7081 | David Hunter | 211 | 5 | 9.3.2.15 | 253 | 41 | E | Y | 253.41 | 41 | 9.3.2.15 |  |  | Alfred |  |  | "more than one SIFS-separated PV1 frames": number problem -- one ... frames. | Replace "more than one" with "two or more". | Rejected-- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7082 | David Hunter | 211 | 5 | 9.3.6 | 254 | 1 | E | Y | 254.01 | 1 | 9.3.6 |  |  | Alfred |  |  | "into the BSS except when ... received from a STA in which case, the": "except" and "in which case" both begin subclauses in the sentence. | Replace "the BSS except" with "the BSS, except" and replace "from a STA in which case, the" with "from a STA. In that case the". | Rejected-- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7083 | David Hunter | 211 | 5 | 9.3.6 | 254 | 2 | E | Y | 254.02 | 2 | 9.3.6 |  |  | Alfred |  |  | With the addition of 6 lines to the paragraph from 11mc's 9.3.6, that paragraph now includes several separate topics. Break it up into three paragraphs. | Create new paragraphs beginning with "When dot11SSPNInterfaceActivated is false" on page 253 line 64 and beginning with "Unless the MPDU is delivered" on page 254 line 7. | Rejected-- The comment fails to identify a technical issue. The additions are a logical continuation of the topic covered by the REVmc paragraph. These lines add a necessary exception for the S1G case to the rule specified by that paragraph. | [7 empty] | 2015-04-17 10:25
7084 | David Hunter | 211 | 5 | 9.3.6 | 254 | 21 | E | Y | 254.21 | 21 | 9.3.6 |  |  | Alfred |  |  | "An S1G relay STA shall forward an MPDU with any group address in the Address 1 field originated from its associated AP to the S1G relay AP.": this sentence has enough qualifications on qualifications that it is not clear what is qualifying what. | Replace "An S1G relay STA shall forward an MPDU with any group address in the Address 1 field originated from its associated AP to the S1G relay AP." with "If an MPDU originates from an S1G relay STA's associated AP, and if the MPDU has any group address in its Address 1 field, then the STA shall forward that MPDU to the S1G relay AP." | Rjected- The comment fails to specify a technical issue. Please note that there is no ambiguity in the current description as it describes the normative behavior for forwarding group addressed frames. | [7 empty] | 2015-04-17 10:25
7085 | David Hunter | 211 | 5 | 9.3.7 | 254 | 42 | E | Y | 254.42 | 42 | 9.3.7 |  |  | Alfred |  |  | "For an S1G STA the EIFS is equal to DIFS if the PPDU that causes the EIFS gives a PHY-RXEND.indication primitive that does not contain FormatViolation.": what in the world is this trying to say? | We can guess that the receipt of the PPDU triggers the PHY to invoke the .indication primitive, and that this statement is assuming the indication does not report a FormatViolation. But this sentence badly needs replacement. | Rejected-- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. The sentence essentially says that the EIFS is equal to DIFS if the EIFS is invoked becsuse of an FCS failure rather than a FormatViolation. | [7 empty] | 2015-04-17 10:25
7086 | David Hunter | 211 | 5 | 9.20a | 271 | 57 | E | Y | 271.57 | 57 | 9.20a |  |  | Yongho |  |  | "identifying the BSS from which a reception originates so that": it is hard to imagine an origination of a reception -- but much easier the origin of a received PPDU. And "reception process in the case when the reception is not from the BSS": because a PPDU has been transmitted from a BSS doesn't mean that the reception is from the BSS. | Replace "reception originates" with "received PPDU originates". And on line 58 replace "process in the case when the reception is not" with "process when the received PPDU is not". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7087 | David Hunter | 211 | 5 | 9.22.2.9 | 276 | 56 | E | Y | 276.56 | 56 | 9.22.2.9 |  |  | Yongho |  |  | "may transmit an NDP CF-End frame (after PIFS) to truncate any active RID or NAV.": the parenthetical remark weakens the connection that the frame is transmited to truncate the RID or NAV. | Replace "may transmit an NDP CF-End frame (after PIFS) to truncate any active RID or NAV." with "may, after PIFS, transmit an NDP CF-End frame to truncate any active RID or NAV." | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7088 | David Hunter | 211 | 5 | 9.22.2.9 | 276 | 62 | E | Y | 276.62 | 62 | 9.22.2.9 |  |  | Yongho |  |  | "An S1G STA that transmits an NDP CF-End frame shall set its Duration field to 0 and shall not initiate any further frame exchange sequences within the current TXOP.": normally "its" applies to the subject (the STA) and "not initiate any further" is redundant. | Replace "set its Duration field" with "set the frame's Duration field" and replace "shall not initiate any further frame exchange sequences" with "shall initiate no other frame exchange sequences". Also replace "within" with the simpler "in". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7089 | David Hunter | 211 | 5 | 9.22.2.9 | 276 | 42 | T | Y | 276.42 | 42 | 9.22.2.9 |  |  | Alfred |  |  | "An S1G STA that receives an NDP CF-End frame should reset its NAV and can start contending for the medium without further delay.": per the IEEE Style Manual, norrmative and informative statements are not to be mixed. But this statement puts both into one sentence. | Replace "and can start contending" with "and may start contending". That seems to be what was intended. | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7090 | David Hunter | 211 | 5 | 9.22.2.9 | 277 | 63 | E | Y | 277.63 | 63 | 9.22.2.9 |  |  | Yongho |  |  | "8 microseconds boundaries": in American English nouns used as adjectives are singular. | Replace "microseconds boundaries" with "microsecond boundaries". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7091 | David Hunter | 211 | 5 | 9.22.2.9 | 277 | 63 | T | Y | 277.63 | 63 | 9.22.2.9 |  |  | Alfred |  |  | "allows for any inaccuracies": Editorial part: more accurately: "accommodates". Technical part: but it can't possibly allow for all inaccuracies. | Replace "allows for any inaccuracies" with "accommodates almost all inaccuracies". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. The sentence is a note that gives the reader some context on allowing flexible NAV boundaries and does not intend to provide an exhaustive list of all possible inaccuracies. | [7 empty] | 2015-04-17 10:25
7092 | David Hunter | 211 | 5 | 9.22.2.9 | 277 | 64 | T | Y | 277.64 | 64 | 9.22.2.9 |  |  | Alfred |  |  | "allows for any inaccuracies ... to the NAV counter at the receiving STA prior to the reception of the CF-End frame.": exactly what is happening prior to the receipt of the CF-End frame? The inaccuracies? | Just delete "prior to reception of the CF-End frame". | Rejected -- The comment fails to identify a technical issue and is asking a question. The response to the question is "Yes". | [7 empty] | 2015-04-17 10:25
7093 | David Hunter | 211 | 5 | 9.22.2.9 | 278 | 3 | E | Y | 278.03 | 3 | 9.22.2.9 |  |  | Yongho |  |  | "Duration field of the received CF-End frame adjusted by subtraction of aSIFSTime": the adjustment is a process of _subtracting_. And "to transmit the CF-End frame in unit of microseconds." is more clearly put: " to transmit the CF-End frame (in units of microseconds)." -- and there generally is moore than one unit of microseconds. And in the next sentence "If" begins a subordinate clause that should be separated from the main sentence by a comma. | Replace "by subtraction of" with "by subtracting the value of". Replace "frame in unit of microseconds." with "frame (in units of microseconds)." Replace "negative value the Duration field" with "negative value, the Duration field". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7094 | David Hunter | 211 | 5 | 9.22.5.1 | 278 | 28 | E | Y | 278.28 | 28 | 9.22.5.1 |  |  | Alfred |  |  | "with dot11RAWOperationImplemented equal to true": 'with' is too generic (is this attribute just floating somewhere in the ESS?) and attributes aren't equal to their values (but _have_ values). These same problems are in the three sentences starting with line 28. | Replace: "An S1G STA with dot11RAWOperationImplemented equal to true shall set the RAW Operation Support field in all S1G Capabilities elements it transmits to 1." with: "An S1G STA whose dot11RAWOperationImplemented value is true shall set the RAW Operation Support field in all S1G Capabilities element it transmits to 1." Replace: "An S1G STA with dot11RAWOperationImplemented equal to false shall set the RAW Operation Support field in the S1G Capabilities element it transmits to 0 with: "An S1G STA whose dot11RAWOperationImplemented value is false shall set the RAW Operation Support field in all S1G Capabilities elements it transmits to 0." On line 33 replace "with" with "whose", replace "equal to" with "value is" and replace "procedure as" with "procedure, as". And on line 38 replace "element with the RAW Operation Support field equal to 0." with "element whose RAW Operation Support field value is 0.". | Rejected- The comment fails to identify a technical issue. The terminology used in these sentences is correct and widely used in REVmc D4.0 as well (e.g., P130L07). | [7 empty] | 2015-04-17 10:25
7095 | David Hunter | 211 | 5 | 9.52 | 336 | 35 | E | Y | 336.35 | 35 | 9.52 |  |  | Yongho |  |  | "using the same as the signalling of individually addressed BUs": missing a word. | Replace "the same as the signallng of" with "the same signalling as the signalling of" | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7096 | David Hunter | 211 | 5 | 10.1.2.2 | 343 | 55 | T | Y | 343.55 | 55 | 10.1.2.2 |  |  | Alfred |  |  | "Within an IBSS in S1G band, the generation and/or reception of a Beacon frame and all references to it, refer to that of the S1G Beacon frame.": what is this trying to say? If it is only that the only Beacon frames in an S1G IBSS are S1G Beacon frames, then say that directly. | Replace "Within an IBSS in S1G band, the generation and/or reception of a Beacon frame and all references to it, refer to that of the S1G Beacon frame." with "All Beacon frames transmitted in an S1G IBSS shall be S1G Beacon frames." | Rejected- The comment fails to identify a technical issue and is asking a question. And the self-response that the comment contains is correct i.e., the sentence specifies that only S1G Beacon frames are generated in an S1G IBSS. However this is already clear in the existing text and no further changes are required. | [7 empty] | 2015-04-17 10:25
7097 | David Hunter | 211 | 5 | 10.1.3.8 | 344 | 28 | E | Y | 344.28 | 28 | 10.1.3.8 |  |  | Yongho |  |  | "for a WNM STA and for a DMG STA, and for an S1G STA.": too many "and"s. | Replace "for a WNM STA and for a DMG STA, and for an S1G STA." with "for a WNM STA, a DMG STA and an S1G STA." | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7098 | David Hunter | 211 | 5 | 10.1.3.8 | 344 | 46 | T | Y | 344.46 | 46 | 10.1.3.8 |  |  | Alfred |  |  | "The AID that is assigned to an S1G STA shall be such that the decimal value of its 11 LSBs is greater": a rather backward form of requirement. | Replace "The AID that is assigned to an S1G STA shall be such that the decimal value of its 11 LSBs is greater" with "The decimal value of the 11 LSBs of the AID assigned to an S1G STA shall be greater". | Rejected -- The comment fails to identify a technical issue. The existing sentence and the proposed change are technically equivalent. | [7 empty] | 2015-04-17 10:25
7099 | David Hunter | 211 | 5 | 10.1.3.10.1 | 346 | 3 | E | Y | 346.03 | 3 | 10.1.3.10.1 |  |  | Yongho |  |  | "10.1.3.10.1 General": just naming a subclause "General" is not informative -- especially when that subclause is referenced elsewhere. | Replace "General" with "General S1G synchronization". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7100 | David Hunter | 211 | 5 | 10.48 | 367 | 36 | E | Y | 367.36 | 36 | 10.48 |  |  | Yongho |  |  | "10.48 Dynamic AID assignment operation": this subclause specifies general MAC functionality, not just MLME features. | Move "10.48 Dynamic AID assignment operation" to a location between 9.20 and 9.21 (so this subclause becomes the new 9.21). Also rename it to "S1G dynamic AID assignment". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7101 | David Hunter | 211 | 5 | 10.49 | 369 | 35 | E | Y | 369.35 | 35 | 10.49 |  |  | Yongho |  |  | "10.49 System information update procedure": this subclause specifies MAC function operation, not just MLME features. But this operation is part of the S1G operation, so make it a subclause of the "S1G BSS operation" clause. After moving the "S1G BSS operation" subclause from 10.50 to the new 9.42, make the current 10.49 subclause the new 9.42.2. | Move subclause "10.49 Channel selection methods for an S1G BSS" to a location between "Basic S1G BSS functionality"(the new 9.42.1) and "Channel selection methods" (the new 9.42.3). Also rename this subclause "S1G BSS channel selection methods". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7102 | David Hunter | 211 | 5 | 10.50. | 370 | 5 | T | Y | 370.05 | 5 | 10.50. |  |  | Alfred |  |  | "10.50 S1G BSS operation": this subclause specifies basic MAC functionality, not just MLME features. | Move the full subclause "10.50 S1G BSS operation", except for 10.50.7, to a new subclause 9.42. | Rejected -- The comment fails to identify a technical issue. Please note that BSS operation for different amendments is generally defined as a subclause of clause 10 and the TGah is doing the same for the 11ah amendment as well. For instance refer to REVmc D4.0 subclause 10.40 (VHT BSS Operation) for the 11ac amendment. | [7 empty] | 2015-04-17 10:25
7103 | David Hunter | 211 | 5 | 10.50.2 | 371 | 52 | E | Y | 371.52 | 52 | 10.50.2 |  |  | Yongho |  |  | "10.50.2 Channel selection methods for an S1G BSS": a heading should not be a description. | Replace "Channel selection methods for an S1G BSS" to "S1G BSS channel selection methods". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7104 | David Hunter | 211 | 5 | 10.50.3 | 372 | 42 | E | Y | 372.42 | 42 | 10.50.3 |  |  | Yongho |  |  | "10.50.3 Channel Switching methods for an S1G BSS": a heading should not be a description. Also "channel switching" is the name of a functionality, so does not need initial caps. | Replace "Channel Switching methods for an S1G BSS" with "S1G BSS channel switching methods". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7105 | David Hunter | 211 | 5 | 10.50.7 | 374 | 1 | E | Y | 374.01 | 1 | 10.50.7 |  |  | Yongho |  |  | "S1G BSS type and STA type": what is such a general operation specification doing buried at the end of the MLME clause? This material does not belong in the MLME clause. | Move subclause 10.50.7 to a location between 9.2.5 and 9.2.6 (so it becomes the new 9.2.6). | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7106 | David Hunter | 211 | 5 | 10.50.7 | 374 | 30 | E | Y | 374.3 | 30 | 10.50.7 |  |  | Yongho |  |  | "minimum MCS restrictions": this mention needs a new reference to the new normative subclause on how minimum MCS restrictions shall be used. | Add a reference to a new subclause on the functional operations for minimum MCS restrictions. | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25
7107 | David Hunter | 211 | 5 | 10.51 | 374 | 33 | E | Y | 374.33 | 33 | 10.51 |  |  | Yongho |  |  | "Support for energy limited STAs": this subclause is a specification of functional operations, not just MLME components. Move it into the MAC functional specification. | After the TG creates the new subclause 9.42 on S1G operations, rename this subclause "9.42.9 Support for energy limited STAs". | Rejected- The comment is out of scope: i.e., it is not on changed text, text affected by changed text or text that is the target of an existing valid unsatisfied comment. | [7 empty] | 2015-04-17 10:25

## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-15/0527r2
Venue Date: | May 2015
First Author: | Yongho Seok (NEWRACOM)
Subject: | TGah LB211 comments on D5.0
Full Date: | 2015-05-11
Author(s): | Yongho Seok (NEWRACOM), Alfred Asterjadhi (Qualcomm), Zander Lei (I2R)
| Address: | 9008 Research Drive, Irvine, CA 92618
Phone:
Fax:
| email: | yongho.seok@newracom.com
Abstract:
This document contains the proposed resolutions for comments submitted from David Hunter on LB211 TGah D5.0.
- CIDs: 7026, 7027, 7028, 7029, 7030, 7031, 7032, 7033, 7034, 7035, 7036, 7037, 7038, 7039, 7040, 7041, 7042, 7043, 7044, 7045, 7046, 7047, 7048, 7049, 7050, 7051, 7052, 7053, 7054, 7055, 7056, 7057, 7058, 7059, 7060, 7061, 7062, 7063, 7064, 7065, 7066, 7067, 7068, 7069, 7070, 7071, 7072, 7073, 7074, 7075, 7076, 7077, 7078, 7079, 7080, 7081, 7082, 7083, 7084, 7085, 7086, 7087, 7088, 7089, 7090, 7091, 7092, 7093, 7094, 7095, 7096, 7097, 7098, 7099, 7100, 7101, 7102, 7103, 7104, 7105, 7106, 7107
(82 CIDs)