## Slide 1: P802.11ai Report to EC on Conditional Approval to go to Sponsor Ballot
Date: 2015-07-15
Authors:

## Slide 2: Abstract
This document contains the report to the IEEE 802 Executive Committee in support of a request for conditional approval to send IEEE P802.11ai Draft 6.0 to Sponsor Ballot.
This document was approved during the plenary session of the 802.11 working group on 17 July 2015.
  Passed in the Working Group xx yes, x no , x abstain

## Slide 3: 802.11 WG Letter Ballot Results – P802.11ai
Ballot ID | Ballot Close Date | Title | Ballot Type | Pool | Return | %Return | Abstain | %Abstain | Approve | Disapprove | %Approve
201 | 07 May 2014 | Technical Letter Ballot for P802.11ai draft 2.0 | Technical | 336 | 263 | 78 | 28 | 11 | 195 | 34 | 85
204 | 14 Oct 2014 | Technical Letter Ballot for P802.11ai draft 3.0 | Recirculation | 336 | 274 | 82 | 28 | 10 | 214 | 28 | 88
204.1 |  | LB 204 Post-Ballot vote change |  | 336 | 274 | 82 | 28 | 10 | 217 | 25 | 90
209 | 24 Feb 2015 | Technical Letter Ballot for P802.11ai draft 4.0 | Recirculation | 336 | 280 | 83 | 22 | 8 | 230 | 25 | 90
209.1 |  | LB 209 Post-Ballot vote change |  | 336 | 280 | 83 | 22 | 8 | 232 | 23 | 91
213 | 26 Jun 2015 | Technical Letter Ballot for P802.11ai draft 5.0 | Recirculation | 336 | 281 | 84 | 21 | 7 | 238 | 20 | 92
213.1 |  | LB 213 Post-Ballot vote change |  | 336 | 281 | 84 | 21 | 7 | 250 | 8 | 97
Note: Post-ballot change of vote as indicated in e-mail to 802.11 WG Chair

## Slide 4: 802.11 WG Letter Ballot Comments – P802.11ai
Ballot ID | Ballot Close Date | Title | Total Number of Comments received (Yes and No voters)
201 | 07 May 2014 | Technical Letter Ballot for P802.11ai Draft 2.0 | 1186 (543 T, 643 E)
204 | 14 Oct 2014 | First Recirculation Ballot for P802.11ai Draft 3.0 | 999 (474 T, 525 E)
209 | 24 Feb 2015 | First Recirculation Ballot for P802.11ai Draft 4.0 | 491 (255 T, 236 E)
213 | 26 Jun 2015 | First Recirculation Ballot for P802.11ai Draft 5.0 | 35 (23 T, 12 E)
Total |  |  | 2711 (1295 T, 1416 E)

## Slide 5: Unsatisfied comments by commenter
Voter | LB201 | LB204 | LB209 | LB213 | Total
Matthew FISCHER | 2 |  |  |  | 2
Mark HAMILTON (*) | 7 |  | 10 | 1 | 18
Joseph KWAK (*) | 7 |  |  |  | 7
James LEPP | 1 | 1 |  |  | 2
Stephen McCANN | 1 |  |  |  | 1
Michael MONTEMURRO | 5 |  |  |  | 5
Mark RISON | 1 | 24 | 13 |  | 38
Qi WANG (*) | 38 | 5 |  |  | 43
TOTAL | 62 | 30 | 23 | 1 | 116
(*) Commenter contacted after each ballot to ask which comments are satisfied / unsatisfied. Commenter provided no response.
Total number of unsatisfied comments from unresponsive commenter: 68
Total number of unsatisfied comments based on feedback from commenter: 48

## Slide 6: Unsatisfied Comments – Topics
Frame Formats (Cls 8) – 11 comments
MLME (Cls. 10) – 16 comments
Security (Cls. 11) – 14 comments
General (no Cls. Specified) – 7 comments
Unresponsive Commenters – 68 comments
  Break-down of comments from unresponsive commenters:
    Gen (no Cls specified) – 1 comment
    Layer Management (Cls 6) – 11 comments
    Frame Format (Cls 8) – 28 comments
    MAC sublayer (Cls 9) – 1 comments
    MLME (Cls 10) – 25 comments
    Annex – 2 comments

## Slide 7: Unsatisfied comments
The composite of all unsatisfied comments and the resolutions approved by the comment resolution committee received during working group ballot may be found in the embedded document on the right:
  Double click on the icon to the right to open this.
  The information is also available at https://mentor.ieee.org/802.11/dcn/15/11-15-0925-02-00ai-tgai-comments-from-all-wg-letter-ballots.xlsx

## Slide 8: TGai Timeline
 | Open | Close
Fourth recirculation D6.0 | 16-July-15 | 31-July-15
Fifth recirculation (of unchanged draft D6.0) | 17-Aug-15 | 01-Sep-15
First sponsor ballot | 03-Sep-15 | 03-Oct-15
Second sponsor ballot | 21-Mar-16 | 5-Apr-15
Third sponsor ballot | 18-Jul-16 | 2-Aug-16
Fourth sponsor ballot (unchanged) | 18-Sep-16 | 3-Oct-16
EC to RevCom July 2016 |  | 
RevCom to Standards Board Sep 2016 |  | 

## Slide 9: References
Comment Spreadsheet
  Double click on the icon to the right
  The information is also available at https://mentor.ieee.org/802.11/dcn/15/11-15-0925-02-00ai-tgai-comments-from-all-wg-letter-ballots.xlsx