## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-15/1021r3
Venue Date: | November 2015
First Author: | Jiamin CHEN, Huawei/HiSilicon
Subject: | Comments on 802.11aj (45GHz) D0.6
Full Date: | 2015-11-10
Author(s): | Name(s) | Jiamin CHEN | Shiwen He | Xiaoming PENG
| Affiliation | Huawei/HiSilicon | SEU | I2R
Address
Phone:
Fax:
| email: | jiamin.chen@mail01.huawei.com | shiwenhe@seu.edu.cn | pengxm@i2r.a-star.edu.sg
Abstract:
This document contains comments submitted by members of 802.11 working group on 802.11aj (45GHz)D0.6. This document is periodically updated to reflect the status of those comments.

## Comments
CommentID | Commenter | Clause Number | Page | Line | Type of Comment | Comment | Proposed Change | Resolution | DuplicateOfCID | Edited? | Assignee | MotionNumber | ImplementationStatus | Remark
1 | Dejian Li | 9.37 | 62 | 20 | T | There is no specified QMG Beacon frame in this draft. | Define the format of the QMG Beacon frame, and use the correct name "QMG Beacon" for all the "Beacon" frames. | Revised. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
2 | Dejian Li | 3.2 | 1 | 12 | T | It seems that a QMG STA may use the channel access mechanism specified in subclause "9.33 DMG channel access", because a "CBAP" appears here. What is the relationship of DMG and QMG channel access mechanisms? | If some DMG mechanisms are applicable for a QMG STA, then clarify them. |  |  | Yes | Shiwen He | Motion 1 in 11-15/1236r3.
3 | Dejian Li | 26.1.1 | 82 | 10 | T | The wording "millimeter waves WLAN" is ambiguous. | Change "millimeter waves WLAN" to a QMG STA | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
4 | Dejian Li | 26.1.1 | 82 | 19 | T | There is no specified frequency band and channel bandwidths for QMG operating classes. | Define the QMG operating classes in Annex E. | Revised. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
5 | Dejian Li | 26.4.4.6 | 110 | 27 | E | The number is missed in "in Table ". | Change "in Table" to "in Table 26-12". | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
6 | Jiamin Chen | 3.3 | 2 | 10 | G | The abbreviation STF (Short Training Field) already defined in 802.11REVmc 4.0. | Remove the abbreviation STF (Short Training Field) . | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
7 | Jiamin Chen | 3.3 | 2 | 3 | G | Abbreviations may be defined for terms that are used frequently throughout the document. But don't create abbreviations for: * Terms used only a handful of times * Names of fields, structures, elements or frames (See 802.11 Style Guide 11-09/1034r11) | Consider to remove acronyms for a field name in 3.3. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
8 | Jiamin Chen | 3.3 | 2 | 6 | G | "QMG: Q-band Millimeter-wave Multiple Gigabit". Usually an acronym is formed by combining all the initial letters of a series of words. | Change to "QMG: Q-band Multiple Gigabit" or "QMMG: Q-band Millimeter-wave Multiple Gigabit". | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
9 | Jiamin Chen | 3.3 | 2 | 20 | G | ZCZ: Zero Correlation Zone (ZCZ) Sequence. Usually an acronym is formed by combining initial letters of a series of words. | Change to "ZCZ: Zero Correlation Zone (Sequence)" or "ZCZS: Zero Correlation Zone Sequence." | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
10 | Jiamin Chen | 8.1 | 4 | 7 | E | Remove the two paragraphs to avoid potential confusion and conflict if there is no change to the corresponding paragraphs in .11REVmc4.0. If there be, use underline and strikethrough to show the modification to the REVmc if applicable. | Remove the following two paragraphs. Do as noted throughout the draft. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
11 | Jiamin Chen | 8.2.3 | 4 | 38 | T | Change the title of the Figure 8-1a to "QMG MAC frame format" if this MAC frame format is only defined for QMG. The changes made for QMG in this spec shall not impact the existing spec defined for non-QMG STAs. | Change the title of the Figure 8-1a to "MAC frame format for QMG STA". | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
12 | Jiamin Chen | 8.3.1.10 | 8 | 50 | T | Change the title of the Figure 8-29a to "QMG Control Wrapper frame" if this frame format is only defined for QMG. | Change the title of the Figure 8-29a to "QMG Control Wrapper frame" . | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
13 | Jiamin Chen |  | 9 | 19 | E | The order number in the table will be administered by the ANA. | Replace 67 and 68 by "<ANA>" and precede table by an editorial comment: "The <ANA> flags below will be replaced with numbers assigned by the 802.11 assigned numbers authority." Ditto throughout the draft. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
14 | Jiamin Chen | 8.4.1.29 | 19 | 1 | E | Here the values should be shown as digits. | Change "zeros" to "0s". Ditto throughout the draft. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
15 | Jiamin Chen | 9.3.2.6 | 38 | 23 | E | Unnecessary noun in noun phrase. The SIFS is already noun phrase and do not need any following nouns:"spacing"/"period"/"Interval". | Remove "period". Ditto throughout the draft. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
16 | Jiamin Chen | 9.7.5.1 | 39 | 39 | T | It needs to declare if the two paragraphs here are only applicable for QMG STA. | "For QMG STAs, ..." | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
17 | Jiamin Chen | 9.7.5.3 | 39 | 60 | T | Show the changes to REVmc by using underline and strikethrough if applicable. | Do as noted in the comment. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
18 | Jiamin Chen | 9.7.5.6 | 40 | 25 | T | It needs to declare if this subclause is only applicable for QMG STA and need an editor instruction to indicate whether it is newly added at the end of the existing subclause. | Do as noted in the comment. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
19 | Jiamin Chen | 9.7.6.5.5 | 44 | 52 | E | If the paragraph is new, use "insert" instead of "change" in the editor instruction. Otherwise, use underline and strikethrough to show the changes. | Do as noted in the comment. Ditto throughout the draft. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
20 | Jiamin Chen | 9.9 | 46 | 1 | E | The title of the subclause 9.9 looks like it is a new subclause, but the content shows not. | Create a new subclause for QMG Control field operation. Change the editor instructions accordingly. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
21 | Jiamin Chen | 9.1 | 46 | 43 | E | Make it clear the position at where the new sentence will be inserted. | Change the editor instruction accordingly or copy related txt here. Fix the same problems throughout the draft. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
22 | Jiamin Chen | 9.28.3.3 | 56 | 51 | E | Capitalize all of the first letter of the frame name. | Change to "...QMG Capabilities Info field...". Ditto throughout the draft. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
23 | Jiamin Chen | 9.37.2.1 | 63 | 60 | E | Values are shown as digits when representing the value of fields. | Change "zero" to "0". Ditto throughout the draft. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
24 | Jiamin Chen | 10.3 | 73 | 40 | E | If there is no change for the subclause 10.3, remove it from the draft. | Do as noted in the comment. Fix the same problems throughout the draft. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
25 | Jiamin Chen | 26.1.3.2 | 83 | 7 | T | The corresponding subclause DMG PMD sublayer in 11ad is removed based on comment resolution for REVmc (see CID35/64/65 in 11-13/233r56 and REVmc4.1). | Remove this subclause. Ditto at 26.1.3.3 and throughout the draft. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He, Jiamin Chen | Motion 1 in 11-15/1080r3.
26 | Jiamin Chen | 26.3.5 | 95 | 53 | E | Use of "which" should generally be preceded by a comma or preposition. | Add comma before which. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
27 | Jiamin Chen | 26.3.5.4 | 96 | 29 | E | The font size in the figure is too big. | Correct the font size in the figure. Ditto throughout the draft. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
28 | Jiamin Chen | 26.3.6 | 99 | 9 | E | Here the values should be shown as digits. | Change "ones" to "1s". Ditto throughout the draft. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
29 | Jiamin Chen | 16.13.1 | 156 | 39 | E | Do not miss out the "noun" part of the noun phrase. | Insert "primitive" after "PHY-CCA.indication(BUSY)". Ditto throughout the draft. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
30 | Jiamin Chen | 26.14.2 | 159 | 44 | E | All "true" and "false" should be lower case, except where they are part of pseudo-code or code. | Change "False/Boolean" to "false/Boolean". Ditto throughout the draft. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
31 | Jiamin Chen | 26.16.1 | 168 | 37 | T | The corresponding subclause DMG PMD sublayer in 11ad is removed based on comment resolution for REVmc (see CID35/64/65 in 11-13/233r56 and REVmc4.1). | Remove this subclause and do as noted by the resolutions for CID35/64/65 in 11-13/233r56. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He, Jiamin Chen | Motion 1 in 11-15/1080r3.
32 | Jiamin Chen | C.3 |  |  | T | Need MIB to manage QMG. | Add MIB in Annex C. | Revised. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
33 | Yongho Seok | 26.13.2 | 157 | 46 | T | "After receiving a valid QMG-SIG indicating a supported mode, the PMD indicates to the PLCP the type of PHY of the packet according the SC/OFDM subfield in the QMG-SIG field." The SC/OFDM subfield in the QMG-SIG field is not defined in Figure 26-12--QMG | Clarify what is a detection mechanism of SC/OFDM. Suggestion is to remove the SC/OFDM subfield in the QMG-SIG field. And, follow the same detection mechanism from 802.11ad. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
34 | Yongho Seok | 26.8 | 146 | 1 | T | It seems that new ZCZ sequence has been proposed for MIMO operation in a millimeter wave. But, IEEE 802.11ay is also developing MIMO operation in a millimeter wave. If both technologies are implemented on single chip, it is reasonable to use keep a simila | Please develope the unified MIMO operation for 45GHz and 60GHz. | Rejected. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.
35 | Yongho Seok | 8.3.1.10 | 8 | 41 | T | "Change the Figure 8-29 as follows." The editing instruction doesn't make sense because the changed part on the Figure 8-29 is not shown. | Please provide the correct editing instruction for understanding what has been changed. - use underline if new words are added - use strikethrough if old words are deleted Also, please review all editing instructions throughout a draft. | Accepted. See 11-15/1054r6. |  | Yes | Shiwen He | Motion 1 in 11-15/1080r3.

## Revision History
Revision | Date | Description
R0 | 2014-08-27 | Comments received from CC20.

## References
References:
1. This document utilizes the template in the IEEE 802.11 comment spreadsheet.